## Cover sheet
3GPP TSG-RAN WG5 Meeting #94-e | [8 empty] | R5-220036
Electronic Meeting, Feb 21 – Mar 4, 2022
Agenda Item: | 7.4.2
Source: | CMCC
Title: | WP - UE Conformance Test Aspects for High power UE (power class 2) for NR band n34
Work item code: | NR_UE_PC2_n34-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At RAN#93e meeting in September 2021, a Release 17 work item for UE Conformance Test Aspects for High power UE (power class 2) for NR band n34 (NR_UE_PC2_n34-UEConTest) was approved [1]. The objective of this work item is to define the UE conformance requirements corresponding to WID on NR PC2 n34 UE with Unique identifier 930053. This work item will cover RF conformance test specifications with NR PC2 n34. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 53% (+8%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 53.5% (+7.8%)
FR1 |  | 53.5% (+7.8%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
RF test cases | 38.521-1 | 61.1% (+11.1%) |  |  | 61.1% (+11.1%)
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
5 References
[1] RP-211980 | New WID on UE Conformance - High power UE (power class 2) for NR band n34 - CMCC (Supporting companies: CATT, Ericsson, Huawei, Hisilicon, OPPO, ZTE)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for High power UE (power class 2) for NR band n34 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_UE_PC2_n34-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for NR PC2 n34 support comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title |  | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
53.5% (+7.8%)
21
4.9 (+0)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-2 | A.4.3.1 | <Title> | Introduction of common implementation conformance statements for Rel-17 PC2 n39 UE | CMCC | RAN5#94 (Feb-22) | R5-216466 | CMCC Dan Song <songdan@chinamobile.com> | 0.3 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.521-1 | 6.2.1.3 | MOP Minimum conformance requirements | add the power class and toleranxe values for the band, including descriptive text after the table | CMCC | RAN5#94 (Feb-22) | R5-218383 | CMCC Dan Song <songdan@chinamobile.com> | 0.2 | 100% | 100% |  | 100%
3 |  | 38.521-1 | 6.2.1.4.2 | MOP test procedure | update the test procedure | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> The needed changes have been introduced by R5-216000 under "LTE_NR_B41_Bn41_PC29dBm-UEConTest" WI. No further changes needed in this WI. | 0.2 | 100% | 100% |  | 100%
4 |  | 38.521-1 | 6.2.1.4.3 | MOP message contents | update the message contents, if needed | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> The needed changes have been introduced by R5-216000 under "LTE_NR_B41_Bn41_PC29dBm-UEConTest" WI. No further changes needed in this WI. | 0.2 | 100% | 100% |  | 100%
5 |  | 38.521-1 | 6.2.1.5 | MOP test requirement | add the test requirement for PC2 | CMCC | RAN5#94 (Feb-22) | R5-218383 | CMCC Dan Song <songdan@chinamobile.com> | 0.2 | 100% | 100% |  | 100%
6 |  | 38.521-1 | 6.2.2.3 | MPR Minimum conformance requirements | add the MPR for dual TX | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> The needed changes have been introduced by R5-216001 under "LTE_NR_B41_Bn41_PC29dBm-UEConTest" WI. No further changes needed in this WI. | 0.2 | 100% | 100% |  | 100%
7 |  | 38.521-1 | 6.2.2.4.1 | MPR initial conditions | test configuration table for PC2 | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> The needed changes have been introduced by R5-216001 under "LTE_NR_B41_Bn41_PC29dBm-UEConTest" WI. No further changes needed in this WI. | 0.2 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 6.2.2.4.2 | MPR test procedure | update test procedure for PC2 | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> The needed changes have been introduced by R5-216001 under "LTE_NR_B41_Bn41_PC29dBm-UEConTest" WI. No further changes needed in this WI. | 0.2 | 100% | 100% |  | 100%
9 |  | 38.521-1 | 6.2.2.4.2 | MPR message contents | update the message contents | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> The needed changes have been introduced by R5-216001 under "LTE_NR_B41_Bn41_PC29dBm-UEConTest" WI. No further changes needed in this WI. | 0.2 | 100% | 100% |  | 100%
10 |  | 38.521-1 | 6.2.2.4.2 | MPR test requirements | update the test requirements for PC2 | CMCC | RAN5#94 (Feb-22) | R5-218385 | CMCC Dan Song <songdan@chinamobile.com> | 0.2 | 100% | 100% |  | 100%
11 |  | 38.521-1 | 6.2.4.3 | Configured Tx Power Minimum conformance requirements | add the configured tx power requirements |  |  |  |  | 0.2 | 0% | 0% |  | 0%
12 |  | 38.521-1 | 6.2.4.4.3 | Configured Tx Power message contents | update message contents, if needed |  |  |  |  | 0.2 | 0% | 0% |  | 0%
13 |  | 38.521-1 | 6.2.4.5 | Configured Tx Power; Test Requirements | update test requirements |  |  |  |  | 0.2 | 0% | 0% |  | 0%
14 |  | 38.521-1 | 6.2D.1.3 | MOP for UL MIMO | add the minimum conformance requirements | CMCC | RAN5#94 (Feb-22) | R5-218384 | CMCC Dan Song <songdan@chinamobile.com> | 0.2 | 100% | 100% |  | 100%
15 |  | 38.521-1 | 6.2D.1.5 | MOP for UL MIMO | add the test requirements | CMCC | RAN5#94 (Feb-22) | R5-220138 | CMCC Dan Song <songdan@chinamobile.com> | 0.2 | 100% | 100% |  | 100%
16 |  | 38.521-1 | 6.5.2.4.1.3 | NR ACLR minimum conformance requirements | minimum conformance requirement |  |  |  |  | 0.2 | 0% | 0% |  | 0%
17 |  | 38.521-1 | 6.5.2.4.1.4.2 | NR ACLR test procedure | update test procedure for PC2 |  |  |  |  | 0.2 | 0% | 0% |  | 0%
18 |  | 38.521-1 | 6.5.2.4.1.4.3 | NR ACLR message contents | update message contents for PC2 |  |  |  |  | 0.2 | 0% | 0% |  | 0%
19 |  | 38.521-1 | 6.5.2.4.1.5 | NR ACLR test requirement | update test requirement for PC2 |  |  |  |  | 0.2 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | <Clause> | <Title> | Add new ICS statements.
20 |  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
21 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for 38.521-1 Rel-17 PC2 n39 test case. | CMCC | RAN5#94 (Feb-22) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.