## Cover sheet
3GPP TSG-RAN WG5 meeting#94-e | [10 empty] | R5-220435
Electronic Meeting, February 21 - March 4, 2022
Agenda Item: | 7.4.2
Source: | Rapporteur (Ericsson)
Title: | UE Conformance Test Aspects – UE Conformance Test Aspects – Rel-15 CA configurations Work Plan
Work item code: | LTE_CA_R15-UEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
At the RAN#76 meeting in September 2017 the Rel-15 RAN5 work item for UE Conformance Test Aspects of Rel-15 CA configurations was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items for Rel-15 CA configurations. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'Summary Work Plan' shows the status for each Rel-15 CA configuration. For each company assigned CA configurations that is ongoing and not yet completed a specific work sheet with the detailed work plan is provided. Note: This work plan is limited to the addition of new and update of existing LTE CA test cases for the new types of CA configuration introduced by this basket work item as endorsed by RAN5 in R5-215708 at RAN5#92-e. Completed CA configuration are listed in TS 36.521-2 clause A.4.6. Tracking of the responsible companies and guidlines for introducing new LTE CA configurations can be found in the RAN5 Permanent Reference Document [2] PRD20 . Introducing new LTE CA Configuration shall be in accordance to the guidelines in [2] PRD20.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 75% (+1%) | 67 (+6) | 100
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 75.3% (+1%) | 67 (+6) | 100
FDD |  | 78.8% (+1.3%) | 45 (+4) | 64
TDD |  | 74.7% (+1.4%) | 41 (+4) | 63
FDD + TDD |  | 72.9% (+0.5%) | 53 (+2) | 77
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE RF/RRM
4UL RF Tx test cases | 36.521-1 Tx 4UL | 86.4% | 17 | 22 | 86.4% | 17 | 22 | 86.4% | 17 | 22 | 86.4% | 17 | 22
6DL RF Rx test cases | 36.521-1 Rx 6DL | 100% | 9 | 9 | 100% | 9 | 9 | 100% | 9 | 9 | 100% | 9 | 9
6DL RF Rx test cases Demod/QSI reporting | 36.521-1 Perf 6DL | 85.5% (+2.3%) | 19 (+2) | 24 | 100% (+3.3%) | 6 (+1) | 6 | 72% (+4%) | 2 (+1) | 5 | 84.6% | 11 | 13
6DL RRM test cases | 36.521-3 RRM 6DL | 50% | 3 | 6 | 50% | 3 | 6 | 50% | 3 | 6 | 50% | 3 | 6
7DL RF Rx test cases | 36.521-1 Rx 7DL | 44.4% | 4 | 9 | 44.4% | 4 | 9 | 44.4% | 4 | 9 | 44.4% | 4 | 9
7DL RF Rx test cases Demod/QSI reporting | 36.521-1 Perf 7DL | 72.4% (+3.1%) | 12 (+2) | 24 | 95% (+5%) | 3 (+1) | 6 | 76.7% (+5%) | 3 (+1) | 6 | 50% | 6 | 12
7DL RRM test cases | 36.521-3 RRM 7DL | 50% (+6.7%) | 3 (+2) | 6 | 50% (+6.7%) | 3 (+2) | 6 | 50% (+6.7%) | 3 (+2) | 6 | 50% (+6.7%) | 3 (+2) | 6
5 References
[1] RP-160754 | New Work Item Proposal: UE Conformance Test Aspects – Rel-14 CA configurations; Supporting companies: Ericsson, Spirent Communications, Dish Network, LGE, Orange, Keysight, Qualcomm, BlackBerry, Rohde & Schwarz, DOCOMO, China Unicom, Verizon, SoftBank Corp., Bureau Veritas, Sprint, Motorola Mobility, Sporton, Huawei, Telecom Italia, Anritsu, KTL, CMCC, KDDI
[2] RAN5 PRD20 | E-UTRA CA configuration handling in RAN5 (Release 10 and later releases)
Download PRD20 from here: ftp://ftp.3gpp.org/TSG_RAN/WG5_Test_ex-T1/PRD/
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects – Rel-15 CA configurations | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_CA_R15-UEConTest
WP Scope: |  | This work plan is limited to the addition of new and update of existing Rel-15 LTE CA test cases for the new types of CA configuration introduced by this basket work item as endorsed by RAN5 in R5-215708 at RAN5#92-e. Completed CA configuration are listed in TS 36.521-2 clause A.4.6. Tracking of the responsible companies and guidlines for introducing new LTE CA configurations can be found in the RAN5 Permanent Reference Document [2] PRD20 . Introducing new LTE CA Configuration shall be in accordance to the guidelines in [2] PRD20. | [12 empty] | vs Area
WP Resp: |  | Leif Mattisson, Ericsson |  |  | leif.mattisson@ericsson.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD | FDD + TDD
[14 empty] | 78.8% (+1.3%) | 74.7% (+1.4%) | 72.9% (+0.5%)
[14 empty] | 64 | 63 | 77
[14 empty] | 64 | 63 | 77
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
4UL LTE CA test cases
TS 36.521-1: 4UL CA RF test cases - Tx
1 | Y | 36.521-1 Tx 4UL | 6.2.2A.5 | UE Maximum Output Power for CA (4UL CA) | Add test case variant for 4UL | 3in | RAN5#83 (May-19) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
2 | Y | 36.521-1 Tx 4UL | 6.2.3A.5 | Maximum Power Reduction (MPR) for CA (4UL CA) | Add test case variant for 4UL | 3in | RAN5#83 (May-19) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
3 | Y | 36.521-1 Tx 4UL | 6.2.4A.5 | Additional Maximum Power Reduction (A-MPR) for CA (4UL CA) | Add test case variant for 4UL | 3in | RAN5#93 (Nov-21) |  | Remains: Test configuration and test requirements | 1 | 50% | 50% |  | 50% | 50% | 50%
4 | Y | 36.521-1 Tx 4UL | 6.2.5A.6 | Configured UE transmitted Output Power for CA (4UL CA) | Add test case variant for 4UL | 3in | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
5 | Y | 36.521-1 Tx 4UL | 6.3.2A.5 | Minimum Output Power for CA (4UL CA) | Add test case variant for 4UL | 3in | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
6 | Y | 36.521-1 Tx 4UL | 6.3.3A.5 | UE Transmit OFF power for CA (4UL CA) | Add test case variant for 4UL | 3in | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
7 | Y | 36.521-1 Tx 4UL | 6.3.4A.1.5 | General ON/OFF time mask for CA (4UL CA) | Add test case variant for 4UL | Samsung | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
8 | Y | 36.521-1 Tx 4UL | 6.3.5A.1.6 | Power Control Absolute power tolerance for CA (4UL CA) | Add test case variant for 4UL | Samsung | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
9 | Y | 36.521-1 Tx 4UL | 6.3.5A.2.5 | Power Control Relative power tolerance for CA (4UL CA) | Add test case variant for 4UL | CETECOM | RAN5#94-e (Feb-22) |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
10 | Y | 36.521-1 Tx 4UL | 6.3.5A.3.5 | Aggregate Power Control Tolerance for CA (4UL CA) | Add test case variant for 4UL | Samsung | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
11 | Y | 36.521-1 Tx 4UL | 6.5.1A.5 | Frequency Error for CA (4UL CA) | Add test case variant for 4UL | KTL | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
12 | Y | 36.521-1 Tx 4UL | 6.5.2A.1.5 | Error Vector Magnitude (EVM) for CA (4UL CA) | Add test case variant for 4UL | KTL | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
13 | Y | 36.521-1 Tx 4UL | 6.5.2A.2.5 | Carrier leakage for CA (4UL CA) | Add test case variant for 4UL | KTL | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
14 | Y | 36.521-1 Tx 4UL | 6.5.2A.3.5 | In-band emissions for non allocated RB for CA (4UL CA) | Add test case variant for 4UL | KTL | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
15 | Y | 36.521-1 Tx 4UL | 6.6.1A.5 | Occupied bandwidth for CA (4UL CA) | Add test case variant for 4UL | KTL | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
16 | Y | 36.521-1 Tx 4UL | 6.6.2.1A.5 | Spectrum Emission Mask for CA (4UL) | Add test case variant for 4UL | CETECOM | RAN5#93-e (Nov-21) | 36.521-1: R5-217467 R5-218263 36.521-2: R5-218265 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
17 | Y | 36.521-1 Tx 4UL | 6.6.2.2A.5 | Additional Spectrum Emission Mask for CA (4UL CA) | Add test case variant for 4UL | CETECOM | RAN5#94-e (Feb-22) | 36.521-1: R5-217462 R5-217467 36.521-2: R5-218265 | Test configuration and test requirements depend on completion of TC 6.2.4A.5 | 1 | 50% | 50% |  | 50% | 50% | 50%
18 | Y | 36.521-1 Tx 4UL | 6.6.2.3A.5 | Adjacent Channel Leakage power Ratio for CA (4UL CA) | Add test case variant for 4UL | CETECOM | RAN5#93-e (Nov-21) | 36.521-1: R5-217467 R5-218264 36.521-2: R5-218265 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
19 | Y | 36.521-1 Tx 4UL | 6.6.3.1A.5 | Transmitter Spurious emissions for CA (4UL CA) | Add test case variant for 4UL | CETECOM | RAN5#93-e (Nov-21) | 36.521-1: R5-217464 R5-217467 36.521-2: R5-218265 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
20 | Y | 36.521-1 Tx 4UL | 6.6.3.2A.5 | Spurious emission band UE co-existence for CA (4UL CA) | Add test case variant for 4UL | CETECOM | RAN5#94-e (Feb-22) | 36.521-1: R5-217465 R5-217467 36.521-2: R5-218265 | Test configuration and test requirements FFS | 1 | 50% | 50% |  | 50% | 50% | 50%
21 | Y | 36.521-1 Tx 4UL | 6.6.3.3A.5 | Additional spurious emissions for CA (4UL CA) | Add test case variant for 4UL | CETECOM | RAN5#94-e (Feb-22) | 36.521-1: R5-217466 R5-217467 36.521-2: R5-218265 | Test configuration and test requirements depend on completion of TC 6.2.4A.5 | 1 | 50% | 50% |  | 50% | 50% | 50%
22 | Y | 36.521-1 Tx 4UL | 6.7A.5 | Transmit intermodulation for CA (4UL CA) | Add test case variant for 4UL | Samsung | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
6DL LTE CA test cases
TS 36.521-1: 6DL RF Rx test cases
23 | Y | 36.521-1 Rx 6DL | 7.3A.11 | Reference sensitivity level for 6DL CA | Add test case variant for 6DL | KDDI | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
24 | Y | 36.521-1 Rx 6DL | 7.4A.9 | Maximum input level for 6DL CA | Add test case variant for 6DL | KDDI | RAN5#93 (Nov-21) | 36.521-1: R5-217291 36.521-2: R5-217292 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
25 | Y | 36.521-1 Rx 6DL | 7.4A.9_H | Maximum input level for 6DL CA for 256QAM in DL | Add test case variant for 6DL | KDDI | RAN5#93 (Nov-21) | 36.521-1: R5-217291 36.521-2: R5-217292 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
26 | Y | 36.521-1 Rx 6DL | 7.5A.9 | Adjacent Channel Selectivity (ACS) for 6DL CA | Add test case variant for 6DL | Tejet | RAN5#86-e (Feb-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
27 | Y | 36.521-1 Rx 6DL | 7.6.1A.9 | In-band blocking for 6DL CA | Add test case variant for 6DL | Tejet | RAN5#88-e (Aug-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
28 | Y | 36.521-1 Rx 6DL | 7.6.2A.9 | Out-of-band blocking for 6DL CA | Add test case variant for 6DL | Tejet | RAN5#88-e (Aug-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
29 | Y | 36.521-1 Rx 6DL | 7.6.3A.9 | Narrow band blocking for 6DL CA | Add test case variant for 6DL | Tejet | RAN5#88-e (Aug-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
30 | Y | 36.521-1 Rx 6DL | 7.7A.9 | Spurious response for 6DL CA | Add test case variant for 6DL | Tejet | RAN5#88-e (Aug-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
31 | Y | 36.521-1 Rx 6DL | 7.8.1A.9 | Wideband intermodulation for 6DL CA | Add test case variant for 6DL | Tejet | RAN5#86-e (Feb-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
TS 36.521-1: 6DL Demod/QSI reporting test cases
32 | Y | 36.521-1 Perf 6DL | 8.2.1.1.1_A.6 | FDD PDSCH Single Antenna Port Performance for CA (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  | 100%
33 | Y | 36.521-1 Perf 6DL | 8.2.1.3.1_A.5 | FDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  | 100%
34 | Y | 36.521-1 Perf 6DL | 8.2.1.4.2_A.5 | FDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  | 100%
35 | Y | 36.521-1 Perf 6DL | 8.2.2.1.1_A.5 | TDD PDSCH Single Antenna Port Performance for CA (6DL CA) | Add test case variant for 6DL | LGE | RAN5#93 (Nov-21) |  | Remains: Applicability spec, Annex F and Annex G | 1 | 80% | 80% |  |  | 80%
36 | Y | 36.521-1 Perf 6DL | 8.2.2.3.1_A.5 | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (6DL CA) | Add test case variant for 6DL | LGE | RAN5#93 (Nov-21) |  | Remains: Applicability spec, Annex F and Annex G | 1 | 80% | 80% |  |  | 80%
37 | Y | 36.521-1 Perf 6DL | 8.2.2.4.2_A.5 | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (6DL CA) | Add test case variant for 6DL | LGE | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0%
38 | Y | 36.521-1 Perf 6DL | 8.2.3.1.1.5 | TDD FDD CA PDSCH Single Antenna Port Performance for FDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  |  |  | 100%
39 | Y | 36.521-1 Perf 6DL | 8.2.3.1.2.5 | TDD FDD CA PDSCH Single Antenna Port Performance for TDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  |  |  | 100%
40 | Y | 36.521-1 Perf 6DL | 8.2.3.2.1.5 | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for FDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  |  |  | 100%
41 | Y | 36.521-1 Perf 6DL | 8.2.3.2.2.5 | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for TDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  |  |  | 100%
42 | Y | 36.521-1 Perf 6DL | 8.2.3.3.1.5 | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for FDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  |  |  | 100%
43 | Y | 36.521-1 Perf 6DL | 8.2.3.3.2.5 | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for TDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% |  |  |  | 100%
44 | Y | 36.521-1 Perf 6DL | 8.7.1.1_A.6 | FDD Sustained data rate performance for CA (6DL CA) | Add test case variant for 6DL | Qualcomm | RAN5#91-e (May-21) | R5-194236 R5-194240 |  | 1 | 100% | 100% |  | 100%
45 | Y | 36.521-1 Perf 6DL | 8.7.1.1_H.6 | FDD Sustained data rate performance for CA (6DL CA) for 256QAM in DL | Add test case variant for 6DL | Qualcomm | RAN5#91-e (May-21) | R5-194236 R5-194240 |  | 1 | 100% | 100% |  | 100%
46 | Y | 36.521-1 Perf 6DL | 8.7.2.1_A.6 | TDD sustained data rate performance for CA (6DL CA) | Add test case variant for 6DL | SRTC | RAN5#85 (Nov-19) |  |  | 1 | 100% | 100% |  |  | 100%
47 | Y | 36.521-1 Perf 6DL | 8.7.2.1_H.6 | TDD sustained data rate performance for CA (6DL CA) for 256QAM in DL | Add test case variant for 6DL | SRTC | RAN5#85 (Nov-19) |  |  | 1 | 100% | 100% |  |  |  | 100%
48 | Y | 36.521-1 Perf 6DL | 8.7.5.1.5 | TDD FDD CA Sustained data rate performance for FDD PCell (6DL CA) | Add test case variant for 6DL | Qualcomm | RAN5#91-e (May-21) | R5-194236 R5-194240 |  | 1 | 100% | 100% |  |  |  | 100%
49 | Y | 36.521-1 Perf 6DL | 8.7.5.1_H.5 | TDD FDD CA Sustained data rate performance for FDD PCell (6DL CA) for 256QAM in DL | Add test case variant for 6DL | Qualcomm | RAN5#91-e (May-21) | R5-194236 R5-194240 |  | 1 | 100% | 100% |  |  |  | 100%
50 | Y | 36.521-1 Perf 6DL | 8.7.5.2.5 | TDD FDD CA Sustained data rate performance for TDD PCell (6DL CA) | Add test case variant for 6DL | Qualcomm | RAN5#91-e (May-21) | R5-194236 R5-194240 |  | 1 | 100% | 100% |  |  |  | 100%
51 | Y | 36.521-1 Perf 6DL | 8.7.5.2_H.5 | TDD FDD CA Sustained data rate performance for TDD PCell (6DL CA) for 256QAM in DL | Add test case variant for 6DL | Qualcomm | RAN5#91-e (May-21) | R5-194236 R5-194240 |  | 1 | 100% | 100% |  |  |  | 100%
52 | Y | 36.521-1 Perf 6DL | 9.6.1.1_A.5 | FDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (6DL CA) | Add test case variant for 6DL | Dekra | RAN5#94-e (Feb-22) | 36.521-1: R5-206896 R5-217191 R5-220675 R5-221754 36.521-2: R5-215923 |  | 1 | 100% (+20%) | 100% (+20%) |  | 100%
53 | Y | 36.521-1 Perf 6DL | 9.6.1.2_A.5 | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (6DL CA) | Add test case variant for 6DL | Dekra | RAN5#94-e (Feb-22) | 36.521-1: R5-206897 R5-217193 R5-220675 R5-221754 36.521-2: R5-216831 |  | 1 | 100% (+20%) | 100% (+20%) |  |  | 100%
54 | Y | 36.521-1 Perf 6DL | 9.6.1.3.5 | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for FDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
55 | Y | 36.521-1 Perf 6DL | 9.6.1.4.5 | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for TDD PCell (6DL CA) | Add test case variant for 6DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 36.521-3: 6DL RRM test cases
56 | Y | 36.521-3 RRM 6DL | 8.16.95 | 6DL CA Event Triggered Reporting under Deactivated SCells in Non-DRX with generic duplex modes | Add test case variant for 6DL | Bureau Veritas | RAN5#86-e (Feb-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
57 | Y | 36.521-3 RRM 6DL | 8.16.96 | 6DL CA Event Triggered Reporting on Deactivated SCell with PCell and SCell Interruptions in Non-DRX with generic duplex modes | Add test case variant for 6DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
58 | Y | 36.521-3 RRM 6DL | 8.16.97 | 6DL CA Activation and Deactivation of Known SCell in Non-DRX with generic duplex modes | Add test case variant for 6DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
59 | Y | 36.521-3 RRM 6DL | 8.16.98 | 6DL CA Activation and Deactivation of Unknown SCell in Non-DRX with generic duplex modes | Add test case variant for 6DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
60 | Y | 36.521-3 RRM 6DL | 9.1.71 | 6DL RSRP for E-UTRAN in Carrier Aggregation with generic duplex modes | Add test case variant for 6DL | Dekra | RAN5#94-e (Feb-22) | 36.521-3: R5-206898 R5-216836 R5-221755 R5-221756 36.521-2: R5-215923 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
61 | Y | 36.521-3 RRM 6DL | 9.2.58 | 6DL RSRQ for E-UTRAN in Carrier Aggregation with generic duplex modes | Add test case variant for 6DL | Dekra | RAN5#94-e (Feb-22) | 36.521-3: R5-206899 R5-215924 R5-221756 36.521-2: R5.215923 |  | 1 | 100% | 100% |  | 100% | 100% | 100%
7DL LTE CA test cases
TS 36.521-1: 7DL RF Rx test cases
62 | Y | 36.521-1 Rx 7DL | 7.3A.12 | Reference sensitivity level for 7DL CA | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
63 | Y | 36.521-1 Rx 7DL | 7.4A.10 | Maximum input level for 7DL CA | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
64 | Y | 36.521-1 Rx 7DL | 7.4A.10_H | Maximum input level for 7DL CA for 256QAM in DL | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
65 | Y | 36.521-1 Rx 7DL | 7.5A.10 | Adjacent Channel Selectivity (ACS) for 7DL CA | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
66 | Y | 36.521-1 Rx 7DL | 7.6.1A.10 | In-band blocking for 7DL CA | Add test case variant for 7DL | Tejet | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
67 | Y | 36.521-1 Rx 7DL | 7.6.2A.10 | Out-of-band blocking for 7DL CA | Add test case variant for 7DL | Tejet | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
68 | Y | 36.521-1 Rx 7DL | 7.6.3A.10 | Narrow band blocking for 7DL CA | Add test case variant for 7DL | Tejet | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
69 | Y | 36.521-1 Rx 7DL | 7.7A.10 | Spurious response for 7DL CA | Add test case variant for 7DL | Tejet | RAN5#91-e (May-21) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
70 | Y | 36.521-1 Rx 7DL | 7.8.1A.10 | Wideband intermodulation for 7DL CA | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TS 36.521-1: 7DL Demod/QSI reporting test cases
71 | Y | 36.521-1 Perf 7DL | 8.2.1.1.1_A.7 | FDD PDSCH Single Antenna Port Performance for CA (7DL CA) | Add test case variant for 7DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 90% | 90% |  | 90%
72 | Y | 36.521-1 Perf 7DL | 8.2.1.3.1_A.6 | FDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (7DL CA) | Add test case variant for 7DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 90% | 90% |  | 90%
73 | Y | 36.521-1 Perf 7DL | 8.2.1.4.2_A.6 | FDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (7DL CA) | Add test case variant for 7DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 90% | 90% |  | 90%
74 | Y | 36.521-1 Perf 7DL | 8.2.2.1.1_A.6 | TDD PDSCH Single Antenna Port Performance for CA (7DL CA) | Add test case variant for 7DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 80% | 80% |  |  | 80%
75 | Y | 36.521-1 Perf 7DL | 8.2.2.3.1_A.6 | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (7DL CA) | Add test case variant for 7DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 80% | 80% |  |  | 80%
76 | Y | 36.521-1 Perf 7DL | 8.2.2.4.2_A.6 | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (7DL CA) | Add test case variant for 7DL | LGE | RAN5#93-e (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0%
77 | Y | 36.521-1 Perf 7DL | 8.2.3.1.1.6 | TDD FDD CA PDSCH Single Antenna Port Performance for FDD PCell (7DL CA) | Add test case variant for 7DL | LGE | RAN5#90-e (Feb-21) |  |  | 1 | 100% | 100% |  |  |  | 100%
78 | Y | 36.521-1 Perf 7DL | 8.2.3.1.2.6 | TDD FDD CA PDSCH Single Antenna Port Performance for TDD PCell (7DL CA) | Add test case variant for 7DL | LGE | RAN5#90-e (Feb-21) |  |  | 1 | 100% | 100% |  |  |  | 100%
79 | Y | 36.521-1 Perf 7DL | 8.2.3.2.1.6 | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for FDD PCell (7DL CA) | Add test case variant for 7DL | LGE | RAN5#90-e (Feb-21) |  |  | 1 | 100% | 100% |  |  |  | 100%
80 | Y | 36.521-1 Perf 7DL | 8.2.3.2.2.6 | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for TDD PCell (7DL CA) | Add test case variant for 7DL | LGE | RAN5#90-e (Feb-21) |  |  | 1 | 100% | 100% |  |  |  | 100%
81 | Y | 36.521-1 Perf 7DL | 8.2.3.3.1.6 | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for FDD PCell (7DL CA) | Add test case variant for 7DL | LGE | RAN5#90-e (Feb-21) |  |  | 1 | 100% | 100% |  |  |  | 100%
82 | Y | 36.521-1 Perf 7DL | 8.2.3.3.2.6 | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for TDD PCell (7DL CA) | Add test case variant for 7DL | LGE | RAN5#90-e (Feb-21) |  |  | 1 | 100% | 100% |  |  |  | 100%
83 | Y | 36.521-1 Perf 7DL | 8.7.1.1_A.7 | FDD Sustained data rate performance for CA (7DL CA) | Add test case variant for 7DL | SRTC | RAN5#87-e (May-20) |  |  | 1 | 100% | 100% |  | 100%
84 | Y | 36.521-1 Perf 7DL | 8.7.1.1_H.7 | FDD Sustained data rate performance for CA (7DL CA) for 256QAM in DL | Add test case variant for 7DL | SRTC | RAN5#87-e (May-20) |  |  | 1 | 100% | 100% |  | 100%
85 | Y | 36.521-1 Perf 7DL | 8.7.2.1_A.7 | TDD sustained data rate performance for CA (7DL CA) | Add test case variant for 7DL | SRTC | RAN5#87-e (May-20) |  |  | 1 | 100% | 100% |  |  | 100%
86 | Y | 36.521-1 Perf 7DL | 8.7.2.1_H.7 | TDD sustained data rate performance for CA (7DL CA) for 256QAM in DL | Add test case variant for 7DL | SRTC | RAN5#87-e (May-20) |  |  | 1 | 100% | 100% |  |  | 100%
87 | Y | 36.521-1 Perf 7DL | 8.7.5.1.6 | TDD FDD CA Sustained data rate performance for FDD PCell (7DL CA) | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
88 | Y | 36.521-1 Perf 7DL | 8.7.5.1_H.6 | TDD FDD CA Sustained data rate performance for FDD PCell (7DL CA) for 256QAM in DL | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
89 | Y | 36.521-1 Perf 7DL | 8.7.5.2.6 | TDD FDD CA Sustained data rate performance for TDD PCell (7DL CA) | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
90 | Y | 36.521-1 Perf 7DL | 8.7.5.2_H.6 | TDD FDD CA Sustained data rate performance for TDD PCell (7DL CA) for 256QAM in DL | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
91 | Y | 36.521-1 Perf 7DL | 9.6.1.1_A.6 | FDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (7DL CA) | Add test case variant for 7DL | Dekra | RAN5#94-e (Feb-22) | 36.521-1: R5-220675 R5-221754 36.521-2: R5-216831 |  | 1 | 100% (+30%) | 100% (+30%) |  | 100%
92 | Y | 36.521-1 Perf 7DL | 9.6.1.2_A.6 | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (7DL CA) | Add test case variant for 7DL | Dekra | RAN5#94-e (Feb-22) | 36.521-1: R5-220675 R5-221754 36.521-2: R5-216831 |  | 1 | 100% (+30%) | 100% (+30%) |  |  | 100%
93 | Y | 36.521-1 Perf 7DL | 9.6.1.3.6 | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for FDD PCell (7DL CA) | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
94 | Y | 36.521-1 Perf 7DL | 9.6.1.4.6 | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for TDD PCell (7DL CA) | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 36.521-3: 7DL RRM test cases
95 | Y | 36.521-3 RRM 7DL | 8.16.99 | 7DL CA Event Triggered Reporting under Deactivated SCells in Non-DRX with generic duplex modes | Add test case variant for 7DL | Bureau Veritas | RAN5#86-e (Feb-20) |  |  | 1 | 100% | 100% |  | 100% | 100% | 100%
96 | Y | 36.521-3 RRM 7DL | 8.16.100 | 7DL CA Event Triggered Reporting on Deactivated SCell with PCell and SCell Interruptions in Non-DRX with generic duplex modes | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
97 | Y | 36.521-3 RRM 7DL | 8.16.101 | 7DL CA Activation and Deactivation of Known SCell in Non-DRX with generic duplex modes | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
98 | Y | 36.521-3 RRM 7DL | 8.16.102 | 7DL CA Activation and Deactivation of Unknown SCell in Non-DRX with generic duplex modes | Add test case variant for 7DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
99 | Y | 36.521-3 RRM 7DL | 9.1.72 | 7DL RSRP for E-UTRAN in Carrier Aggregation with generic duplex modes | Add test case variant for 7DL | Dekra | RAN5#94-e (Feb-22) | 36.521-3: R5-211753 R5-216837 R5-221755 R5-221756 36.521-2: R5-216831 |  | 1 | 100% (+20%) | 100% (+20%) |  | 100% | 100% | 100%
100 | Y | 36.521-3 RRM 7DL | 9.2.59 | 7DL RSRQ for E-UTRAN in Carrier Aggregation with generic duplex modes | Add test case variant for 7DL | Dekra | RAN5#94-e (Feb-22) | 36.521-3: R5-211754 R5-221755 R5-221756 36.521-2: R5-216831 |  | 1 | 100% (+20%) | 100% (+20%) |  | 100% | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.