## Summary
Work plan summary:
Rel-15 5GC Protocol Test Cases (TS 38.523-1)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Rel-15 5GC Protocol Test Cases (TS 38.523-1) | SA Option 2 (SA NR) | 99.92% | 100% | 99.83%
NSA Option 3 (EN-DC)
SA Option 5
|  | NSA Option 4 (NE-DC) | Implicitly covered by SA NR test cases
NSA Option 7 (NGEN-DC)
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of test cases applicable for FR1+FR2
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| Rel-15 5GC Protocol Test Cases (TS 38.523-1) | SA Option 2 (SA NR) | 57 | 57 | 57 | 57 | 57 | 56 | 0 | 0
NSA Option 3 (EN-DC)
SA Option 5
|  | NSA Option 4 (NE-DC) | Implicitly covered by SA NR test cases
NSA Option 7 (NGEN-DC)

## Protocol 5GC
WP Title: | Rel-15 5GC Protocol Test Cases (TS 38.523-1) | [11 empty] | WP item applicability | [10 empty] | End of work plan columns. Note! Do not remove this column. | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
[13 empty] | RAN-CN interface options dependency | [11 empty] | WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan section covers the 5GC protocol test cases for SA option 2 and 5 and NSA options 4 and 7. | [11 empty] | 5GC/NR |  |  |  | 5GC/LTE | EPC/LTE | 5GC/NR master |  |  |  | 5GC / LTE master
WP Resp: | Xiaozhong Chen, CATT |  |  |  | chenxiaozhong@catt.cn
TS Resp: | Stoyan Baev, Samsung |  |  |  | stoyan.baev@partner.samsung.com | [7 empty] | SA |  |  |  |  | NSA
[13 empty] | Opt.2 |  |  |  | Opt. 5 | Opt.3 | Opt.4 |  |  |  | Opt. 7
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. |  |  | FR1 | FR2 | FR1+FR2 |  |  |  | FR1 | FR2 | FR1+FR2 |  |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[25 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[14 empty] | 99.92% | [5 empty] | NE-DC implicitly covered by SA NR test cases
[11 empty] | Overall |  |  | 100% | 99.83%
[7 empty] | Overall #WP items: Post WI close #WP items: | [6 empty] | 59 0 | 59 1 | 0 0 | 0 0 |  |  | 0 0 | 0 0 | 0 0 | 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS mobility management
|  | 38.523-1 | 9.1 | 5GS mobility management | New sub-clause | [13 empty] | 1
|  | 38.523-1 | 9.1.1 | Primary authentication and key agreement | New sub-clause
1 | Y | 38.523-1 | 9.1.1.1 | EAP based primary authentication and key agreement / EAP-AKA' related procedures | **** TP1: [TS 24,501:5.4.1.2.2.6B] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends an EAP-Request/AKA'-Identity message within AUTHENTICATION REQUEST THEN: the UE sends an EAP-Response/AKA'-Identity message within AUTHENTICATION RESPONSE **** TP2: [TS 24,501:5.4.1.2.2.4] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST with the sequence number in AUTN is not correct THEN: the UE sends an EAP-response/AKA'-synchronization-failure message within AUTHENTICATION RESPONSE **** TP3: [TS 24,501:5.4.1.2.2.3] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends an EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST THEN: the UE sends an EAP-response/AKA'-challenge message within AUTHENTICATION RESPONSE **** TP4: [TS 24,501:5.4.1.2.2.8] WITH: the UE in 5GMM-REGISTERED-INITIATED state and SS initiates an EAP based primary authentication and key agreement procedure WHEN: the SS sends an EAP-success message within AUTHENTICATION RESULT THEN: the UE considers the procedure complete and authenctication procedure succeed | CMCC | Opt 2: RAN5#86 (Feb-20) | R5-192392 R5-197292 R5-198235 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
115 | Y | 38.523-1 | 9.1.1.2 | EAP based primary authentication and key agreement / Reject | **** TP1: [TS 24,501:5.4.1.2.2.4] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST with the SNN check fails THEN: the UE sends an EAP-response/AKA'-authentication-reject message within AUTHENTICATION RESPONSE **** TP2: [TS 24,501:5.4.1.2.2.6] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends an EAP-Request/AKA'-notification message within AUTHENTICATION REQUEST THEN: the UE sends an EAP-Response/AKA'-notification message within AUTHENTICATION RESPONSE **** TP3: [TS 24,501:5.4.1.2.2.11] WITH: the UE in 5GMM-REGISTERED-INITIATED state and SS initiates an EAP based primary authentication and key agreement procedure WHEN: the SS sends an an EAP-failure message within AUTHENTICATION REJECT THEN: the UE deletes the stored 5G-GUTI, last visited registered TAI and ngKSI and enter state 5GMM-DEREGISTERED, the USIM is considered invalid until switching off the UE | Tejet/ZTE | Opt 2: RAN5#86 (Feb-20) | R5-192800 R5-197297 R5-198242 R5-201142 R5-205579 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
3 | Y | 38.523-1 | 9.1.1.3 | EAP based primary authentication and key agreement / EAP message transport / Abnormal | **** TP1: [TS 24,501:5.4.1.2.4.5 a)] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST with ngKSI is already in use THEN: the UE sends an AUTHENTICATION FAILURE message with 5GMM cause #71 "ngKSI already in use" **** TP2: [TS 24,501:5.4.1.2.4.5 e)] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the third time SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST with ngKSI is already in use THEN: the UE locally releases the RRC connection and treats the active cell as barred **** TP3: [TS 24,501:5.4.1.2.4.5 e)] WITH: the UE in 5GMM-REGISTERED-INITIATED state, the SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST with ngKSI is already in use and the UE sends an AUTHENTICATION FAILURE message WHEN: T3520 times out THEN: the UE locally releases the RRC connection and treats the active cell as barred **** TP4: [TS 24,501:5.4.1.2.4.5 c)] Editor's note: Transmission failure WITH: the UE in 5GMM-REGISTERED state and 5GMM-IDLE mode over 3GPP access, starts SERVICE REQUEST procedure after received a paging request from the network WHEN: the SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST and the UE fails on transmission of AUTHENTICATION RESPONSE message by entering a cell with TAI not in the TAI list THEN: the UE initiates a mobility registration update procedure **** TP5: [TS 24,501:5.4.1.2.4.5 b)] Editor's note: Transmission failure WITH: the UE in 5GMM-REGISTERED state and initiates a mobility registration update procedure WHEN: the SS sends the EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST and the UE fails on transmission of AUTHENTICATION RESPONSE message with the indication from lower layers THEN: the UE re-initiate the mobility registration update procedure | CMCC | Opt 2: RAN5#86 (Feb-20) | R5-192393 R5-197102 R5-200616 R5-202655 R5-206349 R5-220454 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
4 | Y | 38.523-1 | 9.1.1.4 | 5G AKA based primary authentication and key agreement / 5G-AKA related procedures | **** TP1: [TS 24,501:5.4.1.3.7 c)] Editor's note: MAC code failure WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST with invalid MAC code THEN: the UE sends an AUTHENTICATION FAILURE message to the network, with the 5GMM cause #20 "MAC failure". **** TP2: [TS 24,501:5.4.1.3.7 d)] Editor's note: Non-5G authentication unacceptable WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST with the "separation bit" in the AMF field of AUTN supplied by the core network is set to 0 THEN: the UE sends an AUTHENTICATION FAILURE message to the network, with the 5GMM cause #26 "non-5G authentication unacceptable". **** TP3: [TS 24,501:5.4.1.3.7 f)] Editor's note: synch failure WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST with the sequence number SQN to be out of range THEN: the UE sends an AUTHENTICATION FAILURE message to the network, with the 5GMM cause #21 "synch failure" and a re-synchronization token AUTS provided by the USIM. **** TP4: [TS 24,501:5.4.1.3.3] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST THEN: the UE process the 5G authentication challenge data and respond with an AUTHENTICATION RESPONSE message **** TP5: [TS 24,501:5.4.1.3.3] WITH: the UE in 5GMM-REGISTERED-INITIATED state and sends out an AUTHENTICATION RESPONSE message WHEN: the SS proceeds with the registration procedure THEN: the UE consider the authentication procedure complete and succeed | Spreadtrum | Opt 2: RAN5#84 (Aug-19) | R5-197217 |  | 1 | 90% |  | 4 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
5 | Y | 38.523-1 | 9.1.1.5 | 5G AKA based primary authentication and key agreement / Reject | **** TP1: [TS 24,501:5.4.1.3.5] WITH: the UE in 5GMM-REGISTERED-INITIATED state and SS initiates a 5G AKA based primary authentication and key agreement procedure WHEN: the SS sends an a AUTHENTICATION REJECT message THEN: the UE deletes the stored 5G-GUTI, last visited registered TAI and ngKSI and enter state 5GMM-DEREGISTERED, the USIM is considered invalid until switching off the UE | Keysight | Opt 2: RAN5#85 (Nov-19) | R5-198937 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
6 | Y | 38.523-1 | 9.1.1.6 | 5G AKA based primary authentication and key agreement / Abnormal | **** TP1: [TS 24,501:5.4.1.3.7 e)] Editor's note: ngKSI already in use WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST with ngKSI is already in use THEN: the UE sends an AUTHENTICATION FAILURE message to the network, with the 5GMM cause #71 "ngKSI already in use". **** TP2: [TS 24,501:5.4.1.3.7 g), k)] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the third time SS initiates 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST with ngKSI is already in use THEN: the UE locally releases the RRC connection and treats the active cell as barred **** TP3: [TS 24,501:5.4.1.3.7 g)] WITH: the UE in 5GMM-REGISTERED-INITIATED state, the SS sends an AUTHENTICATION REQUEST with ngKSI is already in use and the UE sends an AUTHENTICATION FAILURE message WHEN: T3520 times out THEN: the UE locally releases the RRC connection and treats the active cell as barred **** TP4: [TS 24,501:5.4.1.3.7 i)] WITH: the UE in 5GMM-REGISTERED state and 5GMM-IDLE mode over 3GPP access, starts SERVICE REQUEST procedure after received a paging request from the network WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST and the UE fails on transmission of AUTHENTICATION RESPONSE message by entering a cell with TAI not in the TAI list THEN: the UE initiates a mobility registration update procedure **** TP5: [TS 24,501:5.4.1.3.7 h)] WITH: the UE in 5GMM-REGISTERED state and initiates a mobility registration update procedure WHEN: the SS initiates a 5G AKA based primary authentication and key agreement procedure by sending AUTHENTICATION REQUEST and the UE fails on transmission of AUTHENTICATION RESPONSE message with the indication from lower layers THEN: the UE re-initiate the mobility registration update procedure | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-192801 R5-197077 R5-198936 R5-201084 R5-206350 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.2 | Security mode control | New sub-clause
7 | Y | 38.523-1 | 9.1.2.1 | NAS security mode command | **** TP1: [TS 24,501:5.4.2.3] WITH: the UE is in 5GMM-REGISTERED-INITIATED state and the SS initiates the NAS security mode control procedure by sending a SECURITY MODE COMMAND message during initial registration procedure WHEN: the SS sends an integrity protected SECURITY MODE COMMAND message including not matching replayed security capabilities THEN: the UE sends a SECURITY MODE REJECT message and does not start applying the NAS security in both UL and DL **** TP2: [TS 24,501:5.4.2.3] WITH: the UE is in 5GMM-REGISTERED-INITIATED state and the SS initiates the NAS security mode control procedure by sending a SECURITY MODE COMMAND message during initial registration procedure WHEN: the UE receives an integrity protected SECURITY MODE COMMAND message including IMEISV request THEN: the UE send an integrity protected and ciphered SECURITY MODE COMPLETE message including IMEISV and starts applying the NAS Security in both UL and DL | CATT/TDIA | Opt 2: RAN5#82 (Feb-19) | R5-192815 R5-194857 R5-198939 R5-202656 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
118 | Y | 38.523-1 | 9.1.2.2 | Protection of initial NAS signalling messages | **** TP1: [TS 24,501:2006-04-04] WITH: the UE is switched-off with no a valid 5G NAS security context WHEN: the UE is switchd on THEN: the UE sends a REGISTRATION REQUEST message including cleartext IEs only **** TP2: [TS 24,501:2006-04-04] WITH: the UE is in 5GMM-REGISTERED-INITIATED state WHEN: the UE is activating a 5G NAS security context resulting from a security mode control procedure THEN: the UE sends SECURITY MODE COMPLETE message with the entire REGISTRATION REQUEST message | Ericsson | Opt 2: RAN5#82 (Feb-19) | R5-192399 R5-194481 R5-197078 R5-201085 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
127 | Y | 38.523-1 | 9.1.2.3 | Integrity protection / Correct functionality of 5G NAS integrity algorithm / SNOW3G | **** TP1: [TS 24,501:4.4.4] WITH: successful completion of 5G authentication and key agreement (AKA) procedure WHEN: UE receives a an integrity protected SECURITY MODE COMMAND message instructing to start integrity protection using algorithm SNOW3G THEN: UE transmits an integrity protected SECURITY MODE COMPLETE using SNOW3G and starts applying the NAS Integrity protection in both UL and DL **** TP2: [TS 24,501:4.4.4] WITH: Integrity protection successful started by executing Security Mode Procedure WHEN: UE receives a IDENTITY REQUEST message (requested identification parameter is not SUCI), without integrity protected THEN: UE does not transmit IDENTITY Response | CATT/TDIA | Opt 2: RAN5#85 (Nov-19) | R5-198006 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
128 | Y | 38.523-1 | 9.1.2.4 | Integrity protection / Correct functionality of 5G NAS integrity algorithm / AES | **** TP1: [TS 24,501:4.4.4] WITH: successful completion of 5G authentication and key agreement (AKA) procedure WHEN: UE receives a an integrity protected SECURITY MODE COMMAND message instructing to start integrity protection using algorithm AES THEN: UE transmits an integrity protected SECURITY MODE COMPLETE using AES and starts applying the NAS Integrity protection in both UL and DL **** TP2: [TS 24,501:4.4.4] WITH: Integrity protection successful started by executing Security Mode Procedure WHEN: UE receives a IDENTITY REQUEST message (requested identification parameter is not SUCI), without integrity protected THEN: UE does not transmit IDENTITY Response | CATT/TDIA | Opt 2: RAN5#85 (Nov-19) | R5-198940 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
129 | Y | 38.523-1 | 9.1.2.5 | Integrity protection / Correct functionality of 5G NAS integrity algorithm / ZUC | **** TP1: [TS 24,501:4.4.4] WITH: successful completion of 5G authentication and key agreement (AKA) procedure WHEN: UE receives a an integrity protected SECURITY MODE COMMAND message instructing to start integrity protection using algorithm ZUC THEN: UE transmits an integrity protected SECURITY MODE COMPLETE using ZUC and starts applying the NAS Integrity protection in both UL and DL **** TP2: [TS 24,501:4.4.4] WITH: Integrity protection successful started by executing Security Mode Procedure WHEN: UE receives a IDENTITY REQUEST message (requested identification parameter is not SUCI), without integrity protected THEN: UE does not transmit IDENTITY Response | CATT/TDIA | Opt 2: RAN5#85 (Nov-19) | R5-198941 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
130 | Y | 38.523-1 | 9.1.2.6 | Ciphering and deciphering / Correct functionality of 5G NAS encryption algorithm / SNOW3G | **** TP1: [TS 24,501:4.4.4] WITH: successful completion of 5G authentication and key agreement (AKA) procedure WHEN: UE receives a SECURITY MODE COMMAND instructing to start ciphering using algorithm SNOW3G THEN: UE sends a SECURITY MODE COMPLETE message ciphered with SNOW3G and starts applying the NAS ciphering in both UL and DL | CATT/TDIA | Opt 2: RAN5#85 (Nov-19) | R5-198944 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
131 | Y | 38.523-1 | 9.1.2.7 | Ciphering and deciphering / Correct functionality of 5G NAS encryption algorithm / AES | **** TP: [TS 24,501:4.4.4] WITH: successful completion of 5G authentication and key agreement (AKA) procedure WHEN: UE receives a SECURITY MODE COMMAND instructing to start ciphering using algorithm AES THEN: UE sends a SECURITY MODE COMPLETE message ciphered with AES and starts applying the NAS ciphering in both UL and DL | CATT/TDIA | Opt 2: RAN5#85 (Nov-19) | R5-198942 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
132 | Y | 38.523-1 | 9.1.2.8 | Ciphering and deciphering / Correct functionality of 5G NAS encryption algorithm / ZUC | **** TP: [TS 24,501:4.4.4] WITH: successful completion of 5G authentication and key agreement (AKA) procedure WHEN: UE receives a SECURITY MODE COMMAND instructing to start ciphering using algorithm ZUC THEN: UE sends a SECURITY MODE COMPLETE message ciphered with ZUC and starts applying the NAS ciphering in both UL and DL | CATT/TDIA | Opt 2: RAN5#85 (Nov-19) | R5-198943 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.3 | Identification | New sub-clause
100 | Y | 38.523-1 | 9.1.3.1 | Identification procedure | **** TP1: [TS 24,501:5.4.3.5] WITH: The UE is in 5GMM-REGISTERED-INITIATED state and the SS sends an IDENTITY REQUEST message WHEN: UE detects transmission failure of IDENTITY RESPONSE message THEN: The UE re-initiates the Initial registration procedure **** TP2: [TS 24,501:5.4.3.5] WITH: The UE is in 5GMM-CONNECTED mode and the SS sends an IDENTITY REQUEST message WHEN: The UE receives the unprotected IDENTITY REQUEST message with identity type as SUCI THEN: UE transmits the IDENTITY RESPONSE message with identity type set to SUCI **** TP3: [TS 24,501:5.4.3.5] WITH: The UE is in 5GMM-CONNECTED mode and the SS sends an IDENTITY REQUEST message WHEN: the UE receives an IDENTITY REQUEST with identity type set as IMEISV THEN: UE transmits an IDENTITY RESPONSE with identity type set as IMEISV **** TP4: [TS 24,501:5.4.3.5] WITH: The UE is in 5GMM-CONNECTED mode and the SS sends an IDENTITY REQUEST message WHEN: the UE receives an IDENTITY REQUEST with identity type set as “IMEI” THEN: UE transmits an IDENTITY RESPONSE with identity type set as “IMEI” **** TP5: [TS 24,501:5.4.3.5] WITH: The UE is in 5GMM-CONNECTED mode and the SS sends an IDENTITY REQUEST message WHEN: the UE receives an IDENTITY REQUEST with identity type set as “5G-GUTI” and has no valid 5G-GUTI available THEN: UE transmits an IDENTITY RESPONSE with identity type set as “No identity” | R&S | Opt 2: RAN5#82 (Feb-19) | R5-192389 R5-194858 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.4 | Generic UE configuration update | New sub-clause
10 | Y | 38.523-1 | 9.1.4.1 | Generic UE configuration update / New 5G-GUTI, NITZ, registration requested, network slicing indication, new allowed NSSAI / Acknowledgement from the UE | **** TP1: [TS 24,501:5.4.4.3] WITH: UE in 5GMM-REGISTERED state WHEN: UE receives a new 5G-GUTI in the CONFIGURATION UPDATE COMMAND message and acknowledgement from the UE is requested THEN: UE sends a CONFIGURATION UPDATE COMPLETE message and UE shall consider new 5G-GUTI as valid **** TP2: [TS 24,501:5.4.4.3] WITH: UE in 5GMM-REGISTERED state WHEN: UE receives a NITZ information in the CONFIGURATION UPDATE COMMAND message and acknowledgement from the UE is not requested THEN: UE updates NITZ information **** TP3: [TS 24,501:5.4.4.3] WITH: UE in 5GMM-REGISTERED state WHEN: UE receives CONFIGURATION UPDATE COMMAND message indicating “registration requested” and contains no other parameters THEN: UE deletes any stored allowed NSSAI for this PLMN and then release the existing N1 NAS signalling connection, starts a mobility registration procedure **** TP4: [TS 24,501:5.4.4.3] WITH: UE in 5GMM-REGISTERED state WHEN: UE receives a new allowed NSSAI in the CONFIGURATION UPDATE COMMAND message and registration is not requested THEN: UE replaces any stored allowed NSSAI for this PLMN with new allowed NSSAI **** TP5: [TS 24,501:5.4.4.3] WITH: UE in 5GMM-REGISTERED state WHEN: UE receives a Network Slicing subscription change indication set to "Network slicing subscription changed" in the CONFIGURATION UPDATE COMMAND message and registration is not requested THEN: UE deletes the network slicing information for each and every PLMN except for the current PLMN and default configured NSSAI | Qualcomm | Opt 2: RAN5#93 (Nov-21) | R5-195209 R5-198147 R5-198186 R5-201143 R5-202657 R5-205383 R5-216482 R5-221451 R5-220549 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.5 | Registration | New sub-clause
|  | 38.523-1 | 9.1.5.1 | Initial registration | New sub-clause
12 | Y | 38.523-1 | 9.1.5.1.1 | Initial registration / Success / 5G-GUTI reallocation, last visited TAI | **** TP1: [TS 24,501:5.5.1.2.2] WITH: the UE is 5GMM-REGISTERED state with no valid 5G-GUTI but available SUCI WHEN: the UE is switched off and switched on THEN: the UE sends a REGISTRATION REQUEST message including the SUCI in the 5GS mobile identity IE **** TP2: [TS 24,501:5.5.1.2.2] WITH: the UE is 5GMM-REGISTERED state with a cell belong to a non-equivalent PLMN with assigned 5G-GUTI and last visited registered TAI WHEN: the UE is switched off and switched on with a cell belong to another PLMN THEN: the UE sends a REGISTRATION REQUEST message including the 5G-GUTI assigned by the last PLMN in the 5GS mobile identity IE and the last visited registered TAI **** TP3: [TS 24,501:5.5.1.2.2] WITH: the UE is 5GMM-REGISTERED state with a cell belong to an equivalent PLMN with assigned 5G-GUTI WHEN: the UE is switched off and switched on with a cell belong to another PLMN THEN: the UE sends a REGISTRATION REQUEST message including the 5G-GUTI assigned by the equivalent PLMN in the 5GS mobile identity IE **** TP4: [TS 24,501:5.5.1.2.2] WITH: the UE is 5GMM-REGISTERED state with an assigned 5G-GUTI WHEN: the UE is switched off and switched on with a cell belong to the same PLMN THEN: the UE sends a REGISTRATION REQUEST message including the 5G-GUTI assigned by the last registered PLMN in the 5GS mobile identity IE | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-188159 R5-190698 R5-194859 R5-197079 R5-200254 R5-203412 R5-215404 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
13 | Y | 38.523-1 | 9.1.5.1.2 | Initial registration / 5GS services / Equivalent PLMN list handling | **** TP1: [TS 24,501:5.5.1.2.4] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends REGISTRATION ACCEPT message included a new set of equivalent PLMNs THEN: the UE replaces the old equivalent PLMN list with the new equivalent PLMN list **** TP2: [TS 24,501:5.5.1.2.4] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends REGISTRATION ACCEPT message that does not include a EPLMN list THEN: the UE deletes the old EPLMN list **** TP3: [TS 24,501:5.5.1.3.4] WITH: the UE in 5GMM-REGISTERED state the SS sending REGISTRATION ACCEPT message that include a EPLMN list WHEN: the UE detects that an entry in EPLMN list Is also present in FPLMN list and no emergency PDU session is established THEN: the UE deletes PLMN Id from the EPLMN list that is present in FPLMN list | R&S | Opt 2: RAN5#86 (Feb-20) | R5-195211 R5-197085 R5-201086 R5-201372 R5-206353 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
14 | Y | 38.523-1 | 9.1.5.1.3 | Initial registration / 5GS services / NSSAI handling | **** TP1: [TS 24,501:5.5.1.2.2] WITH: UE is switched off with a valid USIM inserted WHEN: UE receives REGISTRATION ACCEPT message with allowed NSSAI THEN: UE shall replace any stored allowed NSSAI for the current PLMN with new allowed NSSAI for the current PLMN **** TP2: [TS 24,501:5.5.1.2.2] WITH: UE has sent a REGISTRATION REQUEST message including Requested NSSAI WHEN: UE receives REGISTRATION ACCEPT message with Rejected NSSAI with reject casue “S-NSSAI not available in the current PLMN” THEN: UE shall add the rejected S-NSSAI(s) in the rejected NSSAI for the current PLMN and not attempt to use the Rejected NSSAI in the current PLMN until switching off the UE or the UICC containing the USIM is removed **** TP3: [TS 24,501:5.5.1.2.2] WITH: UE receives REGISTRATION ACCEPT message with Rejected NSSAI with reject casue “S-NSSAI not available in the current PLMN” WHEN: UE has been switched off, then switched on THEN: UE shall delete the stored Rejected NSAAI and shall send the NSSAI in Requested NSSAI IE of the REGISTRATION REQUEST message as per the configured and Allowed NSSAI for current PLMN **** TP4: [TS 24,501:5.5.1.2.4] WITH: UE has sent a REGISTRATION REQUEST message including Requested NSSAI WHEN: UE receives REGISTRATION ACCEPT message with Rejected NSSAI with reject casue “S-NSSAI not available in the current registration area” THEN: UE shall add the rejected S-NSSAI(s) in the rejected NSSAI for the current PLMN and registration area combination and not attempt to use the Rejected NSSAI in the current registration area until switching off the UE, the UE moving out of the current registration area or the UICC containing the USIM is removed **** TP5: [TS 24,501:5.5.1.2.4] WITH: UE receives REGISTRATION ACCEPT message with Rejected NSSAI with reject casue “S-NSSAI not available in the current registration area” WHEN: UE has been moved out of the current registration area THEN: UE shall delete the stored Rejected NSAAI for the current PLMN as well as registration area combination and shall send the NSSAI in Requested NSSAI IE of the REGISTRATION REQUEST message as per the configured and Allowed NSSAI for current PLMN | Qualcomm | Opt 2: RAN5#93 (Nov-21) | R5-192390 R5-198951 R5-200680 R5-202658 R5-206352 R5-216483 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
126 | Y | 38.523-1 | 9.1.5.1.3a | Initial registration / 5GS services / NSSAI handling / NSSAI storage | **** TP1: [TS <TS#1>:FFS] WITH: UE is switched off with a valid USIM inserted WHEN: UE has configured NSSAI associated with HPLMN, configured NSSAI associated with a current PLMN with mapping to the Configured NSSAI for the HPLMN and UE is powered up or switched on THEN: UE transmits REGISTRATION REQUEST message with Requested NSSAI using the configured NSSAI associated with current PLMN and mapping of each S-NSSAI of the requested NSSAI to the S-NSSAIs of the configured NSSAI for the HPLMN **** TP2: [TS <TS#1>:FFS] WITH: UE is switched off with a valid USIM inserted WHEN: UE has neither allowed NSSAI for the current PLMN nor configured NSSAI for the current PLMN and has a default configured NSSAI and UE is powered up or switched on THEN: UE transmits REGISTRATION REQUEST message with Requested NSSAI using the default configured NSSAI and also includes Network slicing indication IE with the Default configured NSSAI indication bit set to "Requested NSSAI created from default configured NSSAI" **** TP3: [TS <TS#1>:FFS] WITH: UE is switched off with a valid USIM inserted WHEN: UE has no allowed NSSAI for the current PLMN, no configured NSSAI for the current PLMN, and no configured NSSAI not associated with a PLMN and UE is powered up or switched on THEN: UE transmits REGISTRATION REQUEST message and does not include a Requested NSSAI | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-197267 R5-198189 R5-215716 |  | 1 | 90% |  | 4 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
119 | Y | 38.523-1 | 9.1.5.1.4 | Initial registration / 5GS services / MICO mode / TAI list handling | **** TP1: [TS 24,501:5.5.1.2.2] WITH: the UE is in 5GMM-DEREGISTERED and is switched off WHEN: the UE supports MICO mode and requests the use of MICO mode THEN: the UE includes the MICO indication IE in the REGISTRATION REQUEST message **** TP2: [TS 24,501:5.5.1.2.4] WITH: the UE receiving REGISTRATION ACCEPT message WHEN: the REGISTRATION ACCEPT message included an MICO indication IE indicating "all PLMN registration area allocated" THEN: the UE treats all TAIs in the current PLMN as a registration area and deletes its old TAI list **** TP3: [TS 24,501:5.5.1.2.4] WITH: The UE detecting a better NG cell in same PLMN WHEN: the UE treats all TAIs in the current PLMN as a registration area and has deleted its old TAI list as a result of REGISTRATION ACCEPT message included MICO indication IE indicating “all PLMN registration area allocated” THEN: the UE does not perform the REGISTRATION procedure for mobility **** TP4: [TS 24,501:5.5.1.2.4] WITH: The UE detecting a better NG cell in a different PLMN WHEN: the UE transmits the REGISTRATION REQUEST THEN: the UE sets the IE 5GS registration type to “mobility registration updating” and performs a REGISTRATION procdure for Mobility | R&S | Opt 2: RAN5#93 (Nov-21) | R5-192388 R5-216484 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
17 | Y | 38.523-1 | 9.1.5.1.5 | Initial registration / Abnormal / Failure after 5 attempts | **** TP1: [TS 24,501:5.5.1.2.7] WITH: The UE in 5GMM-REGISTERED-INITIATED state and T3510 timer expired WHEN: T3511 timer expires and registration attempt counter is less than 5 THEN: UE restarts the initial registration procedure **** TP2: [TS 24,501:5.5.1.2.7] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives lower layer failure before the REGISTRATION ACCEPT or REGISTRATION REJECT message is received THEN: UE restarts the initial registration procedure **** TP3: [TS 24,501:5.5.1.2.7] WITH: The UE has sent initial REGISTRAION REQUEST message WHEN: UE receives a REGISTRATION REJECT message including 5GMM cause value #95 THEN: UE deletes 5G-GUTI, last visited TAI and ngKSI, performs a PLMN selection after timer T3502 timeout | MediaTek | Opt 2: RAN5#82 (Feb-19) | R5-192391 R5-195350 R5-196355 R5-198952 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
18 | Y | 38.523-1 | 9.1.5.1.6 | Initial registration / Rejected / Illegal UE | **** TP1: [TS 24,501:5.5.1.2.5] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #3 (Illegal UE) THEN: the UE deletes the stored 5G-GUTI, last visited registered TAI and ngKSI, deletes the list of equivalent PLMNs and enter state 5GMM-DEREGISTERED, the USIM is considered invalid until switching off the UE | Starpoint | Opt 2: RAN5#83 (May-19) | R5-194448 R5-198325 |  | 1 | 90% |  | 3 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
24 |  | 38.523-1 | 9.1.5.1.7 | Void | **** TP1: [] WITH: WHEN: THEN: | CATT/TDIA |  | R5-192394 R5-193898 |  | 0 |  |  | 2 |  |  |  | 1 | 1 |  |  |  |  | 2
104 | Y | 38.523-1 | 9.1.5.1.8 | Initial registration / Rejected / Serving network not authorized | **** TP1: [TS 24,501:5.5.1.2.5] WITH: the UE has sent initial REGISTRAION REQUEST message WHEN: the UE receives a REGISTRATION REJECT with cause #73 (Serving network not authorized THEN: the UE stores the PLMN identity in the "forbidden PLMN list" and does not attmept to register on a cell belong to that PLMN | CATT/TDIA | Opt 2: RAN5#93 (Nov-21) | R5-192396 R5-201002 R5-203413 R5-205866 R5-210191 R5-214548 R5-217816 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
102 | Y | 38.523-1 | 9.1.5.1.9 | Initial registration / Abnormal / Change of cell into a new tracking area | **** TP1: [TS 24,501:5.5.1.2.7 h) i)] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the UE receives transmission failure of REGISTRATION COMPLETE message indication with TAI change from lower layers THEN: the UE restarts the registration procedure with 5G-GUTI allocated during the last registration procedure | Starpoint | Opt 2: RAN5#86 (Feb-20) | R5-195208 R5-197081 R5-198299 R5-201087 R5-202659 R5-204460 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
19 | Y | 38.523-1 | 9.1.5.1.10 | Initial registration / Rejected / PLMN not allowed | **** TP1: [TS 24,501:5.5.1.2.5] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #11 (PLMN not allowed) THEN: the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, deletes the list of equivalent PLMNs, stores the PLMN identity in the "forbidden PLMN list" and performs a PLMN selection. | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-192383 R5-195681 R5-198948 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
20 | Y | 38.523-1 | 9.1.5.1.11 | Initial registration / Rejected / Tracking area not allowed | **** TP1: [TS 24,501:] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #12 (Tracking area not allowed) THEN: the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, stores the current TAI in the list of "5GS forbidden tracking areas for regional provision of service". **** TP2: [TS 24,501:] WITH: the UE is in 5GMM-DEREGISTERED.LIMITED-SERVICE state and the TAI of the current cell belongs to the list of "forbidden tracking areas for regional provision of service" WHEN: the UE enters a cell belonging to a tracking area not in the list of "forbidden tracking areas for regional provision of service" THEN: the UE attempts to registration **** TP3: [TS 24,501:] WITH: the UE is in 5GMM-DEREGISTERED.LIMITED-SERVICE state and the list of "forbidden tracking areas for regional provision of service" contains more than one TAI WHEN: the UE selects a cell belonging to one of the TAIs in the list of "forbidden tracking areas for regional provision of service" THEN: the UE does not attempt to registration **** TP4: [TS 24,501:] WITH: the UE is switched off or the UICC containing the USIM is removed WHEN: UE is powered on in the cell belonging to the TAI which was in the list of "forbidden tracking areas for regional provision of service" before the UE was switched off or the USIM is inserted again on that cell THEN: UE performs registration on that cell | CAICT | Opt 2: RAN5#93 (Nov-21) | R5-192386 R5-198946 R5-216490 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
21 | Y | 38.523-1 | 9.1.5.1.12 | Initial registration / Rejected / Roaming not allowed in this tracking area | **** TP1: [TS 24,501:5.5.1.2.5] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #13 (Roaming not allowed in this tracking area) THEN: the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, deletes the list of equivalent PLMNs, stores the current TAI in the list of "5GS forbidden tracking areas for roaming **** TP2: [TS 24,501:5.5.1.2.5] WITH: the initial registration request cannot be accepted by the network WHEN: the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #13 (Roaming not allowed in this tracking area) THEN: The UE performs a PLMN selection **** TP3: [TS 24,501:5.5.1.2.5] WITH: the UE is in 5GMM-DEREGISTERED.LIMITED-SERVICE or 5GMM-DEREGISTERED.PLMN-SEARCH state and the TAI of the current cell belongs to the list of "forbidden tracking areas for roaming" WHEN: the UE enters a cell belonging to a tracking area not in the list of "forbidden tracking areas for roaming" THEN: the UE attempts to registration **** TP4: [TS 24,501:5.5.1.2.5] WITH: the UE is in 5GMM-DEREGISTERED.LIMITED-SERVICE or 5GMM-DEREGISTERED.PLMN-SEARCH state and the list of "forbidden tracking areas for roaming" contains more than one TAI WHEN: the UE selects a cell belonging to one of the TAIs in the list of "forbidden tracking areas for roaming" THEN: the UE does not attempt to registration **** TP5: [TS 24,501:5.5.1.2.5] WITH: the UE is switched off or the UICC containing the USIM is removed WHEN: UE is powered on in the cell belonging to the TAI which was in the list of "forbidden tracking areas for roaming" before the UE was switched off or the USIM is inserted again on that cell THEN: UE performs registration on that cell | CAICT | Opt 2: RAN5#93 (Nov-21) | R5-192387 R5-197084 R5-198947 R5-216491 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
103 | Y | 38.523-1 | 9.1.5.1.13 | Initial registration / Rejected / No suitable cells in tracking area | **** TP1: [TS 24,501:5.5.1.2.5] WITH: the UE has sent initial REGISTRAION REQUEST message WHEN: the UE receives a REGISTRATION REJECT with cause #15 (No suitable cells in tracking area) THEN: the UE sets the 5GS update status to 5U3 ROAMING NOT ALLOWED and delete any 5G-GUTI, last visited registered TAI and ngKSI **** TP2: [TS 24,501:5.5.1.2.5] WITH: the UE is in 5GMM-DEREGISTERED.LIMITED-SERVICE state and the current TAI in the list of "forbidden tracking areas for roaming" WHEN: the UE re-selects a cell that belongs to the TAI where UE was rejected THEN: the UE does not attempt to perform registration **** TP3: [TS 24,501:5.5.1.2.5] WITH: the UE has sent initial REGISTRAION REQUEST message WHEN: the UE receives a REGISTRATION REJECT with cause #15 (No suitable cells in tracking area) THEN: the UE searchs for a suitable cell in another tracking area | CATT/TDIA | Opt 2: RAN5#86 (Feb-20) | R5-192824 R5-193884 R5-203505 R5-216492 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
23 | Y | 38.523-1 | 9.1.5.1.14 | Initial registration / Rejected / Congestion / Abnormal / T3346 | **** TP1: [TS 24,501:5.5.1.2.7] WITH: the UE in 5GMM-REGISTERED-INITIATED state WHEN: the UE receives a REGISTRATION REJECT with cause #22 (Congestion) with T3346 included and the UE is NOT configured for High Priority Access in the selected PLMN THEN: the UE does not start the Initial registration until T3346 expires **** TP2: [TS 24,501:5.5.1.2.7] WITH: The UE has received initial REGISTRATION REJECT with T3346 included WHEN: upon expiry of T3346 THEN: UE starts the Initial registration procedure **** TP3: [TS 24,501:5.5.1.2.7] WITH: The UE has received initial REGISTRATION REJECT with T3346 included WHEN: the timer T3346 is running and the UE needs to perform initial registration for emergency services THEN: UE starts the Initial registration procedure **** TP4: [TS 24,501:5.5.1.2.7] WITH: The UE has received initial REGISTRATION REJECT with T3346 included WHEN: the timer T3346 is running and the UE detects a cell better than serving cell on other PLMN (S criterion for detected cell > S criterion for serving cell THEN: UE starts the Initial registration procedure on the detected cell **** TP5: [TS 24,501:5.5.1.2.7] WITH: The UE has received initial REGISTRATION REJECT with T3346 included WHEN: the timer T3346 is running and the UE detects a cell better than serving cell on same PLMN (S criterion for detected cell > S criterion for serving cell THEN: UE starts the Initial registration procedure on the detected cell after T3346 expiry | R&S | Opt 2: RAN5#93 (Nov-21) | R5-185080 R5-187707 R5-192340 R5-194868 R5-197086 R5-201144 R5-204463 R5-216493 |  | 1 | 90% |  | 13 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
134 | Y | 38.523-1 | 9.1.5.1.15 | Initial registration / Success / Extended and spare fields in UE network capability | **** TP1: [TS TS 24.007:11.2.2.1; TS TS 24.501:5.5.1.2.2, 5.5.1.2.3, and 5.5.1.2.4] WITH: UE is powered on and has sent a REGISTRATION REQUEST message } ensure that WHEN: UE receives additional octets in REGISTRATION ACCEPT that it does not comprehend (those added in later versions of the protocols without using the mechanisms defined in TS 24.007 c) or d) THEN: the UE ignores the contents of these octets and transmits REGISTRATION COMPLETE | NTT DOCOMO | Opt 2: RAN5#91 (May-21) | R5-211402 R5-217079 R5-220367 |  | 1 | 90% |  | 11 | 100% | 100% |  | 1 |  | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.5.2 | Mobility and periodic registration update | New sub-clause
25 | Y | 38.523-1 | 9.1.5.2.1 | Mobility registration update / TAI list handling | **** TP1: [TS 24,501:5.5.1.3.2] WITH: the UE in 5GMM-REGISTERED state and 5GMM-IDLE mode over 3GPP access WHEN: the UE detects entering a tracking area which is not in the list of forbidden TAs and is not in the list of tracking areas that the UE previously registered THEN: the UE initiates and successfully completes the registration procedure for mobility registration update **** TP2: [TS 24,501:5.5.1.3.2] WITH: the UE in state 5GMM-REGISTERED, and 5GMM-IDLE mode over 3GPP access WHEN: the UE detects entering a tracking area which is not in the list of forbidden TAs and is in the list of tracking areas that the UE previously registered THEN: the UE does not initiate the registration procedure for mobility registration update **** TP3: [TS 24,501:5.5.1.3.2] WITH: the UE in state 5GMM-REGISTERED, and 5GMM-IDLE mode over 3GPP access WHEN: the UE receives a new TAI list during a Mobility registration update procedure THEN: the UE shall delete its old TAI list and store the received TAI list | Samsung | Opt 2: RAN5#86 (Feb-20) | R5-187796 R5-190701 R5-192341 R5-200587 R5-206351 R5-216494 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
26 | Y | 38.523-1 | 9.1.5.2.2 | Periodic registration update / Accepted | **** TP1: [TS 24,501:5.5.1.3.2] WITH: the UE in 5GMM-REGISTERED state and 5GMM-IDLE mode over 3GPP access WHEN: the periodic registration updating timer T3512 expires THEN: the UE initiates the registration procedure for mobility and periodic registration update and indicates "periodic registration updating" in the 5GS registration type IE **** TP2: [TS 24,501:5.5.1.3.2] WITH: the UE in 5GMM-REGISTERED state and the initiates the periodic registration procedure WHEN: the SS sends a REGISTRATION ACCEPT message included a new T3512 value IE THEN: the UE uses the new value in T3512 value IE as periodic registration update timer (T3512) | CATT/TDIA | Opt 2: RAN5#82 (Feb-19) | R5-190708 R5-192806 R5-200205 R5-217080 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
29 |  | 38.523-1 | 9.1.5.2.3 | Void | **** TP1: [TS 24,501:5.5.1.3.2] WITH: the UE in RRC_INACTIVE state WHEN: the UE enters a cell in the current registration area belonging to an equivalent PLMN of the registered PLMN and not belonging to the registered PLMN THEN: the UE initiates and successfully completes the registration procedure for mobility registration update | CATT/TDIA | [6 empty] | 4 |  |  |  | 1 | 1 | 1 |  |  |  | 1
30 | Y | 38.523-1 | 9.1.5.2.4 | Mobility registration update / The lower layer requests NAS signalling connection recovery | **** TP1: [TS 24,501:5.5.1.3.2] WITH: UE in state 5GMM-REGISTERED, and 5GMM-CONNECTED mode over 3GPP access and does not have signalling or user uplink data pending WHEN: UE receives an indication of "RRC Connection failure" from the lower layers THEN: UE initiates and successfully completes the registration procedure for mobility registration update | Samsung | Opt 2: RAN5#82 (Feb-19) | R5-190702 R5-192398 R5-193869 R5-194514 R5-197080 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
32 |  | 38.523-1 | 9.1.5.2.5 | Void | **** TP1: [] WITH: WHEN: THEN: |  |  |  |  | 0 |  |  | 4 |  |  |  | 1 | 1 | 1 |  |  |  | 1
33 |  | 38.523-1 | 9.1.5.2.6 | Void | **** TP1: [TS 24,501:5.5.1.3.2] Editor's note: FFS WITH: the UE in 5GMM-REGISTERED state WHEN: the UE needs to change the slice(s) currently registered to THEN: the UE shall initiate the mobility and periodic registration updating procedure | Samsung | Opt 2: RAN5#85 (Nov-19) | R5-198086 R5-201119 R5-203658 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
34 | Y | 38.523-1 | 9.1.5.2.7 | Mobility and periodic registration update / Rejected / UE identity cannot be derived by the network | **** TP1: [TS 24,501:5.5.1.3.5] WITH: UE in state 5GMM-REGISTERED on an NGC cell WHEN: UE initiates a Mobility and periodic registration procedure on an NGC cell and receives a REGISTRATION REJECT message including 5GMM cause value #9 (UE identity cannot be derived by the network) THEN: UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, enters the state 5GMM-DEREGISTERED 5U2 NOT UPDATED, and, subsequently automatically initiates the initial registration procedure | Samsung | Opt 2: RAN5#83 (May-19) | R5-195212 R5-198772 |  | 1 | 90% |  | 3 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
35 | Y | 38.523-1 | 9.1.5.2.8 | Mobility and periodic registration update / Rejected / Implicitly de-registered | **** TP1: [TS 24,501:5.5.1.3.5] WITH: UE in state 5GMM-REGISTERED on an NGC cell WHEN: UE initiates a Mobility and periodic registration procedure on an NGC cell and receives a REGISTRATION REJECT message including 5GMM cause value #10 (implicitly de-registered) THEN: UE deletes any partial native 5G security context, enters the state 5GMM-DEREGISTERED.NORMAL-SERVICE, and, initiates a new registration procedure for initial registration | Samsung | Opt 2: RAN5#86 (Feb-20) | R5-195213 R5-196755 R5-200206 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
36 |  | 38.523-1 | 9.1.5.2.9 | Void | **** TP1: [TS 24,501:5.5.1.3.7] Editor's note: FFS WITH: UE initiates a Mobility and periodic registration procedure in 5GMM-REGISTERED state WHEN: UE changes the cell into a new tracking area before the registration procedure for mobility and periodic registration update has been completed THEN: UE shall abort registration procedure for mobility and periodic registration update and re-initiate immediately **** TP2: [TS 24,501:5.5.1.3.7] WITH: UE initiates a Mobility and periodic registration procedure in 5GMM-REGISTERED state WHEN: UE receives a CONFIGURATION UPDATE COMMAND message before the registration procedure for mobility and periodic registration update has been completed THEN: UE shall ignore the message and proceed with the mobility and periodic registration update procedure | MediaTek |  | R5-190705 R5-198786 R5-204462 R5-206280 R5-211333 |  |  | 90% |  | 6 |  |  |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.6 | De-registration | New sub-clause
|  | 38.523-1 | 9.1.6.1 | UE-initiated de-registration | New sub-clause
42 | Y | 38.523-1 | 9.1.6.1.1 | UE-initiated de-registration / Switch off / Abnormal / De-registration and 5GMM common procedure collision | **** TP1: [TS 24,501:5.5.2.2.1] WITH: the UE in 5GMM-REGISTERED state WHEN: the UE is switched off THEN: the UE shall send DEREGISTRATION REQUEST message with De-registration type IE indicated to "Switch off" **** TP2: [TS 24,501:5.5.2.2.6 d)] WITH: the UE in 5GMM-DEREGISTERED-INITIATED state WHEN: the UE receives a DEREGISTRATION REQUEST message before the UE-initiated de-registration procedure has been completed THEN: the UE ignores the message and shall continue de-registration procedure **** TP3: [TS 24,501:5.5.2.2.6 d)] WITH: the UE in 5GMM-DEREGISTERED-INITIATED state WHEN: the UE receives a DEREGISTRATION REQUEST message before the UE-initiated de-registration procedure has been completed THEN: the UE ignores the message and shall continue de-registration procedure **** TP4: [TS 24,501:5.5.2.1] WITH: the UE in 5GMM-REGISTERED state WHEN: the USIM is removed from the UE THEN: the UE shall send DEREGISTRATION REQUEST message with De-registration type IE indicated to "Switch off" | CATT/TDIA | Opt 2: RAN5#81 (Nov-18) | R5-187797 R5-192397 R5-194867 R5-197087 |  | 1 | 90% |  | 1 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
44 | Y | 38.523-1 | 9.1.6.1.2 | UE-initiated de-registration / Normal de-registration / Abnormal / Transmission failure without TAI change from lower layers, de-registration and 5GMM common procedure collision, T3521 timeout | **** TP1: [TS 24,501:5.5.2.2.6 c)] WITH: the UE in 5GMM-REGISTERED state WHEN: the UE initiates "normal de-registration" type deregistration from 5GS services over 3GPP access THEN: the UE sends DEREGISTRATION REQUEST message with De-registration type IE indicated to "Normal de-registration" and starts timer T3521 **** TP2: [TS 24,501:5.5.2.2.6 h)] WITH: the UE in 5GMM-DEREGISTERED-INTIATED state WHEN: Transmission failure of DEREGISTRATION REQUEST message indication without TAI change from lower layers THEN: the UE restarts the de-registration procedure **** TP3: [TS 24,501:5.5.2.2.6 c)] WITH: the UE in 5GMM-DEREGISTERED-INTIATED state WHEN: the UE receives a message used in a 5GMM common procedure before the de-registration procedure has been completed THEN: both the 5GMM common procedure and the de-registration procedure shall continue **** TP4: [TS 24,501:5.5.2.2.6 c)] WITH: the UE in 5GMM-DEREGISTERED-INTIATED state WHEN: the first four expiries of the timer T3521 THEN: the UE shall retransmit the DEREGISTRATION REQUEST message and shall reset and restart timer T3521 **** TP5: [TS 24,501:5.5.2.2.6 c)] WITH: the UE in 5GMM-DEREGISTERED-INTIATED state WHEN: On the fifth expiry of timer T3521 THEN: the detach procedure shall be aborted and the UE perform local detach | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-192802 R5-195349 R5-198949 R5-201145 |  | 1 | 90% |  | 4 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
47 | Y | 38.523-1 | 9.1.6.1.3 | UE-initiated de-registration / Abnormal / Change of cell into a new tracking area | **** TP1: [TS 24,501:5.5.2.2.6 f)] WITH: UE in 5GMM-DEREGISTERED-INITIATED state and de-registration request is not due to switch off WHEN: UE changes into a new tracking area that is not in the stored TAI list THEN: UE aborts the de-registration procedure and initiates a mobility registration procedure **** TP2: [TS 24,501:5.5.2.2.6 f)] WITH: UE in 5GMM-REGISTERED-INITIATED state for a mobility registration procedure due to change of cell into a new tracking area list during UE-initiated de-registration procedure WHEN: UE receives REGISTRATION ACCEPT message THEN: UE re-initiates the de-registration procedure after completing the mobility registration procedure **** TP3: [TS 24,501:5.5.2.2.6 f)] WITH: UE in 5GMM-DEREGISTERED-INITIATED state and de-registration request is due to switch off WHEN: UE changes into a new tracking area that is not in the stored TAI list THEN: UE aborts the de-registration procedure and enter the state 5GMM-DEREGISTERED | Qualcomm | Opt 2: Post WI close | R5-195210 R5-197082 R5-198185 R5-200208 R5-202660 R5-204464 R5-205385 | ‘Non-suitable’ cell needs to be updated for FR2 | 1 | 90% |  | 16 | 100% | 90% |  | 1 | 1 | 1 |  |  |  | 1
48 |  | 38.523-1 | 9.1.6.1.4 | Void | **** TP1: [TS 24,501:5.5.2.2.6 g)] WITH: UE initiates de-registration procedure for 5GS services over 3GPP access with de-registration type "Normal de-registration" in 5GMM-REGISTERED state WHEN: UE receives transmission failure of DEREGISTRATION REQUEST message indication with TAI change from lower layers and the current TAI is not in the TAI list THEN: UE shall abort the de-registration procedure and re-initiate after successfully performing a registration procedure for mobility update **** TP2: [TS 24,501:5.5.2.2.6 g)] WITH: UE initiates de-registration procedure for 5GS services over 3GPP access with de-registration type "Normal de-registration" in 5GMM-REGISTERED state WHEN: UE receives transmission failure of DEREGISTRATION REQUEST message indication with TAI change from lower layers and the current TAI is still part of the TAI list THEN: UE shall restart the de-registration procedure | MediaTek | Opt 2: RAN5#86 (Feb-20) | R5-190706 R5-196633 R5-198954 R5-201644 R5-204461 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.6.2 | Network-initiated de-registration | New sub-clause | [5 empty] | 90%
50 | Y | 38.523-1 | 9.1.6.2.1 | Network-initiated de-registration / De-registration for 3GPP access / Re-registration required | **** TP1: [TS 24,501:5.5.2.3.2] WITH: the UE in 5GMM-REGISTERED state WHEN: the SS sends a DEREGISTRATION REQUEST message indicates "re-registration required" and the de-registration request is for 3GPP access THEN: the UE sends a DEREGISTRATION ACCEPT message to the network and releases the existing NAS signalling connection, then initiates an initial registration and also re-establishs any previously established PDU sessions. | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-192803 |  | 1 | 90% | 2 | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
51 | Y | 38.523-1 | 9.1.6.2.2 | Network-initiated de-registration / De-registration for 3GPP access / Re-registration not required | **** TP1: [TS 24,501:5.5.2.3.2] WITH: the UE in 5GMM-REGISTERED state WHEN: the SS sends a DEREGISTRATION REQUEST message indicates no 5GMM cause IE, "re-registration not required" and the de-registration request is for 3GPP access THEN: the UE deletes 5G-GUTI, last visited registered TAI, list of equivalent PLMNs, ngKSI, sends a DEREGISTRATION ACCEPT message enter the state 5GMM-DEREGISTERED for 3GPP access. | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-192855 R5-197867 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.7 | Service request | New sub-clause
61 | Y | 38.523-1 | 9.1.7.1 | Service request / Idle mode uplink user data transport / Rejected / Restricted service area, abnormal / T3517, T3525 | **** TP1: [TS 24,501:5.6.1.1 d)] WITH: the UE is in 5GMM-REGISTERED state and 5GMM-IDLE mode over 3GPP access WHEN: the UE has uplink user data pending THEN: the UE sends a SERVICE REQUEST message **** TP2: [TS 24,501:5.6.1.5] WITH: the UE sends a SERVICE REQUEST message WHEN: the UE receives a SERVICE REJECT message including an appropriate 5GMM cause value #28 (Restricted service area) THEN: the UE performs the registration procedure for mobility registration update **** TP3: [TS 24,501:5.6.1.7] WITH: the UE is in 5GMM-REGISTERED state and 5GMM-IDLE mode WHEN: T3517 expired THEN: the UE increases the service request attempt counter, abort the procedure and release locally any resources allocated for the service request procedure. **** TP4: [TS 24,501:5.6.1.7] WITH: the UE is in 5GMM-REGISTERED state and 5GMM-IDLE mode WHEN: the service request attempt counter is equal to 5 THEN: the UE starts timer T3525 and not attempts service request until expiry of timer T3525 | CAICT | Opt 2: RAN5#86 (Feb-20) | R5-192385 R5-194869 R5-196055 R5-198284 R5-201102 R5-202662 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
62 | Y | 38.523-1 | 9.1.7.2 | Service request / Connected mode user data transport / Abnormal / T3517 | **** TP1: [TS 24,501:5.6.1.1 e)] WITH: the UE is in 5GMM-REGISTERED state and 5GMM-CONNECTED mode over 3GPP access WHEN: the UE has user data pending due to no user-plane resources established for PDU session(s) used for user data transport THEN: the UE sends a SERVICE REQUEST message **** TP2: [TS 24,501:5.6.1.7] WITH: the UE sends a SERVICE REQUEST message in 5GMM-CONNECTED mode WHEN: T3517 expired THEN: the UE aborts the procedure and stays in 5GMM-CONNECTED mode | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-192805 R5-197088 R5-198950 R5-201088 R5-202661 |  | 1 | 90% |  | 4 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 9.1.8 | SMS over NAS | New sub-clause | [5 empty] | 90%
16 | Y | 38.523-1 | 9.1.8.1 | SMS over NAS / MO and MT SMS over NAS / Idle mode | **** TP1: [TS 24,501:5.5.1.2.2] WITH: the UE in switched off state with valid USIM inserted WHEN: the UE requests initial registration for SMS over NAS THEN: the UE shall send REGISTRATION REQUEST message with SMS requested bit of the 5GS registration type IE "SMS over NAS supported" **** TP2: [TS 24,501:5.5.1.2.2] WITH: the UE in 5GMM-REGISTERED state WHEN: the UE initiates a periodic registration update and the requirements to use SMS over NAS transport have not changed in the UE THEN: the UE sets the SMS requested bit of the 5GS registration type IE in the REGISTRATION REQUEST message to the same value as indicated by the UE in the last REGISTRATION REQUEST message **** TP3: [TS 24,501:5.5.1.2.2] WITH: the UE in 5GMM_Connected state with NR RRC_IDLE mode and the UE has sent a SERVICE REQUEST message triggered by initiating MO SMS WHEN: UE receives a SERVICE ACCEPT message from SS THEN: UE sends CP-DATA containing RP-DATA RPDU (SMS SUBMIT TPDU) encapsulated in an Uplink NAS transport message **** TP4: [TS 24,501:5.5.1.2.2] WITH: UE has sent CP-DATA containing an RP-DATA RPDU (SMS SUBMIT TPDU) encapsulated in an Uplink NAS transport message WHEN: UE receives a CP-DATA containing an RP-ACK RPDU encapsulated in a Downlink NAS transport message THEN: UE sends a CP-ACK encapsulated in an Uplink NAS Transport message **** TP5: [TS 24,501:5.5.1.2.2] WITH: the UE in 5GMM-REGISTERED state with NR RRC_IDLE mode, UE has received a paging request and UE has completed a SERVICE REQUEST procedure WHEN: UE receives a CP-DATA containing an RP-DATA RPDU (SMS DELIVER TPDU) encapsulated in a Downlink NAS transport message THEN: UE sends a CP-ACK encapsulated in an Uplink NAS transport message followed by a CP-DATA containing an RP-ACK RPDU encapsulated in an Uplink NAS transport message | Qualcomm | Opt 2: RAN5#83 (May-19) | R5-192343 R5-194033 R5-201089 R5-211403 |  | 1 | 90% |  | 3 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
133 | Y | 38.523-1 | 9.1.8.2 | SMS over NAS / Multiple MO and MT SMS over NAS / Connected mode | **** TP1: [TS 24,501:4.5.4.2] WITH: the UE is in 5GMM-REGISTERED state and 5GMM-CONNECTED mode over 3GPP access WHEN: a Multiple MO SMS is initiated at the UE THEN: UE sends CP-DATA containing RP-DATA RPDU (SMS SUBMIT TPDU) encapsulated in an Uplink NAS transport message **** TP2: [TS 24,501:4.5.4.2] WITH: UE has sent CP-DATA containing an RP-DATA RPDU (SMS SUBMIT TPDU) encapsulated in an Uplink NAS transport message and has another MO SMS to send WHEN: UE receives a CP-DATA containing an RP-ACK RPDU encapsulated in a Downlink NAS transport message THEN: UE does not send a final CP-ACK before it sends a CP-DATA containing the successive RP-DATA RPDU (SMS SUBMIT TPDU) encapsulated in an Uplink NAS transport message **** TP3: [TS 24,501:4.5.4.2] WITH: UE has sent CP-DATA containing an RP-DATA RPDU (SMS SUBMIT TPDU) encapsulated in an Uplink NAS transport message and has no further MO SMS to send WHEN: UE receives a CP-DATA containing an RP-ACK RPDU encapsulated in a Downlink NAS transport message THEN: UE sends a CP-ACK encapsulated in an Uplink NAS transport message **** TP4: [TS 24,501:4.5.4.2] WITH: the UE is in 5GMM-REGISTERED state and 5GMM-CONNECTED mode over 3GPP access WHEN: UE receives a CP-DATA containing an RP-DATA RPDU (SMS DELIVER TPDU) encapsulated in a Downlink NAS transport message, and subsequently a second CP-DATA containing an RP-DATA RPDU (SMS DELIVER TPDU) encapsulated in a Downlink NAS transport message with differernt transaction identifier THEN: UE sends twice a CP-ACK encapsulated in an Uplink NAS transport message followed by a CP-DATA containing an RP-ACK RPDU encapsulated in an Uplink NAS transport message | CATT/TDIA | Opt 2: RAN5#87 (May-20) | R5-202222 |  | 1 | 90% |  | 7 | 100% | 100% |  | 1 |  | 1 |  |  |  | 1
|  | 38.523-1 | 9.3 | Inter-system mobility | New sub-clause
|  | 38.523-1 | 9.3.1 | 5GC-EPC Inter-system mobility | New sub-clause
120 | Y | 38.523-1 | 9.3.1.1 | Inter-system mobility registration update / Single-registration mode with N26 / 5GMM-IDLE / 5GC to EPC | **** TP1: [TS 24,501:5.1.4.2] WITH: UE in state 5GMM-REGISTERED and 5GMM-IDLE on a 5GC NR cell and has been previously registered on EPC as well, UE supporting S1 and N1 and operating in single-registration mode, NWK supporting Single-registration mode with N26 interface WHEN: UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable THEN: UE performs a Inter-system change from N1 mode to S1 mode by initiating and successfully completing a TAU procedure, mapped EPC context used | Samsung | Opt 2: RAN5#86 (Feb-20) | R5-195228 R5-196730 R5-200211 R5-211405 R5-213488 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
121 | Y | 38.523-1 | 9.3.1.2 | Inter-system mobility registration update / Single-registration mode with N26 / 5GMM-IDLE / EPC to 5GC | **** TP1: [TS 24,501:4.4.2.5] WITH: UE in state EMM-REGISTERED and EMM-IDLE on an E-UTRA cell and has been previously registered on 5GC, UE supporting S1 and N1 and operating in single-registration mode, NWK supporting Single-registration mode with N26 interface WHEN: UE detects a suitable NGC cell after the serving E-UTRA cell becomes not suitable THEN: UE performs a Inter-system change from S1 mode to N1 mode by initiating and successfully completing a mobility and periodic registration update procedure, mapped 5GC context used | Samsung | Opt 2: RAN5#86 (Feb-20) | R5-195229 R5-196731 R5-201200 R5-205142 R5-211404 R5-212159 R5-216185 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
122 | Y | 38.523-1 | 9.3.1.3 | Inter-system mobility and periodic registration update / Rejected / Single-registration mode with N26 / Handling of EPC relevant parameters | **** TP1: [TS 24,501:5.5.1.3.5] WITH: UE in state 5GMM-REGISTERED on an NGC cell, UE supporting S1 and N1 and operating in single-registration mode, NWK supporting Single-registration mode with N26 interface WHEN: UE initiates a Mobility and periodic registration procedure on an NGC cell and receives a REGISTRATION REJECT message including 5GMM cause value #9 (UE identity cannot be derived by the network THEN: UE deletes the EPS relevant parameters 4G-GUTI, last visited registered TAI and eKSI and enters the state EMM-DEREGISTERED, and, subsequently, when it finds a suitable E-UTRA cell it moves to it and automatically initiates an attach procedure | Samsung | Opt 2: RAN5#86 (Feb-20) | R5-195230 R5-196732 R5-202535 R5-213489 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
5GS session management
|  | 38.523-1 | 10.1 | 5GS session management | New sub-clause
|  | 38.523-1 | 10.1.1 | PDU session authentication and authorization | New sub-clause
74 | Y | 38.523-1 | 10.1.1.1 | PDU session authentication and authorization / During the UE-requested PDU session procedure | **** TP1: [TS 24,501:6.3.1] WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message WHEN: UE receives a PDU SESSION AUTHENTICATION COMMAND message THEN: UE transmits a PDU SESSION AUTHENTICATION COMPLETE message **** TP2: [TS 24,501:6.3.1] WITH: PDU session authentication and authorization procedure is performed during the UE-requested PDU session establishment procedure WHEN: UE receives EAP-failure message in the PDU SESSION ESTABLISHMENT REJECT message THEN: UE consider that the PDU session is not established **** TP3: [TS 24,501:6.3.1] WITH: PDU session authentication and authorization procedure is performed during the UE-requested PDU session establishment procedure WHEN: UE receives EAP-success message in the PDU SESSION ESTABLISHMENT ACCEPT message THEN: UE consider that the PDU session is established | Qualcomm | Opt 2: RAN5#82 (Feb-19) | R5-190710 R5-198184 R5-200213 R5-216186 R5-217279 R5-220550 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
75 | Y | 38.523-1 | 10.1.1.2 | PDU session authentication and authorization / After the UE-requested PDU session procedure | **** TP1: [TS 24,501:6.3.1] WITH: the UE is in 5GMM-REGISTERED state with an established PDU session WHEN: the SS sends a PDU SESSION RELEASE COMMAND message THEN: the UE sends a PDU SESSION AUTHENTICATION COMPLETE message **** TP2: [TS 24,501:6.3.1] WITH: the PDU session authentication and authorization procedure is performed after the UE-requested PDU session procedure establishment WHEN: the SS sends EAP-failure message in the PDU SESSION RELEASE COMMAND message THEN: the 5GSM of the UE in PDU SESSION INACTIVE state **** TP3: [TS 24,501:6.3.1] WITH: the PDU session authentication and authorization procedure is performed after the UE-requested PDU session procedure establishment WHEN: the SS sends EAP-success message in the PDU SESSION AUTHENTICATION RESULT message THEN: the 5GSM of the UE in PDU SESSION ACTIVE state | Keysight | Opt 2: RAN5#83 (May-19) | R5-195226 R5-198322 R5-200214 R5-203785 R5-206354 R5-220551 |  | 1 | 90% |  | 3 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 10.1.2 | Network-requested PDU session modification | New sub-clause
76 | Y | 38.523-1 | 10.1.2.1 | Network-requested PDU session modification / Accepted | **** TP1: [TS 24,501:6.3.2.3] WITH: the UE is in 5GMM-REGISTERED state with an established PDU session WHEN: the SS sends a PDU SESSION MODIFICATION COMMAND message THEN: the UE sends a PDU SESSION MODIFICATION COMPLETE message and modifies the PDU session accordingly **** TP2: [] WITH: the UE in 5GMM-REGISTERED state with an established PDU session has been modified WHEN: the UE has IP packets for transmission where each IP packet matches the modified packet filters configured in the UL TFTs for the PDU session THEN: the UE evaluates the packet filters in the correct evaluation order and transmits IP packets in uplink on the dedicated PDU session associated with the matched packet filter | CATT/TDIA | Opt 2: RAN5#84 (Aug-19) | R5-196039 R5-198972 |  | 1 | 90% |  | 4 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
78 | Y | 38.523-1 | 10.1.2.2 | Network-requested PDU session modification / Abnormal / PDU session in state PDU SESSION INACTIVE | **** TP1: [TS 24,501:6.3.2.4] WITH: the UE is in 5GMM-REGISTERED state with an established PDU session WHEN: the SS sends a PDU SESSION MODIFICATION COMMAND message include the PDU session ID which belong to any PDU session in PDU SESSION INACTIVE state in UE THEN: the UE sends a 5GSM STATUS message and set the 5GSM cause to #43: invalid PDU session identity | CATT/TDIA | Opt 2: RAN5#86 (Feb-20) | R5-192703 R5-194872 R5-201226 R5-206356 R5-217817 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
123 |  | 38.523-1 | 10.1.2.3 | Void | **** TP1: [TS 24,501:6.3.2.4] WITH: the UE in PDU SESSION ACTIVE state and 5GMM-CONNECTED mode WHEN: the UE receives a PDU SESSION MODIFICATION COMMAND message include the Authorized QoS rules IE，the rule operation is "Modify existing QoS flow description" and the associated QoS flow description does not exist THEN: UE sends a PDU SESSION MODIFICATION COMMAND REJECT message with 5GSM cause #83 "semantic error in the QoS operation" **** TP2: [TS 24,501:6.3.2.4] WITH: the UE in PDU SESSION ACTIVE state and 5GMM-CONNECTED mode WHEN: the UE receives a PDU SESSION MODIFICATION COMMAND message include the Authorized QoS rules IE，the rule operation is "Delete existing QoS rule" on the default QoS rule THEN: UE sends a PDU SESSION RELEASE REQUEST message with 5GSM cause #83 "semantic error in the QoS operation" **** TP3: [TS 24,501:6.3.2.4] WITH: the UE in PDU SESSION ACTIVE state and 5GMM-CONNECTED mode WHEN: the UE receives a PDU SESSION MODIFICATION COMMAND message include the Authorized QoS rules IE，the rule operation is " Modify existing QoS rule and add packet filters " and the old QoS rule is not the default QoS rule THEN: { UE sends a PDU SESSION MODIFICATION REQUEST message with 5GSM cause #83 "semantic error in the QoS operation" | CATT/TDIA | [11 empty] | 1
124 |  | 38.523-1 | 10.1.2.4 | Void | **** TP1: [TS 24,501:6.3.2.4] WITH: the UE in PDU SESSION ACTIVE state and 5GMM-CONNECTED mode WHEN: the UE receives a PDU SESSION MODIFICATION COMMAND message include the Authorized QoS rules IE，the rule operation is "Delete existing QoS rule" on the default QoS rule THEN: UE sends a PDU SESSION RELEASE REQUEST message with 5GSM cause #83 "semantic error in the QoS operation" | [7 empty] | 4 |  |  |  | 1 | 1 | 1 |  |  |  | 1
125 |  | 38.523-1 | 10.1.2.5 | Void | **** TP1: [TS 24,501:6.3.2.4] WITH: the UE in PDU SESSION ACTIVE state and 5GMM-CONNECTED mode WHEN: the UE receives a PDU SESSION MODIFICATION COMMAND message include the Authorized QoS rules IE，the rule operation is " Modify existing QoS rule and add packet filters " and the old QoS rule is not the default QoS rule THEN: { UE sends a PDU SESSION MODIFICATION REQUEST message with 5GSM cause #83 "semantic error in the QoS operation" | [7 empty] | 4 |  |  |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 10.1.3 | Network-requested PDU session release | New sub-clause
83 |  | 38.523-1 | 10.1.3.1 | Void | **** TP1: [TS 24,501:6.3.3.3] WITH: the UE is in PDU SESSION ACTIVE state with a S-NSSAI and a DNN which are included in the establishment of the PDU session WHEN: the SS sends a PDU SESSION RELEASE COMMAND message includes 5GSM cause #39 "reactivation requested" THEN: the UE re-initiates the UE requested PDU session establishment procedure for the same [S-NSSAI, DNN] combination **** TP2: [TS 24,501:6.3.3.3] WITH: the UE is in PDU SESSION ACTIVE state with a S-NSSAI and no DNN which are included in the establishment of the PDU session WHEN: the SS sends a PDU SESSION RELEASE COMMAND message includes 5GSM cause #39 "reactivation requested" THEN: the UE re-initiates the UE requested PDU session establishment procedure for the same S-NSSAI with no DNN **** TP3: [TS 24,501:6.3.3.3] WITH: the UE is in PDU SESSION ACTIVE state with no S-NSSAI and a DNN which are included in the establishment of the PDU session WHEN: the SS sends a PDU SESSION RELEASE COMMAND message including 5GSM cause #39 "reactivation requested" THEN: the UE re-initiates the UE requested PDU session establishment procedure for no S-NSSAI with the same DNN | CATT/TDIA |  | R5-187798 R5-197218 R5-200360 R5-202221 | [8 empty] | 1 | 1 | 1
84 | Y | 38.523-1 | 10.1.3.2 | Network-requested PDU session release / Insufficient resources, insufficient resources for specific slice and DNN, abnormal / Invalid PDU session identity | **** TP1: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #26 "insufficient resources" and the Back-off timer value that indicates neither zero nor deactivated THEN: UE does not send a PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST message until timer T3396 expires or timer T3396 is stopped **** TP2: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #26 "insufficient resources" and the Back-off timer value that indicates zero THEN: UE sends a PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST message **** TP3: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #26 "insufficient resources" and the Back-off timer value that indicates deactivated THEN: UE does not send a PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST message until the UE is switched off or the USIM is removed **** TP4: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #67 "insufficient resources for specific slice and DNN" and the Back-off timer value that indicates neither zero nor deactivated THEN: UE does not send a PDU SESSION ESTABLISHMENT REQUEST message or PDU SESSION MODIFICATION REQUEST for the same [S-NSSAI, DNN] combination until timer T3584 expires **** TP5: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #67 "insufficient resources for specific slice and DNN" and the Back-off timer value that indicates zero THEN: UE sends a PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST message for the same [S-NSSAI, DNN] combination **** TP6: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #67 "insufficient resources for specific slice and DNN" and the Back-off timer value that indicates deactivated THEN: UE does not send a PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST message for the same [S-NSSAI, DNN] combination until the UE is switched off or the USIM is removed **** TP7: [TS 24,501:6.3.3.3] WITH: UE is in PDU SESSION ACTIVE state WHEN: UE receives a PDU SESSION RELEASE COMMAND message, in which the PDU session ID belongs to any PDU session in state PDU SESSION INACTIVE in the UE THEN: UE sends 5GSM STATUS message including 5GSM cause #43 "Invalid PDU session identity" | CAICT | Opt 2: RAN5#86 (Feb-20) | R5-192700 R5-194871 R5-201107 R5-201629 R5-206355 |  | 1 | 90% |  | 6 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 10.1.4 | UE-requested PDU session establishment | New sub-clause
93 | Y | 38.523-1 | 10.1.4.1 | UE-requested PDU session establishment / Abnormal / T3580 | **** TP1: [TS 24,501:6.4.1.4.6] WITH: the UE in 5GMM-REGISTERED state and has sent a PDU SESSION ESTABLISHMENT REQUEST message WHEN: On the 1st, 2nd, 3rd, 4th expiry of timer T3580 THEN: the UE retransmits PDU SESSION ESTABLISHMENT REQUEST message **** TP2: [TS 24,501:6.4.1.4.6] WITH: the UE in 5GMM-REGISTERED state and has sent a PDU SESSION ESTABLISHMENT REQUEST message WHEN: on the fifth expiry of timer T3580 THEN: the UE aborts the procedure | Anritsu | Opt 2: RAN5#85 (Nov-19) | R5-199035 R5-201146 R5-200673 R5-202664 R5-206357 R5-213490 R5-217280 R5-217818 |  | 1 | 90% |  | 5 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 10.1.5 | UE-requested PDU session modification | New sub-clause
94 | Y | 38.523-1 | 10.1.5.1 | UE-requested PDU session modification | **** TP1: [TS 24,501:6.4.2.2] WITH: the UE in PDU SESSION ACTIVE state and in 5GMM-CONNECTED mode WHEN: UE is requested to modify of PDU session THEN: the UE sends a PDU SESSION MODIFICATION REQUEST message | CATT/TDIA | Opt 2: RAN5#82 (Feb-19) | R5-192816 R5-197259 R5-217281 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
|  | 38.523-1 | 10.1.6 | UE-requested PDU session release | New sub-clause
96 | Y | 38.523-1 | 10.1.6.1 | UE-requested PDU session release / Abnormal / Collision with network-requested PDU session modification procedure | **** TP1: [TS 24,501:6.4.3.5] WITH: the UE in PDU SESSION ACTIVE state and has sent a PDU SESSION RELEASE REQUEST message WHEN: the UE receives a PDU SESSION MODIFICATION COMMAND message indicates a PDU session that UE wants to release THEN: the UE ignores the PDU SESSION MODIFICATION COMMAND message and proceed with the PDU session release procedure | CAICT | Opt 2: RAN5#82 (Feb-19) | R5-192701 R5-194873 R5-195981 R5-206358 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
97 | Y | 38.523-1 | 10.1.6.2 | UE-requested PDU session release / Abnormal / Collision with network-requested PDU session release procedure | **** TP1: [TS 24,501:6.4.3.5] WITH: the UE in PDU SESSION ACTIVE state and has sent a PDU SESSION RELEASE REQUEST message WHEN: the UE receives a PDU SESSION RELEASE COMMAND message with the PTI IE set to “No procedure transaction identity assigned” indicates a PDU session that UE wants to release THEN: the UE aborts the UE-requested PDU session release procedure and proceed with the network-requested PDU session release procedure | CAICT | Opt 2: RAN5#82 (Feb-19) | R5-192702 R5-194874 R5-206359 |  | 1 | 90% |  | 2 | 100% | 100% |  | 1 | 1 | 1 |  |  |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
|  |  |  | With: | the UE in 5GMM-REGISTERED-INITIATED state
|  |  |  | When: | the UE receives transmission failure of REGISTRATION COMPLETE message indication with TAI change from lower layers
|  |  |  | Then: | the UE restarts the registration procedure with 5G-GUTI allocated during the last registration procedure
|  |  |  | TP Conformance Requirement TS and Clause(s): |  |  | 24.501 | 5.5.1.2.7 h) i)
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B7: Y = the WP Pitem is a test case.
Note on K7: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.
Note on AF7: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AG8: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).