## Slide 1: MCC TF160 Status Report (Pre-RAN5#94-e)
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2: Progress – TTCN development (Dec’21-->Feb’22)
Completed:
  5GS Rel-16:
    5G to 3G SRVCC
  IMS over NR/5GC:
    Call Control
  Mission Critical:
    MCPTT client configuration
Started:
  IMS over NR/5GC:
    IMS emergency
Progressed:
  5GS Rel-15:
    NR/5GC single carrier
    NR/5GC NR-DC
  5GS Rel-16:
    NR RACS
    NR SON/MDT
    NR mobility enhancements
    NR private networks
    NR UE power saving
    Network slicing enhancements
  IMS over NR/5GC:
    Supplementary services
  POS:
    Rel-16 NR positioning
  Mission Critical:
    MCPTT on-network group/private call
    MCPTT on-network location
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 3: Progress – TTCN verification (Status on 15th Feb’22)
Completed:
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EPS fallback - voice fallback indication | Rel-16 | None | 2 / 2 | +2 | 
Notes: Completed: Since last report, the TTCN of all remaining test cases has been verified and agreed.

## Slide 4: Progress – TTCN verification (Status on 15th Feb’22)
Progress – 5G (EN-DC, NR/5GC):
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC AS | Rel-15 | WI-503 | 87 / 102 | +1 | Prio1: 87/102 +1 under verification
NR/5GC AS | Rel-15 | WI-503 | 142 / 158 | +1 | Prio1: 87/96 ; Prio2: 55/62 +2 under verification
NR/5GC NR-DC | Rel-15 | WI-503 | 7 / 13 | = | Prio1: 6/11 ; Prio2: 1/2 +2 under verification
NR/5GC NAS | Rel-15 | WI-504 | 68 / 72 | +1 | Prio1: 32/32 ; Prio2: 36/40 +2 under verification
NR/5GC NR CA | Rel-15 | WI-510 | 24 / 31 | +3 | Prio1: 13/15 ; Prio2: 11/16
EN-DC NR CA | Rel-15 | WI-512 | 7 / 17 | = | Prio1: 7/13 ; Prio2: 0/4 +2 under verification
NR/5GC Inter-RAT | Rel-15 | WI-513 | 36 / 38 | = | Prio1: 16/16 ; Prio2: 20/22 +2 under verification
Intra-NR SON/MDT | Rel-16 | WI-517_A | 12 / 30 | +10 | Prio1: 10/24 ; Prio2: 2/6 +12 under verification
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 5: Progress – TTCN verification (Status on 15th Feb’22)
Progress – IMS, Positioning, MCPTT:
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
VoLTE (GSMA IR.92) | Rel-8 | WI-103 | 45 / 51 | = | 
SMS over IMS | Rel-8 | WI-128 | 2 / 5 | = | 
IMS emergency over LTE | Rel-9 | WI-154 | 31 / 35 | = | 
LTE positioning | Rel-9+ | WI-166 | 14 / 27 | = | 
VoWiFi (GSMA IR.51) | Rel-11 | WI-267 | 20 / 34 | = | Prio1: 5/9 ; Prio2: 15/25
VoLTE over CAT-M1 (GSMA NG.108) | Rel-13 | WI-283 | 10 / 11 | = | Left: TC J.15.5(TIR)
SMS over CAT-M1 (GSMA NG.108) | Rel-13 | WI-128M | 1 / 2 | = | Left: TC J.18.1(MO SMS)
MCPTT over LTE | Rel-14 | WI-288, RFT-153 | 35 / 49 | +8 | Prio1: 35/46 ; Prio2: 0/3
IMS eCall over LTE | Rel-14 | WI-298 | 5 / 12 | +3 | 
IMS over NR/5GC | Rel-15 | WI-505 | 54 / 101 | +9 | Prio1: 21/21 ; Prio2: 33/80 +4 under verification
5G Positioning | Rel-15 | WI-506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 6: Progress – TTCN verification (Status on 15th Feb’22)
Progress – 4G (LTE, NB-IoT):
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | WI-088 | 13 / 14 | = | Left: TC 8.4.5.4(LTE to HRPD HO)
LTE/UMTS Inter-RAT | Rel-9 | WI-167 | 11 / 12 | = | Left: TC 13.1.21(emergency call)
LTE/GERAN Inter-RAT | Rel-9 | WI-168 | 3 / 4 | = | Left: TC 13.1.21(emergency call)
LTE/C2K Inter-RAT | Rel-10 | WI-180 | 1 / 2 | = | Left: TC 8.6.5.3(MDT RLF logging)
LTE/GERAN Inter-RAT | Rel-10 | WI-182/184 | 1 / 2 | = | Left: TC 8.6.5.2(MDT RLF logging)
CA intraband cont | Rel-11 | WI-162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | WI-245 | 6 / 9 | = | 
eDRX | Rel-13 | WI-253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | WI-254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | WI-254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | WI-257 | 71 / 73 | = | Left: TCs 22.1.1.M2, 22.4.26
LAA | Rel-13 | WI-272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | WI-295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: Progress – TTCN verification (Status on 15th Feb’22)
Started:
Starting:
Feature | Rel- | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
5G network slicing enhancements | Rel-16 | None | 1 / 5 | +1 | +2 under verification
NR RACS | Rel-16 | None | 2 / 8 | +2 | +1 under verification
Feature | Rel- | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
NR mobility enhancements | Rel-16 | None | 0 / 10 |  | +2 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 8: Summary & open issues from TTCN Workshop #56 (3rd Feb’22)
Test Models – 5G:
  NR RRC connection re-establishment procedure: endorsed TTCN test sequence updates.
  NR ASPs: discussed updates to control the NDI toggle in NR DCIs and the MacBearerRouting field.
  Multi-DNNs: endorsed adding new IP PIXITs required for supporting new 5G slices/DNNs.
  NE-DC: endorsed new test models for NE-DC L3 and NE-DC L2 (PDCP).
  5G V2X: endorsed updated test model & ASPs.
  NR URLLC: discussed NR ASPs updates to support NR DCIs x_2.
  NR SON/MDT: endorsed new test model for NR/WLAN Inter-RAT.
  NR UE power saving: endorsed NR ASP updates to support NR DCI 2_6.
  Prose CRs to TS 38.523-3 proposed at RAN5#94-e for the above.

## Slide 9: Summary & open issues from TTCN Workshop #56 (3rd Feb’22)
Test Models – POS:
  Rel-16 NR positioning: endorsed NR ASP updates for Multi-RTT (UL SRS).
  5G V2X: endorsed addition of GNSS test model for NR sidelink.
  Prose CRs to TS 37.571-4 proposed at RAN5#94-e for the above.
Test Models – MCX:
  MCData:
    endorsed HTTP & SDP ASP updates.
    endorsed test model updates and new ASPs for MSRP (RFC 4975).
    endorsed dedicated EPS Bearer configuration updates.
  MCVideo:
    endorsed new ASPs for transmission control protocol.
    endorsed dedicated EPS Bearer configuration updates.
  Prose CR to TS 36.508, 36.579-5 proposed at RAN5#94-e for the above.

## Slide 10: Status of TTCN tasks in 2022 – 2021 tasks completion
78 | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of Feb’22) / Comments
MCX: PTT, Video, Data | Rel-14 | L | Q3’20 | 106 | Q3’17-Q2’22 | 4 | 51% (@iwd-21wk49)
LTE CA band combinations | R15to16 | L | Q1’22 | n/a | Q1’19-Q1’22 | 0.1 | 38% (@iwd-21wk49)
MTC (even) further enhanced | R14to15 | L | Q4’21 | 18 | Q1’18-Q1’22 | 1 | 11% (@iwd-21wk49)
NB-IoT further enhanced | Rel-15 | L | Q3’21 | 8 | Q2’20-Q1’22 | 0.5 | 60% (@iwd-21wk49)
MCX enhancements | Rel-15 | L | Q2’22 | 67 | Q3’21-Q4’22 | 6 | 23% (@iwd-21wk49)
LTE mobility even further enh. | Rel-16 | L | Q2’22 | 11 | Q4’20-Q2’22 | 1 | Not started
5GS: NR/5GC (option 2) | Rel-15 | N,L | Q1’22 | 447 | Q3’18-Q1’22 | 1 | 95% (@iwd-21wk49)
UE RACS optimisations | Rel-16 | N,L | Q1’22 | 14 | Q4’20-Q1’22 | 1 | 33% (@iwd-21wk49)
NR UE power saving | Rel-16 | N | Q1’22 | 9 | Q4’20-Q1’22 | 0.5 | 11% (@iwd-21wk49)
NR industrial IoT | Rel-16 | N,L | Q1’22 | 6 | Q4’20-Q1’22 | 1 | Not started
5G V2X with NR sidelink | Rel-16 | N,L | Q2’22 | 74 | Q4’20-Q3’22 | 6 | 7% ; Test Model work
Private network support | Rel-16 | N | Q1’22 | 14 | Q4’20-Q1’22 | 0.5 | 64% (@iwd-21wk49)
NR mobility enhancements | Rel-16 | N | Q2’22 | 14 | Q4’20-Q2’22 | 0.5 | 92% (@iwd-21wk49)
NR MIMO enhancements | Rel-16 | N | Q2’22 | 1 | Q4’20-Q2’22 | 0.5 | Not started
NR SON & MDT support | Rel-16 | NLWB | Q1’22 | 47 | Q1’21-Q1’22 | 1 | 80% (@iwd-21wk49)
NR URLLC phy layer enh. | Rel-16 | N | Q2’22 | 5 | Q2’21-Q2’22 | 1 | 5% ; Test Model work
IMS eCall over NR | Rel-16 | N | Q3’22 | 18 | Q3’21-Q3’22 | 2 | Not started
NR positioning support | Rel-16 | N | Q1’22 | 14 | Q2’21-Q1’22 | 0.5 | 35% (@iwd-21wk49)
NW slicing enhancements | Rel-16 | N | Q4’21 | 5 | Q3’21-Q1’22 | 0.1 | 80% (@iwd-21wk49)
NR new/extended bands | R16to17 | N | Q2’22 | n/a | Q1’21-Q2’22 | 0.2 | 48% (@iwd-21wk49)
5G CA/DC band combinations | R16to17 | N,L | Q2’22 | n/a | Q1’21-Q2’22 | 0.2 | 7% (@iwd-21wk49)
Total: |  |  |  | 878 |  | 28.6 | man.months
Notes: Note: TTCN of some features initially started in 2021 will only be completed in 2022 due to availability of prose late in CY2021, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 11: Status of TTCN tasks in 2022 – 2022 tasks & maintenance
2022 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of Feb’22) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q1’22 | 35 | Q1’22-Q4’22 | 6 | 5% ; Test Model work
NR 2-step RACH | Rel-16 | N | Q1’22 | 4 | Q1’22-Q2’22 | 1 | Not started
MR-DC & NR CA enh. | Rel-16 | N,L | Q4’22 | 25 | Q1’22-Q4’22 | 3 | Not started
NR in unlicensed spectrum | Rel-16 | N | Q4’22 | 13 | Q1’22-Q4’22 | 3 | Not started ; no prose
NR FR1 RF requirements | Rel-16 | N | Q2’22 | 6 | Q1’22-Q2’22 | 1 | Not started ; no prose
LTE/NR multi-SIM UEs | Rel-17 | N,L | Q3’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item
NR & MR-DC SON/MDT enh. | Rel-17 | N,L | Q2’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item
Reduced capability NR UEs | Rel-17 | N | Q2’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item
NR multi/broadcast services | Rel-17 | N | Q2’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item
NW slicing enh. Phase2 | Rel-17 | N | Q4’22 | FFS | Q4’22-Q4’23 | 0.4 | New Test Work Item
NR UE power saving enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_UE_pow_sav_enh ; no Test Work Item
NR RAN slicing enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_slice ; no Test Work Item
NR positioning enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_pos_enh ; no Test Work Item
NR sidelink enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_SL_enh ; no Test Work Item
NR sidelink relay | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_SL_relay ; no Test Work Item
NR operation up to 71GHz | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_ext_to_71GHz ; no Test Work Item
NR coverage enh. | Rel-17 | N | Q2’23 | FFS | FFS | FFS | New Test Work Item
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 20 | Q1’22-Q4’22 | 2 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >103 |  | 72.4 | man.months
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12: Status of TTCN funding in 2022
2022 workload is estimated at 101 man.months (mm), see previous slides.
PCG#47/OP#46 approved the 3GPP funding of 58 mm for 2022 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2022.
Current commitments for 2022 are as follows:
3GPP companies / 3GPP MRPs committed to provide 17 mm as voluntary contributions for 2022 TTCN development.
Total resources of 101 mm  no estimated funding gap.
Funding |  | 
Entity | Man.months | Comments
3GPP | 58 | PCG#47/OP#46 approved (decision OP46/08)
CTIA/PTCRB | 12 | 5GS, MCX
GCF | 12 | 5GS, MCX
Qualcomm | 2 | RACS, NPN, IMSoNR eCall
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Man.months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 5GS, V2X, NB-IoT, LCR TDD
Anritsu | 1 | 5GS
Keysight | 1 | 5GS
Rohde&Schwarz | 1 | 5GS
Total: | 17 | 

## Slide 13: Annexes

## Slide 14: TTCN baseline and deliveries – 2022 schedule
One TTCN-2 full deliveries (FDD & LCR TDD) and five TTCN-3 full deliveries / year.
  Q2/Q3/Q4 dates tentative: dependent on RAN/RAN5 meetings being physical or electronic (TBC).
Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
  Rel-17 Stage3 freeze scheduled by 3GPP in March 2022.
  Rel-17 ASN.1 freeze scheduled by 3GPP in June 2022.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 21-Jan |  | 
wk12 | 25-Mar | 21-Mar | 25-Mar | TTCN-3 | 
wk18 |  |  | 29-Apr |  | GCF CAG#70 (3-6 May)
wk24 | 17-Jun | 13-Jun | 17-Jun | TTCN-3 | 
wk30 |  |  | 22-Jul |  | GCF CAG#71 (26-27 Jul)
wk37 | 16-Sep | 12-Sep | 16-Sep | TTCN-3 | 
wk42 |  |  | 14-Oct |  | GCF CAG#72 (18-19 Oct)
wk43 | 28-Oct | 19-Oct | 28-Oct | TTCN3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk48 | 01-Dec | 28-Nov |  | TTCN2 (FDD) | 
wk48 | 02-Dec | 28-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 09-Dec | 05-Dec | 09-Dec | TTCN-3 | 

## Slide 15: 5GS Rel-15 – Protocol test case numbers Before RAN5#94-e
5GS Rel-15 | TCs # | Details
NR/5GC (5G option 2) | Total: 447 | IdleMode: 60, NR L2: 81, NR RRC: 106, 5GC: 57, Multilayer: 32, IMS: 101, POS: 10.
EN-DC (5G option 3) | Total: 125 | NR L2: 71, RRC: 51, EPC: 3, IMS, POS: none.
NE-DC (5G option 4) | Total: 35 | NR L2: 2, NR RRC: 33, IdleMode, 5GC, Multilayer, IMS, POS: none.
TOTAL: | 607 | 
Notes: Legend:
Blue: changes from last MCC TF160 report.