## Cover sheet
3GPP TSG-RAN WG5 Meeting #94-e | [10 empty] | R5-220969
Electronic Meeting, 21st Feb. - 04th Mar. 2022
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance Test Aspects for Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)
Work item code: | DC_Pcmax_3UL_CC-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) work item is to define the UE RF requirements for EN-DC combinations with 3CC uplink and 2 different bands (2CC LTE, 1CC NR FR1) with the example uplink EN-DC combination DC_7C_n78A, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. At the RAN#94 meeting in December 2021 the Rel-16 RAN5 work item for UE Conformance Test Aspects for Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core work item. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 71% (+71%) | 0 | 2 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
NSA Option 3 (EN-DC) |  | 70.8% (+70.8%) | 0 | 2 (+2)
FR1 |  | 70.8% (+70.8%) | 0 | 2 (+2)
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2
NR RF
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3 | 69.7% (+69.7%) | 0 | 2 (+2) | 69.7% (+69.7%) | 0 | 2 (+2)
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+100%) |  |  | 100% (+100%)
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-213228 | New WID on UE Conformance Test Aspects for Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)
Note on B23: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | DC_Pcmax_3UL_CC-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Yaping Zhang, Huawei |  |  | zhangyaping13@huawei.com | [5 empty] | WP item completion |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2
70.8% (+70.8%)
[14 empty] | 9 (+9) | 0 | 0
[14 empty] | 6.5 (+6.5) | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.3 | Reference test conditions | Adding test frequency for DC_7C_n78 with 3UL | Huawei | RAN5#94 (Feb-22) | R5-220960 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NR RF/RRM
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
2 |  | 38.521-3 | 6.1 | General | Adding common uplink configuration for E-UTRA CA | Huawei | RAN5#94 (Feb-22) | R5-220961 |  | 0.2 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
3 | Y | 38.521-3 | 6.2B.1.3_1 | 6.2B.1.3_1 UE Maximum Output Power for Inter-Band EN-DC within FR1 (2 E-UTRA CCs, 1 NR CC) | Adding test cases for Maximum Output Power for inter-band EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | Huawei | RAN5#94 (Feb-22) | R5-221908 | TP analysis is missing. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
4 |  | 38.521-3 | 6.2B.4.1.0 | Minimum conformance requirements | Adding minimum requirements for Configured Output Power for inter-band EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | Huawei | RAN5#94 (Feb-22) | R5-221909 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
5 | Y | 38.521-3 | 6.2B.4.1.3_1 | 6.2B.4.1.3_1 Configured Output Power for Inter-Band EN-DC within FR1 (2 E-UTRA CCs, 1 NR CC) | Adding test cases for Configured Output Power for inter-band EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | Huawei | RAN5#94 (Feb-22) | R5-221909 | TP analysis is missing. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
6 |  | 38.521-3 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances | Huawei | RAN5#94 (Feb-22) | R5-221910 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
7 |  | 38.522 | 4 | Test case conditions and selection criteria | Adding test case condition for inter-band EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | Huawei | RAN5#94 (Feb-22) | R5-220965 |  | 0.2 | 100% (+100%) | 100% (+100%) |  | 100%
8 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Adding test case applicability statements for the new test cases introduced for 38.521-3 | Huawei | RAN5#94 (Feb-22) | R5-220966 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
9 |  | 38.905 | 4.3 | Test point analysis for test cases in TS 38.521-3 | Adding TP analysis for EN-DC RF test cases |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.