## WP scope
Work plan for introduction of PC3 NR CA FR1 configurations into 3GPP UE conformance test specifications
| WP Template: | v1
Note! A copy of the completed work plan shall be attached to the CR to TS 38.508-2 adding the EN-DC configuration(s) to clause A.4.3.1 (see Step 4 of the work plan).
Workplan scope
| Workplan Name |  | Rel-16: CA_n5A-n7A, CA_n5A-n78A, CA_n7A-n78A | [6 empty] | <= Enter WP name
| Company (Contact) |  | Ericsson (Leif Mattisson) | [6 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | RAN5#94-e | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
Target configurations
Note: A work plan can include mutiple target configurations but it is recomended to create separate work plans for Intra band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A13 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs
| Rel-16 | NR CA FR1 | 38.101-1:Table 5.5A.3.1-1 | CA_n5A-n7A | - | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | <RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest
| Rel-16 | NR CA FR1 | 38.101-1:Table 5.5A.3.1-1 | CA_n5A-n78A | - | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | <RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest
| Rel-16 | NR CA FR1 | 38.101-1:Table 5.5A.3.1-1 | CA_n7A-n78A | - | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | <RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest

## WP NR CA PC3 FR1
Work plan for introduction of PC3 NR CA FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of the completed work plan shall be attached to the CR to TS 38.508-2 adding the NR CA configuration(s) to clause A.4.3.1 (see Step 4 below). | [16 empty] | WP Template: v1
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  | CA configurations [DL/UL]
|  | FR1 NR CA configuration(s) without UL CA |  |  | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/-
FR1 NR CA configurations with UL CA
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations |  |  |  |  | 100%
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 100%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1) |  |  |  |  | 100%
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7) |  |  |  |  | 100%
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: Declare completion of EN_DC configurations by CR to TS 38.508-2 (after completion of step 1 to 3) |  |  |  |  | 100%
3. Details
[8 empty] | WP item columns to be filled in |  |  |  | Do not edit |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Bands completed | TCs available
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands completed | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in RAN5 PRD21 worksheet "NR bands". | Leif | RAN5#94-e |  | NR bands n5, n7 and n78 are completed | 1 | 100% | 100%
All | 1-2 | Pre-requisite | 38.521-2 | 6, 7 | All applicable Transmitter (clause 6) and Receiver (clause 7) for the type of NR CA configuraiton completed | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | Set status in column "TCs available" to 100% when all applicable test cases in 38.521-2 are completed for at least one of the same NR CA type of CA configuraion. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. | Leif | RAN5#94-e |  | All test cases for 2DL CA indicated as completed in Rel-15 5G NR WP (R5-216625) | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
TP analysis
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
UL | 3 | TP Analysis | 38.905 | 4.1.2 | Test point (TP) analysis for A-MPR |  | For each UL CA configuration perform an A-MPR TP analysis as described in TR 38.905 clause 4.1.2 for intra-band contiguous UL CA and in clause 4.1.3 for inter-band UL CA. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 38.905. |  | RAN5#94-e |  |  | 1 |  | 0%
All | 2-2 | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For each 2DL- 5DL CA configuration including any intra-band contiguous CCs or any intra-band non-contiguous CCs or any inter-band UL CA CCs perform referense sensitivity TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. | Mats | RAN5#94-e | [R5-220357], [R5-220358], [R5-220359] |  | 1 | 100% | 100%
UL | 2-3 | TP Analysis | 38.905 | 4.1.3.2 | Test point (TP) analysis for UE co-extance test cases for inter-band UL CA |  | For each two band UL CA inter-band configuration perform UE-coexistnce spurious emission TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5#94-e |  |  | 1 |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Test Freq.
1
All | 3.1-1 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1 | Test frequencies | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | - Check that the involved bands have single carrier test frequencies specified in 4.3.1.x - For NR CA configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in in clause A.4.3.2A. | Leif | RAN5#94-e |  | No change needed | 1 | 100% | 100%
All | 3.1-2 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.2 | Test frequencies for CA signalling test | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.2 (protocol testing limited to 2CC NR CA configurations) |  | RAN5#94-e |  | N/A (WP scope is inter-band) | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Clause 5
1
All | 3.2-1 | 36.521-1 - General | 38.521-1 | 5.2A.1 | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For intra-band contiguous and non-contiguos CA configrurations add the CA operating bands to the relevant table in clause 5.2.A.1. | Mats | RAN5#94-e |  | N/A (inter-band only) | 1
All | 3.2-2 | 36.521-1 - General | 38.521-1 | 5.2A.2 | Inter-band CA operating bands | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For inter-band CA configurations add the CA operating bands to the relevant table in clause 5.2A.2. | Mats | RAN5#94-e | [TDOC Jumbo CR TBD] | To be included in jumbo CR provided by China Unicom (Yu Shi) | 1 | 100% | 100%
All | 3.2-3 | 36.521-1 - General | 38.521-1 | 5.5A.1 | Configurations for intra-band contiguous CCs | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For intra-band contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.1. | Mats | RAN5#94-e |  | N/A (inter-band only) | 1
All | 3.2-4 | 36.521-1 - General | 38.521-1 | 5.5A.2 | Configurations for intra-band non-contiguous CCs | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For intra-band non-contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.2. | Mats | RAN5#94-e |  | N/A (inter-band only) | 1
All | 3.2-5 | 36.521-1 - General | 38.521-1 | 5.5A.3 | configurations for inter-band CCs | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For inter-band CA configurations add the CA configurationto the relevant table in clause 5.5A.3. | Mats | RAN5#94-e | [TDOC Jumbo CR TBD] | To be included in jumbo CR provided by China Unicom (Yu Shi) | 1 | 100% | 100%
UL | 3.2-6 | 36.521-1 - General | 38.521-1 | 6.2A.4.0.2 | ΔTIB,c for CA |  | For inter-band CA configurations add ΔTIB,c for the CA configuraiton to the relevant table in clause 6.2A.4.0.2. |  | RAN5#94-e |  |  | 1 |  | 0%
All | 3.2-7 | 36.521-1 - General | 38.521-1 | 7.3A.0.3 | ΔRIB,c for CA | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For inter-band CA configurations add ΔRIB,c for the CA configuration to the relevant table in clause 7.3A.0.3. | Mats | RAN5#94-e | [R5-220361], [R5-220362] |  | 1 | 100% | 100%
All | 3.2-8 | 36.521-1 - General | 38.521-1 | 7.3A.0.4 | Reference sensitivity exceptions due to UL harmonic interference for CA | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For inter-band CA configurations add the reference sensitivity exceptions, Uplink configuration and MSD for inter-band CA to the relevant table in clause 7.3A.0.4. | Mats | RAN5#94-e | [R5-220361], [R5-220362] |  | 1 | 100% | 100%
All | 3.2-9 | 36.521-1 - General | 38.521-1 | 7.3A.0.5 | Reference sensitivity exceptions due to intermodulation interference due to 2UL CA | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For inter-band CA configurations add Reference sensitivity and Uplink/Downlink configurations for the CA configuration to the relevant table in clause 7.3A.0.5. | Mats | RAN5#94-e | [R5-220360], [R5-220361] |  | 1 | 100% | 100%
All | 3.2-10 | 36.521-1 - General | 38.521-1 | 7.3A.0.6 | Reference sensitivity exceptions due to cross band isolation for CA | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | For inter-band CA configurations add Reference sensitivity and Uplink/Downlink configurations for the CA configuration to the relevant table in clause 7.3A.0.6. | Mats | RAN5#94-e | [R5-220362] |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
UL | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.3 | UE maximum output power for Inter-band CA |  | For configurations including any inter-band UL CA CCsc add the UE maximum output power for inter-band UL CA to Table 6.2A.1.0.3-1. |  | RAN5#94-e |  |  | 1 |  | 0% |  | 0% |  | 0%
UL | 3.1-2 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.4 | UE maximum output power for Intra-band contiguous CA |  | For configurations including any Intra-band contiguous UL CA add the UE maximum output power for Intra-band contiguous UL CA to Table 6.2A.1.0.4-1. |  | RAN5#94-e |  |  | 1 |  | 0% |  | 0% |  | 0%
UL | 3.3-3 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.1 | UE maximum output power for CA (2UL CA) |  | For any FR1 Inter-band/Intra-band non-contiguous 2UL CA configurations add the test requirements for Inter-band/Intra-band non-contiguous 2UL CA to Table 6.2A.1.1.5-1. |  | RAN5#94-e |  |  | 1 |  | 0% |  | 0% |  | 0%
UL | 3.3-4 | 38.521-1- RF Tx | 38.521-1 | 6.2A.3.1 | UE additional maximum output power reduction for CA (2 UL CA) |  | For inter-band CA (2 UL CA) add the Initial Conditions to Table 6.2A.3.1.4.1-1; Add tables for inter-band CA (2 UL CA) in Section 6.2A.3.1.5 Test requirement. |  | RAN5#94-e |  |  | 1 |  | 0% |  | 0% |  | 0%
UL | 3.3-5 | 38.521-1- RF Tx | 38.521-1 | 6.5A.3.2 | Inter-band spurious emission for UE co-existence Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 5) |  | For configurations with inter-band UL CA: - Add the minimum conformance requirements - If the TP analysis in Step 2 (WP item 5) shows that additional TPs more than the default TP#1 and TP#2 are needed add all test points (including default TPs if applicable) based on the TP analysis done in Step 2 (WP item 5). - Add test requirement based on the TP analysis done in Step 2 (WP item 4-2). |  | RAN5#94-e |  |  | 1 |  | 0% |  | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.4-1 | 36.521-1-RF Rx | 38.521-1 | 7.3A.1~4 | Reference sensitivity power level for 2DL to 5DL CA Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 4-1) | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | Add test configuration and test requirements for any exceptional requirements based on TR 38.905 reference sensitivity TP analysis in Step 2 (WP item 4-1). | Mats | RAN5#94-e | [R5-220360], [R5-220361], [R5-220362] |  | 1 | 100% | 100% |  | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
| 3.5-1 |  |  |  |  | - | No changes needed |  | RAN5#94-e |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 |  |  |  |  | - | No changes needed |  | RAN5#94-e |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: Declare completion of EN_DC configurations by CR to TS 38.508-2 (after completion of step 1 to 3)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.1 | Declaration of NR CA configurations completion | CA_n5A-n7A/- CA_n5A-n78A/- CA_n7A-n78A/- | The completion of NR CA configurations covered by this work plan is done by a CR to TS 36.508-2 adding the CA Physical Layer Baseline Implementation Capabilities for the CA configurations in Annex A.4.3.1. Any exceptions for not completed parts need to be stated in the CR cover sheet and as a note for the entry of the CA configuration in the CA Physical Layer Baseline Implementation Capabilities table. This work plan shall be attached to the CR in the TDOC zip-file. | Leif | RAN5#94-e | [R5-221006] |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N26: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N34: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N44: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N52: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N68: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N79: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N86: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N93: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N100: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.