## Cover sheet
3GPP TSG-RAN WG5 Meeting #94-e | [10 empty] | R5-221148
Electronic Meeting, Feb 21st - Mar 4th 2022
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE 5G NR Application Layer Data Throughput Performance
Work item code: | FS_UE_5GNR_App_Data_Perf
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
A RAN5 Study Item concerning UE Application Layer Data Throughput Performance was approved at the RAN#84 meeting in June 2019[1]. The SID was further revised at the RAN5-89-e meeting in Novembewr 2020 [2]. The objective of this Study Item is to define test procedures to measure UE data throughput performance at the application-layer for 5G. In particular the SI is expected to cover: (1) Fixed reference measurement channels, already defined existing fixed reference measurement channels scenarios already defined in core and test specifications; (2) Variable reference measurement channels, including study the feasibility of defining requirements with link adaptation in RAN4 and RAN5 to define application layer throughput procedures based on VRC scenarios defined by RAN4. The result of the study is to be presented in a new technical report: TR 37.901-5. The purpose of present document is to provide a work plan for the RAN5 study item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+4%) | 24 (+8) | 26 (-1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 99.9% (+3.7%) | 24 (+8) | 26 (-1)
FR1 |  | 99.9% (+3.7%) | 24 (+8) | 26 (-1)
FR2
FR1 + FR2
NSA Option 3 (EN-DC) |  | 99.9% (+3.7%) | 24 (+8) | 26 (-1)
FR1 |  | 99.9% (+3.7%) | 24 (+8) | 26 (-1)
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
Study on 5G NR Application Layer Data Throughput Performance | 37.509-5
5 References
[1] RP-191590 | New SID: Study on 5G NR Application Layer Data Throughput Performance
[2] R5-206285 | Study on 5G NR Application Layer Data Throughput Performance (Updated SID)
[3] R5-211367 | WP - 5G NR User Equipment (UE) Application Layer Data Throughput Performance
[3] R5-215645 | WP - 5G NR User Equipment (UE) Application Layer Data Throughput Performance
[4] R5-217513 | WP - 5G NR User Equipment (UE) Application Layer Data Throughput Performance
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE 5G NR Application Layer Data Throughput Performance | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | FS_UE_5GNR_App_Data_Perf
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 study item UE 5G NR Application Layer Data Throughput Performance with the outcome presented in TR 37.905-5. | [13 empty] | vs Area
WP Resp: |  | Vijay Balasubramanian, Qualcomm |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | Vijay Balasubramanian, Qualcomm |  |  | vijayb@qti.qualcomm.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 99.9% (+3.7%) |  |  | 99.9% (+3.7%)
[15 empty] | 72 (-1) | 0 | 0 | 72 (-1) | 0 | 0
[15 empty] | 112.5 (-1) | 0 | 0 | 112.5 (-1) | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Application Layer Data Throughput Performance
TR 37.901-5: Study on 5G NR Application Layer Data Throughput Performance
Introduction
1 |  | 37.901-5 | 1 | Scope |  |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
2 |  | 37.901-5 | 2 | References |  |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
3 |  | 37.901-5 | 3 | Definitions |  |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
4 |  | 37.901-5 | 4 | Background and Study Item Objective |  |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
5 |  | 37.901-5 | 4.1 | Study Item Objective | Technical objective of this study item | Qualcomm | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
Study & Conclusions
6 |  | 37.901-5 | 5 | Study on 5G NR UE Application Layer Data Throughput Performance |  |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
7 |  | 37.901-5 | 5.1 | Definition of Application Layer Data Throughput Performance |  | Qualcomm | RAN5#89-e (Nov-20) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
8 |  | 37.901-5 | 5.2 | Parameters for Measurement |  | Qualcomm | RAN5#89-e (Nov-20) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
9 |  | 37.901-5 | 5.3 | Test Configurations | Clause title |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
10 |  | 37.901-5 | 5.4 | Transport and Application Layer Protocols | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
11 |  | 37.901-5 | 5.5 | Test Environment | Clause title |  | RAN5#93 (Nov-21) | R5-218278 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
12 |  | 37.901-5 | 5.6 | Data Transfer Scenarios | Clause title |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
13 |  | 37.901-5 | 5.7 | Statistical Analysis | Clause title | Qualcomm | RAN5#89-e (Nov-20) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
14 |  | 37.901-5 | 5.8 | Impact of Modem Performance in Application Layer Throughput | Clause title | Qualcomm | RAN5#92 (Aug-21) | R5-211782 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
15 |  | 37.901-5 | 5.9 | Test System Uncertainty and Test Tolerance | Clause title |  | RAN5#93 (Nov-21) | R5-217181 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
96 |  | 37.901-5 | 5.10 | Feasibility of Defining Link Adaptation Absolute Physical Layer Requirements | Clause title | Qualcomm | RAN5#92 (Aug-21) | R5-216139 | RAN4 test points/simulation details are added | 75 |  |  |  |  | 100% |  |  | 100%
16 |  | 37.901-5 | 6 | Conclusions | Clause title |  | RAN5#92 (Aug-21) | R5-210597 R5-221785 |  | 0.5 | 100% (+30%) | 100% (+30%) | 100% (+30%) |  | 100% |  |  | 100%
Test Procedures
17 |  | 37.901-5 | Annex A | 5G NR UE Application Layer Data Throughput Test Procedures | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
18 |  | 37.901-5 | Annex A.1 | Introduction/Purpose of Annex | <Task> |  | RAN5#89-e (Nov-20) |  | Subclauses may be added to cover Applicability and leverage rules. As needed refer back to TS 38.521-4 to avoid repetition | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
CONDUCTED TCP DOWNLINK - STATIC CHANNEL
19 |  | 37.901-5 | Annex A.2 | 5G NR /TCP Downlink Throughput /Conducted/Static Peak Throughput for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
20 |  | 37.901-5 | Annex A.2.1 | 5G NR /TCP Downlink Throughput /Conducted/Static Channel Peak Throughput tests for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
21 | Y | 37.901-5 | Annex A.2.1.1 | 5G NR /TCP Downlink Throughput /Conducted/Static Channel/ SA and NSA (no Downlink Split Bearer) |  | Qualcomm | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
22 | Y | 37.901-5 | Annex A.2.1.2 | 5G NR /TCP Downlink Throughput /Conducted/Static Channel/NSA (Downlink Split Bearer) |  | Qualcomm | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
CONDUCTED TCP DOWNLINK - FADING (FRC)
23 |  | 37.901-5 | Annex A.3 | 5G NR /TCP Downlink Throughput /Conducted for Fixed Reference Channel (FRC) Scenarios with Fading for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
24 |  | 37.901-5 | Annex A.3.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
25 |  | 37.901-5 | Annex A.3.1.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC/2Rx for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
26 | Y | 37.901-5 | Annex A.3.1.1.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC/2Rx FDD /FR1 PDSCH mapping Type A performance - for SA and NSA |  | Keysight | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
27 | Y | 37.901-5 | Annex A.3.1.1.2 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC/2Rx TDD /FR1 PDSCH mapping Type A performance - for SA and NSA |  | Keysight | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
28 |  | 37.901-5 | Annex A.3.1.2 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC/4Rx for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
29 | Y | 37.901-5 | Annex A.3.1.2.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC/4Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA |  | Qualcomm | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
30 | Y | 37.901-5 | Annex A.3.1.2.2 | 5G NR /TCP Downlink Throughput /Conducted/Fading/FRC/4Rx TDD/FR1 PDSCH mapping Type A performance - for SA and NSA |  | Keysight | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
CONDUCTED UDP DOWNLINK - STATIC CHANNEL
31 |  | 37.901-5 | Annex A.4 | 5G NR /UDP Downlink Throughput /Conducted/Static Peak Throughput for SA and NSA | Clause title | Qualcomm | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
32 |  | 37.901-5 | Annex A.4.1 | 5G NR /UDP Downlink Throughput /Conducted/Static Channel Peak Throughput tests for SA and NSA | Clause title | Qualcomm | RAN5#89-e (Nov-20) |  | Phy parameters from SDR | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
33 | Y | 37.901-5 | Annex A.4.1.1 | 5G NR /UDP Downlink Throughput /Conducted/Static Channel/ SA and NSA (no Downlink Split Bearer) |  | Qualcomm | RAN5#89-e (Nov-20) |  | Covers SA and non-split bearer NSA cases which are leveraged between each other as per 4.2 of TS 38.521-4 | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
34 | Y | 37.901-5 | Annex A.4.1.2 | 5G NR /UDP Downlink Throughput /Conducted/Static Channel/NSA (Downlink Split Bearer) |  |  | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
CONDUCTED UDP DOWNLINK - FADING (FRC)
35 |  | 37.901-5 | Annex A.5 | 5G NR /UDP Downlink Throughput /Conducted for Fixed Reference Channel (FRC) Scenarios with Fading for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
36 |  | 37.901-5 | Annex A.5.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
37 |  | 37.901-5 | Annex A.5.1.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC/2Rx for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
38 | Y | 37.901-5 | Annex A.5.1.1.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC/2Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA |  | Keysight | RAN5#89-e (Nov-20) |  | title updated | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
39 | Y | 37.901-5 | Annex A.5.1.1.2 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC/2Rx TDD/FR1 PDSCH mapping Type A performance - for SA and NSA |  | Keysight | RAN5#89-e (Nov-20) |  | title updated | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
40 |  | 37.901-5 | Annex A.5.1.2 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC/4Rx for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
41 | Y | 37.901-5 | Annex A.5.1.2.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC/4Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Keysight | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
42 | Y | 37.901-5 | Annex A.5.1.2.2 | 5G NR /UDP Downlink Throughput /Conducted/Fading/FRC/4Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Keysight | RAN5#89-e (Nov-20) |  |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
RADIATED TCP DOWNLINK - STATIC CHANNEL
43 |  | 37.901-5 | Annex A.6 | 5G NR /TCP Downlink Throughput/Radiated/Static Peak Throughput for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  | E-UTRA is a functional link | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
44 | Y | 37.901-5 | Annex A.6.1 | 5G NR /TCP Downlink Throughput /Radiated/Static Channel Peak Throughput tests for SA and NSA |  | Qualcomm | RAN5#89-e (Nov-20) |  | Phy parameters from SDR | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
RADIATED TCP DOWNLINK - FADING (FRC)
45 |  | 37.901-5 | Annex A.7 | 5G NR /TCP Downlink Throughput /Radiated for Fixed Reference Channel Scenarios (FRC) with Fading | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
46 |  | 37.901-5 | Annex A.7.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/FRC | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
47 |  | 37.901-5 | Annex A.7.1.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/FRC/2Rx | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
48 | Y | 37.901-5 | Annex A.7.1.1.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/FRC/2Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA |  | Qualcomm | RAN5#92 (Aug-21) | R5-214097 R5-220513 | Editor’s note: Test points 2-2, 2-6 are currently not testable for n260 and n259 pending further optimization of maximum testable SNR in TS 38.521-4 | 1 | 95% | 95% | 95% |  | 95% |  |  | 95%
49 |  | 37.901-5 | Annex A.7.1.2 | 5G NR /TCP Downlink Throughput /Radiated/Fading/FRC/4Rx | Clause title |  | RAN5#92 (Aug-21)
50 |  | 37.901-5 | Annex A.7.1.2.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/FRC/4Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA |  |  | RAN5#92 (Aug-21) | R5-210593 R5-220514 | No RAN4 requirement for radiated 4Rx at this time | 0
RADIATED UDP DOWNLINK - STATIC CHANNEL
51 |  | 37.901-5 | Annex A.8 | 5G NR /UDP Downlink Throughput/Radiated/Static Peak Throughput for SA and NSA | Clause title |  | RAN5#89-e (Nov-20) |  | E-UTRA is a functional link | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
52 | Y | 37.901-5 | Annex A.8.1 | 5G NR /UDP Downlink Throughput /Radiated/Static Channel Peak Throughput tests for SA and NSA | <Task> |  | RAN5#89-e (Nov-20) |  | Phy parameters from SDR | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
RADIATED UDP DOWNLINK - FADING (FRC)
53 |  | 37.901-5 | Annex A.9 | 5G NR /UDP Downlink Throughput /Radiated for Fixed Reference Channel Scenarios (FRC) with Fading | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
54 |  | 37.901-5 | Annex A.9.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/FRC | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
55 |  | 37.901-5 | Annex A.9.1.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/FRC/2Rx | Clause title |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
56 | Y | 37.901-5 | Annex A.9.1.1.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/FRC/2Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA |  | Qualcomm | RAN5#92 (Aug-21) | R5-214097 R5-217179 R5-220513 | Editor’s note: Test points 2-2, 2-6 are currently not testable for n259 pending further optimization of maximum testable SNR in TS 38.521-4 | 1 | 95% | 95% | 95% |  | 95% |  |  | 95%
57 |  | 37.901-5 | Annex A.9.1.2 | 5G NR /UDP Downlink Throughput /Radiated/Fading/FRC/4Rx | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
58 | Y | 37.901-5 | Annex A.9.1.2.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/FRC/4Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA |  |  | RAN5#92 (Aug-21) |  | No RAN4 requirement for radiated 4Rx at this time | 0
CONDUCTED TCP DOWNLINK - FADING (VRC)
59 |  | 37.901-5 | Annex A.10 | 5G NR /TCP Downlink Throughput /Conducted for Variable Reference Channel (VRC) Scenarios with Fading for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
60 |  | 37.901-5 | Annex A.10.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
61 |  | 37.901-5 | Annex A.10.1.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC/2Rx for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
62 | Y | 37.901-5 | Annex A.10.1.1.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC/2Rx FDD /FR1 PDSCH mapping Type A performance - for SA and NSA |  | Qualcomm | RAN5#93 (Nov-21) | R5-216121 R5-217177 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
63 | Y | 37.901-5 | Annex A.10.1.1.2 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC/2Rx TDD /FR1 PDSCH mapping Type A performance - for SA and NSA |  | Qualcomm | RAN5#93 (Nov-21) | R5-216121 R5-217177 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
64 |  | 37.901-5 | Annex A.10.1.2 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC/4Rx for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
65 | Y | 37.901-5 | Annex A.10.1.2.1 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC/4Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#92 (Aug-21) | R5-217172 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
66 | Y | 37.901-5 | Annex A.10.1.2.2 | 5G NR /TCP Downlink Throughput /Conducted/Fading/VRC/4Rx TDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#92 (Aug-21) | R5-217172 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
CONDUCTED UDP DOWNLINK - FADING (VRC)
67 |  | 37.901-5 | Annex A.11 | 5G NR /UDP Downlink Throughput /Conducted for Variable Reference Channel (FRC) Scenarios with Fading for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
68 |  | 37.901-5 | Annex A.11.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
69 |  | 37.901-5 | Annex A.11.1.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC/2Rx for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
70 | Y | 37.901-5 | Annex A.11.1.1.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC/2Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#93 (Nov-21) | R5-216121 R5-217177 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
71 | Y | 37.901-5 | Annex A.11.1.1.2 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC/2Rx TDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#93 (Nov-21) | R5-216121 R5-217177 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
72 |  | 37.901-5 | Annex A.11.1.2 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC/4Rx for SA and NSA | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
73 | Y | 37.901-5 | Annex A.11.1.2.1 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC/4Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#92 (Aug-21) | R5-217172 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
74 | Y | 37.901-5 | Annex A.11.1.2.2 | 5G NR /UDP Downlink Throughput /Conducted/Fading/VRC/4Rx FDD/FR1 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#92 (Aug-21) | R5-217172 R5-221784 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  |  | 100%
RADIATED TCP DOWNLINK - FADING (VRC)
75 |  | 37.901-5 | Annex A.12 | 5G NR /TCP Downlink Throughput /Radiated for Variable Reference Channel Scenarios (VRC) with Fading | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
76 |  | 37.901-5 | Annex A.12.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/VRC | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
77 |  | 37.901-5 | Annex A.12.1.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/VRC/2Rx | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
78 | Y | 37.901-5 | Annex A.12.1.1.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/VRC/2Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#93 (Nov-21) | R5-216121 R5-217178 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
79 |  | 37.901-5 | Annex A.12.1.2 | 5G NR /TCP Downlink Throughput /Radiated/Fading/VRC/4Rx | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
80 |  | 37.901-5 | Annex A.12.1.2.1 | 5G NR /TCP Downlink Throughput /Radiated/Fading/VRC/4Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA | <Task> |  | RAN5#92 (Aug-21) |  | No RAN4 requirement for radiated 4Rx at this time | 0
RADIATED UDP DOWNLINK - FADING (VRC)
81 |  | 37.901-5 | Annex A.13 | 5G NR /UDP Downlink Throughput /Radiated for Variable Reference Channel Scenarios (VRC) with Fading | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
82 |  | 37.901-5 | Annex A.13.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/VRC | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
83 |  | 37.901-5 | Annex A.13.1.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/VRC/2Rx | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
84 | Y | 37.901-5 | Annex A.13.1.1.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/VRC/2Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA | <Task> | Qualcomm | RAN5#92 (Aug-21) | R5-216121 R5-217178 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
85 |  | 37.901-5 | Annex A.13.1.2 | 5G NR /UDP Downlink Throughput /Radiated/Fading/VRC/4Rx | Clause title |  | RAN5#92 (Aug-21) |  |  | 0
86 |  | 37.901-5 | Annex A.13.1.2.1 | 5G NR /UDP Downlink Throughput /Radiated/Fading/VRC/4Rx TDD/FR2 PDSCH mapping Type A performance - for SA and NSA | <Task> |  | RAN5#92 (Aug-21) |  | No RAN4 requirement for radiated 4Rx at this time | 0
TBD |  | 37.901-5 |  | TCP Uplink Throughput/Conducted | <Task> |  | TBD |  | Placeholder/FFS | TBD
TBD |  | 37.901-5 |  | UDP Uplink Throughput/Conducted | <Task> |  | TBD |  | Placeholder/FFS | TBD
TBD |  | 37.901-5 |  | TCP Bidirectional Throughput/Conducted | <Task> |  | TBD |  | Placeholder/FFS | TBD
TBD |  | 37.901-5 |  | UDP Bidirectional Throughput/Conducted | <Task> |  | TBD |  | Placeholder/FFS | TBD
TBD |  | 37.901-5 |  | App Tput Procedures for multiple NR CCs (and multiple LTE CCs for NSA) | <Task> |  | TBD |  | Placeholder/FFS | TBD
TBD |  | 37.901-5 |  | Stress Tests | <Task> |  | TBD |  | Placeholder/FFS | TBD
Annex X
87 |  | 37.901-5 | Annex B | Specific Test Conditions and Environment | <Task> |  | RAN5#92 (Aug-21) | R5-218279 R5-221786 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
88 |  | 37.901-5 | Annex C | Specific Connection Diagrams | <Task> |  | RAN5#92 (Aug-21) | R5-210594 | Most connection diagrams will be referenced from 38.521-4 within the test procedures | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
89 |  | 37.901-5 | Annex D | E-UTRA anchor configuration for testing | <Task> | Qualcomm | RAN5#89-e (Nov-20) | R5-214097 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
90 |  | 37.901-5 | Annex E | E-UTRA Anchor Configuration for NSA testing Diagrams | <Task> | Qualcomm | RAN5#92 (Aug-21) | R5-218279 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
91 |  | 37.901-5 | Annex F | Embedded Data Client Recommendations | <Task> | Qualcomm | RAN5#89-e (Nov-20) | R5-218279 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
0
93 |  | 37.901-5 | Annex H | OTA Procedures | <Task> |  | RAN5#92 (Aug-21) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
94 |  | 37.901-5 | Annex I | Reference Test Points | <Task> |  | RAN5#89-e (Nov-20) |  |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
95 |  | 37.901-5 | Annex X | Change History | <Task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.