## Slide 1: RAN5#94-e TTCN Sidebar
Friday 25th February 2022

## Slide 2: Agenda
TTCN Workshop#56 follow-up
  Review of Action Points
  Updates on:
    R5w220005 - NR RRC connection re-establishment
      R5s220197(R&S), R5s220201(R&S)
    R5w220008 - MCX Dedicated Radio Bearers
    R5w220014 - 5G V2X
R5-220671 - NR MAC TC 7.1.1.9.1 (R&S)
NR RRC TC 8.2.2.2.1 (R&S)
  PDCP Duplication / RRC Test model
MCX XSDs handling (TF160)
TTCN baseline and deliveries – 2022 schedule

## Slide 3: TTCN Workshop#56 follow-up
Action 56.1:
  SS Vendors & TF160: To investigate which proposal for the NDI toggle they prefer: R5w220021 or R5s211710. By 11th February.
  Feedback on preference:
    R5w220021: R&S,
    R5s211710: TF160, Anritsu, Keysight.
Action 56.2:
  Action 56.2: TF160: To update R5s211710 to correct the identified issue. By 11th February.
  => Done, R5s211710_MCC160Comments uploaded on 17th February.

## Slide 4: TTCN Workshop#56 follow-up
Action 56.3:
  SS Vendors: To investigate the proposed ASP update for NR CA in R5w220022. By 11th February.
  Feedback on preference:
    Current ASP defs: Keysight,
    R5w220022: R&S, Anritsu,
    Either: TF160.

## Slide 5: TTCN Workshop#56 follow-up
Action 56.4:
  SS Vendors: To check proposed ASP updates for NR URLLC enhancements in R5w220017. By 11th February.
  => No feedback received.
Action 56.5:
  TF160: To check if DRX is configured or not in R5w220024. By 11th February.
  => Done, e-mail sent on 7th February.
Action 56.6:
  UPV/EHU: To check if they can provide values to remove the FFS listed in R5w220008 for MCData. By 11th February.
  => Done, e-mail sent on 16th February.

## Slide 6: TTCN Workshop#56 follow-up
R5w220005 - NR RRC connection re-establishment:
  R5s220197(R&S), R5s220201(R&S)
  => R5w220005r2 prepared.
R5w220008 - MCX Dedicated Radio Bearers:
  Further ASP updates
  => R5w220008r1 prepared.

## Slide 7: TTCN Workshop#56 follow-up
R5w220014 - 5G V2X:
  Further ASP updates: NR_SL_ResourcePool_Type
Added SL_PSSCH_TxParameters :
  In reception it is set according to UE applied transmission parameters.
  In transmission it is set to the NR-SS-UE transmission parameters to be selected acc. to TS 38.321 clause 5.22.1.1. It includes MCS limitations (Min /Max) and HARQ process maximum retransmission parameters.
Added SL_X_Overhead: used for NR-SS-UE to calculate the TBS

## Slide 8: NR MAC TC 7.1.1.9.1
R5-220671 - NR MAC TC 7.1.1.9.1 (R&S)

## Slide 9: NR RRC TC 8.2.2.2.1
NR RRC TC 8.2.2.2.1 (R&S)
  PDCP Duplication / RRC Test model

## Slide 10: MCX XSDs handling
Analysis of XSDs in latest MC Rel-16 core spec versions:
  24.281 (MCVideo)
    some additional definitions, backward compatible
  24.282 (MCData)
    syntax error corrected;
    some additional definitions, backward compatible
  24.379 (MCPTT)
    EmergencyTriggeringCriteria defined
  24.481 (Group configuration)
    minor correction
  24.484 (Mission Critical Services configuration management)
    syntax errors corrected;
    changes of element names not affecting current TTCN, new fields
    MCVideo user profile with many changes, hard to analyse
  33.180 (Security)
    no changes
=> In iwd-22wk12 upgrade the XSDs to latest Rel-16 version for the following specs:
  24.282 (MCData): Rel-16 Sep’21
  24.379 (MCPTT): Rel-16 Dec’21
  24.484 (Mission Critical Services configuration management): Rel-16 Dec’21

## Slide 11: TTCN baseline and deliveries – 2022 schedule
One TTCN-2 full deliveries (FDD & LCR TDD) and five TTCN-3 full deliveries / year.
  Q2/Q3/Q4 dates tentative: dependent on RAN/RAN5 meetings being physical or electronic (TBC).
Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
  Rel-17 Stage3 freeze scheduled by 3GPP in March 2022.
  Rel-17 ASN.1 freeze scheduled by 3GPP in June 2022.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 21-Jan |  | 
wk12 | 25-Mar | 21-Mar | 25-Mar | TTCN-3 | 
wk16 wk18 |  |  | 14-Apr 29-Apr |  | GCF CAG#70 (19-22 Apr) 10DR: 11 Apr (3-6 May)
wk24 | 17-Jun | 13-Jun | 17-Jun | TTCN-3 | 
wk30 |  |  | 22-Jul |  | GCF CAG#71 (26-27 Jul)
wk37 | 16-Sep | 12-Sep | 16-Sep | TTCN-3 | 
wk42 |  |  | 14-Oct |  | GCF CAG#72 (18-19 Oct)
wk43 | 28-Oct | 19-Oct | 28-Oct | TTCN3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk48 | 01-Dec | 28-Nov |  | TTCN2 (FDD) | 
wk48 | 02-Dec | 28-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 09-Dec | 05-Dec | 09-Dec | TTCN-3 |