## Common Test Env
WP Title: | Rel-15 5GS Common Test Environment (TS 38.508-1 and TS 36.508) | [9 empty] | WP item applicability | [7 empty] | End of work plan columns. Note! Do not remove this column. | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
[11 empty] | RAN-CN interface options dependency | [8 empty] | WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan section covers tasks for all SA and NSA options. NR aspects for SA (Stand-Alone) will be part of TS 38.508-1, while LTE aspects of NSA (Non Stand-Alone) will also impact TS 36.508 (see work plan items below for details). | [9 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Bo Jönsson, Ericsson |  |  | bo.jonsson@ericsson.com
TS Resp: | Bo Jönsson, Ericsson |  |  | bo.jonsson@ericsson.com | [6 empty] | SA |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 |  | Opt. 4 |  | Opt. 7 |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[20 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[10 empty] | Overall | 98.18% |  |  | 98.25% |  | 50% | [5 empty] | Anritsu | Hiroyuki.Baba@anritsu.com
[22 empty] | Ericsson 1 | bo.jonsson@ericsson.com
[6 empty] | Overall #WP items: Post WI close #WP items: |  |  |  |  | 55 0 |  |  | 57 0 |  | 2 0 | [5 empty] | Ericsson 2 | petter.karlsson@ericsson.com
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [9 empty] | Phase number (1,2 etc) and completion (%) per option | [10 empty] | NTT DoCoMo | takahiro.arai.kw@nttdocomo.com
TS 38.508 work tasks - Claus 1 - 4: Common part | [21 empty] | Sprint | Scott.Probasco@sprint.com
| 38.508-1 | 1,2,3 | Scope, References, Definitions | [18 empty] | Ericsson 3 | calle.hagenfeldt@ericsson.com
1 | 38.508-1 | 1,2,3 | Scope, References, Definitions |  | Ericsson 1 | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#79 (May-18) | R5-176779, R5-184087 |  | 1 | 100% | 2 | 100% | 1 | 1 | 100% | 1 |  | 1 |  |  |  | Anritsu 2 | Narendra.Kalahasti@anritsu.com
| 38.508-1 | 4.1 - 4.2 | Common test environment | [18 empty] | Qualcomm | yogesht@qti.qualcomm.com
3 | 38.508-1 | 4.1 | Environmental conditions |  | NTT DoCoMo | <Autofilled> | R5-181697, R5-183920 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
4 | 38.508-1 | 4.2 | Common requirements of test equipment |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-176995, R5-182792 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1 |  |  |  | InterTek | bruce.hsueh@intertek.com
| 38.508-1 | 4.3.1 | Test frequencies (General info and skeleton tables. Specific test frequency values for the different NR band and NR/MR-DC band combinations are handled by the NR band/band-combination work plan) | [18 empty] | Keysight | mohit.kanchan@keysight.com
| 38.508-1 | 4.3.1.1 | Test frequencies for NR operating bands in FR1 | [18 empty] | CATT | chenxiaozhong@CATT.CN
5 | 38.508-1 | 4.3.1.1.1 | Operating bands in FR1 |  | Sprint | Opt 2: RAN5#81 (Nov-18) | R5-180577, R5-182108, R5-181973, R5-183256, R5-185250-R5-185270, R5-184471 - R5-184477 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1 |  |  |  | Ericsson 4 | leif.mattisson@ericsson.com
6 | 38.508-1 | 4.3.1.1.2, 4.3.1.1.3 | NR CA in FR1 |  | Sprint | Opt 2: RAN5#83 (May-19) | R5-191274 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1 |  |  |  | Huawei | guchunying@huawei.com
60 | 38.508-1 | 4.3.1.1.4 | Operating bands for NR DC in FR1 |  | Sprint | Opt 2: RAN5#83 (May-19) | R5-191274 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1 |  |  |  | Huawei | guchunying@huawei.com
61 | 38.508-1 | 4.3.1.1.5 | Operating band combination for SUL in FR1 |  | Sprint | Opt 2: RAN5#83 (May-19) | R5-191274 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
| 38.508-1 | 4.3.1.2 | Test frequencies for NR operating bands in FR2
62 | 38.508-1 | 4.3.1.2.1 | Operating bands in FR2 | Create general info and skeleton tables for NR bands. | Sprint | Opt 2: RAN5#81 (Nov-18) | R5-180577, R5-182108, R5-181973, R5-184474 - R5-184477 |  | 1 | 100% | 1 | 100% | 1 | 2 |  | 1 |  | 1
63 | 38.508-1 | 4.3.1.1.2, 4.3.1.1.3 | NR CA in FR2 |  | Ericsson 4 | Opt 2: RAN5#83 (May-19) | R5-194881, R5-194882, R5-194884 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
Test frequencies NR Inter-band CA FR1+FR2
58 | 38.508-1 | 4.3.1.3.1 | Test frequencies NR CA band combinations | Create general info and skeleton tables for SA NR CA band combinations. | Ericsson 4 | Opt 2: RAN5#84 (Aug-19) | R5-196874, R5-196875, R5-196159, R5-196468, R5-196469, R5-196873 |  | 1 | 100% | 4 | 100% | 1 | 4 |  | 1 |  | 1
Test frequencies MR-DC
57 | 38.508-1 | 4.3.1.3.2 | Test frequencies for NR operation with other radios (MR-DC with 2 bands) | Create general info and skeleton tables for DC LTE-NR band combinations with one LTE and one NR band for EN-DC, NE-DC and NGEN-DC. | Sprint | Opt 3: RAN5#79 (May-18) | R5-180577, R5-182108, R5-181973, R5-183218, R5-185173 R5-191302 | Test freqeuncy details for MR DC configurations is handled by the NR band & CA/DC configuration work plan. | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
59 | 38.508-1 | 4.3.1.3.3 - 4.3.1.3.x | Test frequencies for NR operation with other radios (MR-DC with 3 or more bands) | Create general info and skeleton tables for DC LTE-NR band combinations with > 2 bands. | Sprint | Opt 3: RAN5#81 (Nov-18) | R5-191302 | Test frequency details for MR DC configurations is handled by the NR band & CA/DC configuration work plan. | 1 | 100% | 1 |  | 1 | 2 | 100% | 1 |  | 1
55 | 38.508-1 | 4.3.1.3.3 - 4.3.1.3.x | Test frequencies for E-UTRA (MR-DC) |  | Sprint | Opt 3: RAN5#79 (May-18) | R5-183218, R5-185173 | Legacy E-UTRA test frequencies are re-used. Specific needs handled by the NR band and MR DC configuration work plan. | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 4.3.2 | Radio conditions
8 | 38.508-1 | 4.3.2.1 | Radio conditions conducted testing | Definition of radio conditions for NR and DC LTE-NR band combination conducted testing (sub-6GHz) |  | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-182063 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
9 | 38.508-1 | 4.3.2.2 | Radio conditions OTA testing | Definition of radio conditions for NR and DC LTE-NR band combination Over The Air (OTA) testing (mmWave) | FFS | Opt 2: Post WI close Opt 3: Post WI close |  |  | 1 | 0% | 16 | 0% | 1 | 16 | 0% | 1 |  | 16
| 38.508-1 | 4.3.3 | Physical channel allocations
10 | 38.508-1 | 4.3.3.1 | Physical channel allocations E-UTRA | Definition of physical channel allocations for E-UTRA | Ericsson 2 | Opt 3: RAN5#79 (May-18) | R5-182067 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
45 | 38.508-1 | 4.3.3.2 | Physical channel allocations NR for protocol testing | Definition of physical channel allocations for NR and protocol testing | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-182067, R5-183234 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
46 | 38.508-1 | 4.3.3.2 | Physical channel allocations NR for RF testing | Definition of physical channel allocations for NR and RF testing | Ericsson 2 | <Autofilled> | R5-182067, R5-185133 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
| 38.508-1 | 4.3.4 | Signal levels
12 | 38.508-1 | 4.3.4.1 | Signal levels conducted testing | Definition of signal levels for NR for conducted testing (sub-6GHz) | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-182091, R5-183255 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
13 | 38.508-1 | 4.3.4.2 | Signal levels OTA testing | Definition of signal levels for NR for Other The Air (OTA) testing (mmWave) | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-182091 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 4.3.6 | Physical layer parameters
| 38.508-1 | 4.3.6.1 | Downlink physical layer parameters
14 | 38.508-1 | 4.3.6.1.1.1, 4.3.6.1.1.2 | Physical layer parameters for scheduling of PUSCH | Definition of DCI Formats 0_0 and 0_1 | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-180066, R5-181972, R5-182288 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
82 | 38.508-1 | 4.3.6.1.2.1, 4.3.6.1.2.2 | Physical layer parameters for scheduling of PDSCH | Definition of NR DCI Formats 1_0 and 1_1 | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-180066, R5-181972, R5-182288 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
83 | 38.508-1 | 4.3.6.1.3.x | Physical layer parameters for other purposes | Definition of physical layer parameters for NR DCI Format 2_0, 2_1, 2_2, 2_3 | Ericsson 2 | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) | R5-180066, R5-181972 | Chapter void. | 1 | 100% | 4 | 100% | 1 | 5 | 100% | 1 |  | 1
| 38.508-1 | 4.4 | Reference system configurations
15 | 38.508-1, 36.508 | 4.4 | Reference system configurations | Definition of reference system configurations for NSA LTE-NR testing | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-182110, R5-182349 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
100 | 38.508-1 | 4.4.3.1.2 | Combinations of system information blocks for NE-DC |  |  | Opt 4: Post WI close |  |  | 1 | 0% | 1 |  | 1 | 1 |  | 16 | 0% | 1
| 38.508-1 | 4.5 | Generic procedures
19 | 38.508-1 | 4.5 | Generic procedures EN-DC | Definition of generic procedures for NSA LTE-NR testing of option 3 | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-176917, R5-176918, R5-181311, R5-180966, R5-181035, R5-182065, R5-181813, R5-182066, R5-182312, R5-182313, R5-183264 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
20 | 38.508-1 | 4.5 | Generic procedures SA NR | Definition of generic procedures for SA NR testing of option 2 | Ericsson 1 | Opt 2: RAN5#81 (Nov-18) | R5-188122, R5-188123, R5-187753 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
99 | 38.508-1 | 4.5 | Generic procedures NR-DC | Definition of generic procedures for NR-DC | Ericsson 1 | Opt 2: RAN5#87 (May-20) | R5-200956, R5-201222, R5-200957, R5-200958, R5-200959, R5-200960, R5-200961, R5-202024, R5-203079 |  | 1 | 100% | 7 | 100% | 1 | 1 |  | 1 |  | 1
95 | 38.508-1 | 4.5 | Generic procedures SA E-UTRA | Definition of generic procedures for SA NR testing of option 5 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
21 | 38.508-1 | 4.5 | Generic procedures NGEN-DC | Definition of generic procedures for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
22 | 38.508-1 | 4.5 | Generic procedures NE-DC | Definition of generic procedures for NSA LTE-NR testing of option 4 |  | Opt 4: RAN5#93 (Nov-21) | R5-217792, R5-217793, R5-217794, R5-217799, R5-217801, R5-217095, R5-217867 |  | 1 | 100% | 1 |  | 1 | 1 |  | 1 | 100% | 1
94 | 38.508-1 | 4.5 | IMS registration | Definition of IMS registration in generic procedures for NR testing of option 2. | Ericsson 1, Qualcomm | Opt 2: RAN5#82 (Feb-19) | R5-192740 |  | 1 | 100% | 2 | 100% | 1 | 1 |  | 1 |  | 1
97 | 38.508-1 | 4.5 | Generic procedures and environment for 0 and > 2 multi PDUs/PDNs. | Definition of multi PDUs/PDNs environment (default messages) and enhance generic procedures for the case when number of PDUs/PDNs =0 or > 2 | MediaTek | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) | R5-196035 |  | 1 | 100% | 4 | 100% | 1 | 5 | 100% | 1 |  | 1
| 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents
43 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3. | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-176920, R5-180382, R5-180383, R5-180709, R5-180773, R5-180775, R5-181812, R5-182109, R5-182064, R5-182062, R5-181786, R5-181971, R5-182249, R5-182263, R5-182381, R5-183082, R5-183083, R5-183084, R5-183087, R5-183210, R5-183211, R5-183212, R5-183214, R5-183215, R5-183216, R5-183249 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
47 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents. Measurement. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3. Measurement. | NTT DoCoMo | Opt 3: RAN5#81 (Nov-18) | R5-182068, R5-183086, R5-183090, R5-183260 |  | 1 | 100% | 1 |  | 1 | 2 | 100% | 1 |  | 1
48 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents SRB3. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3. SRB3. | Ericsson 3 | Opt 3: RAN5#81 (Nov-18) | R5-181974 |  | 1 | 100% | 1 |  | 1 | 2 | 100% | 1 |  | 1
53 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents. PSCell Add, Mod and Release conditions. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.PSCell Add, Mod and Release conditions. | Qualcomm | Opt 3: RAN5#79 (May-18) |  |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
49 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents MCG PDCP condition. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.MCG PDCP condition. | Ericsson 1 | Opt 3: RAN5#79 (May-18) |  |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1 |  |  |  | Ericsson 4 | leif.mattisson@ericsson.com
84 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents SRB1 and SRB2 NR PDCP condition. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.SRB1 and SRB 2 NR PDCP condition. | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-185028 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
54 | 38.508-1 | 4.6.4 | Default NG-RAN RRC message and information elements contents.Default structure, UE capability information elements A to L. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.Default structure, UE capability.information elements A to L. | InterTek | Opt 3: RAN5#79 (May-18) | R5-181893, R5-183250 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
50 | 38.508-1 | 4.6.4 | Default NG-RAN RRC message and information elements contents.Default structure, UE capability information elements M to U. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.Default structure, UE capability.information elements M to U. | Ericsson 3 | Opt 3: RAN5#79 (May-18) | R5-181893, R5-183088 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
23 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for SA NR testing of option 2 and 5 | Ericsson 1 | Opt 2: RAN5#81 (Nov-18) | R5-185030, R5-185032, R5-185033, R5-185038, R5-187745, R5-187661, R5-187750, R5-187754, R5-187755, R5-187756, R5-187757, R5-187680, R5-187762, R5-187764, R5-186575, R5-186612, R5-186613, R5-186641, R5-186665, R5-186666, R5-186682, R5-186691, R5-186692, R5-186714, R5-186734, R5-186744, R5-186911, R5-186912, R5-186913, R5-186918, R5-186920, R5-186921, R5-186922, R5-186923, R5-186925, R5-187172, R5-187175 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
93 | 38.508-1 | 4.6.2 | Default NG-RAN RRC message and information elements contents.System information blocks | Definition of NG-RAN RRC default messages for SA NR testing of option 2 and 5.System information blocks. | Huawei, Hisilicon | Opt 2: RAN5#81 (Nov-18) | R5-187673, R5-186987, R5-186988, R5-186989, R5-186990 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
90 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for SA NR testing of option 2 and 5 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
24 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
25 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for NSA LTE-NR testing of option 4 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
| 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents
26 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for SA NR testing option 2 and 5 | Ericsson 1 | Opt 2: RAN5#81 (Nov-18) | R5-184783, R5-184785, R5-187677, R5-188107, R5-187166, R5-187678, R5-187759, R5-187679, R5-187760, R5-187761, R5-186916, R5-187159, R5-187160, R5-187161, R5-187162 R5-187163, R5-187164 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
91 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for SA NR testing option 2 and 5 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
27 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
28 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for NSA LTE-NR testing of option 4 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
| 38.508-1 | 4.8 | Reference configurations
42 | 38.508-1 | 4.8 | Reference configurations | Definition of reference configurations for specific test case purposes. |  |  | R5-180265 |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
52 | 38.508-1 | 4.8 | Reference configurations. To configure m+n SCG bearers where m are AM RLC and n UM RLC. | Definition of reference configurations for specific test case purposes.To configure m+n SCG bearers where m are AM RLC and n UM RLC | Ericsson 3 | Opt 3: RAN5#79 (May-18) |  |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 4.9 | Test procedures
87 | 38.508-1 | 4.9 | Test procedures | Definition of test procedures for specific test case purposes. |  | Opt 3: RAN5#79 (May-18) | R5-185037 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
96 | 38.508-1 | 4.9 | Test procedure to configure SCC for CA RF test cases. | Definition of common procedure used by RF CA test cases to configur SCC | Ericsson 4 | Opt 2: RAN5#83 (May-19) | R5-194367 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
98 | 38.508-1 | 4.9 | Test procedure to configure SCC for EN-DC RF test cases. | Definition of common procedure used by RF CA test cases to configur SCC | Ericsson 4 | Opt 3: RAN5#85 (Nov-19) | R5-194367, R5-198956 |  | 1 | 100% |  |  | 1 | 6 | 100% | 1 |  | 1
TS 38.508 work tasks - Clause 5: Test environment for RF test
| 38.508-1 | 5.1 | Requirements of test equipment
| 38.508-1 | 5.1.1 | Requirements for transmission and reception tests
31 | 38.508-1 | 5.1.1.1 | Requirements common for conducted and OTA tests | Describe the test equipment requirements which are specific to transmission and reception tests and common for conducted and OTA tests. | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-187271 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
64 | 38.508-1 | 5.1.1.2 | Requirements for conducted tests | Describe the test equipment requirements which are specific to conducted test environment for transmission and reception tests. | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-187271 | No specific needs for this sub-clause identified for NSA Opt.3 Phase 1.5 | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
65 | 38.508-1 | 5.1.1.3 | Requirements for OTA tests | Describe the test equipment requirements which are specific to OTA test environment for transmission and reception tests. | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-187271 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 5.1.2 | Requirements for performance tests
66 | 38.508-1 | 5.1.2.1 | Requirements common for conducted and OTA performance tests | Describe the test equipment requirements which are specific to performance tests and common for conducted and OTA tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206112 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
67 | 38.508-1 | 5.1.2.2 | Requirements for conducted for performance conducted tests | Describe the test equipment requirements which are specific to conducted test environment for performance tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206112 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
68 | 38.508-1 | 5.1.2.3 | Requirements for OTA tests | Describe the test equipment requirements which are specific to OTA test environment for performance tests. | Anritsu | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#82 (Feb-19) | R5-176995, R5-177271 |  | 1 | 100% | 2 | 100% | 1 | 3 | 100% | 1 |  | 1
| 38.508-1 | 5.2 | Reference test conditions
| 38.508-1 | 5.2.1 | Signal levels
69 | 38.508-1 | 5.2.1.1 | Signal levels for conducted testing |  | Anritsu | <Autofilled> | R5-176995, R5-183255 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
70 | 38.508-1 | 5.2.1.2 | Signal levels for OTA |  | Anritsu | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#82 (Feb-19) | R5-176995, R5-182091, R5-187272, R5-187802 |  | 1 | 100% | 2 | 100% | 1 | 3 | 100% | 1 |  | 1
TS 38.508 work tasks - Clause 6: Test environment for Signalling test
| 38.508-1 | 6.1 | Requirements of test equipment
33 | 38.508-1 | 6.1.1 | Requirements common for conducted and OTA tests | Describe the test equipment requirements which are specific to signalling tests and common for conducted and OTA tests. | Anritsu 2 | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
71 | 38.508-1 | 6.1.2 | Requirements for conducted test method | Describe the test equipment requirements which are specific to conducted test environment for signalling tests. | Anritsu 2 | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206308 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
72 | 38.508-1 | 6.1.3 | Requirements for OTA test method | Describe the test equipment requirements which are specific to OTA test environment for signalling tests. | Anritsu, Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-185168, R5-187681 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
85 | 38.508-1 | 6.1.4 | Requirements for timer tolerances | Describe the test equipment requirements which are specific to timer tolerances for signalling tests. |  | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-185040 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 6.2 | Reference test conditions
| 38.508-1 | 6.2.1 | Physical Channel Allocations
73 | 38.508-1 | 6.2.1.1 | Antennas |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-183255, R5-187747 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
78 | 38.508-1 | 6.2.1.2 | Downlink physical channels and physical signals |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-183255, R5-187747 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 6.2.2 | Signal levels
79 | 38.508-1 | 6.2.2.1 | Signal Levels for conducted testing |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-176995, R5-183255, R5-187747 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
80 | 38.508-1 | 6.2.2.2 | Signal Levels for OTA testing |  | Anritsu 2, Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-185168, R5-184893 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 6.2.3 | Defaul test frequencies
81 | 38.508-1 | 6.2.3 | Default test frequencies |  | Ericsson 4 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#82 (Feb-19) | R5-185177 R5-187752 R5-191301 |  | 1 | 100% | 1 | 100% | 1 | 3 | 100% | 1 |  | 1
| 38.508-1 | 6.3 | Reference system configurations
86 | 38.508-1 | 6.3.1 | Cell configurations | Describe different types of SS cell configurations. | FFS | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-185040 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
89 | 38.508-1 | 6.3 | Configurations for 5GC | Describe different types of configurations for 5GC. | CATT, Rohde-Schwarz | Opt 2: RAN5#82 (Feb-19) | R5-187660 |  | 1 | 100% | 2 | 100% | 1 | 2 |  | 1 |  | 1
88 | 38.508-1 | 6.3.9.1 | Test procedures 5GC | Definition of test procedures for 5GC specific test case purposes. | CATT | Opt 2: RAN5#82 (Feb-19) | R5-187763, R5-187676 R5-192744 R5-192745 |  | 1 | 100% | 2 | 100% | 1 | 1 |  | 1 |  | 1
TS 38.508 work tasks - Clause 7: Test environment for RRM tests
| 38.508-1 | 7.1 | Requirements of test equipment
34 | 38.508-1 | 7.1.1 | Requirements common for conducted and OTA tests | Describe the test equipment requirements which are specific to RRM tests and common for conducted and OTA tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206113 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
35 | 38.508-1 | 7.1.2 | Requirements for conducted test method | Describe the test equipment requirements which are specific to conducted test environment for RRM tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206113 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
75 | 38.508-1 | 7.1.3 | Requirements for OTA test method | Describe the test equipment requirements which are specific to OTA test environment for RRM tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
| 38.508-1 | 7.2 | Reference test conditions
76 | 38.508-1 | 7.2.1.1 | Signal Levels for conducted testing |  | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206115 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
77 | 38.508-1 | 7.2.1.1 | Signal Levels for OTA testing |  | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206115 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
TS 38.508 work tasks - Annexes
| 38.508-1 | Annex A | Connection Diagrams
36 | 38.508-1 | Annex A | Connection Diagrams, General part | Introduction clause etc | Keysight | <Autofilled> | R5-183916 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
37 | 38.508-1 | Annex A.3.1 | Connection Diagrams, Test equipment part | Connection diagram for test equipment part | Keysight | <Autofilled> | R5-183916 | Remains: connection diagrams for transmitter tests using Spectrum Analyser and Signal Generator (cl A.3.1.3). Specific details for test case authors to decide. | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
38 | 38.508-1 | Annex A.3.2 | Connection Diagrams, UE part | Connection diagram for UE part | Keysight | <Autofilled> | R5-183916 | Remains: connection diagrams for 3 and 4 antenna ports.Specific details for test case authors to decide. | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
TS 36.508 work tasks
| 36.508 | 4.6 | Default RRC message and information elements contents
40 | 36.508 | 4.6 | Default RRC message and information elements contents | Definition of E-UTRA RAN RRC default messages for NSA LTE-NR testing of option 3 | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-176919, R5-182073 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
92 | 36.508 | 4.6 | Default RRC message and information elements contents | Definition of E-UTRA RAN RRC default messages for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.
Note on AA6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AB7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).

## Deliverables
Deliverables:
Deliverables |  | Standalone (SA) Targets |  | Non-Standalone (NSA) Targets
Target ID | Phase | SA Option 2 | SA Option 5 | NSA Option 3 | NSA Option 4 | NSA Option 7
1 | Phase 1 | RAN5#81 (Nov-18) | FFS | RAN5#79 (May-18) | RAN5#93 (Nov-21) | FFS
1.5 | Phase 1 | - | - | RAN5#80 (Aug-18) | - | -
2 | Phase 2 | RAN5#82 (Feb-19) | FFS | RAN5#81 (Nov-18) | RAN5#94 (Feb-22) | FFS
3 | Phase 3 | RAN5#83 (May-19) | FFS | RAN5#82 (Feb-19) | - | FFS
4 | Phase 4 | RAN5#84 (Aug-19) | FFS | RAN5#83 (May-19) | - | FFS
5 | Phase 5 | RAN5#85 (Nov-19) | FFS | RAN5#84 (Aug-19) | - | FFS
6 | Phase 6 | RAN5#86 (Feb-20) | FFS | RAN5#85 (Nov-19) | - | FFS
7 | Phase 7 | RAN5#87 (May-20) | FFS | RAN5#86 (Feb-20) | - | FFS
8 | Phase 8 | RAN5#88 (Aug-20) | FFS | RAN5#87 (May-20) | - | FFS
9 | Phase 9 | RAN5#89 (Nov-20) | FFS | RAN5#88 (Aug-20) | - | FFS
10 | Phase 10 | RAN5#90 (Feb-21) | FFS | RAN5#89 (Nov-20) | - | FFS
11 | Phase 11 | RAN5#91 (May-21) | FFS | RAN5#90 (Feb-21) | - | FFS
12 | Phase 12 | RAN5#92 (Aug-21) | FFS | RAN5#91 (May-21) | - | FFS
13 | Phase 13 | RAN5#93 (Nov-21) | FFS | RAN5#92 (Aug-21) | - | FFS
14 | Phase 14 | RAN5#94 (Feb-22) | FFS | RAN5#93 (Nov-21) | - | FFS
15 | Phase 15 | RAN5#95 (May-22) | FFS | RAN5#94 (Feb-22) | - | FFS
16 | Phase 16 | Post WI close | FFS | Post WI close | Post WI close | FFS