## Summary
Work plan summary:
Rel-15 5GS Protocol Test Models (TS 38.523-3, TS 36.523-3, TS 34.229-3, TS 37.571-4)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Rel-15 5GS Protocol Test Models (TS 38.523-3, TS 36.523-3, TS 34.229-3, TS 37.571-4) | SA Option 2 (SA NR) | 100% | 100% | 100%
|  | NSA Option 3 (EN-DC) | 100% | 100% | 100%
|  | SA Option 5 | 19.46% | 19.46% | 19.46%
|  | NSA Option 4 (NE-DC) | 100% | 100% | 100%
|  | NSA Option 7 (NGEN-DC) | 21.33% | 21.33% | 21.33%
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of test cases applicable for FR1+FR2
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| Rel-15 5GS Protocol Test Models (TS 38.523-3, TS 36.523-3, TS 34.229-3, TS 37.571-4) | SA Option 2 (SA NR)
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)

## Protocol Test Models
WP Title: | Rel-15 5GS Protocol Test Models (TS 38.523-3, TS 36.523-3, TS 34.229-3, TS 37.571-4) | [9 empty] | WP item applicability
RAN-CN interface options dependency
WP Scope: | This work plan section covers the specification of the 5GS Test Models to be used for the implementation of the 5GS protocol test cases in TTCN-3. This work plan section covers all SA and NSA options, including also IMS & positioning aspects. This work plan section does not cover the TTCN-3 development plans of 5GS protocol test cases. | [9 empty] | 5GC/NR |  | 5GC/LTE |  | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Olivier Genoud, MCC TF160 |  |  | Olivier.Genoud@etsi.org
TS Resp: | Olivier Genoud, MCC TF160 |  |  | Olivier.Genoud@etsi.org | [6 empty] | SA |  |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 |  | Opt. 3 |  | Opt. 4 |  | Opt. 7
[10 empty] | Overall | 100% |  | 19.46% |  | 100% |  | 100% |  | 21.33%
Overall (all TSs)
[6 empty] | Overall #WP items: Post WI close #WP items: |  |  |  |  | 65 0 |  | 28 19 |  | 49 0 |  | 34 0 |  | 36 26
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option
TS 38.523-3 work tasks
1 | 38.523-3 | 4 | Test system architecture | New clause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
2 | 38.523-3 | 4.1 | General system architecture |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180678, R5181773 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
3 | 38.523-3 | 4.2 | Component architecture |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180678, R5181773 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
4 | 38.523-3 | 5 | Test models | New clause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
5 | 38.523-3 | 5.1 | EN-DC | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
101 | 38.523-3 | 5.1.1 | Layer 3 | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
6 | 38.523-3 | 5.1.1.1 | Single NR carrier - Phase1 |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5181773, R5-183237 | LTE 1CC + NR FR1 1CC | 6 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
61 | 38.523-3 | 5.1.1.1 | Single NR carrier - Phase2 |  | MCC TF160 | Opt 3: RAN5#81 (Nov-18) | R5-188105 | LTE xCC + NR FR1 1CC, where x<=3; and LTE 1CC + NR FR2 1CC | 2 | 100% | 1 |  | 1 |  | 2 | 100% | 1 |  | 1
76 | 38.523-3 | 5.1.1.2 | NR carrier aggregation |  | MCC TF160 | Opt 3: RAN5#82 (Feb-19) | R5-191206, R5-213516, R5-214620 | LTE xCC + NR FR1/FR2 yCC, where x<=3, y<=2 | 2 | 100% | 1 |  | 1 |  | 3 | 100% | 1 |  | 1
7 | 38.523-3 | 5.1.2 | Layer 2 | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
8 | 38.523-3 | 5.1.2.1 | PDCP |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5-183237, R5-188105, R5-198994, R5-217830 |  | 2 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
9 | 38.523-3 | 5.1.2.2 | RLC |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5-183237 |  | 2 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
104 | 38.523-3 | 5.1.2.3 | MAC | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
10 | 38.523-3 | 5.1.2.3.1 | Single NR carrier |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5-183237, R5-213516 |  | 2 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
62 | 38.523-3 | 5.1.2.3.2 | NR carrier aggregation |  | MCC TF160 | Opt 3: RAN5#82 (Feb-19) | R5-191206, R5-221467 | LTE xCC + NR FR1/FR2 yCC, where x<=3, y<=2 | 4 | 100% | 1 |  | 1 |  | 3 | 100% | 1 |  | 1
44 | 38.523-3 | 5.2 | NR/5GC |  | MCC TF160 |  | R5-188106 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
44 | 38.523-3 | 5.2.1 | Layer 3 |  | MCC TF160 |  | R5-188106 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
78 | 38.523-3 | 5.2.1.1 | Single NR carrier |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106, R5-192812 | SC FR1 and FR2 | 6 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
79 | 38.523-3 | 5.2.1.2 | NR carrier aggregation |  | MCC TF160 | Opt 2: RAN5#83 (May-19) | R5-195241, R5-213516 | FR1 xCC, where x<=4 | 6 | 100% | 3 | 100% | 1 |  | 1 |  | 1 |  | 1
107 | 38.523-3 | 5.2.1.3 | Inter-RAT NR/E-UTRA |  | MCC TF160 | Opt 2: RAN5#83 (May-19) | R5-195241 |  | 6 | 100% | 3 | 100% | 1 |  | 1 |  | 1 |  | 1
115 | 38.523-3 | 5.2.1.4 | NR supplementary uplink |  | MCC TF160 | Opt 2: RAN5#85 (Nov-19) | R5-198993 |  | 4 | 100% | 5 | 100% | 1 |  | 1 |  | 1 |  | 1
127 | 38.523-3 | 5.2.1.5 | NR-NR dual connectivity |  | MCC TF160 | Opt 2: RAN5#88 (Aug-20) | R5-204475, R5-206369 |  | 4 | 100% | 8 | 100% | 1 |  | 1 |  | 1 |  | 1
145 | 38.523-3 | 5.2.1.5A | NR-E-UTRA dual connectivity |  | MCC TF160 | Opt 4: RAN5#94 (Feb-22) | R5-221467 | SC FR1 and FR2 | 4 | 100% | 1 |  | 1 |  | 1 |  | 2 | 100% | 1
80 | 38.523-3 | 5.2.2 | Layer 2 | New subclause |  |  | R5-188106 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
81 | 38.523-3 | 5.2.2.1 | SDAP |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
129 | 38.523-3 | 5.2.2.2 | PDCP | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
82 | 38.523-3 | 5.2.2.2.1 | Single NR carrier |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
130 | 38.523-3 | 5.2.2.2.2 | NR-NR dual connectivity |  | MCC TF160 | Opt 2: RAN5#88 (Aug-20) | R5-204475 |  | 2 | 100% | 8 | 100% | 1 |  | 1 |  | 1 |  | 1
146 | 38.523-3 | 5.2.2.2.3 | NR-E-UTRA dual connectivity |  | MCC TF160 | Opt 4: RAN5#94 (Feb-22) | R5-221467 |  | 2 | 100% | 1 |  | 1 |  | 1 |  | 2 | 100% | 1
83 | 38.523-3 | 5.2.2.3 | RLC |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
105 | 38.523-3 | 5.2.2.4 | MAC | New subclause |  |  | R5-188106 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
84 | 38.523-3 | 5.2.2.4.1 | Single NR carrier |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106, R5-213516 | SC FR1 and FR2 | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
85 | 38.523-3 | 5.2.2.4.2 | NR carrier aggregation |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) | R5-192812, R5-221467 | FR1 xCC, where x<=4 | 4 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
128 | 38.523-3 | 5.2.2.4.3 | NR dual connectivity |  | MCC TF160 |  |  | Confirmed as not needed | 0 |  | 13 |  | 1 |  | 1 |  | 1 |  | 1
45 | 38.523-3 | 5.3 | Void | New subclause | MCC TF160 |  |  | Was NE-DC | 0 |  | 1 |  | 1 |  | 1 |  | 2 |  | 1
46 | 38.523-3 | 5.4 | E-UTRA/5GC |  | MCC TF160 | Opt 5: FFS |  |  | 12 | 0% | 1 |  | 16 | 0% | 1 |  | 1 |  | 1
47 | 38.523-3 | 5.5 | NGEN-DC |  | MCC TF160 | Opt 7: FFS |  |  | 12 | 0% | 1 |  | 1 |  | 1 |  | 1 |  | 16 | 0%
11 | 38.523-3 | 6 | System interface | New clause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
12 | 38.523-3 | 6.1 | Upper tester interface |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-180678, R5-198992, R5-217830 |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
13 | 38.523-3 | 6.2 | Abstract system primitives | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
14 | 38.523-3 | 6.2.1 | Introduction |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180678 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
15 | 38.523-3 | 6.2.2 | General requirements and assumptions |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180678 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
16 | 38.523-3 | 6.2.3 | E-UTRAN ASP definitions |  | MCC TF160 | Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-180678 |  | 2 | 65% | 1 |  | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
17 | 38.523-3 | 6.2.4 | NR ASP definitions |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS |  |  | 2 | 82.5% | 1 | 100% | 1 |  | 1 | 100% | 2 | 100% | 16 | 30%
18 | 38.523-3 | 7 | Test methods and design considerations | New clause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
19 | 38.523-3 | 7.1 | Common aspects | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
20 | 38.523-3 | 7.1.1 | Introduction |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5181773 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
59 | 38.523-3 | 7.1.2 | Physical layer aspects | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
63 | 38.523-3 | 7.1.2.1 | Search spaces and DCI |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-191204, R5-202677 |  | 2 | 82.5% | 1 | 100% | 1 |  | 1 | 100% | 2 | 100% | 16 | 30%
64 | 38.523-3 | 7.1.2.2 | Downlink resource allocation |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-186727, R5-192858, R5-193993, R5-201150, R5-202677, R5-206369, R5-211417 |  | 2 | 82.5% | 1 | 100% | 1 |  | 1 | 100% | 2 | 100% | 16 | 30%
65 | 38.523-3 | 7.1.2.3 | Uplink grant |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-186727, R5-192858, R5-193994, R5-197222, R5-198992, R5-198994, R5-201150 |  | 2 | 82.5% | 1 | 100% | 1 |  | 1 | 100% | 2 | 100% | 16 | 30%
100 | 38.523-3 | 7.1.2.4 | Data scheduling |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-186727, R5-192858, R5-195241, R5-201150 |  | 2 | 82.5% | 2 | 100% | 1 |  | 3 | 100% | 2 | 100% | 16 | 30%
114 | 38.523-3 | 7.1.2.5 | Noise generator |  | MCC TF160 | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-197222 |  | 2 | 100% | 4 | 100% | 1 |  | 5 | 100% | 1 | 100% | 1 | 100%
60 | 38.523-3 | 7.1.3 | System information |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-186727, R5-192858 |  | 4 | 68% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 10%
22 | 38.523-3 | 7.1.4 | Cell handling - 1 cell |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-186727, R5-192858 |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
66 | 38.523-3 | 7.1.4 | Cell handling - multi-cells |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) Opt 5: FFS Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-185172, R5-186727, R5-192858 |  | 2 | 72% | 2 | 100% | 16 | 30% | 3 | 100% | 2 | 100% | 16 | 30%
21 | 38.523-3 | 7.1.5 | Timing aspects | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
73 | 38.523-3 | 7.1.5.1 | SS time |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS |  |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
74 | 38.523-3 | 7.1.5.2 | Cell(s) timing - 1 cell |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS |  |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
75 | 38.523-3 | 7.1.5.2 | Cell(s) timing - multi-cells |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-184696, R5-198992, R5-204475, R5-211417, R5-217830 |  | 2 | 72% | 1 | 100% | 16 | 30% | 2 | 100% | 2 | 100% | 16 | 30%
143 | 38.523-3 | 7.1.6 | Test modes | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
144 | 38.523-3 | 7.1.6.1 | RLC test modes |  | MCC TF160 | Opt 2: RAN5#93 (Nov-21) Opt 5: FFS Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-217830 |  | 2 | 72% | 13 | 100% | 16 | 30% | 14 | 100% | 1 | 100% | 16 | 30%
24 | 38.523-3 | 7.2 | EN-DC | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
25 | 38.523-3 | 7.2.1 | Introduction |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5181773 |  | 1 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
26 | 38.523-3 | 7.2.2 | Physical layer aspects | New subclause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
28 | 38.523-3 | 7.2.2.1 | Search spaces and DCI |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5-183237, R5-195955 |  | 4 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
30 | 38.523-3 | 7.2.3 | System information |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5181773 |  | 2 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
77 | 38.523-3 | 7.2.4 | Bearers |  | MCC TF160 | Opt 3: RAN5#81 (Nov-18) | R5188105 |  | 2 | 100% | 1 |  | 1 |  | 2 | 100% | 1 |  | 1
103 | 38.523-3 | 7.2.5 | Random Access procedure |  | MCC TF160 | Opt 3: RAN5#82 (Feb-19) | R5-191206, R5-193994, R5-213516 |  | 1 | 100% | 1 |  | 1 |  | 3 | 100% | 1 |  | 1
108 | 38.523-3 | 7.2.6 | PSCell change |  | MCC TF160 | Opt 3: RAN5#83 (May-19) | R5-195240, R5-197222, R5-204475, R5-206369, R5-211417, R5-213516 |  | 1 | 100% | 1 |  | 1 |  | 4 | 100% | 1 |  | 1
48 | 38.523-3 | 7.3 | NR/5GC |  | MCC TF160 |  | R5188106 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
86 | 38.523-3 | 7.3.1 | Introduction |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5188106 |  | 1 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
26 | 38.523-3 | 7.3.2 | Physical layer aspects - Phase1 |  |  | Opt 2: RAN5#81 (Nov-18) | R5188106 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
30 | 38.523-3 | 7.3.3 | System information - Phase1 |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5188106 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
95 | 38.523-3 | 7.3.3 | System information - Phase2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) | R5-192812, R5-195241, R5-198993, R5-211417 |  | 2 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
77 | 38.523-3 | 7.3.4 | Paging and Short Message - Phase1 |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5188106 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
96 | 38.523-3 | 7.3.4 | Paging and Short Message - Phase2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) | R5-192812, R5-195241, R5-196754, R5-198993, R5-201150, R5-202677 |  | 2 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
106 | 38.523-3 | 7.3.5 | RRC connection control - Phase2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) | R5-192812, R5-197222 |  | 2 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
109 | 38.523-3 | 7.3.5 | RRC connection control - Phase3 |  | MCC TF160 | Opt 2: RAN5#83 (May-19) | R5-195240, R5-198993, R5-202677, R5-204475, R5-206369, R5-211417, R5-217830, R5-221467 |  | 2 | 100% | 3 | 100% | 1 |  | 1 |  | 1 |  | 1
116 | 38.523-3 | 7.3.6 | Bearers |  | MCC TF160 | Opt 2: RAN5#85 (Nov-19) | R5-198993 |  | 2 | 100% | 5 | 100% | 1 |  | 1 |  | 1 |  | 1
132 | 38.523-3 | 7.3.7 | Processing delay testing for RRC procedures |  | MCC TF160 | Opt 2: RAN5#90 (Feb-21) | R5-211417, R5-213516 |  | 2 | 100% | 10 | 100% | 1 |  | 1 |  | 1 |  | 1
49 | 38.523-3 | 7.4 | Void |  | MCC TF160 |  |  | Was NE-DC | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
50 | 38.523-3 | 7.5 | E-UTRA/5GC |  | MCC TF160 | Opt 5: FFS |  |  | 20 | 0% | 1 |  | 16 | 0% | 1 |  | 1 |  | 1
51 | 38.523-3 | 7.6 | NGEN-DC |  | MCC TF160 | Opt 7: FFS |  |  | 20 | 0% | 1 |  | 1 |  | 1 |  | 1 |  | 16 | 0%
32 | 38.523-3 | 8 | Other SS requirements with TTCN-3 impact | New clause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
33 | 38.523-3 | 8.1 | Codec requirements - Phase1 |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-180678 |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
97 | 38.523-3 | 8.1 | Codec requirements - Phase2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) | R5-201150 |  | 2 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
34 | 38.523-3 | 8.2 | External function definitions - Phase1 |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-180678, R5-197223 |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
98 | 38.523-3 | 8.2 | External function definitions - Phase2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) | R5-192812, R5-202677 |  | 2 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
35 | 38.523-3 | 9 | IXIT proforma | New clause |  |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
36 | 38.523-3 | 9.1 | Introduction |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180678, R5-181773, R5-197223 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
37 | 38.523-3 | 9.2 | E-UTRA and NR PIXIT |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-180678, R5-181773, R5-183237, R5-191206, R5-197223, R5-198993, R5-201150, R5-204475, R5-206369, R5-217830, R5-221467 |  | 2 | 72% | 1 | 100% | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
38 | 38.523-3 | 9.3 | 5GC PIXIT - Phase1 |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5181773, R5-183237, R5-188106 |  | 4 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
99 | 38.523-3 | 9.3 | 5GC PIXIT - Phase2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) Opt 5: FFS Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-192812, R5-195241, R5-195373, R5-197223 |  | 4 | 65% | 2 | 100% | 16 | 30% | 1 |  | 2 | 100% | 16 | 30%
39 | 38.523-3 | 10 | Postambles | New clause | MCC TF160 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
53 | 38.523-3 | 10.1 | Introduction |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-181773 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
54 | 38.523-3 | 10.2 | EN-DC |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5-181773, R5-204475 |  | 2 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
55 | 38.523-3 | 10.3 | NR/5GC | New subclause | MCC TF160 |  | R5-188106 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
87 | 38.523-3 | 10.3.1 | UE postamble states and procedures |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106, R5-195241, R5-202677, R5-214620 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
88 | 38.523-3 | 10.3.2 | Switch/Power off procedure in State 1N-A |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106, R5-195241 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
89 | 38.523-3 | 10.3.3 | Switch/Power off procedure in State 2N-A |  | MCC TF160 | Opt 2: RAN5#83 (May-19) | R5-188106, R5-195241 |  | 2 | 100% | 3 | 100% | 1 |  | 1 |  | 1 |  | 1
90 | 38.523-3 | 10.3.4 | Switch/Power off procedure in State 3N-A |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106, R5-195241 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
131 | 38.523-3 | 10.3.4A | Switch/Power off procedure in State 3N-A with T3540 started |  | MCC TF160 | Opt 2: RAN5#87 (May-20) | R5-202677 |  | 2 | 100% | 7 | 100% | 1 |  | 1 |  | 1 |  | 1
91 | 38.523-3 | 10.3.5 | Switch/Power off procedure in NR DEREGISTERED |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) | R5-188106, R5-195241 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
133 | 38.523-3 | 10.3.6 | Switch/Power off procedure after EMERGENCY CALL RELEASED in RRC_IDLE |  | MCC TF160 | Opt 2: RAN5#90 (Feb-21) | R5-214620 |  | 2 | 100% | 10 | 100% | 1 |  | 1 |  | 1 |  | 1
134 | 38.523-3 | 10.3.7 | Switch/Power off procedure after EMERGENCY CALL RELEASED in RRC_CONNECTED |  | MCC TF160 | Opt 2: RAN5#90 (Feb-21) | R5-214620 |  | 2 | 100% | 10 | 100% | 1 |  | 1 |  | 1 |  | 1
56 | 38.523-3 | 10.5 | NE-DC |  | MCC TF160 |  |  | Nothing needs to be added: NR/5GC postambles can be used. | 0 |  | 1 |  | 1 |  | 1 |  |  |  | 1
57 | 38.523-3 | 10.6 | E-UTRA/5GC |  | MCC TF160 | Opt 5: FFS |  |  | 2 | 0% | 1 |  | 16 | 0% | 1 |  | 1 |  | 1
58 | 38.523-3 | 10.7 | NGEN-DC |  | MCC TF160 | Opt 7: FFS |  |  | 2 | 0% | 1 |  | 1 |  | 1 |  | 1 |  | 16 | 0%
111 | 38.523-3 | 11 | Guidelines on test execution | New clause | MCC TF160 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
112 | 38.523-3 | 11.1 | Introduction |  | MCC TF160 | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | 4 | 100% | 1 | 100% | 5 | 100% | 1 | 100% | 1 | 100%
113 | 38.523-3 | 11.2 | EN-DC |  | MCC TF160 | Opt 3: RAN5#84 (Aug-19) | R5-201150 |  | 1 | 100% | 1 |  | 1 |  | 5 | 100% | 1 |  | 1
113 | 38.523-3 | 11.3 | NR/5GC |  | MCC TF160 | Opt 2: RAN5#84 (Aug-19) | R5-198993, R5-201150, R5-202677, R5-204475, R5-206369, R5-211417, R5-213516, R5-214620, R5-217830, R5-221467 |  | 1 | 100% | 4 | 100% | 1 |  | 1 |  | 1 |  | 1
40 | 38.523-3 | Annex A | Test Suites |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-181773, R5-186729 |  | 1 | 60% | 1 | 100% | 16 | 0% | 1 | 100% | 2 | 100% | 16 | 0%
41 | 38.523-3 | Annex B | NR TBS tables |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-183237, R5-184333, R5-186727, R5-192858, R5-193993 |  | 10 | 82.5% | 1 | 100% | 1 |  | 1 | 100% | 2 | 100% | 16 | 30%
42 | 38.523-3 | Annex C | Style guide and design principles |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180678, R5-183237 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
43 | 38.523-3 | Annex D | TTCN-3 definitions | New clause | MCC TF160 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
67 | 38.523-3 | Annex D | EN-DC Phase 1 |  | MCC TF160 | Opt 3: RAN5#79 (May-18) | R5181773, R5-183237 |  | 10 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
68 | 38.523-3 | Annex D | EN-DC Phase 2 |  | MCC TF160 | Opt 3: RAN5#81 (Nov-18) |  |  | 4 | 100% | 1 |  | 1 |  | 2 | 100% | 1 |  | 1
93 | 38.523-3 | Annex D | EN-DC Phase 3 |  | MCC TF160 | Opt 3: RAN5#82 (Feb-19) |  |  | 2 | 100% | 1 |  | 1 |  | 3 | 100% | 1 |  | 1
69 | 38.523-3 | Annex D | NR/5GC Phase 1 |  | MCC TF160 | Opt 2: RAN5#81 (Nov-18) |  |  | 10 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
92 | 38.523-3 | Annex D | NR/5GC Phase 2 |  | MCC TF160 | Opt 2: RAN5#82 (Feb-19) |  |  | 10 | 100% | 2 | 100% | 1 |  | 1 |  | 1 |  | 1
71 | 38.523-3 | Annex D | NE-DC |  | MCC TF160 | Opt 4: RAN5#94 (Feb-22) |  |  | 2 | 100% | 1 |  | 1 |  | 1 |  | 2 | 100% | 1
72 | 38.523-3 | Annex D | NGEN-DC |  | MCC TF160 | Opt 7: FFS |  |  | 2 | 0% | 1 |  | 1 |  | 1 |  | 1 |  | 16 | 0%
TS 36.523-3 work tasks
110 | 36.523-3 | 7.1.4.12 | IP packets used for Loopback Mode B |  | MCC TF160 | Opt 3: RAN5#83 (May-19) | R5-193983 |  | 1 | 100% | 1 |  | 1 |  | 4 | 100% | 1 |  | 1
52 | 36.523-3 | Annex D | TTCN-3 definitions |  | MCC TF160 | Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS |  |  | 12 | 65% | 1 |  | 16 | 30% | 1 | 100% | 2 | 100% | 16 | 30%
TS 34.229-3 work tasks
124 | 34.229-3 | 5.2 | IMS CC test model |  | MCC TF160 | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 7: FFS | R5-200257 |  | 6 | 33.33% | 6 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
125 | 34.229-3 | 5.3 | Upper Tester (UT) |  | MCC TF160 | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 7: FFS | R5-200257 |  | 1 | 33.33% | 6 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
126 | 34.229-3 | 6 | ASP definitions |  | MCC TF160 | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 7: FFS | R5-200257 |  | 1 | 33.33% | 6 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
TS 37.571-4 work tasks
115 | 37.571-4 | 6B | NG-RAN NR positioning system architecture and test models |  | MCC TF160 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
117 | 37.571-4 | 6B.1 | Test system architecture |  | MCC TF160 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
118 | 37.571-4 | 6B.1.1 | General system architecture |  | MCC TF160 | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 7: FFS |  |  | 1 | 33.33% | 4 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
119 | 37.571-4 | 6B.1.2 | Component architecture |  | MCC TF160 | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 7: FFS | R5-198142 |  | 4 | 33.33% | 5 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
120 | 37.571-4 | 6B.2 | Test models |  | MCC TF160 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
121 | 37.571-4 | 6B.2.1 | NR GNSS positioning test model |  | MCC TF160 | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 7: FFS |  |  | 4 | 33.33% | 4 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
122 | 37.571-4 | 6B.2.2 | NR indoor positioning test model |  | MCC TF160 | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 7: FFS |  |  | 4 | 33.33% | 4 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
123 | 37.571-4 | 6B.2.3 | NR OTDOA (LTE) positioning test model |  | MCC TF160 | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 7: FFS | R5-198142 |  | 4 | 33.33% | 5 | 100% | 16 | 0% | 1 |  | 1 |  | 16 | 0%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.

## Deliverables
Deliverables:
Deliverables |  | Standalone (SA) Targets |  | Non-Standalone (NSA) Targets
Phase # | Label | SA Option 2 | SA Option 5 | NSA Option 3 | NSA Option 4 | NSA Option 7
1 | Phase 1 | RAN5#81 (Nov-18) | FFS | RAN5#79 (May-18) | RAN5#93 (Nov-21) | FFS
1.5 | Phase 1 | - | - | RAN5#80 (Aug-18) | - | -
2 | Phase 2 | RAN5#82 (Feb-19) | FFS | RAN5#81 (Nov-18) | RAN5#94 (Feb-22) | FFS
3 | Phase 3 | RAN5#83 (May-19) | FFS | RAN5#82 (Feb-19) | FFS | FFS
4 | Phase 4 | RAN5#84 (Aug-19) | FFS | RAN5#83 (May-19) | FFS | FFS
5 | Phase 5 | RAN5#85 (Nov-19) | FFS | RAN5#84 (Aug-19) | FFS | FFS
6 | Phase 6 | RAN5#86 (Feb-20) | FFS | RAN5#85 (Nov-19) | FFS | FFS
7 | Phase 7 | RAN5#87 (May-20) | FFS | RAN5#86 (Feb-20) | FFS | FFS
8 | Phase 8 | RAN5#88 (Aug-20) | FFS | RAN5#87 (May-20) | FFS | FFS
9 | Phase 9 | RAN5#89 (Nov-20) | FFS | RAN5#88 (Aug-20) | FFS | FFS
10 | Phase 10 | RAN5#90 (Feb-21) | FFS | RAN5#89 (Nov-20) | FFS | FFS
11 | Phase 11 | RAN5#91 (May-21) | FFS | RAN5#90 (Feb-21) | FFS | FFS
12 | Phase 12 | RAN5#92 (Aug-21) | FFS | RAN5#91 (May-21) | FFS | FFS
13 | Phase 13 | RAN5#93 (Nov-21) | FFS | RAN5#92 (Aug-21) | FFS | FFS
14 | Phase 14 | RAN5#94 (Feb-22) | FFS | RAN5#93 (Nov-21) | FFS | FFS
15 | Phase 15 | FFS | FFS | RAN5#94 (Feb-22) | FFS | FFS
16 | Phase 16 | Post WI close | FFS | Post WI close | Post WI close | FFS