## WP scope
Work plan for introduction of NR FR1 bands and/or CBW extensions to existing bands into 3GPP UE conformance test specifications
| WP template: | PRD21, WP NR band and CBW FR1 v1.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | DRAFT_r2 WP NR band and CBW FR1 v1.0 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | TBD | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 0%
Target configurations
Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of band | TS and Source Table | NR band / NR band CBW Extension | CBWs SCS[kHz]:[MHz]+...+[MHz] | PC3 Status | PC2 completed? | PC1.5 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Band Sort Key
|  |  |  | nX | SCS15:5+10+15+20 SCS30:10+15+20 SCS60:- | Completed |  |  | <=RAN5#93-e | [5 empty] | n008
|  |  |  | nX CBW (35) | SCS15:+35 SCS30:+35 SCS60:- | Pending | [8 empty] | n008 CBW z35z
Based on checklist in R5-217767
+ WP items for new BCS (1-2, 1-3, 1-4, 2-2b, 3.1-1b, 3.2-3b, 3.2-4b, 3.4-1b)
and for BCS0 configurations 3.2-10
Dummy NR band nX and CBW extension nX (CBW (35)
included for review purposes of the WP template

## WP NR band and CBW FR1
Work plan for introduction of NR FR1 bands and/or CBW extensions to existing bands into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [12 empty] | WP template: PRD21, WP NR band and CBW FR1 v1.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New NR band(s) |  |  |  | New Band | nX
|  | New CBW(s) to existing band(s) |  |  |  | New CBW | nX CBW (35)
|  | All configurations |  |  |  | All | nX, nX CBW (35)
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 0%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 0%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations |  |  |  |  | 0%
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 0%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1) |  |  |  |  | 0%
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6) |  |  |  |  | 0%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7) |  |  |  |  | 0%
|  | Step 3.5: CR(s) for RRM and Location Services test cases (TS 38.533 and TS 37.571-1) |  |  |  |  | 0%
|  | Step 3.6: CRs to protocol test cases (TS 38.523-3) |  |  |  |  | 0%
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 0%
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Bands completed
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
New CBW | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | NR band completed for initial set of CBWs | nX CBW (35) | Set status in column "Bands completed" to 100% if NR band and its initial set of CBWs is confirmed as completed in RAN5 PRD21 worksheet "NR bands". |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
TP analysis
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
New Band | 2-1a | TP Analysis | 38.905 | 4.1.2 | Test point (TP) analysis for A-MPR - New band | nX | If new NS value is introduced by the new band then document the test point analysis A-MPR and single carrier else clear the status column. |  | TBD |  |  | 1 | 0% | 0%
New CBW | 2-1b | TP Analysis | 38.905 | 4.1.2 | Test point (TP) analysis for A-MPR - New CBW | nX CBW (35) | Check if there is a need to updated the test point analysis for A-MPR and single carrier case due to the addition of the new channel bandwidth |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Test Freq.
1
New Band | 3.1-1a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.1.x | Test frequencies for New band(s) | nX | Add test frequencies for the new band(s). |  | TBD |  |  | 1 | 0% | 0%
New CBW | 3.1-1b | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.1.x | Test frequencies for new CBW(s) | nX CBW (35) | Add test frequencies for the new CBW(s). |  | TBD |  |  | 1 | 0% | 0%
New Band | 3.1-2a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.1.x | Low, Mid, High test channel bandwidth for RF testing | nX | Specify the Low, Mid and High Test Channel bandwidths for the NR band used for RF testing. |  | TBD |  |  | 1 | 0% | 0%
New CBW | 3.1-2b | 38.508-1 - (4) Common | 38.508-1 | Tables 4.3.1.0A-1, 4.3.1.0B-1, 4.3.1.0C-1 | Low, Mid, High test channel bandwidth for RF testing | nX CBW (35) | Check if the new CBW impacts the selection of Low, Mid and High Test Channel bandwidths used for RF testing. |  | TBD |  |  | 1 | 0% | 0%
New Band | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.1 | Test frequencies for protocol testing for New band | nX | Add test frequencies for protocol testing and the new band for the chosen default channel bandwidth. |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Clause 5
1
New Band | 3.2-1 | 36.521-1 - General | 38.521-1 | 5.2 | Operating band | nX | Add the operating band |  | TBD |  |  | 1 | 0% | 0%
New CBW | 3.2-2 | 36.521-1 - General | 38.521-1 | 5.3.2 | Minimum guard band | nX CBW (35) | Add the minimu m guard band for the new CBW if not already specified. |  | TBD |  |  | 1 | 0% | 0%
All | 3.2-3 | 36.521-1 - General | 38.521-1 | 5.3.5 | Channel bandwidth | nX, nX CBW (35) | Add the channel bandwidths for the band |  | TBD |  |  | 1 | 0% | 0%
New Band | 3.2-4 | 36.521-1 - General | 38.521-1 | 5.3.6 | Asymmetric Channel bandwidth | nX | Add the asymmetric channel bandwidths for the band if applicable. If not applicable for the band then clear the status column |  | TBD |  |  | 1 | 0% | 0%
New Band | 3.2-5 | 36.521-1 - General | 38.521-1 | 5.4.2.3 | NR-ARFCN | nX | Add the applicable NR-ARFCN for the band |  | TBD |  |  | 1 | 0% | 0%
New Band | 3.2-6 | 36.521-1 - General | 38.521-1 | 5.4.3.3 | SS raster | nX | Add the applicable SS raster for the band |  | TBD |  |  | 1 | 0% | 0%
New Band | 3.2-7 | 36.521-1 - General | 38.521-1 | FDD: 5.4.4 TDD: N/A | FDD TX-RX frequency seperation | nX | FDD band: Add the default UE TX-RX frequency separation for the band TDD band: Clear the status column (no change needed) |  | TBD |  |  | 1 | 0% | 0%
New CBW | 3.2-8 | 36.521-1 - General | 38.521-1 | Annex A | Measurement channels | nX CBW (35) | Check if there is a need to add the new channel bandwidth to UL or DL RMC. |  | TBD |  |  | 1 | 0% | 0%
New CBW | 3.2-9 | 36.521-1 - General | 38.521-1 | Annex C | Downlink physical channels | nX CBW (35) | Check if there is a need to add the new channel bandwidth to default downlink power levels |  | TBD |  |  | 1 | 0% | 0%
New CBW | 3.2-10 | 36.521-1 - General | 38.521-1 | Annex D | Characteristics of the Interfering Signal | nX CBW (35) | Check if there is a need to add the new channel bandwidth to description of interference signals. |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 |  |  | 2
New CBW | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.1 | General | nX CBW (35) | Check if need to add new channel bandwidth to common uplink configuration. |  | TBD |  |  | 1 | 0% | [6 empty] | 0%
New Band | 3.3-2 | 38.521-1- RF Tx | 38.521-1 | 6.2.1 | UE maximum output power | nX | Add minimum requirement and test requirement for the band |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.3-3a | 38.521-1- RF Tx | 38.521-1 | 6.2.2 | UE maximum output power reduction - New band | nX | Add test requirement vs appliable power classes for the band. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-3b | 38.521-1- RF Tx | 38.521-1 | 6.2.2 | UE maximum output power reduction - New CBW | nX CBW (35) | Check if need to add new channel bandwidth to uplink configuration for almost contiguous allocation. |  | TBD |  |  | 1 | 0% | [6 empty] | 0%
New Band | 3.3-4a | 38.521-1- RF Tx | 38.521-1 | 6.2.3 | UE additional maximum output power reduction - New Band Note! This WP item is dependent on Reference TP analysis (Step 2, WP item G1122-1a) | nX | Add minimum requirement and test requirement for the band. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item 2-2a for TR 38.905). |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New CBW | 3.3-4b | 38.521-1- RF Tx | 38.521-1 | 6.2.3 | UE additional maximum output power reduction - New CBW Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 2-1b) | nX CBW (35) | Check if need to add new channel bandwidth to minimum requirement, test configuration and test requirement. Add relevant test points (TPs) based on the TP analysis if the new channel bandwidth has impact to an NS value and corresponding emission requirements (see check item 2-2b for TR 38.905). |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New Band | 3.3-5 | 38.521-1- RF Tx | 38.521-1 | 6.2C.3 | UE maximum output power for SUL | nX | For SUL bands: Add test requirement for the SUL band. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-6 | 38.521-1- RF Tx | 38.521-1 | 6.2C.4 | UE maximum output power reduction for SUL | nX | For SUL bands: Add test requirement for the SUL band. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-7 | 38.521-1- RF Tx | 38.521-1 | 6.2C.5 | UE additional maximum output power reduction for SUL | nX | For SUL bands: 1. Add minimum requirement and test requirement for the SUL band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item 2-2 for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New Band | 3.3-8 | 38.521-1- RF Tx | 38.521-1 | 6.2D.1 | UE maximum output power for UL MIMO | nX | For bands supporting UL MIMO: Add minimum requirement and test requirement for the band. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.3-9 | 38.521-1- RF Tx | 38.521-1 | 6.2D.2 | UE maximum output power reduction for UL MIMO | nX | For bands supporting UL MIMO: Add test requirement for the band. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-10 | 38.521-1- RF Tx | 38.521-1 | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | nX | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New CBW | 3.3-11 | 38.521-1- RF Tx | 38.521-1 | 6.3.1 | Minimum output power | nX CBW (35) | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-12 | 38.521-1- RF Tx | 38.521-1 | 6.3.2 | Transmit OFF power | nX CBW (35) | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-13 | 38.521-1- RF Tx | 38.521-1 | 6.3.3.2 | General ON/OFF time mask | nX CBW (35) | Check if need to add new channel bandwidth to test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-14 | 38.521-1- RF Tx | 38.521-1 | 6.3.3.6 | SRS time mask | nX CBW (35) | Check if need to add new channel bandwidth to test configuration and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-15 | 38.521-1- RF Tx | 38.521-1 | 6.3.4.2 | Absolute power tolerance | nX CBW (35) | Check if need to add new channel bandwidth to test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-16 | 38.521-1- RF Tx | 38.521-1 | 6.3.4.3 | Power Control Relative power tolerance | nX CBW (35) | Check if need to add new channel bandwidth to test configuration and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.3-17 | 38.521-1- RF Tx | 38.521-1 | 6.3C.1 | Minimum output power for SUL | nX | For SUL bands: If the CBW of SUL band is not included in table 6.3C.1.5-1, adding test requirements for the missing CBW for SUL band. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-18 | 38.521-1- RF Tx | 38.521-1 | 6.3C.2 | Transmit OFF power for SUL | nX | For SUL bands: If the CBW of SUL band is not included in table 6.3C.2.5-1 and 6.3C.2.5-2, adding test requirements for the missing CBW for SUL band. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-19 | 38.521-1- RF Tx | 38.521-1 | 6.3C.3 | Transmit ON/OFF time mask for SUL | nX | For SUL bands: If the CBW of SUL band is not included in tables in 6.3C.1.5, adding test requirements for the missing CBW for SUL band in 6.3C.3.1.5. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-20 | 38.521-1- RF Tx | 38.521-1 | 6.3C.4.1 | Absolute power tolerance for SUL | nX | For SUL bands: If the CBW of SUL band is not included in tables in 6.3C.4.1.5, adding test requirements for the missing CBW for SUL band in 6.3C.4.1.5. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-21 | 38.521-1- RF Tx | 38.521-1 | 6.3C.4.2 | Relative power tolerance for SUL | nX | For SUL bands: If the CBW of SUL band is not included in table 6.3C.4.2.4-1, adding test parameters for the missing CBW for SUL band in6.3C.4.2.4-1 For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  | 0%
New CBW | 3.3-22 | 38.521-1- RF Tx | 38.521-1 | 6.3D.1 | Minimum output power for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-23 | 38.521-1- RF Tx | 38.521-1 | 6.3D.2 | Transmit OFF power for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-24 | 38.521-1- RF Tx | 38.521-1 | 6.3D.3 | Transmit ON/OFF time mask for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-25 | 38.521-1- RF Tx | 38.521-1 | 6.3.D.4.1 | Absolute power tolerance for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-26 | 38.521-1- RF Tx | 38.521-1 | 6.3.D.4.2 | Power Control Relative power tolerance for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-27 | 38.521-1- RF Tx | 38.521-1 | 6.5.1 | Occupied bandwidth | nX CBW (35) | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-28 | 38.521-1- RF Tx | 38.521-1 | 6.5.2.2 | Spectrum Emission Mask | nX CBW (35) | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.3-29a | 38.521-1- RF Tx | 38.521-1 | 6.5.2.3 | Additional spectrum emission mask . New band | nX | If new NS value introduced by the band then add requirements for the new NS value as needed. If not then clear the status column. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-29b | 38.521-1- RF Tx | 38.521-1 | 6.5.2.3 | Additional spectrum emission mask - New CBW | nX CBW (35) | Check if there is a need to add the new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.3-30 | 38.521-1- RF Tx | 38.521-1 | 6.5.3.2 | Spurious emissions for UE co-existence | nX | Add protection requirements for the new bands and existing bands against the new band |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-31 | 38.521-1- RF Tx | 38.521-1 | 6.5.2.4.1 | NR ACLR | nX CBW (35) | Check if there is a need to add the new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-32 | 38.521-1- RF Tx | 38.521-1 | 6.5.2.4.2 | UTRA ACLR | nX CBW (35) | Check if there is a need to add new channel bandwidth to test requirement. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-33a | 38.521-1- RF Tx | 38.521-1 | 6.5.3.3 | Additional spurious emissions - New band | nX | If new NS value introduced by the band and additional requirement is specified for the NS value then add requirements for the new NS value as needed. If not then clear the status column. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-33b | 38.521-1- RF Tx | 38.521-1 | 6.5.3.3 | Additional spurious emissions - New CBW | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-34 | 38.521-1- RF Tx | 38.521-1 | 6.5C.1 | Occupied bandwidth for SUL | nX CBW (35) | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-35 | 38.521-1- RF Tx | 38.521-1 | 6.5C.2.2 | Spectrum Emission Mask for SUL | nX CBW (35) | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-36a | 38.521-1- RF Tx | 38.521-1 | 6.5C.2.3 | Additional spectrum emission mask for SUL - New band | nX | For SUL bands: If new NS value introduced by the band and additional requirement is specified for the NS value then add requirements for the new NS value as needed. If not then clear the status column. For other bands: clear the status column |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-36b | 38.521-1- RF Tx | 38.521-1 | 6.5C.2.3 | Additional spectrum emission mask for SUL - New CBW | nX CBW (35) | For bands supporting SUL Band: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-37 | 38.521-1- RF Tx | 38.521-1 | 6.5C.2.4.1 | NR ACLR for SUL | nX CBW (35) | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-38a | 38.521-1- RF Tx | 38.521-1 | 6.5C.2.4.2 | UTRA ACLR for SUL - New band | nX | For SUL bands: If new NS value introduced by the band: add the NS value for SUL band in table 6.5C.2.4.2.4-2. For other bands: clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-38b | 38.521-1- RF Tx | 38.521-1 | 6.5C.2.4.2 | UTRA ACLR for SUL - New CBW | nX CBW (35) | For bands supporting SUL Band: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-39 | 38.521-1- RF Tx | 38.521-1 | 6.5C.3.3 | Additional spurious emissions for SUL Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 2-1a) | nX | For SUL bands: If new NS value introduced by the band: add test configuration for the NS value for SUL band in table 6.5C.3.3.4.as per test points analysis (see check item 2-1a for TR 38.905) For other bands: clear the status column |  | TBD |  |  | 1 | 0% |  |  | 0%
New Band | 3.3-40a | 38.521-1- RF Tx | 38.521-1 | 6.5D.1 | Occupied bandwidth for UL MIMO - New band | nX | For bands supporting UL MIMO: 1. Check if band need to be added to Table 6.5D.1.4.1-2: Test frequency exceptions for Occupied Bandwidth. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-40b | 38.521-1- RF Tx | 38.521-1 | 6.5D.1 | Occupied bandwidth for UL MIMO - New CBW | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.3-41 | 38.521-1- RF Tx | 38.521-1 | 6.5D.2.2 | Spectrum Emission Mask for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-42a | 38.521-1- RF Tx | 38.521-1 | 6.5D.2.3 | Additional spectrum emission mask for UL MIMO - New band Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 2-1a) | nX | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New CBW | 3.3-42b | 38.521-1- RF Tx | 38.521-1 | 6.5D.2.3 | Additional spectrum emission mask for UL MIMO - New CBW | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-43 | 38.521-1- RF Tx | 38.521-1 | 6.5D.2.4.1 | NR ACLR for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-44a | 38.521-1- RF Tx | 38.521-1 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO - New band Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 2-1a) | nX | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New CBW | 3.3-44b | 38.521-1- RF Tx | 38.521-1 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO - New CBW | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New Band | 3.3-45a | 38.521-1- RF Tx | 38.521-1 | 6.5D.3.3 | Additional spurious emissions for UL MIMO - New band | nX | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.3-45b | 38.521-1- RF Tx | 38.521-1 | 6.5D.3.3 | Additional spurious emissions for UL MIMO - New CBW | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | 0% |  |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 |  |  | 2
New Band | 3.4-1a | 38.521-1-RF Rx | 38.521-1 | 7.3.2 | Reference sensitivity power level - New band | nX | Add minimum requirement, test configuration, and test requirement for the band |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
New CBW | 3.4-1b | 38.521-1-RF Rx | 38.521-1 | 7.3.2 | Reference sensitivity power level - New CBW | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-2 | 38.521-1-RF Rx | 38.521-1 | 7.4 | Maximum input level | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-3 | 38.521-1-RF Rx | 38.521-1 | 7.4D | Maximum input level for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.4-4 | 38.521-1-RF Rx | 38.521-1 | 7.5 | Adjacent channel selectivity | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.4-5a | 38.521-1-RF Rx | 38.521-1 | 7.6.2 | In-band blocking - New band | nX | Add minimum requirement and test requirement for the band |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-5b | 38.521-1-RF Rx | 38.521-1 | 7.6.2 | In-band blocking - New CBW | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.4-6a | 38.521-1-RF Rx | 38.521-1 | 7.6.3 | Out-of-band blocking - New band | nX | Add minimum requirement and test requirement for the band |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-6b | 38.521-1-RF Rx | 38.521-1 | 7.6.3 | Out-of-band blocking - New CBW | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New Band | 3.4-7a | 38.521-1-RF Rx | 38.521-1 | 7.6.4 | Narrow band blocking - New band | nX | Add minimum requirement and test requirement for the band |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-7b | 38.521-1-RF Rx | 38.521-1 | 7.6.4 | Narrow band blocking - New CBW | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-8 | 38.521-1-RF Rx | 38.521-1 | 7.7 | Spurious response | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
New CBW | 3.4-9 | 38.521-1-RF Rx | 38.521-1 | 7.7D | Spurious response for UL MIMO | nX CBW (35) | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | 0% |  |  |  | 0%
New CBW | 3.4-10 | 38.521-1-RF Rx | 38.521-1 | 7.8 | Intermodulation characteristics | nX CBW (35) | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RRM and Location Services test cases (TS 38.533 and TS 37.571-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | New band group | [5 empty] | Other Areas
[14 empty] | 1 | [5 empty] | 2
New band | 3.5-1 | 38.533-RRM | 38.533 | 3A.4.1 | NR band group RRM | nX | Add band to NR band groups in clause 3A.4. If the NR bands introduces a new NR Band group, an analysis of the impact should be provided |  | TBD |  |  | 1 | 0% | 0%
New band | 3.5-1 | 37.571-1-LCS | 37.571-1 | 4.12.3 | NR band group Location Services | nX | No need to add NR band groups in TS 37.571-1 for location services test cases as clause 4.12.2 refers to TS 38.533 clause 3A.4 for the NR band groups. |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-3)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
38.623-3
1
New band | 3.6-1 | 38.523-1 | 38.523-3 | 11 | Protocol test execution | nX | If the band's overall bandwidth is less than 4*default CBW then add protocol test execution guideline (some protocol test cases use up to 4 inter-frequency cells). If the band's overall bandwidth is larger than 4*default CBWnot then there is no impact on 38.523-3. |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
New Band | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.1 | Band ICS | nX | Add Baseline Implementation Capabilities for the new band to the relevant table in clause A.4.3.1. FDD: Table A.4.3.1-1 TDD: Table A.4.3.1-2 SUL: Table A.4.3.1-5 SDL: Table A.4.3.1-6 |  | TBD |  |  | 1 | 0% | 0%
New Band | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.1 | Power class capability | nX | If power classes PC1, PC1.5, PC2 or PC4 covered by the band addition work item then add the applicable NR power class Baseline Implementation Capabilities to the relevant table in clause A.4.3.1. PC1, PC1.5, PC2, PC4: Tables A.4.3.1-4x |  | TBD |  |  | 1 | 0% | 0%
New Band | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.9 | Additional capabilities for UE declared capability | nX | Add the additional applicable capabilities for the NR band in Tables A.4.3.9-4x. |  | TBD |  |  | 1 | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N27: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N34: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N43: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N54: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N70: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N131: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N151: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N159: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N166: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.