## Cover sheet
3GPP TSG-RAN WG5 Meeting #95-e | [10 empty] | R5-222140
Online, , 9th May 2022 - 20th May 2022
Agenda Item: | 7.4.2
Source: | NIST
Title: | WP UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15
Work item code: | MCenhUEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#89 meeting, RAN5 work item UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15 [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+36%) | 62 (+21) | 62 (-8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Applications) |  | 100% (+36.2%) | 62 (+21) | 62 (-8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | Applications
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
Mission Critical Services
MC Common test environment | 36.579-1 | 100% (+0.6%) | 3 (+1) | 3 (+1) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
MCPTT UE test cases | 36.579-2 | 100% | 23 | 23 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
MC Server Application test cases | 36.579-3 |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Applicability and ICS MC test cases | 36.579-4 | 100% (+66.7%) |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
MC Test suite (TTCN) | 36.579-5 |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
MC Video UE test cases | 36.579-6 | 100% (+57.4%) | 27 (+14) | 27 (-7) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
MC Data UE test cases | 36.579-7 | 100% (+72.1%) | 9 (+6) | 9 (-2) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
5 References
[1] RP-201487 | New WID - UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15
[2] RP-212956 | Revised WID on Enhancements for Mission Critical Services - MCenhUEConTest
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | MCenhUEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Jason Kahn, NIST |  |  | jason.kahn@nist.gov | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | Applications
100% (+36.2%)
104 (-9)
71.2 (-6.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
Mission Critical Services
TS 36.579-1: MC Common test environment
|  | 36.579-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
1 | Y | 36.579-1 | 5.3A.24 | UE initiated MCPTT functional alias status determination and subscription |  | NIST | RAN5#95 (May-22) | R5-213588 |  | 1 | 100% | 100% |  | 100%
2 | Y | 36.579-1 | 5.3A.25 | UE initiated MCPTT functional alias status change |  | NIST | RAN5#95 (May-22) | R5-213588 |  | 1 | 100% | 100% |  | 100%
3 |  | 36.579-1 | 5.3B | Generic test procedures for UE MCVideo operation |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
4 |  | 36.579-1 | 5.3C | Generic test procedures for UE MCData operation |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
5 |  | 36.579-1 | 5.5.3 | Default SDP message and other information elements | Update for MCData Data signalling messages | NIST | RAN5#95 (May-22) | R5-222141 |  | 1 | 100% | 100% |  | 100%
6 |  | 36.579-1 | 5.5.6 | Default MCPTT media plane control messages and other information elements | Update for Rel-15 additions | NIST, Samsung, MCC TF160 | RAN5#95 (May-22) | R5-206422, R5-206108, R5-210994, R5-213265 |  | 1 | 100% | 100% |  | 100%
7 |  | 36.579-1 | 5.5.7 | Default MCX group management messages and other information elements | Update for Rel-15 additions | MCC TF160, UPV/EHU, Nemergent Solutions, NIST | RAN5#95 (May-22) | R5-206448, R5-206450, R5-213266, R5-217905 |  | 1 | 100% | 100% |  | 100%
8 |  | 36.579-1 | 5.5.8 | Default MCS configuration management messages and other information elements | Update for Rel-15 additions | NIST, UPV/EHU, Nemergent Solutions | RAN5#95 (May-22) | R5-206423, R5-206450, R5-206084, R5-221545 |  | 1 | 100% | 100% |  | 100%
9 | Y | 36.579-2 | 5.5.9.1 | MIKEY-SAKKE I_MESSAGE | Addition of default message for CSK download scenario | NIST | RAN5#95 (May-22) | R5-216282 |  | 1 | 100% | 100% |  | 100%
10 |  | 36.579-1 | 5.5.11 | Default MCVideo Transmission Control Messages and other Information Elements | Update for Rel-15 additions | NIST | RAN5#95 (May-22) | R5-213267 |  | 1 | 100% | 100% |  | 100%
11 | Y | 36.579-1 | 5.5.14 | Default MCVideo Call Control Off-network Messages and Other Information Elements | Addition for off-network MCVideo call control default messages | NIST | RAN5#95 (May-22) | R5-222142 |  | 1 | 100% | 100% |  | 100%
TS 36.579-2: MCPTT UE test cases
|  | 36.579-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
12 |  | 36.579-2 | 5 | MCPTT Client Configuration |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
13 | Y | 36.579-2 | 5.6 | Configuration / Downoad CSK | To verify the MCS Client can properly download a new CSK initiated by the SS and then properly use the new CSK See TS 24.379 clause 7.2.5 See TS 33.180 clause 9.2.1.4 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-216283, R5-216644 |  | 1 | 100% | 100% |  | 100%
14 | Y | 36.579-2 | 5.7 | Configuration / Subscription to group dynamic data / De-subscribe | To verify the MCS Client can properly subscribe to group dynamic data and then de-subscribe See TS 24.379 clause 9.2.1.6 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-215601, R5-217976 |  | 1 | 100% | 100% |  | 100%
15 | Y | 36.579-2 | 5.8 | Configuration / Functional Alias / Functional alias status determination / Activate functional alias / Deactivate functional alias | To verify the MCS Client can properly determine the status of a functional alias, activate a functional alias, and deactivate a functional alias See TS 24.379 clause 9A.2.1.2, 9A.2.1.3 | NIST | RAN5#95 (May-22) | R5-213597 |  | 1 | 100% | 100% |  | 100%
16 |  | 36.579-2 | 6 | MCPTT Client on-network operation |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
17 |  | 36.579-2 | 6.1 | Group Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
18 |  | 36.579-2 | 6.1.1 | Pre-arranged Group Call |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
19 | Y | 36.579-2 | 6.1.1.19 | On-network / On-demand Pre-arranged Group Call / Active functional alias / Client Originated (CO) | To very the MCPTT Client can originate an On-demand Pre-arranged Group Call using an active functional alias TS 24.379 clause 10.1.1.2.1.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213255, R5-216646 |  | 1 | 100% | 100% |  | 100%
20 | Y | 36.579-2 | 6.1.1.20 | On-network / On-demand Pre-arranged Group Call / Multi Talker | To verify that the MCPTT Client can properly process the Floor Release Multi Talker message See 24.380 clauses 6.2.4.3.7, 6.2.4.4.10, 6.2.4.5.9, 6.2.4.6.9, 6.2.4.9.14 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213598, R5-216647 |  | 1 | 100% | 100% |  | 100%
21 |  | 36.579-2 | 6.1.2 | Chat Group Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
22 | Y | 36.579-2 | 6.1.2.13 | On-network / Chat Group Call / Join Chat Group Session / Active functional alias / Client Originated (CO) | To verify the MCPTT Client can join a chat group sessions using an active functional alias See TS 24.379 clause 10.1.2.2.1.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213599, R5-216648 |  | 1 | 100% | 100% |  | 100%
23 | Y | 36.579-2 | 6.1.2.14 | On-network / Chat Group Call / Chat Group Call Using Pre-established Session / Active functional alias / Client Originated (CO) | To verify the MCPTT Client can join a chat group sessions using a pre-established session and using an active functional alias See TS 24.379 clause 10.1.2.2.2.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213600, R5-216649 |  | 1 | 100% | 100% |  | 100%
24 |  | 36.579-2 | 6.1.3 | Conference Event Package | New sub-clause header | NIST | RAN5#95 (May-22) | R5-217907 |  | 0.1 | 100% | 100% |  | 100%
25 | Y | 36.579-2 | 6.1.3.1 | On-network / Conference Event Package / Subscription to Conference Event Package / Termination of subscription | To verify the MCPTT Client can subscribe to the conference state event package when a group call is ongoing and the ongoing group call is not initiated as a broadcast group call by sending a SIP SUBSCRIBE request to obtain information of the status of a group session To verify the MCPTT Client can terminate the subscription See TS 24.379 clause 10.1.3.2 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217907, R5-222363 |  | 1 | 100% | 100% |  | 100%
26 |  | 36.579-2 | 6.1.4 | Remote Change of Selected Group | New sub-clause header | NIST | RAN5#95 (May-22) | R5-217908 |  | 0.1 | 100% | 100% |  | 100%
27 | Y | 36.579-2 | 6.1.4.1 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Originated (CO) | To verify the MCPTT Client can send a group selection change request to change the selected group of a targeted MCPTT user to a specific MCPTT group See TS 24.379 clause 10.1.4.2.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217908, R5-222364 |  | 1 | 100% | 100% |  | 100%
28 | Y | 36.579-2 | 6.1.4.2 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Terminated (CT) | To verify the MCPTT Client can, upon receiving a "SIP MESSAGE request for group selection change request for terminating client", change to a specific MCPTT group See TS 24.379 clause 10.1.4.2.2 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217909, R5-222365 |  | 1 | 100% | 100% |  | 100%
29 |  | 36.579-2 | 6.1.5 | Remotely initiated group call | New sub-clause header | NIST | RAN5#95 (May-22) | R5-217910 |  | 0.1 | 100% | 100% |  | 100%
30 | Y | 36.579-2 | 6.1.5.1 | On-network / Remotely initiated group call / Client Originated (CO) | To verify the MCPTT Client can, upon receiving a request from the requesting MCPTT user to send a remotely initiated group call request to the remote MCPTT user for a targeted MCPTT group, generate and send a SIP MESSAGE request See TS 24.379 clause 10.1.5.2.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217910, R5-222366 |  | 1 | 100% | 100% |  | 100%
31 | Y | 36.579-2 | 6.1.5.2 | On-network / Remotely initiated group call / Client Terminated (CT) | To verify the MCPTT Client can, upon receiving a "SIP MESSAGE request for remotely initiated group call request for terminating client", invoke the procedures of subclause 10.1.1.2.1.1 to originate an MCPTT group call to the targeted MCPTT group and then generate and send a SIP MESSAGE request See TS 24.379 clause 10.1.5.2.2 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217911, R5-222367 |  | 1 | 100% | 100% |  | 100%
32 |  | 36.579-2 | 6.2 | Private Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
33 | Y | 36.579-2 | 6.2.18 | On-network / Private call / Ambient listening call / Remote initiated ambient listening call / Pre-established session / Ambient listening call release / Client Originated (CO) | To verify the MCPTT Client can initiate an ambient listening call using a pre-established session To verify the MCPTT Client can release an ambient listening call using a pre-established session See TS 24.379 clause 11.1.6.2.2.1, 11.1.6.2.2.3, 11.1.6.2.2.4 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217912, R5-222368 |  | 1 | 100% | 100% |  | 100%
34 | Y | 36.579-2 | 6.2.19 | On-network / Private call / Ambient listening call / Remote initiated ambient listening call / Pre-established session / Ambient listening call release / Client Terminated (CT) | To verify the MCPTT Client can receive an ambient listening call using a pre-established session To verify the MCPTT Client can release an ambient listening call using a pre-established session See TS 24.379 clause 11.1.6.2.2.2, 11.1.6.2.2.5, 11.1.6.2.2.4 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-217913, R5-222368 |  | 1 | 100% | 100% |  | 100%
35 | Y | 36.579-2 | 6.2.20 | On-network / First-to-answer call / On-demand session / Client Originated (CO) | To verify the MCPTT Client can initiate a first-to-answer call See TS 24.379 clause 11.1.1.2.1.1 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213590, R5-216650 |  | 1 | 100% | 100% |  | 100%
36 | Y | 36.579-2 | 6.2.21 | On-network / First-to-answer call / On-demand session / Client Terminated (CT) | To verify the MCPTT Client can terminate a first-to-answer call See TS 24.379 clause 11.1.1.2.1.2 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213591, R5-216651 |  | 1 | 100% | 100% |  | 100%
37 | Y | 36.579-2 | 6.2.22 | On-network / First-to-answer call / Pre-established session / Client Originated (CO) | To verify the MCPTT Client can initiate a first-to-answer call using a pre-established session See TS 24.379 clause 11.1.1.2.2.1 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213592, R5-216652 |  | 1 | 100% | 100% |  | 100%
38 | Y | 36.579-2 | 6.2.23 | On-network / First-to-answer call / Pre-established session / Client Terminated (CT) | To verify the MCPTT Client can terminated a first-to-answer call using a pre-established session See TS 24.379 clause 11.1.1.2.2.2 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213593, R5-217906, R5-216657 |  | 1 | 100% | 100% |  | 100%
39 | Y | 36.579-2 | 6.2.24 | On-network / Private call / Remotely initiated private call / Client Originated (CO) | To verify the MCPTT Client can originate a remotely initated private call. See TS 24.379 clause 11.1.7.2.1 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213594, R5-217977 |  | 1 | 100% | 100% |  | 100%
40 | Y | 36.579-2 | 6.2.25 | On-network / Private call / Remotely initiated private call / On-demand session / Client Terminated (CT) | To verify the MCPTT Client can originate a remotely initated private call. See TS 24.379 clause 11.1.7.2.2 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213595, R5-217978 |  | 1 | 100% | 100% |  | 100%
41 | Y | 36.579-2 | 6.2.26 | On-network / Private call / Remotely initiated private call / Pre-established session / Client Terminated (CT) | To verify the MCPTT Client can initiate an ambient listening call using a pre-established session To verify the MCPTT Client can release an ambient listening call using a pre-established session See TS 24.379 clause 11.1.6.2.2.1, 11.1.6.2.2.3, 11.1.6.2.2.4 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213596, R5-217979 |  | 1 | 100% | 100% |  | 100%
42 |  | 36.579-2 | 6.4 | MBMS |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
43 | Y | 36.579-2 | 6.4.2 | On-network / MBMS / Multi Talker | To verify that the MCPTT Client can properly process the Floor Release Multi Talker message when using MBMS. See 24.380 clauses 6.2.4.3.7, 6.2.4.4.10, 6.2.4.5.9, 6.2.4.6.9, 6.2.4.9.14 | NIST | RAN5#95 (May-22) | R5-217633 |  | 1 | 100% | 100% |  | 100%
TS 36.579-4: Applicability and ICS MC test cases
|  | 36.579-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
44 |  | 36.579-4 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 37.579-x. | Samsung, NIST | RAN5#95 (May-22) | R5-211254, R5-223384 |  | 1 | 100% | 100% |  | 100%
45 |  | 36.579-4 | A.4 | ICS proforma tables |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
46 |  | 36.579-4 | A.4.1 | Implementation Types | Additions for Rel-15 for the new test cases introduced in 37.579-x. | NIST | RAN5#95 (May-22) | R5-223384 |  | 1 | 100% | 100% |  | 100%
47 |  | 36.579-4 | A.4.2 | Additional information | Additions for Rel-15 for the new test cases introduced in 37.579-x. | Samsung | RAN5#95 (May-22) | R5-211254 |  | 1 | 100% | 100% |  | 100%
TS 36.579-5: MC Test suite (TTCN)
|  | 36.579-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
TS 36.579-6: MC Video UE test cases
|  | 36.579-6 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
48 |  | 36.579-6 | 6 | On-Network Test Scenarios |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
49 |  | 36.579-6 | 6.1 | Group Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
50 |  | 36.579-6 | 6.1.1 | Pre-Arranged Group Call |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
51 | Y | 36.579-6 | 6.1.1.12 | On-network / On-demand Pre-arranged Group Call / Transmission Control State Transitions / Client Originated (CO) | To verufy that the MCVideo Client can properly handle all of the Transmission Control messages | NIST | RAN5#95 (May-22) | R5-213256 |  | 1 | 100% | 100% |  | 100%
52 | Y | 36.579-6 | 6.1.1.13 | On-network / On-demand Pre-arranged Group Call / Reception Control State Transitions / Client Terminated (CT) | To verufy that the MCVideo Client can properly handle all of the Reception Control messages | NIST | RAN5#95 (May-22) | R5-213257 |  | 1 | 100% | 100% |  | 100%
53 | Y | 36.579-6 | 6.1.2.5 | On-network / Chat Group Call / Emergency Call / Imminent Peril Call / Client Originated (CO) | To verify that a device can originate an emergency chat group call. | NIST | RAN5#95 (May-22) | R5-215599 |  | 1 | 100% | 100% |  | 100%
54 |  | 36.579-6 | 6.1.3 | Subscription to Conference Event Package | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221553 |  | 0.1 | 100% | 100% |  | 100%
55 | Y | 36.579-6 | 6.1.3.1 | On-network / Conference Event Package / Subscription to Conference Event Package / Termination of subscription | To verify that a MCVideo Client is able to request subscription to status updates through the Conference State Events Package. This can occur at any time while the Client is connected to a Group Call. See also TS 24.281 clause 9.2.3, 4.4.2, 9.2.1.2.1 See also TS 24.481 clause 7.2.8 See also TS 33.180 clause 7.3 | NIST | RAN5#95 (May-22) | R5-221553 |  | 1 | 100% | 100% |  | 100%
56 |  | 36.579-6 | 6.1.4 | Remote change of selected group | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221551 |  | 0.1 | 100% | 100% |  | 100%
57 | Y | 36.579-6 | 6.1.4.1 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Originated (CO) | To verify that a request from a given user to change the selected Group of a target user executes properly See also TS 24.281 clause 9.2.4.2, 9.2.4.3 See also TS 24.481 clause 6.3 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221551, R5-222372 |  | 1 | 100% | 100% |  | 100%
58 | Y | 36.579-6 | 6.1.4.2 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Terminated (CT) | To verify that a MCVideo target user receiving a request to change Groups executes properly See also TS24.281 clause 9.2.4.2, 9.2.4.3 See also TS 24.481 clause 6.3 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221552, R5-222373 |  | 1 | 100% | 100% |  | 100%
59 |  | 36.579-6 | 6.3 | Emergnecy Alert | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221548 |  | 0.1 | 100% | 100% |  | 100%
60 | Y | 36.579-6 | 6.3.1 | On-network / Emergency alert / Cancel emergency alert / Client Originated (CO) | To verify that an Emergency Alert sent from one User reaches the rest of the indicated User Group. To verify that an Emergency Alert notification can be originated (transmitted) properly. To verify that a transmitted Emergency Alert contains the proper information To verify that an Emergency Alert can be properly authenticated See also TS 24.281 clause 4.6.3, 6.2.8.1.6, 11.2.1.1, 11.2.1.2 See also TS 24.481 clause 7.2.8 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221548, R5-222370 |  | 1 | 100% | 100% |  | 100%
61 | Y | 36.579-6 | 6.3.2 | On-network / Emergency Alert / Emergency alert origination / Emergency alert cancellation / Client Terminated (CT) | To verify that an Emergency Alert sent from one User reaches the rest of the indicated User Group. To verify that an Emergency Alert notification can be terminated (received) properly. To verify that a received Emergency Alert contains the proper information To verify that an Emergency Alert can be properly authenticated See also TS 24.281 clause 4.6.3, 6.2.8.1.6, 11.2.1, 11.2.1.3 See also TS 24.481 clause 7.2.8 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221554, R5-222370 |  | 1 | 100% | 100% |  | 100%
62 |  | 36.579-6 | 6.4 | Video Pull | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221546 |  | 0 | 100% | 100% |  | 100%
63 | Y | 36.579-6 | 6.4.1 | On-network / Video pull call / One-to-one video pull call / Client Originated (CO) |  | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221546, R5-222374 |  | 1 | 100% | 100% |  | 100%
64 |  | 36.579-6 | 6.5 | Video Push | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221547 |  | 0 | 100% | 100% |  | 100%
65 | Y | 36.579-6 | 6.5.1 | On-network / Video push call / One-to-one video push call / Client Originated (CO) |  | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221547, R5-222375 |  | 1 | 100% | 100% |  | 100%
66 |  | 36.579-6 | 6.6 | Capability information sharing | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221549 | This will be a place holder for when the core spec contains information for this subject matter | 0 | 100% | 100% |  | 100%
67 |  | 36.579-6 | 6.7 | Ambient viewing call | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221549 |  | 0 | 100% | 100% |  | 100%
68 | Y | 36.579-6 | 6.7.1 | On-network / On-demand ambient viewing call / Remote initiated ambient viewing call / Client Originated (CO) |  | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221549, R5-222371 |  | 1 | 100% | 100% |  | 100%
69 | Y | 36.579-6 | 6.7.2 | On-network / On-demand ambient viewing call / Remote initiated ambient viewing call / Client Terminated (CT) |  | NIST, MCC TF160 | RAN5#95 (May-22) | R5-221550, R5-222371 |  | 1 | 100% | 100% |  | 100%
70 |  | 36.579-6 | 6.8 | Use of MBMS transmission | New sub-clause header | NIST | RAN5#95 (May-22) | R5-221555 |  | 0.1 | 100% | 100% |  | 100%
71 | Y | 36.579-6 | 6.8.1 | On-network / MBMS / MBMS Bearer Announcement / MBMS Bearer Listening Status / Transition to MBMS from Unicast / MBMS Transmission Control / Transition to Unicast from MBMS |  | NIST | RAN5#95 (May-22) | R5-221555 |  | 1 | 100% | 100% |  | 100%
72 |  | 36.579-6 | 7 | Off-Network Test Scenarios |  | NIST | RAN5#95 (May-22) | R5-222149 |  | 0.1 | 100% | 100% |  | 100%
73 |  | 36.579-6 | 7.1 | Group Calls | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222149 |  | 0.1 | 100% | 100% |  | 100%
74 |  | 36.579-6 | 7.1.1 | Basic Group Calls | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222149 |  | 0.1 | 100% | 100% |  | 100%
75 | Y | 36.579-6 | 7.1.1.1 | Off-network / Group Call / Basic Group Call / Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Upgrade to Imminent Peril Call / Downgrade from Imminent Peril Call / Release call / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222149 |  | 1 | 100% | 100% |  | 100%
76 | Y | 36.579-6 | 7.1.1.2 | Off-network / Group Call / Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Upgrade to Imminent Peril Call / Downgrade from Imminent Peril Call / Release call / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222150 |  | 1 | 100% | 100% |  | 100%
77 | Y | 36.579-6 | 7.1.1.3 | Off-network / Group Call / Emergency Call / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222151 |  | 1 | 100% | 100% |  | 100%
78 | Y | 36.579-6 | 7.1.1.4 | Off-network / Group Call / Emergency Call / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222152 |  | 1 | 100% | 100% |  | 100%
79 | Y | 36.579-6 | 7.1.1.5 | Off-network / Group Call / Imminent Peril Call / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222153 |  | 1 | 100% | 100% |  | 100%
80 | Y | 36.579-6 | 7.1.1.6 | Off-network / Group Call / Imminent Peril Call / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222154 |  | 1 | 100% | 100% |  | 100%
81 |  | 36.579-6 | 7.1.2 | Broadcast Group Calls | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222155 |  | 0 | 100% | 100% |  | 100%
82 | Y | 36.579-6 | 7.1.2.1 | Off-network / Group Call / Broadcast Group Call / Broadcast Group Call Retransmitting / Broadcast Group Call Release / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222155 |  | 1 | 100% | 100% |  | 100%
83 | Y | 36.579-6 | 7.1.2.2 | Off-network / Group Call / Broadcast Group Call / Originator Releases Call / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222156 |  | 1 | 100% | 100% |  | 100%
84 |  | 36.579-6 | 7.2 | Private Call | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222157 |  | 0.1 | 100% | 100% |  | 100%
85 | Y | 36.579-6 | 7.2.1 | Off-network / Private Call / Automatic Commencement Mode / No response to private call setup request / Private call setup request accepted / Release call / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222157 |  | 1 | 100% | 100% |  | 100%
86 | Y | 36.579-6 | 7.2.2 | Off-network / Private Call / Automatic Commencement Mode / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222158 |  | 1 | 100% | 100% |  | 100%
87 | Y | 36.579-6 | 7.2.3 | Off-network / Private Call / Manual Commencement Mode / Call Released before establishment completion / Call request rejected / Call establishment successful / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222159 |  | 1 | 100% | 100% |  | 100%
88 | Y | 36.579-6 | 7.2.4 | Off-network / Private Call / Manual Commencement Mode / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222160 |  | 1 | 100% | 100% |  | 100%
89 |  | 36.579-6 | 7.3 | Emergency Alerts | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222161 |  | 0.1 | 100% | 100% |  | 100%
90 | Y | 36.579-6 | 7.3.1 | Off-network / Emergency Alert / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222161 |  | 1 | 100% | 100% |  | 100%
91 | Y | 36.579-6 | 7.3.2 | Off-network / Emergency Alert / Client Terminated (CO) |  | NIST | RAN5#95 (May-22) | R5-222162 |  | 1 | 100% | 100% |  | 100%
TS 36.579-7: MC Data UE test cases
|  | 36.579-7 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
92 |  | 36.579-7 | 6 | On-Network Test Scenarios |  |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  | 100%
93 | Y | 36.579-7 | 6.2.13 | On-network / File Distribution (FD) / Accessing list of deferred data group communications / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-213420 |  | 1 | 100% | 100% |  | 100%
94 |  | 36.579-7 | 6.3 | Enhanced Status (ES) | New sub-clause header |  | RAN5#95 (May-22) | R5-217914 |  | 0 | 100% | 100% |  | 100%
95 | Y | 36.579-7 | 6.3.1 | On-network / Enhanced Status (ES) / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-217914 |  | 1 | 100% | 100% |  | 100%
96 | Y | 36.579-7 | 6.3.2 | On-network / Enhanced Status (ES) / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-217915 |  | 1 | 100% | 100% |  | 100%
97 |  | 36.579-7 | 7.1 | Short Data Service (SDS) | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222143 |  | 0 | 100% | 100% |  | 100%
98 | Y | 36.579-7 | 7.1.1 | Off-network / Short Data Service (SDS) / Standalone SDS using signalling control plane / One-to-one SDS message / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222143 |  | 1 | 100% | 100% |  | 100%
99 | Y | 36.579-7 | 7.1.2 | Off-network / Short Data Service (SDS) / Standalone SDS using signalling control plane / One-to-one SDS message / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222144 |  | 1 | 100% | 100% |  | 100%
100 | Y | 36.579-7 | 7.1.3 | Off-network / Short Data Service (SDS) / Standalone SDS using signalling control plane / Group SDS message / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222145 |  | 1 | 100% | 100% |  | 100%
101 | Y | 36.579-7 | 7.1.4 | Off-network / Short Data Service (SDS) / Standalone SDS using signalling control plane / Group SDS message / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222146 |  | 1 | 100% | 100% |  | 100%
102 |  | 36.579-7 | 7.2 | Enhanced Status (ES) | New sub-clause header | NIST | RAN5#95 (May-22) | R5-222147 |  | 0 | 100% | 100% |  | 100%
103 | Y | 36.579-7 | 7.2.1 | Off-network / Enhanced Status (ES) / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-222147 |  | 1 | 100% | 100% |  | 100%
104 | Y | 36.579-7 | 7.2.2 | Off-network / Enhanced Status (ES) / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-222148 |  | 1 | 100% | 100% |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.