## WP scope
Work plan for introduction of NR-DC PC3 FR1 configurations into 3GPP UE conformance test specifications
| WP template: | WP NR-DC PC3 FR1 v1.1.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | DRAFT WP NR-DC PC3 FR1 v1.1.0 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | TBD | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 0%
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs
|  |  |  | DC_nXA-nYA | DC_nXA-nYA

## WP NR-DC PC3 FR1
Work plan for introduction of NR-DC PC3 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR-DC PC3 FR1 v1.1.0
1. Configurations covered by the work plan
|  | Type of NR-DC configurations |  |  |  | WP item Applicability Label | NR-DC configurations [DL/UL]
|  | New NR-DC configuration without UL NR-DC |  |  |  | DL/-
|  | New NR-DC configuration with UL NR-DC |  |  |  | DL/UL | DC_nXA-nYA/DC_nXA-nYA
|  | All configurations |  |  |  | All | DC_nXA-nYA/DC_nXA-nYA
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 0%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 0%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR-DC configurations |  |  |  |  | 0%
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 0%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1) |  |  |  |  | 0%
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6) |  |  |  |  | 0%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7) |  |  |  |  | 0%
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 0%
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Bands completed | TCs available | BSC0 completed | Impacted CBWs identified | Bands new CBWs completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands completed | DC_nXA-nYA/DC_nXA-nYA | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in RAN5 PRD21 worksheet "NR bands". |  | TBD |  |  | 1 | 0% |  | 0%
All | 1-2 | Pre-requisite | 38.521-1 | 6, 7 | All applicable Transmitter (clause 6) and Receiver (clause 7) for the type of NR-DC configuration completed | DC_nXA-nYA/DC_nXA-nYA | Set status in column "TCs available" to 100% when all applicable test cases in 38.521-1 are completed for at least one of the same NR-DC type of NR-DC configuration. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. |  | TBD |  |  | 1 | 0% |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR-DC configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
DL/UL | 2 | TP Analysis | 38.905 | 4.1.2.2 | Test point (TP) analysis for A-MPR | DC_nXA-nYA/DC_nXA-nYA | For each UL NR-DC configuration perform an A-MPR TP analysis as described in TR 38.905 clause 4.1.2.2 for intra-band contiguous UL CA and inter-band UL NR-DC. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 38.905. |  | TBD |  |  | 1 | 0% |  | 0%
All | 2-1a | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity | DC_nXA-nYA/DC_nXA-nYA | For each NR-DC configuration >=2DL perform reference sensitivity TP analysis as described in TR 38.905, Annex B.9. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | TBD |  |  | 1 | 0% |  | 0%
DL/UL | 2-2 | TP Analysis | 38.905 | 4.1.3.2 | Test point (TP) analysis for UE co-extance test cases for inter-band UL NR-DC | DC_nXA-nYA/DC_nXA-nYA | For each two band UL NR-DC inter-band configuration perform UE-coexistence spurious emission TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
All | 3.1-1 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.1.3, 4.3.1.1.5, 4.3.1.1.7 | Test frequencies | DC_nXA-nYA/DC_nXA-nYA | - Add the NR-DC configuration to the relevant test frequency table in clause 4.3.1.1.7 - Check that the involved bands have single carrier test frequencies specified in 4.3.1.x - For NR-DC configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in clause 4.3.1.1.3 and 4.3.1.1.5 respectively. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.1-2 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.6 | Test frequencies for NR-DCsignalling test | DC_nXA-nYA/DC_nXA-nYA | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.6 (protocol testing limited to 2CC NR-DC configurations) |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Clause 5 | Discussion paper
[15 empty] | 1 | 1
All | 3.2-0.0 | 38.521-1 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. |  | If it is thought there are no configuration specific changes needed for Chapter 6/7 or only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7 or why only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | TBD |  |  | 1 |  |  |  | 0%
All | 3.2-0 | 38.521-1 - General | 38.521-1 | 3.2 | Symbols | DC_nXA-nYA/DC_nXA-nYA | Check if new symbols need to be added for the new NR-DC band combos. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-1 | 38.521-1 - General | 38.521-1 | 5.2A.1 | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. | DC_nXA-nYA/DC_nXA-nYA | For intra-band contiguous and non-contiguos CA configrurations add the NR-DC operating bands to the relevant table in clause 5.2A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-2 | 38.521-1 - General | 38.521-1 | 5.5B | Inter-band NR-DC operating bands | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC configurations add the NR-DC operating bands to the relevant table in clause 5.5B Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-3 | 38.521-1 - General | 38.521-1 | 5.5A.1 | Configurations for intra-band contiguous CCs | DC_nXA-nYA/DC_nXA-nYA | For intra-band contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-4 | 38.521-1 - General | 38.521-1 | 5.5A.2 | Configurations for intra-band non-contiguous CCs | DC_nXA-nYA/DC_nXA-nYA | For intra-band non-contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.2. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
DL/UL | 3.2-5 | 38.521-1 - General | 38.521-1 | 6.2B.4.0.2 | ΔTIB,c for NR-DC | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC configurations add ΔTIB,c for the NR-DC configuration to the relevant table in clause 6.2B.4.0.2. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-6 | 38.521-1 - General | 38.521-1 | 7.3A.0.3 | ΔRIB,c for NR-DC | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC configurations add ΔRIB,c for the NR-DC configuration to the relevant table in clause 7.3A.0.3. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-7 | 38.521-1 - General | 38.521-1 | 7.3A.0.4 | Reference sensitivity exceptions due to UL harmonic interference for NR-DC | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC configurations add the reference sensitivity exceptions, Uplink configuration and MSD for inter-band NR-DC to the relevant table in clause 7.3A.0.4. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-8 | 38.521-1 - General | 38.521-1 | 7.3A.0.5 | Reference sensitivity exceptions due to intermodulation interference due to 2UL NR-DC | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC configurations add Reference sensitivity and Uplink/Downlink configurations for the NR-DC configuration to the relevant table in clause 7.3A.0.5. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-9 | 38.521-1 - General | 38.521-1 | 7.3A.0.6 | Reference sensitivity exceptions due to cross band isolation for NR-DC | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC configurations add Reference sensitivity and Uplink/Downlink configurations for the NR-DC configuration to the relevant table in clause 7.3A.0.6. |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
DL/UL | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.2B.1.0.3 | UE maximum output power for Inter-band NR-DC | DC_nXA-nYA/DC_nXA-nYA | For configurations including any inter-band UL NR-DC CCsc add the UE maximum output power for inter-band UL NR-DC to Table 6.2B.1.0.3-1. |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
DL/UL | 3.1-2 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.4 | UE maximum output power for Intra-band contiguous CA | DC_nXA-nYA/DC_nXA-nYA | For configurations including any Intra-band contiguous UL CA add the UE maximum output power for Intra-band contiguous UL CA to Table 6.2A.1.0.4-1. |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
DL/UL | 3.3-3 | 38.521-1- RF Tx | 38.521-1 | 6.2B.1.1 | UE maximum output power for NR-DC (2UL NR-DC) | DC_nXA-nYA/DC_nXA-nYA | For any FR1 Inter-band/Intra-band non-contiguous 2UL NR-DC configurations add the test requirements for Inter-band/Intra-band non-contiguous 2UL NR-DC to Table 6.2B.1.1.5-1. |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
DL/UL | 3.3-4 | 38.521-1- RF Tx | 38.521-1 | 6.2B.3.1, 6.2.3.4.1, 6.2.3.5 | UE additional maximum output power reduction for NR-DC | DC_nXA-nYA/DC_nXA-nYA | For inter-band NR-DC add the Initial Conditions to clause 6.2.3.4.1; Add tables for inter-band NR-DC in Section 6.2.3.5 Test requirement. |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0% | 0%
DL/UL | 3.3-5 | 38.521-1- RF Tx | 38.521-1 | 6.5A.3.2 | Inter-band spurious emission for UE co-existence Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 5) | DC_nXA-nYA/DC_nXA-nYA | For configurations with inter-band UL NR-DC: - Add the minimum conformance requirements - If the TP analysis in Step 2 (WP item 5) shows that additional TPs more than the default TP#1 and TP#2 are needed add all test points (including default TPs if applicable) based on the TP analysis done in Step 2 (WP item 5). - Add test requirement based on the TP analysis done in Step 2 (WP item 4-2). |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.4-1 | 38.521-1-RF Rx | 38.521-1 | 7.3A.1~4 | Reference sensitivity power level for 2DL to 5DL NR-DC Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 2-2a) | DC_nXA-nYA/DC_nXA-nYA | Add test configuration and test requirements for any exceptional requirements based on TR 38.905 reference sensitivity TP analysis in Step 2 (WP item 2-2a). |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted NR-DC config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.2.1 | NR-DC including Intra-band contiguous CCs | DC_nXA-nYA/DC_nXA-nYA | Add configurations for Intra-band contiguous CA within FR1 to the relevant table in clause A.4.3.2A.2.1 |  | TBD |  |  | 1 | 0% |  | 0%
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.3.1 | NR-DC including Intra-band non-contiguous CCs | DC_nXA-nYA/DC_nXA-nYA | Add configurations for NR Intra-band non-contiguous CA within FR1 to the relevant table in clause A.4.3.2A.3.1 |  | TBD |  |  | 1 | 0% |  | 0%
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.1.0a | NR Inter-band NR-DC | DC_nXA-nYA/DC_nXA-nYA | Add NR-DC configurations for NR Inter-band NR-DC within FR1 to the relevant table in clause A.4.3.2B.1.0a.1 |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N27: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N35: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N45: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N53: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N70: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N81: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N88: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N95: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N102: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.1.0 | RAN5#95-e | Initial version