## Summary
Work plan summary:
Rel-15 5GS NE-DC Maintenance Workplan for protocol testing
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Rel-15 5GS NE-DC Maintenance Workplan for protocol testing | NSA Option 4 (NE-DC) | 14.52% | 15.81% | 13.23%
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of FR1+FR2 specific test cases
|  |  | Overall | Completed for at least one of FR1, FR2 or FR1+FR2 | Overall | Completed | Overall | Completed | Overall | Completed
| Rel-15 5GS NE-DC Maintenance Workplan for protocol testing | NSA Option 4 (NE-DC) | 31 | 4 | 31 | 4 | 31 | 0 | 0 | 0

## WP
WP Title: | Rel-15 5GS NE-DC Maintenance Workplan for protocol testing | [20 empty] | End of work plan columns. Note! Do not remove this column.
WP Scope: | This work plan section covers NE-DC protocol test cases to be completed under maintenace and WI codes: TEI15_Test, 5GS_NR_LTE-UEConTest.
WP Resp: | Luting Kong, CMCC |  |  |  | kongluting@chinamobile.com | [7 empty] | SA NR |  |  | EN-DC |  |  | NE-DC
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Outstanding issues | Weight | WP item compl. | FR1 | FR2 | FR1+FR2 | FR1 | FR2 | FR1+FR2 | FR1 | FR2 | FR1+FR2
[12 empty] | Overall | [6 empty] | 14.52%
[19 empty] | 15.81% | 13.23%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
RRC | [5 empty] | Responsible: Luting Kong, CMCC
RRC Connection Reconfiguration / Radio Bearer Addition, Modification and Release
274 | Y | 38.523-1 | 8.2.2.2.3 | Split SRB Establishment and Release / NE-DC | **** TP1: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: UE receives an RRCReconfiguration message on SRB1 to configure split SRB1 and split SRB2 with PDCP duplication activated THEN: UE configures the split SRBs and sends an RRCReconfigurationComplete message on split SRB1 with the PDCP PDU duplicated on the MCG and SCG path **** TP2: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC and split SRB configured WHEN: UE receives an RRCReconfiguration message on split SRB1 over the SCG path to release split SRB1 and split SRB2 THEN: UE releases split SRB1 and split SRB2 and sends an RRCReconfigurationComplete message on SRB1 over the MCG path **** TP3: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state in NE-DC mode with split SRB1 and split SRB2 configured with PDCP duplication WHEN: UE receives a CounterCheck on split SRB1 over the SCG path THEN: UE replies with CounterCheckResponse on split SRB1 duplicated on the MCG and SCG path **** TP4: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state in NE-DC mode with split SRB1 and split SRB2 configured with PDCP duplication WHEN: UE receives a IDENTITY REQUEST on split SRB2 over the SCG path THEN: UE replies with IDENTITY RESPONSE on split SRB2 duplicated on the MCG and SCG path | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
243 | Y | 38.523-1 | 8.2.2.5.3 | PSCell addition, modification and release / Split DRB / NE-DC | **** TP1: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCReconfiguration message to add EUTRA PSCell with Split DRB THEN: UE configures the PSCell and sends an RRCReconfigurationComplete message **** TP2: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: UE receives an RRCReconfiguration message to modify Split DRB THEN: UE reconfigures the Split DRB and sends an RRCReconfigurationComplete message **** TP3: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: UE receives an RRCReconfiguration message to release EUTRA PSCell with Split DRB THEN: UE releases the PSCell and Split DRB and sends an RRCReconfigurationComplete message | CMCC | RAN5#97 (Nov-22) | R5-217814 | FFS in Table 8.2.2.5.3.3.3-4 needs to be updated | NE-DC: FFS in Table 8.2.2.5.3.3.3-4 needs to be updated | 1 | 90% | [6 empty] | 90% | 90%
244 | Y | 38.523-1 | 8.2.2.7.3 | Bearer Modification / Handling for bearer type change without security key change / NE-DC | **** TP1: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC with SCG WHEN: UE receives an RRCReconfiguration message to modify SCG DRB to Split DRB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP2: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC with Split DRB WHEN: UE receives an RRCReconfiguration message to modify Split DRB to MCG DRB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP3: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC and MCG DRB WHEN: UE receives an RRCReconfiguration message to modify MCG DRB to Split DRB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP4: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC with Split DRB WHEN: UE receives an RRCReconfiguration message to modify Split DRB to SCG DRB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP5: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC with SCG WHEN: UE receives an RRCReconfiguration message to modify SCG DRB to MCG DRB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP6: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC and MCG DRB WHEN: UE receives an RRCReconfiguration message to modify MCG DRB to SCG DRB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
245 | Y | 38.523-1 | 8.2.2.8.3 | Bearer Modification / Handling for bearer type change with security key change / NE-DC | **** TP1: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC and SCG WHEN: UE receives an RRCReconfiguration message to modify the SN terminated SCG DRB to MN terminated SCG DRB with security key change to kgNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP2: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and and MN terminated SCG DRB established with security key kgNB WHEN: UE receives an RRCReconfiguration message to modify the MN terminated SCG DRB to SN terminated Split DRB with security key change to s-KeNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP3: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and SN terminated Split DRB established with security key s-KeNB WHEN: UE receives an RRCCReconfiguration message to modify the SN terminated Split DRB to MN terminated Split DRB with security key change to kgNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP4: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and, and MN terminated Split DRB established with security key kgNB WHEN: UE receives an RRCReconfiguration message to modify the MN terminated Split DRB to SN terminated MCG DRB with security key change to s-KeNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP5: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and, and SN terminated MCG DRB established with security key s-keNB WHEN: UE receives an RRCReconfiguration message to modify the SN terminated MCG DRB to MN terminated MCG DRB with security key change to kgNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP6: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and, and MN terminated MCG DRB established with security key kgNB WHEN: UE receives an RRCReconfiguration message to modify the MN terminated MCG DRB to SN terminated Split DRB with security key change to s-KeNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP7: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and, and SN terminated Split DRB established with security key s-keNB WHEN: UE receives an RRCReconfiguration message to modify the SN terminated Split DRB to MN terminated SCG DRB with security key change to kgNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP8: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and, and MN terminated SCG DRB established with security key kgNB WHEN: UE receives an RRCReconfiguration message to modify the MN terminated SCG DRB to SN terminated MCG DRB with security key change to s-KeNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message **** TP9: [TS 38,331:FFS; TS 36,331:FFS; TS 37.340:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and, and SN terminated MCG DRB established with security key s-keNB WHEN: UE receives an RRCReconfiguration message to modify the SN terminated MCG DRB to MN terminated SCG DRB with security key change to kgNB THEN: UE reconfigures the DRB and sends an RRCReconfigurationComplete message | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
246 | Y | 38.523-1 | 8.2.2.9.3 | Bearer Modification / Uplink data path / Split DRB Reconfiguration / NE-DC | **** TP1: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and MCG and split WHEN: UE receives an RRCCReconfiguration message to change the primaryPath to NR radio path from EUTRA THEN: UE changes the uplink data path to NR radio path and sends an RRCReconfigurationComplete message **** TP2: [TS 38,331:FFS; TS 36,331:FFS] WITH: UE in RRC_CONNECTED state with NE-DC, and MCG and Split WHEN: UE receives an RRCCReconfiguration message to change the primaryPath from NR radio path to EUTRA THEN: UE changes the uplink data path to EUTRA radio path and sends an RRCReconfigurationComplete message | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
Measurement configuration control and reporting / Handovers
258 | Y | 38.523-1 | 8.2.3.1.2 | Measurement configuration control and reporting / Inter-RAT measurements / Event B1 / Measurement of NR cells / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG, and performed the inter RAT measurement for E-UTRA cell and not detected entering condition for the event B1 is met WHEN: UE detects entering condition for the event B1 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG, and having completed the radio bearer establishment and performed the inter RAT measurement for E-UTRA cell and not detected entering condition for the event B1 is met WHEN: UE detects entering condition for the event B1 is met THEN: UE transmits a MeasurementReport **** TP3: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG, and performed the inter RAT measurement for E-UTRA cell and detected entering condition for the event B1 is met WHEN: UE detects leaving condition for the event B1 is met THEN: UE does not transmit any MeasurementReport | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
259 | Y | 38.523-1 | 8.2.3.2.2 | Measurement configuration control and reporting / Inter-RAT measurements / Event B1 / Measurement of NR cells / RSRQ based measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG, and performed the inter RAT measurement for E-UTRA cell, configured b1-Threshold set to threshold-RSRQ and not detected entering condition for the event B1 is met WHEN: UE detects entering condition for the event B1 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG, and having completed the radio bearer establishment and performed the inter RAT measurement for E-UTRA cell, configured b1-Threshold set to threshold-RSRQ and not detected entering condition for the event B1 is met WHEN: UE detects entering condition for the event B1 is met THEN: UE transmits a MeasurementReport **** TP3: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG, and performed the inter RAT measurement for E-UTRA cell, configured b1-Threshold set to threshold-RSRQ and detected entering condition for the event B1 is met WHEN: UE detects leaving condition for the event B1 is met THEN: UE does not transmit any MeasurementReport | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
247 | Y | 38.523-1 | 8.2.3.4.2 | Measurement configuration control and reporting / Event A1 / Measurement of NR PSCell / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurement configured for event A1 with event based periodical reporting WHEN: Serving E-UTRA cell becomes better than absolute threshold plus hysteresis THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A1 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state in NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A1 ongoing WHEN: Serving E-UTRA cell becomes worse than absolute threshold minus hysteresis THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements are re-configured for event A1 with event based reporting to report on leaving condition WHEN: Serving E-UTRA cell becomes worse than absolute threshold minus hysteresis THEN: UE sends MeasurementReport message when leaving condition for event A1 is satisfied | CMCC | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
248 | Y | 38.523-1 | 8.2.3.5.2 | Measurement configuration control and reporting / Event A2 / Measurement of NR PSCell / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurement configured for event A2 with event based periodical reporting WHEN: Serving E-UTRA cell becomes worse than absolute threshold minus hysteresis THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A2 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A2 ongoing WHEN: Serving E-UTRA cell becomes better than absolute threshold plus hysteresis THEN: UE stops sending MeasurementReport message | CMCC | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
249 | Y | 38.523-1 | 8.2.3.6.2 | Measurement configuration control and reporting / Event A3 / Measurement of Neighbour NR cells / Intra-frequency measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (E-UTRA PDCP) and SCG and intra-frequency measurements configured for event A3 WHEN: Entry condition for event A3 is not met for neighbor E-UTRA cell THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (E-UTRA PDCP) and SCG and intra-frequency measurements configured for event A3 WHEN: Neighbour E-UTRA cell becomes offset better than serving E-UTRA PSCell THEN: UE sends MeasurementReport with correct measId for event A3 **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A3 WHEN: Neighbour NR cell becomes offset better than serving NR PCell THEN: UE sends MeasurementReport with correct measId for event A3 and includes measurement result for the PSCELL. | CMCC | Opt 4: Post WI close | R5-221443 R5-223345 | FFS in Table 8.2.3.6.2.3.3-11, and Fr2 power levels to be defined | NE-DC: EUTRA and FR2 cell power to be defined for OTA test environment . FFS in Table 8.2.3.6.2.3.3-11, | 1 | 90% | [6 empty] | 100% | 80%
250 | Y | 38.523-1 | 8.2.3.6.2a | Measurement configuration control and reporting / Event A3 / Measurement of Neighbor NR cell / Inter-frequency measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (E-UTRA PDCP) and SCG and inter-frequency measurements configured for event A3 WHEN: Entry condition for event A3 is not met for neighbor E-UTRA cell THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (E-UTRA PDCP) and SCG and inter-frequency measurements configured for event A3 WHEN: Neighbour E-UTRA cell becomes offset better than serving E-UTRA PSCell THEN: UE sends MeasurementReport with correct measId for event A3 **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A3 WHEN: Neighbour NR cell becomes offset better than serving NR PCell THEN: UE sends MeasurementReport with correct measId for event A3 and includes measurement result for the PSCELL. | CMCC | Opt 4: Post WI close | R5-221444 R5-223346 | FFS in Table 8.2.3.6.2.3.3-11, and Fr2 power levels to be defined | NE-DC: EUTRA and FR2 cell power to be defined for OTA test environment . FFS in Table 8.2.3.6.2.3.3-11, | 1 | 90% | [6 empty] | 100% | 80%
251 | Y | 38.523-1 | 8.2.3.6.2b | Measurement configuration control and reporting / Event A3 / Measurement of Neighbor NR cell / Inter-band measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (E-UTRA PDCP) and SCG and inter-band measurements configured for event A3 WHEN: Entry condition for event A3 is not met for neighbor E-UTRA cell THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (E-UTRA PDCP) and SCG and inter-band measurements configured for event A3 WHEN: Neighbour E-UTRA cell becomes offset better than serving E-UTRA PSCell THEN: UE sends MeasurementReport with correct measId for event A3 **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A3 WHEN: Neighbour NR cell becomes offset better than serving NR PCell THEN: UE sends MeasurementReport with correct measId for event A3 and includes measurement result for the PSCELL. | CMCC | Opt 4: Post WI close | R5-221445 R5-223347 | FFS in Table 8.2.3.6.2.3.3-11, and Fr2 power levels to be defined | NE-DC: EUTRA and FR2 cell power to be defined for OTA test environment . FFS in Table 8.2.3.6.2.3.3-11, | 1 | 90% | [6 empty] | 100% | 80%
252 | Y | 38.523-1 | 8.2.3.7.2 | Measurement configuration control and reporting / Event A4 / Measurement of Neighbour NR cells / Intra-frequency measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and intra-frequency measurements configured for event A4 with event based periodical reporting WHEN: Neighbour E-UTRA cell becomes better than absolute threshold THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A4 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A4 ongoing WHEN: Neighbour E-UTRA cell becomes worse than absolute threshold THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A4 with event based periodical reporting WHEN: Neighbour NR cell becomes better than absolute threshold THEN: UE sends MeasurementReport at regular intervals while entering condition for event A4 is satisfied, and includes measurement result for the PSCELL. | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
253 | Y | 38.523-1 | 8.2.3.7.2a | Measurement configuration control and reporting / Event A4 / Measurement of Neighbor NR cell / Inter-frequency measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and inter-frequency measurements configured for event A4 with event based periodical reporting WHEN: Neighbour E-UTRA cell becomes better than absolute threshold THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A4 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A4 ongoing WHEN: Neighbour E-UTRA cell becomes worse than absolute threshold THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A4 with event based periodical reporting WHEN: Neighbour NR cell becomes better than absolute threshold THEN: UE sends MeasurementReport at regular intervals while entering condition for event A4 is satisfied, and includes measurement result for the PSCELL. | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
254 | Y | 38.523-1 | 8.2.3.7.2b | Measurement configuration control and reporting / Event A4 / Measurement of Neighbor NR cell / Inter-band measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and inter-band measurements configured for event A4 with event based periodical reporting WHEN: Neighbour E-UTRA cell becomes better than absolute threshold THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A4 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A4 ongoing WHEN: Neighbour E-UTRA cell becomes worse than absolute threshold THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A4 with event based periodical reporting WHEN: Neighbour NR cell becomes better than absolute threshold THEN: UE sends MeasurementReport at regular intervals while entering condition for event A4 is satisfied, and includes measurement result for the PSCELL. | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
255 | Y | 38.523-1 | 8.2.3.8.2 | Measurement configuration control and reporting / Event A5 / Measurement of Neighbour NR cells / Intra-frequency measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and intra-frequency measurements configured for event A5 with event based periodical reporting WHEN: Serving E-UTRA PSCell becomes worse than absolute threshold1 and neighbour E-UTRA cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport message at regular intervals while entering conditions for event A5 are satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A5 ongoing WHEN: Serving E-UTRA PSCell becomes better than absolute threshold1 or neighbour E-UTRA cell becomes worse than absolute threshold2 THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A5 with event based periodical reporting WHEN: Serving NR PCell becomes worse than absolute threshold1 and neighbour NR cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport at regular intervals while entering condition for event A5 are satisfied, and includes measurement result for the PSCELL. | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
256 | Y | 38.523-1 | 8.2.3.8.2a | Measurement configuration control and reporting / Event A5 / Measurement of Neighbor NR cell / Inter-frequency measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and inter-frequency measurements configured for event A5 with event based periodical reporting WHEN: Serving E-UTRA PSCell becomes worse than absolute threshold1 and neighbour E-UTRA cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport message at regular intervals while entering conditions for event A5 are satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A5 ongoing WHEN: Serving E-UTRA PSCell becomes better than absolute threshold1 or neighbour E-UTRA cell becomes worse than absolute threshold2 THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A5 with event based periodical reporting WHEN: Serving NR PCell becomes worse than absolute threshold1 and neighbour NR cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport at regular intervals while entering condition for event A5 are satisfied, and includes measurement result for the PSCELL. | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
257 | Y | 38.523-1 | 8.2.3.8.2b | Measurement configuration control and reporting / Event A5 / Measurement of Neighbor NR cell / Inter-band measurements / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and inter-band measurements configured for event A5 with event based periodical reporting WHEN: Serving E-UTRA PSCell becomes worse than absolute threshold1 and neighbour E-UTRA cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport message at regular intervals while entering conditions for event A5 are satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and periodical measurement reporting triggered by event A5 ongoing WHEN: Serving E-UTRA PSCell becomes better than absolute threshold1 or neighbour E-UTRA cell becomes worse than absolute threshold2 THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.5; TS 36,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.1 and 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and SCG and measurements configured for event A5 with event based periodical reporting WHEN: Serving NR PCell becomes worse than absolute threshold1 and neighbour NR cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport at regular intervals while entering condition for event A5 are satisfied, and includes measurement result for the PSCELL. | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
260 | Y | 38.523-1 | 8.2.3.12.2 | Measurement configuration control and reporting / Inter-RAT measurements / Event B2 / Measurement of NR cells / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for E-UTRA cell and not detected entering condition for the event B2 is met WHEN: UE detects entering condition for the event B2 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for E-UTRA cell and not detected entering condition for the event B2 is met WHEN: UE detects entering condition for the event B2 is met THEN: UE transmits a MeasurementReport **** TP3: [TS 38,331:5.3.5.3, 5.5.5] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for E-UTRA cell and detected entering condition for the event B2 is met WHEN: UE detects leaving condition for the event B2 is met THEN: UE does not transmit any MeasurementReport | CMCC | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
261 | Y | 38.523-1 | 8.2.3.13.2 | PCell Handover with SCG change on same PSCell / mobilityControlInfoSCG / SCG DRB / NE-DC | **** TP1: [TS 36,331:5.3.5.3, 5.3.10.10; TS 38,331:5.3.5.3, 5.3.5.5.1, 5.3.5.5.2, 5.5.4.4, 5.2.2.4.2 and 5.3.5.7] WITH: UE in RRC_CONNECTED state in NE-DC mode, and, MCG(s) (NR PDCP) and SCG DRB established WHEN: UE receives an RRCReconfiguration message with reconfigurationWithSync to handover to target NR PCell involving SCG change with mobilityControlInfoSCG on the same PSCell THEN: UE sends an RRCReconfigurationComplete message | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
262 | Y | 38.523-1 | 8.2.3.14.3 | SCG change with HO /mobilityControlInfoSCG / Split DRB / NE-DC | **** TP1: [TS 36,331:5.3.5.3, 5.3.10.3a4, 5.3.10.10, 5.3.10.11; TS 38,331:5.3.5.3] WITH: UE in RRC_CONNECTED state with NE-DC, and, MCG(s) (NR PDCP) and Split DRB WHEN: UE receives an RRCReconfiguration message to handover from E-UTRA PSCell involving SCG change with mobilityControlInfoSCG to the target E-UTRA cell with Split DRB THEN: UE sends an RRCReconfigurationComplete message | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
263 | Y | 38.523-1 | 8.2.3.17.3 | Measurement configuration control and reporting / SFTD / NE-DC | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.3.1, 5.5.4.1, and 5.5.5.1] WITH: UE in RRC_CONNECTED state in NE-DC mode with reportSFTD-Meas configured for Serving E-UTRA PSCell WHEN: The sfn-OffsetResult and frameBoundaryOffsetResult results for the Serving E-UTRA PSCell becomes available THEN: UE transmits a MeasurementReport message including the MeasResultCellSFTD IE | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
Reconfiguration Failure / Radio link failure
264 | Y | 38.523-1 | 8.2.5.1.3 | Radio link failure / Random access problem / NE-DC | **** TP1: [TS 36,331:5.6.13.4; TS 38,331:5.7.3a] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: UE receives an IP Packet to loopback on SCG DRB and the SS does not respond to the Scheduling Requests from UE THEN: UE encounters random access problem and initiates the SCG failure information procedure to report SCGFailureInformationEUTRA with failureType set to randomAccessProblem | CMCC | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
265 | Y | 38.523-1 | 8.2.5.2.3 | Radio link failure / PSCell out of sync indication / NE-DC | **** TP1: [TS 36,331:5.6.13.4; TS 38,331:5.7.3a] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: UE receives N313 consecutive "out-of-sync" indications for the SpCell from lower layers due to radio link failure THEN: UE initiates the NR SCG failure information procedure to report SCGFailureInformationEUTRA with failureType set to t313-Expiry | CMCC | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
266 | Y | 38.523-1 | 8.2.5.3.3 | Radio link failure / rlc-MaxNumRetx failure / NE-DC | **** TP1: [TS 36,331:5.6.13.4; TS 38,331:5.7.3a] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: The transmitting side of the UE’s AM RLC entity for the SCG DRB has retransmitted an RLC SDU until RETX_COUNT = maxRetxThreshold THEN: The UE shall transmit a SCGFailureInformationEUTRA message with failureType set to ‘rlc-MaxNumRetx’ | Element materials technology | Opt 4: Post WI close | R5-223426 |  | NE-DC: EUTRA and FR2 cell power to be defined for OTA test environment . | 1 | 90% | [6 empty] | 100% | 80%
267 | Y | 38.523-1 | 8.2.5.4.3 | Reconfiguration failure / SCG change failure / NE-DC | **** TP1: [TS 36,331:5.6.13.4; TS 38,331:5.7.3a] WITH: UE in NR RRC_CONNECTED state with NE-DC WHEN: UE receives an RRCReconfiguration message containing RRCConnectionReconfiguration message with MobilityControlInfoSCG for configured PSCell and if T307 of a secondary cell group expires THEN: UE initiates the SCG failure information procedure to report SCGFailureInformationEUTRA with failuretype set to scg-ChangeFailure | Element materials technology | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
MR-DC RRC others
|  | 38.523-1 | 8.2.6.1.3 | Failure information / RLC failure / SCG / NE-DC |  | ZTE
268 | Y | 38.523-1 | 8.2.6.1.3.1 | Failure information / RLC failure / SCG / NE-DC / Intra-band Contiguous CA | **** TP1: [TS 36,331:FFS; TS 38,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and SCG WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE sends the FailureInformation message embedded in ULInformationTransferMRDC to report RLC failure for the SCG | Element materials technology | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
269 | Y | 38.523-1 | 8.2.6.1.3.2 | Failure information / RLC failure / SCG / NE-DC / Inter-band CA | **** TP1: [TS 36,331:FFS; TS 38,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and SCG WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE sends the FailureInformation message embedded in ULInformationTransferMRDC to report RLC failure for the SCG | Element materials technology | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
270 | Y | 38.523-1 | 8.2.6.1.3.3 | Failure information / RLC failure / SCG / NE-DC / Intra-band non Contiguous CA | **** TP1: [TS 36,331:FFS; TS 38,331:FFS] WITH: UE in NR RRC_CONNECTED state with NE-DC, and SCG WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE sends the FailureInformation message embedded in ULInformationTransferMRDC to report RLC failure for the SCG | Element materials technology | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
271 | Y | 38.523-1 | 8.2.6.2.3 | Processing delay / Latency check / NE-DC | **** TP1: [TS 38,331:FFS] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCReconfiguration message with eutra-SCG IE to add an SCG and after 16ms receives an UL grant THEN: UE successfully transmits RRCReconfigurationComplete message | CMCC | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
RRC resume
272 | Y | 38.523-1 | 8.2.7.3.1 | RRC Resume / NE-DC | **** TP1: [TS 36,331:FFS; TS 38,331:FFS] WITH: UE in NR RRC_INACTIVE state and sends RRCResumeRequest message to resume RRC Connection WHEN: UE receives a RRCResume message including mrdc-SecondaryCellGroup set to eutra-SCG THEN: UE successfully transmits RRCResumeComplete message | ZTE | RAN5#97 (Nov-22) |  |  | NE-DC : TC to be drafted | 1 | 0% | [6 empty] | 0% | 0%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A4: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B4: Y = the WP Pitem is a test case.
Note on L4: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.