## TR 38.903 Tx_Rx
WP Title: | TR 38.903 - NR Derivation of test tolerances for RRM and UE radio reception conformance tests | [9 empty] | WP item applicability | [5 empty] | End of work plan columns. Note! Do not remove this column. | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
[11 empty] | RAN-CN interface options dependency | [6 empty] | WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan section covers documentation of the test tolerances for RRM and UE radio reception conformance test cases. This also includes NR OTA Measurement Uncertainty (MU) and Test Tolerances (TT). Note! Content related to specific test cases (this is handled as part of the work plan item for the test case in the TS 38.521-1, TS 38.521-2, TS 38.521-3 and TS 38.533 section of the work plan) | [9 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Ron Borsato, AT&T |  |  | ronald.borsato@att.com
TS Resp: | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [6 empty] | SA |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7 |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[18 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[10 empty] | Overall | 80%
[6 empty] | Overall #WP items: Post WI close #WP items: |  |  |  |  | 48 8 |  |  | 0 0 | 0 0 |  |  |  |  | §
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option | [8 empty] | Anritsu | Hiroyuki.Baba@anritsu.com
Not yet identified test cases | [19 empty] | Rohde & Schwarz | Edwin.Menzel@rohde-schwarz.com
| 38.903 | Annex B | FFS | TT for RF test cases under EC condition |  |  |  | Whether there is need to test under EC is FFS, thus the task force is estimated as lower than NC MOP and Ref Sens with ETC added. | 40 |  | 1 |  | 1 | [6 empty] | Keysight | emilio_ruiz@KEYSIGHT.COM
| Common chapters | [18 empty] | NTT Docomo | takahiro.arai.kw@nttdocomo.com
1 | 38.903 | 2 | References |  | Bureau Veritas | Opt 2: RAN5#87 (May-20) | R5-187148 | Content Unchanged for many meetings. Considered to be stable and complete. | 1 | 100% | 7 | 100% | 1 | [6 empty] | MVG | Kim.Rutkowski@mvg-us.com
2 | 38.903 | 3 | Definitions, symbols and abbreviations |  | Bureau Veritas | Opt 2: RAN5#87 (May-20) | R5-187148 | Content Unchanged for many meetings. Considered to be stable and complete. | 1 | 100% | 7 | 100% | 1 | [6 empty] | Qualcomm1 | mvora@QTI.QUALCOMM.COM
3 | 38.903 | 4 | General Principles |  | Huawei | Opt 2: RAN5#87 (May-20) | R5-174706 | Content Unchanged for many meetings. Considered to be stable and complete. | 1 | 100% | 7 | 100% | 1 | [6 empty] | CAICT | zhangyufeng@CAICT.AC.CN
4 | 38.903 | 5 | Determination of Test System Uncertainties |  | Huawei | Opt 2: RAN5#88 (Aug-20) | R5-182093 |  | 1 | 100% | 8 | 100% | 1 | [6 empty] | AT&T | ronald.borsato@att.com
5 | 38.903 | 6 | Determination of Test Tolerances |  | Huawei | Opt 2: RAN5#87 (May-20) | R5-182093 | Content Unchanged for many meetings. Considered to be stable and complete. | 1 | 100% | 7 | 100% | 1 | [6 empty] | CAICT | zhangyufeng@CAICT.AC.CN
6 | 38.903 | Annex A | Derivation documents for test tolarance |  | Huawei | Opt 2: RAN5#90 (Feb-21) | R5-182093 R5-182670 | Content Unchanged for many meetings. Considered to be stable and complete. Any necessary updates can be addressed as part of maintenance. | 1 | 100% | 10 | 100% | 1 | [6 empty] | CMCC | songdan@chinamobile.com
| MU for RF FR2 Tx/Rx Test Cases | [18 empty] | KDDI | ma-fushiki@kddi.com
| 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | [5 empty] | 0 |  | 1 |  | 1 | [6 empty] | QC1 | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com>
7 | 38.903 | Annex B.1 | Uncertainty budget calculation principle |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-182093 R5-193430 R5-194123 |  | 1 | 100% | 3 | 100% | [7 empty] | QC2 | Hemish Parikh <hparikh@qti.qualcomm.com>
| 38.903 | Annex B.2 | Measurement error contribution descriptions | [5 empty] | 0 |  | 1
8 | 38.903 | Annex B.2.1 | Measurement error contribution descriptions for DFF |  | Huawei,R&S, Anritsu, Keysight, MVG, PCTEST | Opt 2: RAN5#90 (Feb-21) | R5-182093 R5-182465 R5-182473 R5-183008 R5-183009 R5-184819 R5-184976 R5-188059 R5-188060 R5-187023 R5-187148 R5-191249 R5-204888 R5-211932 | Completion of additional terms for ACS and IBB. | 0 | 100% | 10 | 100%
9 | 38.903 | Annex B.2.2 | Measurement error contribution descriptions for IFF |  | Huawei,R&S, Anritsu, Keysight, MVG, PCTEST | Opt 2: RAN5#90 (Feb-21) | R5-182093 R5-182465 R5-182473 R5-183008 R5-183009 R5-184819 R5-184976 R5-188059 R5-191249 R5-204888 R5-211932 | Completion of additional terms for ACS and IBB. | 3 | 100% | 10 | 100%
98 | 38.903 | Annex B.2.3 | Measurement error contribution descriptions for NFTF |  | MVG |  | R5-185352 R5-188059 R5-187023 R5-191249 |  | 0 |  | 10
108 | 38.903 | Annex B.3 | UE maximum output power | MU threshold | R&S, Anritsu, Keysight, MVG, PCTEST | Opt 2: RAN5#85 (Nov-19) | R5-186903 R5-191249 | 1st priority | 1 | 100% | 5 | 100%
10 | 38.903 | Annex B.3.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-184819 R5-184976 R5-186903 R5-187023 R5-191249 | MU factors are determined | 0 |  | 9
14 | 38.903 | Annex B.3.2 | Uncertainty budget format and assessment for IFF |  | R&S, Anritsu, Keysight, MVG, PCTEST | Opt 2: RAN5#85 (Nov-19) | R5-184819 R5-184976 R5-186903 R5-191249 R5-193465 R5-195159 | 1st priority EIRP and TRP are completed Spherical Coverage is completed | 3 | 100% | 5 | 100%
99 | 38.903 | Annex B.3.3 | Uncertainty budget format and assessment for NFTF |  | R&S, Anritsu, Keysight, MVG, PCTEST |  | R5-185352 R5-186903 R5-187023 | MU factors are determined | 0 |  | 9
113 | 38.903 | Annex B.3 | UE maximum output power with ETC |  |  | Opt 2: RAN5#90 (Feb-21) | R5-211935 | 1st priority | 4 | 100% | 10 | 100%
18 | 38.903 | Annex B.4 | UE maximum output power for modulation / channel bandwidth |  |  | Opt 2: RAN5#88 (Aug-20) | R5-204890 | 3rd priority PC3 MU completed. | 4 | 100% | 8 | 100%
19 | 38.903 | Annex B.5 | UE maximum output power with additional requirements |  |  | Opt 2: Post WI close |  | 3rd priority | 4 | 0% | 16 | 0%
20 | 38.903 | Annex B.6 | Configured transmitted power |  |  | Opt 2: Post WI close |  | 3rd priority | 4 | 0% | 16 | 0%
21 | 38.903 | Annex B.7 | Minimum output power |  |  | Opt 2: RAN5#89 (Nov-20) | R5-204891 R5-206825 R5-211175 | 3rd priority Maintenance CR to 38.903 agreed to reflect agreement in R5-206825. | 4 | 100% | 9 | 100%
100 | 38.903 | Annex B.8 | Transmit OFF power | MU threshold |  | Opt 2: RAN5#89 (Nov-20) | R5-187233 R5-191249 R5-204945 R5-206838 | 2nd priority EIRP MU confirmed based on test requirement relaxation. | 1 | 100% | 9 | 100%
22 | 38.903 | Annex B.8.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 | MU factors are determined | 0 |  | 9
26 | 38.903 | Annex B.8.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#89 (Nov-20) | R5-187233 R5-191249 R5-204891 R5-204945 R5-204947 R5-206838 | Band 257 is completed. Other bands are complete from an FR2 MU perspective based on test requirement relaxation but test case may not be acceptable for certain operating bands due to relaxation. EIRP MU confirmed based on test requirement relaxation. | 3 | 100% | 9 | 100%
30 | 38.903 | Annex B.9 | Transmit ON/OFF time mask |  |  | Opt 2: RAN5#94 (Feb-22) | R5-206838 R5-206785 R5-221746 | 3rd priority MU/TT completed. | 4 | 100% | 14 | 100%
115 | 38.903 | Annex B.9a.1 | Absolute power tolerance |  |  | Opt 2: RAN5#92 (Aug-21) | R5-216105 R5-215321 | 3rd priority | 4 | 100% | 12 | 100%
116 | 38.903 | Annex B.9a.2 | Relative power tolerance |  |  | Opt 2: Post WI close | R5-215319 R5-215485 | 3rd priority | 4 | 50% | 16 | 50%
117 | 38.903 | Annex B.9a.3 | Aggregate power tolerance |  |  | Opt 2: RAN5#92 (Aug-21) | R5-216105 R5-215321 | 3rd priority | 4 | 100% | 12 | 100%
102 | 38.903 | Annex B.10 | Frequency Error | MU threshold |  | Opt 2: RAN5#85 (Nov-19) MU: RAN5#85 (Nov-19) TT: RAN5#85 (Nov-19) | R5-187233 R5-191249 | 2nd priority | 1 | 100% | 5MT2 | 100%
31 | 38.903 | Annex B.10.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 | Condition of uncertainty assessment is in brackets | 0 |  | 9
35 | 38.903 | Annex B.10.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#91 (May-21) | R5-187233 R5-214069 | Completed | 3 | 100% | 11 | 100%
39 | 38.903 | Annex B.11 | Carrier leakage |  |  | Opt 2: RAN5#93 (Nov-21) | R5-218402 | 3rd priority | 4 | 100% | 13 | 100%
40 | 38.903 | Annex B.12 | Error Vector Magnitude |  |  | Opt 2: Post WI close | R5-218212 R5-221743 | 3rd priority PC3 PUSCH MU complete. TT is FFS. | 4 | 90% | 16 | 90%
41 | 38.903 | Annex B.13 | In-band emissions |  |  | Opt 2: Post WI close |  | 3rd priority | 4 | 0% | 16 | 0%
42 | 38.903 | Annex B.14 | EVM equalizer spectrum flatness |  |  | Opt 2: Post WI close |  | 3rd priority | 4 | 0% | 16 | 0%
101 | 38.903 | Annex B.15 | Occupied bandwidth | MU threshold |  | Opt 2: RAN5#90 (Feb-21) | R5-187233 R5-191249 R5-204849 R5-204850 | 2nd priority Occupied BW completed for single carrier case. Need clean up CR at the next meeting to align with 38.521-2 CR in R5-211923. | 1 | 100% | 10 | 100%
43 | 38.903 | Annex B.15.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 |  | 0 |  | 9
47 | 38.903 | Annex B.15.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#90 (Feb-21) | R5-187233 | Occupied BW completed for single carrier case. Need clean up CR at the next meeting to align with 38.521-2 CR in R5-211923. | 3 | 100% | 10 | 100%
103 | 38.903 | Annex B.16 | Spectrum emission mask | MU threshold |  | Opt 2: RAN5#85 (Nov-19) | R5-187233 R5-191249 | 2nd priority | 1 | 100% | 5 | 100%
51 | 38.903 | Annex B.16.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 R5-191249 | MU factors are determined | 0 |  | 9
55 | 38.903 | Annex B.16.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#85 (Nov-19) MU: RAN5#85 (Nov-19) TT: RAN5#85 (Nov-19) | R5-187233 R5-193465 R5-191249 R5-195159 | MU factors are determined SEM is completed | 3 | 100% | 5MT2 | 100%
104 | 38.903 | Annex B.17 | Adjacent Channel Leakage Ratio | MU threshold |  | Opt 2: RAN5#87 (May-20) | R5-187233 R5-191249 | 2nd priority | 1 | 100% | 7 | 100%
59 | 38.903 | Annex B.17.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 R5-191249 | MU factors are determined | 0 |  | 9
63 | 38.903 | Annex B.17.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#87 (May-20) | R5-187233 R5-191249 | MU factors are determined ACLR is completed | 3 | 100% | 7 | 100%
105 | 38.903 | Annex B.18 | Spurious emissions (TX) | MU threshold |  | Opt 2: RAN5#90 (Feb-21) | R5-187233 R5-187848 R5-204890 | 2nd priority Spurious Emissions UE Co-Ex MU completed. Additional Spurious Emissions MU added in brackets. | 1 | 100% | 10 | 100%
67 | 38.903 | Annex B.18.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 R5-191249 | MU factors are determined | 0 |  | 9
71 | 38.903 | Annex B.18.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#90 (Feb-21) | R5-187233 R5-191249 R5-194027 R5-204890 R5-206837 R5-211934 | General Spurious Emissions for Bands n257, n258, n260, and n261 are completed. | 3 | 100% | 10 | 100%
109 | 38.903 | Annex B.18a | Beam Correspondence | MU threshold | Keysight | Opt 2: RAN5#93 (Nov-21) | R5-218408 | 1st priority Completed clause structure. | 1 | 100% | 13 | 100%
110 | 38.903 | Annex B.18a.1 | Uncertainty budget format and assessment for DFF | [5 empty] | 0 |  | 9
111 | 38.903 | Annex B.18a.2 | Uncertainty budget format and assessment for IFF |  | Keysight | Opt 2: RAN5#94 (Feb-22) | R5-218408 R5-221629 | MU/TT completed. | 3 | 100% | 14 | 100%
112 | 38.903 | Annex B.18a.3 | Uncertainty budget format and assessment for NFTF | [5 empty] | 0 |  | 9
106 | 38.903 | Annex B.19 | Reference sensitivity power level | MU threshold | R&S, Anritsu, Keysight, MVG, PCTEST | Opt 2: RAN5#85 (Nov-19) | R5-186903 R5-191249 | 1st priority | 1 | 100% | 5 | 100%
75 | 38.903 | Annex B.19.1 | Uncertainty budget format and assessment for DFF |  | R&S, Anritsu, Keysight, MVG, PCTEST |  | R5-186903 |  | 0 |  | 9
79 | 38.903 | Annex B.19.2 | Uncertainty budget format and assessment for IFF |  | R&S, Anritsu, Keysight, MVG, PCTEST | Opt 2: RAN5#85 (Nov-19) | R5-186903 R5-191249 R5-193465 R5-195159 | MU factors are determined EIS spherical coverage is completed | 3 | 100% | 5 | 100%
114 | 38.903 | Annex B.19 | Reference sensitivity power level with ETC | MU threshold |  | Opt 2: RAN5#90 (Feb-21) | R5-186903 R5-191249 | 1st priority | 4 | 100% | 10 | 100%
83 | 38.903 | Annex B.20 | Maximum input level |  |  | Opt 2: Post WI close |  | 3rd priority | 4 | 0% | 16 | 0%
84 | 38.903 | Annex B.21 | Adjacent Channel Selectivity |  |  | Opt 2: RAN5#91 (May-21) | R5-204888 R5-211930 R5-211932 R5-212352 | 3rd priority Add't impact of interferer ACLR confirmed. MU complete. | 4 | 100% | 11 | 100%
85 | 38.903 | Annex B.22 | In-band blocking |  |  | Opt 2: RAN5#91 (May-21) | R5-204889 R5-211931 R5-211932 R5-212352 | 3rd priority Confirmed that IBB MU follows ACS MU. MU complete. | 4 | 100% | 11 | 100%
86 | 38.903 | Annex B.23 | Out-of-band blocking |  |  | Opt 2: Post WI close |  | 3rd priority | 4 | 0% | 16 | 0%
107 | 38.903 | Annex B.25 | Spurious emissions (RX) | MU threshold |  | Opt 2: RAN5#90 (Feb-21) | R5-187233 | 2nd priority | 1 | 100% | 10 | 100%
88 | 38.903 | Annex B.25.1 | Uncertainty budget format and assessment for DFF |  |  |  | R5-187233 R5-191249 | MU factors are determined | 0 |  | 9
92 | 38.903 | Annex B.25.2 | Uncertainty budget format and assessment for IFF |  |  | Opt 2: RAN5#90 (Feb-21) | R5-187233 R5-191249 R5-194027 R5-211934 | Bands n257, n258, n260, and n261 are completed. | 3 | 100% | 10 | 100%
97 | 38.903 | Annex C | Acceptable uncertainty of test system for test cases defined in TS 38.521-3 for radiative testing |  |  | Opt 2: RAN5#90 (Feb-21) |  | Reduced the weighting to account for reuse based on test case grouping. Re-use has been confirmed to date on all -3 test cases. | 10 | 100% | 10 | 100%
<area#5>
| 38.903 | <Clause> | <Title> | [5 empty] | 1 |  | 1 |  | 1 | 1 | 1 | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on AA6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AB7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).

## TR 38.903 Demod
WP Title: | TR 38.903 - NR Derivation of test tolerances for RRM and UE radio reception conformance tests | [9 empty] | WP item applicability | [5 empty] | End of work plan columns. Note! Do not remove this column. | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
[11 empty] | RAN-CN interface options dependency | [6 empty] | WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan section covers documentation of the test tolerances for RRM and UE radio reception conformance test cases. This also includes NR OTA Measurement Uncertainty (MU) and Test Tolerances (TT). Note! Content related to specific test cases (this is handled as part of the work plan item for the test case in the TS 38.521-1, TS 38.521-2, TS 38.521-3 and TS 38.533 section of the work plan) | [9 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Ron Borsato, AT&T |  |  | ronald.borsato@att.com
TS Resp: | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [6 empty] | SA |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7 |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[18 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[10 empty] | Overall | 98.7%
[6 empty] | Overall #WP items: Post WI close #WP items: |  |  |  |  | 9 2 |  |  | 0 0 | 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option | [8 empty] | Anritsu | Hiroyuki.Baba@anritsu.com
Not yet identified test cases | [19 empty] | Rohde & Schwarz | Edwin.Menzel@rohde-schwarz.com
| 38.903 | Annex B | FFS | TT for RF test cases under EC condition |  |  |  | Whether there is need to test under EC is FFS, thus the task force is estimated as lower than NC | 50 |  | 1 |  | 1 | [6 empty] | Keysight | emilio_ruiz@KEYSIGHT.COM
| MU for RF Performance Test Cases | [18 empty] | NTT Docomo | takahiro.arai.kw@nttdocomo.com
| 38.903 | 7 | Grouping of test cases defined in TS 38.521-4 |  |  | Opt 2: Post WI close |  |  | 1 | 0% | 16 | 0% | 1 | [6 empty] | MVG | Kim.Rutkowski@mvg-us.com
103 | 38.903 | Annex D | Acceptable uncertainty of test system for test cases defined in TS 38.521-4 for radiative testing |  |  | Opt 2: RAN5#90 (Feb-21) | R5-202769 R5-204083 R5-204946 R5-205704 | Baseband Combining Approach: gNB MU confirmed. AWGN and signal flatness MU, fading uncertainty, and MU due to finite test time confirmed. Non-ideal isolation MU specified. Overall system uncertainty for Type 1 confirmed. | 40 | 100% | 10 | 100% | 1 | [6 empty] | Qualcomm1 | mvora@QTI.QUALCOMM.COM
99 | 38.903 | Annex D.1 | Uncertainty budget calculation principle |  |  | Opt 2: RAN5#88 (Aug-20) | R5-187024 | Content Unchanged for many meetings. Considered to be stable and complete. | 20 | 100% | 8 | 100% | 1 | [6 empty] | CAICT | zhangyufeng@CAICT.AC.CN
| 38.903 | Annex D.2 | Measurement error contribution descriptions | [5 empty] | 0 |  | 2 |  | 1
100 | 38.903 | Annex D.2.1 | Measurement error contribution descriptions for DNF |  |  | Opt 2: RAN5#90 (Feb-21) | R5-187024 | MU factors are determined | 30 | 100% | 10 | 100% | 1
101 | 38.903 | Annex D.2.2 | Measurement error contribution descriptions for DFF |  |  | Opt 2: RAN5#90 (Feb-21) | R5-187024 | MU factors are determined | 30 | 100% | 10 | 100% | 1
102 | 38.903 | Annex D.2.3 | Measurement error contribution descriptions for IFF |  |  | Opt 2: RAN5#90 (Feb-21) | R5-187024 | MU factors are determined | 30 | 100% | 10 | 100% | 1
104 | 38.903 | Annex D.3 | Assessment of testable DL SNR range and accuracy |  |  | Opt 2: RAN5#90 (Feb-21) | R5-211936 |  | 20 | 100% | 10 | 100% | 1
105 | 38.903 | Annex D.3.1 | Method and Parameters |  |  | Opt 2: Post WI close | R5-211936 | Working assumption for maximum testable SNR confirmed. | 20 | 90% | 16 | 90% | 1
106 | 38.903 | Annex D.3.2.1 | SNR range for SNRRP - SNRBB ≤ 1dB for DFF |  |  |  | R5-211936 | Given that no contributions have been provided for DFF, this item will no longer be tracked for completion level. Will assign the weighting to D.3.2.2. | 20 |  | 14 |  | 1
107 | 38.903 | Annex D.3.2.2 | SNR range for SNRRP - SNRBB ≤ 1dB for IFF |  |  | Opt 2: RAN5#92 (Aug-21) | R5-211936 R5-213851 R5-216102 R5-221747 | Updated working assumption for maximum testable SNR based on acceptable clipping level. Maximum SNR_BB set in brackets for n257, n258, n260, and n261 | 40 | 100% | 12 | 100% | 1
<area#5>
| 38.903 | <Clause> | <Title> | [5 empty] | 1 |  | 1 |  | 1 | 1 | 1 | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on AA6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AB7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).

## TR 38.903 RRM
WP Title: | TR 38.903 - NR Derivation of test tolerances for RRM and UE radio reception conformance tests | [9 empty] | WP item applicability | [5 empty] | End of work plan columns. Note! Do not remove this column. | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
[11 empty] | RAN-CN interface options dependency | [6 empty] | WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan section covers documentation of the test tolerances for RRM and UE radio reception conformance test cases. This also includes NR OTA Measurement Uncertainty (MU) and Test Tolerances (TT). Note! Content related to specific test cases (this is handled as part of the work plan item for the test case in the TS 38.521-1, TS 38.521-2, TS 38.521-3 and TS 38.533 section of the work plan) | [9 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Ron Borsato, AT&T |  |  | ronald.borsato@att.com
TS Resp: | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [6 empty] | SA |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7 |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[18 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[10 empty] | Overall | 76.47%
[6 empty] | Overall #WP items: Post WI close #WP items: |  |  |  |  | 13 4 |  |  | 0 0 | 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option | [8 empty] | Anritsu | Hiroyuki.Baba@anritsu.com
Not yet identified test cases | [19 empty] | Rohde & Schwarz | Edwin.Menzel@rohde-schwarz.com
| 38.903 | Annex B | FFS | TT for RF test cases under EC condition |  |  |  | Whether there is need to test under EC is FFS, thus the task force is estimated as lower than NC | 50 |  | 1 |  | 1 | [6 empty] | Keysight | emilio_ruiz@KEYSIGHT.COM
| MU for RRM Test Cases | [18 empty] | NTT Docomo | takahiro.arai.kw@nttdocomo.com
107 | 38.903 | 8 | Grouping of test cases defined in TS 38.533 |  |  | Opt 2: RAN5#90 (Feb-21) |  | Content Unchanged for many meetings. Considered to be stable and complete. | 1 | 100% | 10 | 100% | 1 | [6 empty] | MVG | Kim.Rutkowski@mvg-us.com
106 | 38.903 | Annex E | Acceptable uncertainty of test system for test cases defined in TS 38.533 for radiative testing |  |  | Opt 2: Post WI close | R5-202195 R5-204887 R5-206836 |  | 40 | 90% | 16 | 90% | 1 | [6 empty] | Qualcomm1 | mvora@QTI.QUALCOMM.COM
103 | 38.903 | Annex E.1 | Uncertainty budget calculation principle |  |  | Opt 2: RAN5#87 (May-20) | R5-187025 | Content Unchanged for many meetings. Considered to be stable and complete. | 1 | 100% | 7 | 100% | 1 | [6 empty] | CAICT | zhangyufeng@CAICT.AC.CN
| 38.903 | Annex E.2 | Measurement error contribution descriptions | [7 empty] | 3 |  | 1
104 | 38.903 | Annex E.2.1 | Measurement error contribution descriptions for DFF |  |  | Opt 2: RAN5#87 (May-20) | R5-187025 R5-202195 | WF on MU elements for study endorsed. Complete from a reference perspective but not fully complete due to incomplete MU elements in referenced annex. | 1 | 100% | 7 | 100% | 1
105 | 38.903 | Annex E.2.2 | Measurement error contribution descriptions for IFF |  |  | Opt 2: RAN5#87 (May-20) | R5-187025 R5-202195 | WF on MU elements for study endorsed. | 1 | 100% | 7 | 100% | 1
| 38.903 | Annex E.3 | Uncertainty assessment for RRM MU quantities | [5 empty] | 1 |  | 10 |  | 1
108 | 38.903 | Annex E.3.1 | Uncertainty assessment for DL AWGN absolute power or wanted DL signal absolute power |  |  | Opt 2: RAN5#90 (Feb-21) | R5-211644 R5-211933 |  | 20 | 100% | 10 | 100% | 1
109 | 38.903 | Annex E.3.2 | Uncertainty assessment for DL applied SNR |  |  | Opt 2: RAN5#90 (Feb-21) |  |  | 20 | 100% | 10 | 100% | 1
110 | 38.903 | Annex E.3.3 | Uncertainty assessment for DL Fading profile uncertainty |  |  | Opt 2: RAN5#90 (Feb-21) |  |  | 20 | 100% | 10 | 100% | 1
111 | 38.903 | Annex E.3.4 | Uncertainty assessment for DL AWGN and signal flatness |  |  | Opt 2: Post WI close |  |  | 20 | 0% | 16 | 0% | 1
112 | 38.903 | Annex E.3.5 | Uncertainty assessment for UL absolute power measurement |  |  | Opt 2: Post WI close | R5-216104 R5-215824 | MU complete except for Influence of Noise as it depends on the UL power level to be measured in the test case which needs further study. | 20 | 80% | 16 | 80% | 1
113 | 38.903 | Annex E.3.6 | Uncertainty assessment for UL relative power measurement |  |  | Opt 2: Post WI close |  |  | 20 | 0% | 16 | 0% | 1
114 | 38.903 | Annex E.3.7 | Uncertainty assessment for UL signal transmit timing relative to DL |  |  | Opt 2: RAN5#90 (Feb-21) |  | Need clean up CR to align with 38.533 CR in R5-210814 | 20 | 100% | 10 | 100% | 1
115 | 38.903 | Annex E.3.8 | Uncertainty assessment for Relative transmit timing accuracy during UE timing adjustment |  |  | Opt 2: RAN5#90 (Feb-21) |  | Need clean up CR to align with 38.533 CR in R5-210814 | 20 | 100% | 10 | 100% | 1
<area#5>
| 38.903 | <Clause> | <Title> | [5 empty] | 1 |  | 1 |  | 1 | 1 | 1 | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on AA6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AB7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).