## Cover sheet
RAN5 meeting #95e | [10 empty] | R5-222579
Electronic Meeting, 9th May 2022 – 20th May 2021
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP - UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum
Work item code: | NR_unlic-UEConTest-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 8
Completion Compensation |  | 6.939e-16%
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% | 0 | 8
FR1 |  | 5% | 0 | 8
FR2 |  | 5%
NSA Option 3 (EN-DC) |  | 5% | 0 | 8
FR1 |  | 5% | 0 | 8
FR2 |  | 5%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-210708 | New WID - UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum
[2]R5-215647 | WP - UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | NR-based access to unlicensed spectrum - (TS 38.521-4) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_unlic-UEConTest-UEConTest
WP Scope: |  | This part of the work plan covers Demodulation and CSI test cases for NR based access to unlicensed spectrum for range 1 (sub-6 GHz) | [13 empty] | vs Area
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 5% | 5% | 5% | 5%
[15 empty] | 18 | 8 | 12 | 2
[15 empty] | 17 | 8 | 11 | 2
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
9 |  | 38.508-1 | 4, 5 | Introduction of General and RF Demod Test Environment for Rel-16 NR-U | [5 empty] | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.508-2: Common ICS
10 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-16 NR-U | [5 empty] | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.509: UE specific testing functions
|  | 38.509 | TBD | TBD | [5 empty] | 1
TS 38.521-4: Demodulation performance requirements (conducted requirements)
1 |  | 38.521-4 | 5.1 | General | Exisiting sub-clause header |  |  |  |  | 0.5 | 0% | 0% | 0% |  | 0% |  | 0%
2 | Y | 38.521-4 | 5.2.2.2.15.1 | 2Rx FDD FR1 PDSCH performance of Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
3 | Y | 38.521-4 | 5.2.3.2.15.1 | 4Rx TDD FR1 PDSCH performance of Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
4 | Y | 38.521-4 | 5.2A.2.3.1 | 2Rx FR1 PDSCH performance of Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
17 | Y | 38.521-4 | 5.2A.3.3.1 | 4Rx FR1 PDSCH performance of Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
TS 38.521-4: CSI reporting requirements (conducted requirements)
18 |  | 38.521-4 | 6.1 | General | Exisiting sub-clause header |  |  |  |  | 0.5 | 0% | 0% | 0% |  | 0% |  | 0%
19 | Y | 38.521-4 | 6.2.2.2.1.3.1 | 2Rx TDD FR1 CQI reporting under AWGN for Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
20 | Y | 38.521-4 | 6.2.3.2.1.3.1 | 4Rx TDD FR1 CQI reporting under AWGN for Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
21 | Y | 38.521-4 | 6.2A.3.1.2.1 | 2Rx FR1 CQI reporting under AWGN for Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
22 | Y | 38.521-4 | 6.2A.4.1.1.1 | 4Rx FR1 CQI reporting under AWGN for Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
TS 38.521-4: Annex
12 |  | 38.521-4 | Annex A | Measurements Channels | [5 empty] | 1 | 0% | 0% |  |  | 0% | 0%
13 |  | 38.521-4 | Annex B | Propagation conditions | [5 empty] | 1 | 0% | 0% |  |  | 0% | 0%
14 |  | 38.521-4 | Annex C | Downlink physical channels | [5 empty] | 1 | 0% | 0% |  |  | 0% | 0%
15 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | [5 empty] | 1 | 0% | 0% |  |  | 0% | 0%
16 |  | 38.521-4 | Annex G | Statistical testing | [5 empty] | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.522: Applicability for Demodulation and CSI test cases
11 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-4 | [5 empty] | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.