## Cover sheet
3GPP TSG-RAN WG5 Meeting #95-e | [10 empty] | R5-222908
Electronic Meeting, 09th May - 20th May 2022
Agenda Item: | 7.4.2
Source: | Huawei, Samsung
Title: | WP UE Conformance Test Aspects for Enhancements on MIMO for NR
Work item code: | NR_eMIMO-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for Enhancements on MIMO for NR work item is to define the UE conformance requirements corresponding to WID on enhancement on MIMO for NR, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for Enhancements on MIMO for NR was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 64% (+7%) | 38 (+8) | 63 (+4)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 58.3% (+6.9%) | 30 (+3) | 45 (+2)
FR1 |  | 69.9% (+5.5%) | 27 | 35 (+2)
FR2 |  | 33.8% (+9%) | 3 (+3) | 11
NSA Option 3 (EN-DC) |  | 74.5% (+6.5%) | 28 (+5) | 39 (+2)
FR1 |  | 87.2% (+0.9%) | 25 (+2) | 31 (+2)
FR2 |  | 41.7% (+17.7%) | 3 (+3) | 9
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 25.2% (+0.2%) |  |  | 34% |  |  | 6% |  |  |  | 32% |  |  | 6%
Common ICS | 38.508-2 | 71% (+0.2%) |  |  | 80% |  |  | 50% |  |  |  | 80% |  |  | 50%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 23.3% (+15%) |  |  | 23.3% (+15%)
FR1 RF Tx test cases | 38.521-1 Tx | 89.6% (+10.8%) | 4 | 4 | 89.6% (+10.8%) | 4 | 4
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2 | 8.3% (+8.3%) | [5 empty] | 8.3% (+8.3%)
FR2 RF Tx test cases | 38.521-2 Tx | 72.5% (+9.8%) | 0 | 2 |  |  |  | 72.5% (+9.8%) | 0 | 2
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 99.1% (+0%) | 20 | 20 | 98.7% | 20 | 20 |  |  |  |  | 100% | 20 | 20
RRM test cases | 38.533 | 47% (+13.2%) | 14 (+8) | 36 (+4) | 38% (+12.9%) | 3 | 10 (+2) | 26.5% (+12.6%) | 3 (+3) | 8 |  | 92.4% (+2.5%) | 5 (+2) | 10 (+2) | 57.9% (+35.6%) | 3 (+3) | 8
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 61.2% (+0.4%) |  |  | 56% |  |  | 51.2% |  |  |  | 100% |  |  | 30%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 53.7% (+0.4%) |  |  | 70% |  |  | 11.2% |  |  |  | 70% |  |  | 30%
Test Point analysis receiver and transmitter test cases | 38.905 | 60% (+6.3%) |  |  | 60% |  |  | 60% (+20%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 31.5% (-0%) | 0 | 1 | 30% | 0 | 1 | 35% | 0 | 1 |  | 30% | 0 | 1 | 35% | 0 | 1
Applicability Protocol test cases | 38.523-2 | 50% |  |  | 50% |  |  | 50% |  |  |  | 50% |  |  | 50%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200895 | New WID on UE Conformance Test Aspects for Enhancements on MIMO for NR; Huawei, Samsung
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for Enhancements on MIMO for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_eMIMO-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Enhancements on MIMO for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 69.9% (+5.5%) | 33.8% (+9%) | 87.2% (+0.9%) | 41.7% (+17.7%)
[15 empty] | 121 (+3) | 54 | 73 (+3) | 29
[15 empty] | 86.4 (+3) | 40.9 | 44.1 (+3) | 17.2
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
117 |  | 38.508-1 | 4.3 | Reference test conditions | Adding necessary test conditions for eMIMO features | Huawei | TBD | R5-205932 |  | 1 | 2.5% | 5% | 0% |  | 10% | 0% | 0% | 0%
118 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for eMIMO features |  | TBD | R5-220808 |  | 1 | 30% | 30% | 30% |  | 30% | 30% | 30% | 30%
119 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Huawei | TBD | R5-205932 R5-217366 |  | 1 | 15% | 15% | 15% |  | 30% | 0% | 30% | 0%
120 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
195 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams | Huawei | TBD | R5-216070 R5-220797 |  | 1 | 50% | 50% | 50% |  | 100% | 0% | 100% | 0%
TS 38.508-2: Common ICS
1 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Lenovo, Motorola Mobility, Huawei, HiSilicon, Bureau Veritas, Ericsson | RAN5#93 (Nov-21) | R5-206414 R5-212938 R5-215095 R5-215933 R5-215184 R5-218307 R5-221830 |  | 0.2 | 65% | 65% | 65% |  | 80% | 50% | 80% | 50%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
2 |  | 38.521-1 | 2 | Reference | Define References made in TS |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
3 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Ericsson | RAN5#89-e (Nov-20) | R5-205557 |  | 0.1 | 100% | 100% |  |  | 100%
4 |  | 38.521-1 | 4 | General | define categories of test requirements |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
5 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
6 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
7 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
8 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
9 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
10 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process | Anritsu | RAN5#95 (May-22) | R5-222481 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
11 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT | Huawei | TBD | R5-223018 |  | 0.1 | 80% (+80%) | 80% (+80%) |  |  | 80%
12 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
13 |  | 38.521-1 | Annex H | Statistical Testing |  |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
14 |  |  | 6.2.2 | UE maximum output power reduction | Adding minimum requirement and additional test point for R16 DMRS | Huawei | RAN5#91-e (May-21) | R5-205791, R5-210782 R5-216141 R5-217215 | Ref: 38.101-1 6.2.2 38.522: No changes needed 38.905: R5-206857, R5-216142 | 1 | 100% | 100% |  |  | 100%
15 |  | 38.521-1 Tx | 6.2.3 | UE additional maximum output power reduction | Adding minimum requirement; Analysing whether additional test point for R16 DMRS is needed Minimum requirment for R16 DMRS is the same as for R15 DMRS. Given the UE can pass the requirements using R15 DMRS, it can be expected that UE can psss the requirements using R16 DMRS. Therefore there is no need to additionally test the R16 DMRS. | Huawei | RAN5#90-e (Feb-21) | R5-210782 R5-217216 | Ref: 38.101-1 6.2.3 38.522: No changes needed 38.905: R5-211809 | 1 | 100% | 100% |  |  | 100%
16 |  | 38.521-1 Tx | 6.4.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK | Adding minimum requirement and additional test point for R16 DMRS | Huawei | RAN5#91-e (May-21) | R5-211807 R5-216141 | Ref: 38.101-1 6.4.2.4.1 38.522: R5-215935 38.905: R5-211810 , R5-216142 | 1 | 100% | 100% |  |  | 100%
17 |  | 38.521-1 Tx | 6.5.2.2 | Spectrum Emission Mask | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-206766 R5-216141 | Ref: 38.101-1 6.5.2.2 38.522: No changes needed 38.905: R5-206857, R5-216142 | 1 | 100% | 100% |  |  | 100%
18 |  | 38.521-1 Tx | 6.5.2.4.1 | NR ACLR | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-206767 R5-216141 R5-217215 | Ref: 38.101-1 6.5.2.4.1 38.522: No changes needed 38.905: R5-206857, R5-216142 | 1 | 100% | 100% |  |  | 100%
19 |  | 38.521-1 Tx | 6.2C.4 | UE maximum output power reduction for SUL | Adding additional test point for R16 DMRS | Huawei | RAN5#91-e (May-21) | R5-211915 R5-217215 | Ref: 38.101-1 6.2C, 6.2.2 38.522: No changes needed 38.905: R5-211811 | 1 | 100% | 100% |  |  | 100%
20 |  | 38.521-1 Tx | 6.2C.5 | UE additional maximum output power reduction for SUL | Adding minimum requirement; Analysing whether additional test point for R16 DMRS is needed |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.2C, 6.2.3 No changes needed | 1 | 100% | 100% |  |  | 100%
21 | Y | 38.521-1 Tx | 6.4C.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK for SUL | Adding test point for R16 DMRS |  | RAN5#91-e (May-21) | R5-211808 R5-216141 | Ref: 38.101-1 6.4.2.5 38.522: R5-210792, R5-215935 38.905: R5-210791, R5-216142 | 1 | 100% | 100% |  |  | 100%
22 |  | 38.521-1 Tx | 6.5C.2.2 | Spectrum Emission Mask for SUL | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-210787 R5-217215 | Ref: 38.101-1 6.5.2.2 38.522: No changes needed 38.905: R5-211811 | 1 | 100% | 100% |  |  | 100%
23 |  | 38.521-1 Tx | 6.5C.2.4.1 | NR ACLR for SUL | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-210788 R5-217215 | Ref: 38.101-1 6.5.2.4.1 38.522: No changes needed 38.905: R5-211811 | 1 | 100% | 100% |  |  | 100%
24 |  | 38.521-1 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#90-e (Feb-21) | R5-205796 | Ref: 38.101-1 6.2D.1 38.522: No changes needed 38.905: R5-206858 | 1 | 100% | 100% |  |  | 100%
25 |  | 38.521-1 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-211133 R5-215185 | Ref: 38.101-1 6.2D.2 FFS:Test requirements for PC2 are missing 38.522: No changes needed 38.905: R5-211134 | 1 | 100% | 100% |  |  | 100%
26 |  | 38.521-1 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Apple | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.2D.3 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
27 |  | 38.521-1 Tx | 6.2D.4 | Configured transmitted power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-214007 | Ref: 38.101-1 6.2D.4 38.522: No changes needed 38.905: R5-213053 | 1 | 100% | 100% |  |  | 100%
28 |  | 38.521-1 Tx | 6.5D.1 | Occupied bandwidth for UL MIMO | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. | Ericsson | RAN5#91-e (May-21) | R5-206894 R5-222873 | Ref: 38.101-1 6.5D.1 Test applicability is TBD Test point analysis is TBD 38.522: R5-222914 38.905: R5-214721, R5-222915 | 1 | 100% (+30%) | 100% (+30%) |  |  | 100%
29 |  | 38.521-1 Tx | 6.5D.2 | Out of band emission for UL MIMO | Sub-title |  |  |  | Sub-title | 0
30 |  | 38.521-1 Tx | 6.5D.2.1 | General | Measurement is changed to sum of both antenna connectors: Updating minimum requirement |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.2 | 0.1 | 0% | 0% |  |  | 0%
31 |  | 38.521-1 Tx | 6.5D.2.2 | Spectrum Emission Mask for UL MIMO | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-223705 | Ref: 38.101-1 6.5D.2 38.522: No changes needed 38.905: R5-223017 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
32 |  | 38.521-1 Tx | 6.5D.2.3 | Additional spectrum emission mask for UL MIMO | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
33 |  | 38.521-1 Tx | 6.5D.2.4.1 | NR ACLR for UL MIMO | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-222939 | Ref: 38.101-1 6.5D.2 38.522: No changes needed 38.905: | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
34 |  | 38.521-1 Tx | 6.5D.2.4.2 | UTRA ACLR for UL MIMO | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-210996 R5-213058 R5-222955 | Ref: 38.101-1 6.5D.2 38.522: R5-218463, R5-222914 38.905: R5-211018 | 1 | 100% | 100% |  |  | 100%
35 |  | 38.521-1 Tx | 6.5D.3_1 | Spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.3 38.522: 38.905: | 0.1 | 0% | 0% |  |  | 0%
36 | Y | 38.521-1 Tx | 6.5D.3_1.1 | General spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-206768 | Ref: 38.101-1 6.5D.3 38.522: R5-210792, R5-218463 38.905: R5-206769 | 1 | 100% | 100% |  |  | 100%
37 | Y | 38.521-1 Tx | 6.5D.3_1.2 | Spurious emission for UE co-existence for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-205799 | Ref: 38.101-1 6.5D.3 38.522: R5-210792, R5-218463 38.905: R5-206769 | 1 | 100% | 100% |  |  | 100%
38 | Y | 38.521-1 Tx | 6.5D.3_1.3 | Additional spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-205800 | Ref: 38.101-1 6.5D.3 38.522: R5-210792, R5-218463 38.905: R5-206769 | 1 | 100% | 100% |  |  | 100%
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
39 |  | 38.521-2 | 2 | Reference | Define References made in TS |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
40 |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Ericsson | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
41 |  | 38.521-2 | 4 | General | define categories of test requirements |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
42 |  | 38.521-2 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
43 |  | 38.521-2 | Annex A | measurement channels | define mesurement channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
44 |  | 38.521-2 | Annex B | Propagation conditions | Define propagation conditions |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
45 |  | 38.521-2 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
46 |  | 38.521-2 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
47 |  | 38.521-2 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process | Anritsu | RAN5#93 (Dec-2021) | R5-222482 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
48 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
49 |  | 38.521-2 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
50 |  | 38.521-2 | Annex H | Statistical Testing |  |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
51 |  | 38.521-2 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Sub-title Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  |  |  |  | 0
196 |  | 38.521-2 Tx | 6.2D.1.0 | General | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei, Apple , SGS | RAN5#93 (Nov-21) | R5-216111 | Ref: 38.101-2 6.2D.1 | 0.1 | 100% | 100% |  |  |  | 100%
197 | Y | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei, Apple , SGS | RAN5#93 (Nov-21) | R5-216111 R5-220791 | Ref: 38.101-2 6.2D.1 38.522: R5-221832 38.905: R5-220794 Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - No test points are defined for 2-layer UL MIMO since there is no configuration satisfying MPR=0dB requirements in RAN4. - Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 ,4 and 5. - Test Procedures for EIRP beam peak Extreme Conditions are FFS. | 1 | 80% | 80% |  |  |  | 80%
198 | Y | 38.521-2 Tx | 6.2D.1.2 | 6.2D.1.2 UE maximum output power - Spherical coverage for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei, Apple , SGS | RAN5#93 (Nov-21) | R5-216111 R5-220791 | Ref: 38.101-2 6.2D.1 38.522: R5-221832 38.905: R5-220794 Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - No test points are defined for 2-layer UL MIMO since there is no configuration satisfying MPR=0dB requirements in RAN4. - Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 ,4 and 5. - Test Procedures for EIRP beam peak Extreme Conditions are FFS. | 1 | 80% | 80% |  |  |  | 80%
52 |  | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#93 (Nov-21) | R5-220792 | Ref: 38.101-2 6.2D.2 38.522: 38.905: Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - OTA test procedure for UL MIMO is still under investigation - Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 and 4. | 1 | 50% | 50% |  |  |  | 50%
53 |  | 38.521-2 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#93 (Nov-21) | R5-223122 | Ref: 38.101-2 6.2D.3 38.522: 38.905: Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 and 4. - OTA test procedure for UL MIMO is still under investigation | 1 | 50% (+50%) | 50% (+50%) |  |  |  | 50%
54 |  | 38.521-2 Tx | 6.2D.4 | Configured transmitted power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#93 (Nov-21) | R5-220793 | Ref: 38.101-2 6.2D.4 38.522: No changes needed 38.905: No changes needed | 1 | 100% | 100% |  |  |  | 100%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
General
55 |  | 38.521-4 | 2 | References | Define References made in TS |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
56 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively |  | RAN5#93 (Nov-21) |  | TS 38.101-4 cl.3 | 0.1 | 0% | 0% |  |  | 0%
57 |  | 38.521-4 | 4 | General | define categories of test requirements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
58 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | define applicability of multi-TRP test cases | Apple | RAN5#93 (Nov-21) | R5-216787 R5-220796 | TS 38.101-4 cl.5.1.1.3 | 0.1 | 100% | 100% |  |  | 100%
59 |  | 38.521-4 | 5.1.1.8 | Applicability of different requirements with Multi-TRP | define test cases selection rule of multi-TRP test cases | Apple | RAN5#93 (Nov-21) | R5-216786 R5-220796 | TS 38.101-4 cl.5.1.1.8 | 0.1 | 100% | 100% |  |  | 100%
195 |  | 38.521-4 | 6.1.1.3 | Applicability of requirements for optional UE features | define applicability of PMI reporting test cases | Huawei | RAN5#93 (Nov-21) | R5-218312 | TS 38.101-4 cl.5.1.1.3 | 0.1 | 100% | 100% |  |  | 100%
Demodulation performance requirements (Conducted requirements) (Clause 5)
60 |  | 38.521-4 | 5.2 | PDSCH demodulation requirements | Sub-title |  |  |  |  | 0
61 |  | 38.521-4 | 5.2.2.1.11 | 2Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
162 |  | 38.521-4 | 5.2.2.1.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-212933 | TS 38.101-4 cl.5.2.2.1.11 Brackets in RAN4 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
163 | Y | 38.521-4 | 5.2.2.1.11_1 | 2Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R5-212933 R5-220796 | TS 38.101-4 cl.5.2.2.1.11 Brackets in RAN4 TS 38.522: R5-212939, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
62 |  | 38.521-4 | 5.2.2.1.12 | 2Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
164 |  | 38.521-4 | 5.2.2.1.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216126 | TS 38.101-4 cl.5.2.2.1.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
165 | Y | 38.521-4 | 5.2.2.1.12_1 | 2Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-216126 | TS 38.101-4 cl.5.2.2.1.12 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
63 |  | 38.521-4 | 5.2.2.1.13 | 2Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
166 |  | 38.521-4 | 5.2.2.1.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216127 | TS 38.101-4 cl.5.2.2.1.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
167 | Y | 38.521-4 | 5.2.2.1.13_1 | 2Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-216127 | TS 38.101-4 cl.5.2.2.1.13 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
64 |  | 38.521-4 | 5.2.2.1.14 | 2Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
168 |  | 38.521-4 | 5.2.2.1.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216128 | TS 38.101-4 cl.5.2.2.1.14 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
169 | Y | 38.521-4 | 5.2.2.1.14_1 | 2Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-216128 R5-220796 | TS 38.101-4 cl.5.2.2.1.14 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
65 |  | 38.521-4 | 5.2.2.2.11 | 2Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
170 |  | 38.521-4 | 5.2.2.2.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-212934 R5-220796 | TS 38.101-4 cl.5.2.2.2.11 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
171 | Y | 38.521-4 | 5.2.2.2.11_1 | 2Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R5-212934 R5-220796 | TS 38.101-4 cl.5.2.2.2.11 TS 38.522: R5-212939, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
66 |  | 38.521-4 | 5.2.2.2.12 | 2Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
172 |  | 38.521-4 | 5.2.2.2.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215084 | TS 38.101-4 cl.5.2.2.2.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
173 | Y | 38.521-4 | 5.2.2.2.12_1 | 2Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-215084 | TS 38.101-4 cl.5.2.2.2.12 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
67 |  | 38.521-4 | 5.2.2.2.13 | 2Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
174 |  | 38.521-4 | 5.2.2.2.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215085 | TS 38.101-4 cl.5.2.2.2.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
175 | Y | 38.521-4 | 5.2.2.2.13_1 | 2Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-215085 | TS 38.101-4 cl.5.2.2.2.13 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
68 |  | 38.521-4 | 5.2.2.2.14 | 2Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
176 |  | 38.521-4 | 5.2.2.2.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216071 | TS 38.101-4 cl.5.2.2.2.14 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
177 | Y | 38.521-4 | 5.2.2.2.14_1 | 2Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-216071 | TS 38.101-4 cl.5.2.2.2.14 TS 38.522: R5-215935, R5-221832 Annex G is FFS | 1 | 100% | 100% | 100% |  | 100% |  | 100%
69 |  | 38.521-4 | 5.2.3.1.11 | 4Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
178 |  | 38.521-4 | 5.2.3.1.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-212935 R5-220796 | TS 38.101-4 cl.5.2.3.1.11 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
179 | Y | 38.521-4 | 5.2.3.1.11_1 | 4Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R5-212935 R5-220796 | TS 38.101-4 cl.5.2.3.1.11 Brackets in RAN4 TS 38.522: R5-212939, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
70 |  | 38.521-4 | 5.2.3.1.12 | 4Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
180 |  | 38.521-4 | 5.2.3.1.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215934 | TS 38.101-4 cl.5.2.3.1.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
181 | Y | 38.521-4 | 5.2.3.1.12_1 | 4Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-215934 | TS 38.101-4 cl.5.2.3.1.12 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
71 |  | 38.521-4 | 5.2.3.1.13 | 4Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
182 |  | 38.521-4 | 5.2.3.1.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216129 | TS 38.101-4 cl.5.2.3.1.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
183 | Y | 38.521-4 | 5.2.3.1.13_1 | 4Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-216129 | TS 38.101-4 cl.5.2.3.1.13 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
72 |  | 38.521-4 | 5.2.3.1.14 | 4Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
184 |  | 38.521-4 | 5.2.3.1.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216130 | TS 38.101-4 cl.5.2.3.1.14 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
185 | Y | 38.521-4 | 5.2.3.1.14_1 | 4Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-216130 R5-220796 | TS 38.101-4 cl.5.2.3.1.14 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
73 |  | 38.521-4 | 5.2.3.2.11 | 4Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
186 |  | 38.521-4 | 5.2.3.2.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-212936 R5-220796 | TS 38.101-4 cl.5.2.3.2.11 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
187 | Y | 38.521-4 | 5.2.3.2.11_1 | 4Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R5-212936 R5-220796 | TS 38.101-4 cl.5.2.3.2.11 Brackets in RAN4 TS 38.522: R5-212939, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
74 |  | 38.521-4 | 5.2.3.2.12 | 4Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
188 |  | 38.521-4 | 5.2.3.2.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215090 | TS 38.101-4 cl.5.2.3.2.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
189 | Y | 38.521-4 | 5.2.3.2.12_1 | 4Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-215090 | TS 38.101-4 cl.5.2.3.2.12 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
75 |  | 38.521-4 | 5.2.3.2.13 | 4Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
190 |  | 38.521-4 | 5.2.3.2.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215091 | TS 38.101-4 cl.5.2.3.2.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
191 | Y | 38.521-4 | 5.2.3.2.13_1 | 4Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-215091 | TS 38.101-4 cl.5.2.3.2.13 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
76 |  | 38.521-4 | 5.2.3.2.14 | 4Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
192 |  | 38.521-4 | 5.2.3.2.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215092 | TS 38.101-4 cl.5.2.3.2.14 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
193 | Y | 38.521-4 | 5.2.3.2.14_1 | 4Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-215092 | TS 38.101-4 cl.5.2.3.2.14 TS 38.522: R5-215935, R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
CSI reporting requirements (Conducted requirements) (Clause 6)
77 |  | 38.521-4 | 6.3 | Reporting of Precoding Matrix Indicator (PMI) | Sub-title | Huawei | RAN5#93 (Nov-21) | R5-220796 | R4-2103833 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
78 | Y | 38.521-4 | 6.3.2.1.6 | 2Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218308 | TS 38.101-4 cl.6.3.2.1.6 Brackets in RAN4 TS 38.522: R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
79 | Y | 38.521-4 | 6.3.2.2.6 | 2Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218309 R5-220796 | TS 38.101-4 cl.6.3.2.2.6 Brackets in RAN4 TS 38.522: R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
80 | Y | 38.521-4 | 6.3.3.1.6 | 4Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218310 R5-220796 | TS 38.101-4 cl.6.3.3.1.6 Brackets in RAN4 TS 38.522: R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
81 | Y | 38.521-4 | 6.3.3.2.6 | 4Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218311 R5-220796 | TS 38.101-4 cl.6.3.3.2.6 Brackets in RAN4 TS 38.522: R5-221832 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
Annex
82 |  | 38.521-4 | Annex A | measurement channels | define mesurement channels | Huawei | RAN5#93 (Nov-21) | R5-212937 R5-215093 R5-217363 R5-220796 | TS 38.101-4 cl.A.3 R.PDSCH.1-2.5 FDD, R.PDSCH.1-3.2 FDD, R.PDSCH.1-3.3 FDD, R.PDSCH.1-3.4 FDD, R.PDSCH.1-11.2 FDD, R.PDSCH.2-2.5 TDD, R.PDSCH.2-3.2 TDD, R.PDSCH.2-3.3 TDD, R.PDSCH.2-3.4 TDD, R.PDSCH.1-16.2 TDD | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
83 |  | 38.521-4 | Annex B | Propagation conditions | Define propagation conditions | Huawei | RAN5#93 (Nov-21) | R5-217364 | TS 38.101-4 cl.B.2 B.2.3.2.3A Beam steering approach with dual cluster beams | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
84 |  | 38.521-4 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Nov-21) |  | No impact in this clause | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
194 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | MU and TT | Huawei | RAN5#93 (Nov-21) | R5-215094 R5-218462 |  | 1 | 100% | 100% | 100% |  | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding applicability for test cases in 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-210792 |  | 1 | 0% | 0% |  |  | 0%
|  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Adding applicability for test cases in 38.521-2 |  |  | R5-221832 |  | 0.3 | 20% | 20% |  |  |  | 20%
|  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 | Huawei |  | R5-212939 R5-215935 R5-218463 R5-221832 |  | 1 | 100% | 100% | 100% |  | 100% |  | 100%
|  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 |  |  | R5-221831 R5-221832 |  | 0.5 | 70% | 75% | 65% |  | 80% | 70% | 100% | 30%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Test cases for measurement performance(~4), Beam Failure Detection and Link Recovery (~8), Pathloss reference signal switching delay(~4) |  |  |  |  | 16 | 0% | 0% |  |  | 0% | 0%
General
85 |  | 38.533 | 2 | References | Define References made in TS |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
86 |  | 38.533 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Huawei | RAN5#93 (Nov-21) | R5-217211 | TS 38.133 cl.3 | 0.1 | 50% | 50% |  |  | 100% | 0%
87 |  | 38.533 | 4 | General | define categories of test requirements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
EN-DC tests within FR1 (Clause 4)
88 |  | 38.533 | 4.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
|  | 38.533 | 4.5.5 | Link recovery procedures | Sub-title |  |  |  |  | 0
89 |  | 38.533 | 4.5.5.0 | Minimum conformance requirements |  | Huawei | RAN5#95 (May-22) | R5-222887 |  | 1 | 100% (+10%) |  | 100% (+10%) |  |  |  | 100%
89 | Y | 38.533 | 4.5.5.5 | EN-DC FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in non-DRX | BFD and LR procedure | Sporton | RAN5#93 (Nov-21) | R5-218320 R5-221650 R5-223305 | TS 38.133 cl.A.4.5.5.5 TS 38.903: R5-221840 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Some test configuration needs to be fixed in RAN4, BW and BWP configuration is missing in test case | 1 | 100% (+10%) |  | 100% (+10%) |  |  |  | 100%
90 | Y | 38.533 | 4.5.5.6 | EN-DC FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in DRX | BFD and LR procedure | Sporton | RAN5#93 (Nov-21) | R5-218321 R5-221651 R5-223305 | TS 38.133 cl.A.4.5.5.6 TS 38.903: R5-221840 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Some test configuration needs to be fixed in RAN4, BW and BWP configuration is missing in test case | 1 | 100% (+10%) |  | 100% (+10%) |  |  |  | 100%
91 |  | 38.533 | 4.6 | Measurement procedures | Sub-title |  |  |  |  | 0
92 |  | 38.533 | 4.6.7 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
93 |  | 38.533 | 4.6.7.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-217203 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 100% |  | 100% |  |  |  | 100%
94 | Y | 38.533 | 4.6.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218313 R5-220986 R5-222998 | TS 38.133 cl.A.4.6.7.1 TS 38.903: R5-220994 TS 38.522: R5-221832 | 1 | 100% |  | 100% |  |  |  | 100%
95 | Y | 38.533 | 4.6.7.2 | EN-DC FR1 SSB based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218314 R5-221653 R5-222998 | TS 38.133 cl.A.4.6.7.2 TS 38.903: R5-220995 TS 38.522: R5-221832 | 1 | 100% |  | 100% |  |  |  | 100%
96 | Y | 38.533 | 4.6.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218315 R5-220988 R5-222998 | TS 38.133 cl.A.4.6.7.3 TS 38.903: R5-220996 TS 38.522: R5-221832 | 1 | 100% |  | 100% |  |  |  | 100%
97 |  | 38.533 | 4.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
98 |  | 38.533 | 4.7.7 | L1-SINR measurement for beam reporting | New Sub-title | Sporton | RAN5#93 (Nov-21) |  | R4-2100938 | 0
99 |  | 38.533 | 4.7.7.0 | Minimum conformance requirements |  | Sporton | RAN5#93 (Nov-21) | R5-218322 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.3, 10.1.x, 10.1.Y1,3 | 0.1 | 100% |  | 100% |  |  |  | 100%
100 |  | 38.533 | 4.7.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement | New Sub-title | Sporton | RAN5#96 (Aug-22) |  |  | 0
100 | Y | 38.533 | 4.7.7.1.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218322 R5-221839 | TS 38.133 cl.A.4.7.7.1 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. | 1 | 90% |  | 90% |  |  |  | 90%
100 | Y | 38.533 | 4.7.7.1.2 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR relative measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218322 R5-221839 | TS 38.133 cl.A.4.7.7.1 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. | 1 | 90% |  | 90% |  |  |  | 90%
101 | Y | 38.533 | 4.7.7.2 | EN-DC FR1 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218464 R5-221839 | TS 38.133 cl.A.4.7.7.2 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. | 1 | 90% |  | 90% |  |  |  | 90%
102 |  | 38.533 | 4.7.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement | New Sub-title | Sporton | RAN5#96 (Aug-22) |  |  | 0
102 | Y | 38.533 | 4.7.7.3.1 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218323 R5-221839 | TS 38.133 cl.A.4.7.7.3 TS 38.903 TS 38.522: R5-221831 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Test applicability is incomplete | 1 | 90% |  | 90% |  |  |  | 90%
102 | Y | 38.533 | 4.7.7.3.2 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR relative measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218323 R5-221839 | TS 38.133 cl.A.4.7.7.3 TS 38.903 TS 38.522: R5-221831 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Test applicability is incomplete | 1 | 90% |  | 90% |  |  |  | 90%
EN-DC tests including FR2 (Clause 5)
103 |  | 38.533 | 5.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
108 |  | 38.533 | 5.5.5.0 | Minimum conformance requirements |  | Huawei | RAN5#94 (Feb-22) | R5-220798 |  | 0.1 | 100% |  | 100% |  |  |  |  | 100%
104 | Y | 38.533 | 5.5.5.6 | EN-DC FR2 Scell CSI-RS-based beam failure detection and link recovery in non-DRX | BFD and LR procedure | Huawei | RAN5#93 (Nov-21) | R5-221833 R5-222890 | TS 38.133 cl.A.5.5.5.6 TS 38.903: R5-221840 TS 38.522: R5-221832 Editor's Note: This test cases is incomplete in following aspects: - RMC is missing in RAN4.-This test case is incomplete for Test frequency f > 40.8 GHz - This test case is incomplete for UE power class other than PC3. | 1 | 90% |  | 90% |  |  |  |  | 90%
105 | Y | 38.533 | 5.5.5.7 | EN-DC FR2 Scell CSI-RS-based beam failure detection and link recovery in DRX | BFD and LR procedure | Huawei | RAN5#93 (Nov-21) | R5-221834 R5-222890 | TS 38.133 cl.A.5.5.5.7 TS 38.903: R5-221840 TS 38.522: R5-221832 Editor's Note: This test cases is incomplete in following aspects: - RMC is missing in RAN4. - This test case is incomplete for Test frequency f > 40.8 GHz - This test case is incomplete for UE power class other than PC3. | 1 | 90% |  | 90% |  |  |  |  | 90%
106 |  | 38.533 | 5.6 | Measurement procedures | Sub-title |  |  |  |  | 0
107 |  | 38.533 | 5.6.56 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
108 |  | 38.533 | 5.6.56.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-223707 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  |  |  | 100%
109 | Y | 38.533 | 5.6.56.1 | EN-DC FR2 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-223001 | TS 38.133 cl.A.5.6.5.1 TS 38.903: R5-223883 TS 38.522: R5-223706 | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  |  | 100%
110 | Y | 38.533 | 5.6.56.2 | EN-DC FR2 SSB based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-223002 | TS 38.133 cl.A.5.6.5.2 TS 38.903: R5-223884 TS 38.522: R5-223706 | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  |  | 100%
111 | Y | 38.533 | 5.6.56.3 | EN-DC FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-223605 | TS 38.133 cl.A.5.6.5.3 TS 38.903: R5-223708 TS 38.522: R5-223706 | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  |  | 100%
112 |  | 38.533 | 5.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
113 |  | 38.533 | 5.7.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
114 |  | 38.533 | 5.7.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.9.5.3, 9.8.4.2, 9.8.3, 10.1.Y.2, 10.1.x.x, 10.1.Y2.3 | 0.1 | 0% |  | 0% |  |  |  |  | 0%
115 | Y | 38.533 | 5.7.6.1 | EN-DC FR2 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance | Huawei | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.7.6.1 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
116 | Y | 38.533 | 5.7.6.2 | EN-DC FR2 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Huawei | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.7.6.2 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
117 | Y | 38.533 | 5.7.6.3 | EN-DC FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Huawei | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.7.6.3 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
NR standalone in FR1 (Clause 6)
118 |  | 38.533 | 6.5 | Signalling characteristics | Sub-title |  |  |  |  | 0
119 |  | 38.533 | 6.5.5.0 | Minimum conformance requirements |  | Huawei | RAN5#95 (May-22) | R5-222887 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
119 | Y | 38.533 | 6.5.5.5 | NR SA FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in non-DRX | BFD and LR procedure | Huawei | RAN5#93 (Nov-21) | R5-223880 | TS 38.133 cl.A.6.5.5.5 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The MU and TT are FFS. - Cell mapping in Annex E is FFS. | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
120 | Y | 38.533 | 6.5.5.6 | NR SA FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in DRX | BFD and LR procedure | Huawei | RAN5#93 (Nov-21) | R5-223881 | TS 38.133 cl.A.6.5.5.6 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The MU and TT are FFS. - Cell mapping in Annex E is FFS. | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
121 |  | 38.533 | 6.6 | Measurement procedures | Sub-title |  |  |  |  | 0
122 |  | 38.533 | 6.6.8 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
123 |  | 38.533 | 6.6.8.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-217207 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 100% | 100% |  |  | 100%
124 | Y | 38.533 | 6.6.8.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218316 R5-220989 R5-222999 | TS 38.133 cl.A.6.6.8.1 TS 38.903: R5-220994 TS 38.522: R5-221832 | 1 | 100% | 100% |  |  | 100%
125 | Y | 38.533 | 6.6.8.2 | NR SA FR1 SSB based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218317 R5-221654 R5-222999 | TS 38.133 cl.A.6.6.8.2 TS 38.903: R5-220997 TS 38.522: R5-221832 | 1 | 100% | 100% |  |  | 100%
126 | Y | 38.533 | 6.6.8.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218318 R5-220991 R5-222999 | TS 38.133 cl.A.6.6.8.3 TS 38.903: R5-220998 TS 38.522: R5-221832 | 1 | 100% | 100% |  |  | 100%
127 |  | 38.533 | 6.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
128 |  | 38.533 | 6.7.9 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
129 |  | 38.533 | 6.7.9.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) | R5-218324 | TS 38.133 cl.9.5.3, 9.8.4.2, 9.8.3, 10.1.X.2, 10.1.x.x, 10.1.Y1.3 | 0.1 | 100% | 100% |  |  | 100%
130 |  | 38.533 | 6.7.9.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement | New Sub-title | Sporton | RAN5#96 (Aug-22) |  |  | 0
130 | Y | 38.533 | 6.7.9.1.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218324 R5-221839 | TS 38.133 cl.A.6.7.9.1 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test Tolerance is FFS | 1 | 90% | 90% |  |  | 90%
130 | Y | 38.533 | 6.7.9.1.2 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR relative measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218324 R5-221839 | TS 38.133 cl.A.6.7.9.1 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test Tolerance is FFS | 1 | 90% | 90% |  |  | 90%
131 | Y | 38.533 | 6.7.9.2 | NR SA FR1 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218325 R5-221839 | TS 38.133 cl.A.6.7.9.2 TS 38.903 TS 38.522: R5-221831 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study | 1 | 90% | 90% |  |  | 90%
132 |  | 38.533 | 6.7.9.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement | L1-SINR measurement performance | Sporton | RAN5#96 (Aug-22) |  |  | 0
132 | Y | 38.533 | 6.7.9.3.1 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218326 R5-221839 | TS 38.133 cl.A.6.7.9.3 TS 38.903 TS 38.522: R5-221831 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Message content is incomplete | 1 | 90% | 90% |  |  | 90%
132 | Y | 38.533 | 6.7.9.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR relative measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218326 R5-221839 | TS 38.133 cl.A.6.7.9.3 TS 38.903 TS 38.522: R5-221831 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Message content is incomplete | 1 | 90% | 90% |  |  | 90%
SA tests in FR2 (Clause 7)
133 |  | 38.533 | 7.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
|  | 38.533 | 7.5.5.0 | Minimum conformance requirements |  | Huawei | RAN5#94 (Feb-22) | R5-220801 |  | 0.1 | [5 empty] | 100%
134 | Y | 38.533 | 7.5.5.6 | NR SA FR2 Scell CSI-RS-based beam failure detection and link recovery in non-DRX | BFD and LR procedure | Huawei | RAN5#93 (Nov-21) | R5-221835 R5-222890 | TS 38.133 cl.A.7.5.5.6 TS 38.903: R5-221840 TS 38.522: R5-221832 Editor's Note: This test cases is incomplete in following aspects: - RMC is missing in RAN4. - This test case is incomplete for Test frequency f > 40.8 GHz - This test case is incomplete for UE power class other than PC3. | 1 | 90% | 90% |  |  |  | 90%
135 | Y | 38.533 | 7.5.5.7 | NR SA FR2 Scell CSI-RS-based beam failure detection and link recovery in DRX | BFD and LR procedure | Huawei | RAN5#93 (Nov-21) | R5-221836 R5-222890 | TS 38.133 cl.A.7.5.5.7 TS 38.903: R5-221840 TS 38.522: R5-221832 Editor's Note: This test cases is incomplete in following aspects: - RMC is missing in RAN4. - This test case is incomplete for Test frequency f > 40.8 GHz - This test case is incomplete for UE power class other than PC3. | 1 | 90% | 90% |  |  |  | 90%
136 |  | 38.533 | 7.6 | Measurement procedures | Sub-title |  |  |  |  | 0
137 |  | 38.533 | 7.6.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
138 |  | 38.533 | 7.6.6.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-223004 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 0% | 0% |  |  |  | 100%
139 | Y | 38.533 | 7.6.6.1 | NR SA FR2 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-223004 | TS 38.133 cl.A.7.6.6.1 TS 38.903: R5-223883 TS 38.522: R5-223706 | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
140 | Y | 38.533 | 7.6.6.2 | NR SA FR2 SSB based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-223882 | TS 38.133 cl.A.7.6.6.2 TS 38.903: R5-223885 TS 38.522: R5-223706 | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
141 | Y | 38.533 | 7.6.6.3 | NR SA FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-223606 | TS 38.133 cl.A.7.6.6.3 TS 38.903: R5-223709 TS 38.522: R5-223706 | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
142 |  | 38.533 | 7.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
143 |  | 38.533 | 7.7.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
144 |  | 38.533 | 7.7.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.9.5.3, 9.8.4.2, 9.8.3, 10.1.Y.2, 10.1.x.x, 10.1.Y2.3 | 0.1 | 0% | 0% |  |  |  | 0%
145 | Y | 38.533 | 7.7.6.1 | NR SA FR2 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-220942 | TS 38.133 cl.A.7.7.6.1 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test applicability is incomplete in TS38.522. - Test Tolerance is FFS - Test frequency f ≤ 40.8 GHz - The test is incomplete for UE power classes other than PC3 - The test is incomplete for test frequencies > 40.8 GHz - The test is incomplete for extreme conditions | 1 | 50% | 50% |  |  |  | 50%
146 | Y | 38.533 | 7.7.6.2 | NR SA FR2 SSB based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-220943 | TS 38.133 cl.A.7.7.6.2 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test applicability is incomplete in TS38.522. - Test Tolerance is FFS - Test frequency f ≤ 40.8 GHz - The test is incomplete for UE power classes other than PC3 - The test is incomplete for test frequencies > 40.8 GHz - The test is incomplete for extreme conditions | 1 | 50% | 50% |  |  |  | 50%
147 | Y | 38.533 | 7.7.6.3 | NR SA FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-220944 | TS 38.133 cl.A.7.7.6.3 TS 38.903 TS 38.522: R5-221831 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test Tolerance is FFS - Test frequency f ≤ 40.8 GHz - The test is incomplete for UE power classes other than PC3 - The test is incomplete for test frequencies > 40.8 GHz - The test is incomplete for extreme conditions | 1 | 50% | 50% |  |  |  | 50%
Annex
148 |  | 38.533 | Annex A | RRM test configurations | RRM test configurations Adding CSI-RS, CSI-IM configurations |  | TBD | R5-217213 R5-218319 | R4-2100938 | 0.1 | 50% | 50% | 50% |  | 100% | 0% | 100% | 0%
149 |  | 38.533 | Annex B | Conditions for RRM requirements applicability for operating bands | Define propagation conditions |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
150 |  | 38.533 | Annex C | Downlink physical channels and propagation conditions | Define downlink physical channels |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
151 |  | 38.533 | Annex D | Deviations from standard test configuration | Define deviations from standard test configuration |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
152 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping |  | TBD | R5-218327 R5-220992 R5-220993 R5-221652 R5-220804 R5-223007 |  | 0.1 | 85% (+25%) | 80% (+25%) | 90% (+25%) |  | 80% | 80% | 100% | 80%
153 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances |  | TBD | R5-220992 R5-220993 R5-221652 R5-221837 R5-223007 |  | 0.1 | 72.5% (+25%) | 80% (+25%) | 65% (+25%) |  | 80% | 80% | 50% | 80%
154 |  | 38.533 | Annex H | Default message contents for RRM |  |  | TBD | R5-217214 R5-221001 R5-221838 |  | 0.1 | 50% | 50% | 50% |  | 50% | 50% | 50% | 50%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
155 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases |  | TBD | R5-220994 R5-220995 R5-220996 R5-220997 R5-220998 R5-221840 |  | 0.3 | 50% | 50% | 50% |  | 70% | 30% | 70% | 30%
156 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | TBD |  |  | 0.5 | 0% | 0% |  |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
157 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | TT analysis for FR1 RF Test cases | Huawei, Ericsson | RAN5#93 (Nov-21) | R5-206857, R5-206858, R5-206769, R5-211809, R5-211810, R5-211811, R5-210791, R5-211018, R5-211134 R5-213053 R5-214721 R5-216142 |  | 1 | 60% | 60% |  |  | 60%
158 |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TT analysis for FR2 RF Test cases |  | RAN5#93 (Nov-21) | R5-220734 R5-221841 R5-222886 |  | 0.3 | 60% (+20%) | 60% (+20%) |  |  |  | 60%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
159 | Y | 38.523-1 | 7.1.1.3.10 | Correct Handling of HARQ process / Multiple CORESETPoolIndex | **** TP1: [TS 38.214:6.1] WITH: UE in RRC_CONNECTED state and is configured with PDCCH-Config that contains two different values of CORESETPoolIndex in ControlResourceSet WHEN: UE receives PDCCHs that schedule two non-overlapping in time domain PUSCHs are associated to different ControlResourceSets having different values of CORESETPoolIndex THEN: UE sends PUSCHs following the scheduling information of PDCCHs | Motorola Mobility | RAN5#91-e (May-21) | R5-206415, R5-210880 | 38.523-2: R5-206416 FFS how to ensure performance of overlapping PDSCH: 1. how to deal with self-interference when 2 PDSCH are transmitted on same channel 2. DMRS needs different CDM group 3. DCI needs different TCI state and scrambling ID | 1 | 65% | 65% | 65% |  | 60% | 70% | 60% | 70%
RRC
160 |  | 38.523-1 | FFS | eMIMO / Measurement configuration control and reporting / RANK 3~4 in enhanced type II codebook | **** TP1: [TS 38.214:6.1] WITH: UE in RRC_CONNECTED state and is configured with typeII-RI-Restriction-r16 of value '1000' WHEN: The PMI reporting is triggered by DCI THEN: UE reports PMI of RANK 4 with enhanced type II codebook | Motorola Mobility | RAN5#91-e (May-21) |  | 38.523-2: 38.508-2: | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
161 |  | 38.523-2 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD | R5-206416 |  | 0.2 | 50% | 50% | 50% |  | 50% | 50% | 50% | 50%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.