## Cover sheet
3GPP TSG-RAN WG5 Meeting #95-e | [10 empty] | R5-223109
Electronic meeting, 9 - 20 May 2022
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP UE Conformance Test NR coverage enhancements RAN5#95e
Work item code: | NR_cov_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The Rel-17 study item “Study on NR coverage enhancements” studied the enhancements of coverage for PUSCH, PUCCH and other channels/signals. In the follow-up WI on NR coverage enhancements, the enhancements for PUSCH, PUCCH and Msg3 PUSCH have been specified. The overall completion level for the core part of NR_cov_enh WI is already 85% at the RAN #94e in December 2021, and the WI core part is expected to be 100% completed at March 2022. The corresponding UE conformance specifications are now required to be implemented in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 2 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 2 (+2)
FR1 |  | 5% (+5%) | 0 | 1 (+1)
FR2 |  | 5% (+5%) | 0 | 1 (+1)
FR1 + FR2 |  | 5% (+5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 0% | [8 empty] | 0%
NR RF/RRM
FR1 RF | 38.521-1 Tx
FR2 RF | 38.521-2 | 0% | 0 | 1 (+1) |  |  |  | 0% | 0 | 1 (+1)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% | [8 empty] | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 0% | [8 empty] | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test NR coverage enhancements | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_cov_enh-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to the WID on NR coverage enhancements. This work item will cover RF and Protocol conformance test specifications. | [12 empty] | vs Area
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 5% (+5%) | 5% (+5%) | 5% (+5%)
[14 empty] | 2 (+2) | 2 (+2) | 4 (+4)
[14 empty] | 1.1 (+1.1) | 1.1 (+1.1) | 0.3 (+0.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.508-2: Common ICS
1 |  | 38.508-2 |  | Adding ICS for Rel-17 coverage enhancement. | [5 empty] | 0.1 | 0% | 0% |  |  |  | 0%
NR RF/RRM
TS 38.521-1: FR1 RF test cases
2 |  | 38.521-1 | F.9.1 | Phase offset measurement for DMRS bundling | Introduction of the measurement point for phase offset measurement. |  | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  | 0%
3 | Y | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | RAN5#98 (March-23) |  | CR is expected to be agreed in RAN4#102e | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases
4 |  | 38.521-2 | F.8.1 | Phase offset measurement for DMRS bundling | Introduction of the measurement point for phase offset measurement. |  | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
5 | Y | 38.521-2 | 6.4.2.6 | Phase continuity requirements for DMRS bundling | Introduction of phase continuty test for DMRS bundling |  | RAN5#98 (March-23) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.522: Applicability for RF test cases
6 |  | 38.522 | 4.0 4.1.1 4.1.2 | Adding test applicability for the new test cases defined in 38.521-1 and 38.521-2. |  | All companies. | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TR 38.903: Test Tolerances analysis RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
7 |  | 38.905 |  | Test point analysis for the new test cases defined in 38.521-1 and 38.521-2. |  | All companies | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | To be added after the implementation of coverage enhancement related IEs in 38.331 after the May RAN2 meeting. | TBD | 0% | 0% |  |  |  | 0%
TS 38.523-2: Applicability for Protocol test cases
|  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | TBD
|  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | TBD
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.