## WP scope
Work plan for introduction of PC3 EN-DC FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP PC3 FR1 DC_7C_n28A-n78A | [6 empty] | <= Enter WP name
| Company (Contact) |  | Ericsson | [6 empty] | <= Enter Responsible Company and Contact
| Target completion |  | RAN5#95-e | [6 empty] | <= Enter target completion date here. Format RAN5#xx (mm-yy), where xx is the RAN5 meeting number and 'mm' and 'yy' is the number of the month and year, e.g. RAN5#94 (02-22)>
Comments
| Overall completion |  | 100%
Target configurations
Copy target configurations from the PRD21 table as values in the table below by: 1. Select the complete rows of the target configurations in PRD21 2. Select cell A12 in the table below and right-click. 3. Select paste option "Paste as values".
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs
| Rel-16 | EN-DC FR1 | 38.101-3:Table 5.5B.4.2-1 | DC_7C_n28A-n78A | DC_7A_n28A | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | <RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest
| Rel-16 | EN-DC FR1 | 38.101-3:Table 5.5B.4.2-1 | DC_7C_n28A-n78A | DC_7A_n78A | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest
| Rel-16 | EN-DC FR1 | 38.101-3:Table 5.5B.4.2-1 | DC_7C_n28A-n78A | DC_7C_n28A | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest
| Rel-16 | EN-DC FR1 | 38.101-3:Table 5.5B.4.2-1 | DC_7C_n28A-n78A | DC_7C_n78A | Ongoing |  |  |  | Telstra | Ericsson (Leif Mattisson) | RAN5#94-e | NR_CADC_NR_LTE_DC_R16-UEConTest

## WP PC3 EN-DC FR1
Work plan for introduction of PC3 EN-DC FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
1. EN-DC configurations covered by the work plan
|  | Type of CA configurations |  |  | CA configurations [DL/UL]
FR1 EN-DC configuration(s) without UL CA
|  | FR1 EN-DC configurations with UL CA |  |  | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A
2. Overall status vs WP steps
Overall Sub-WI
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations |  |  |  |  | 100%
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 100%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3) |  |  |  |  | 100%
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6) |  |  |  |  | 100%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7) |  |  |  |  | 100%
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 100%
3. Details
The strikethrough WP items are not applicable to the type of CA configuration(s) in this Work Plan and can be ignored. You can hide not applicable WP items by filtering on excluding "-" in column H "Impacted CA config(s)". | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Bands completed | E-UTRA CA completed | TCs available
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 1-1 | Pre-requisite | PRD21 | NR band list | All NR bands completed | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in RAN5 TSs and TRs. |  | RAN5#95-e |  | NR bands n5A, n28A and n78A completed | 1 | 100% | 100%
All | 1-2 | Pre-requisite | 36.521-2 | Annex A | All E-UTRA bands completed | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Set status in column "Bands completed" to 100% when all impacted E-UTRA bands have been confirmed completed in RAN5 TSs and TRs. |  | RAN5#95-e |  | E-UTRA bands 7 completed | 1 | 100% | 100%
All | 1-3 | Pre-requisite | PRD20 | E-UTRA CA list work sheet | All E-UTRA CA configurations included in the EN-DC configurations within the WP scope are completed | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Set status in column "E-UTRA CA completed" to 100% when all E-UTRA CA configurations included in the WP scope's EN-DC configurations are listed as completed in RAN5 PRD20. |  | RAN5#95-e |  | CA_7C completed (PRD20) | 1 | 100% |  | 100%
All | 1-4 | Pre-requisite | 38.521-3 | 6, 7 | All applicable Transmitter (clause 6), Receiver (clause 7) for the type of EN-DC configuraiton completed | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Set status in column "TCs available" to 100% when all relevant test cases in 36.521-3 for the WP scope of EN-DC configuration types are completed. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. |  | RAN5#95-e |  |  | 1 | 100% |  |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
TP analysis
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
UL | 2-1 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for MOP | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For each Intra-band contiguous, intra-band non-contiguous and inter-band EN-DC band combination add TP Analysis for Maximum Output Power (MOP) in TR 38.905. The status column "TP analysis" is set to 100% when all required MOP TP analysis have been included in TR 38.905. |  | RAN5#95-e |  | Current TP analysis for inter-band MOP is general and valid for all 2-band EN-DC combos. | 1 | 100% | 100%
UL | 2-2 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for A-MPR for Intra-band contiguous and non-contiguous EN-DC band combinations | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For each Intra-band contiguous and intra-band non-contiguous EN-DC band combination add TP Analysis for A-MPR as described in TR 38.905. The status column "TP analysis" is set to 100% when all required MOP TP analysis have been included in TR 38.905. |  | RAN5#95-e |  | N/A (only EN-DC inter-band in the WP scope) | 1
All | 2-3 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for reference sensitivity | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For each inter-band EN-DC configuration perform referense sensitivity TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5#95-e | R5-220389 |  | 1 | 100% | 100%
UL | 2-4 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for general and UE co-existance spurious emission test cases for EN_DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For each two band EN_DC inter-band configuration perform general spurious emission and UE-coexistance spurious emission TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5#95-e |  | N/A (target configs are 3 band configs. | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Test Freq.
1
All | 3.1-1 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.x | NR Test frequencies | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | - Check that the involved NR bands have single carrier test frequencies specified in 4.3.1.x - For EN-DC configurations including any intra-band EN-DC contiguous CCs or any intra-band EN-DC non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in in clause clause 4.3.1.x. |  | RAN5#95-e |  | Single carrier test frequencies for the single carrier NR bands exist | 1 | 100% | 100%
All | 3.1-2 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.x | EN-DC band combination test frequencies | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For EN-DC Inter-band configurations sdd the CA configuration to the relevant table in one of the clauses in column C. |  | RAN5#95-e | R5-223649 |  | 1 | 100% | 100%
All | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.2 | Test frequencies for EN_DC signalling test | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.2. |  | RAN5#95-e |  | N/A | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Clause 5
1
All | 8 | 36.521-3 - General | 38.521-3 | 5.5B.2 | Intra-band contiguous EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Add band combinations for intra-band contiguous EN-DC to the relevant table in Column C |  | RAN5#95-e |  | N/A | 1
All | 8 | 36.521-3 - General | 38.521-3 | 5.5B.3 | Intra-band non-contiguous EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Add band combinations for intra-band non-contiguous EN-DC to the relevant table in Column C |  | RAN5#95-e |  | N/A | 1
All | 8 | 36.521-3 - General | 38.521-3 | 5.5B.4 | Inter-band EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Add inter-band EN-DC configurations within FR1 to the relevant table in column C. |  | RAN5#95-e | R5-220431 |  | 1 | 100% | 100%
UL | 9 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.4.2.3 .1 | ΔTIB,c for inter-band EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Add ΔTIB,c for inter-band EN-DC within FR1 to the relevant table in clause 6.2B.4.2.3. |  | RAN5#95-e |  | DC_7_n28-n78 already included in 38.521-3. | 1 | 100% | 100%
All | 31 | 36.521-3 - General | 38.521-3 | 7.3B.3.2 | Reference sensitivity ΔRIB,c for Intra-band non-contiguous EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band non-contiguous EN-DC configurations add ΔRIB,c for Intra-band non-contiguous EN-DC to the relevant table in column C. |  | RAN5#95-e |  | N/A | 1
All | 31 | 36.521-3 - General | 38.521-3 | 7.3B.3.3.1 | ΔRIB,c for EN-DC in two bands | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For EN-DC in two bands inter-band EN-DC configurations add ΔRIB,c in relevant table in cclause 7,3B.3.3.1 |  | RAN5#95-e |  | N/A | 1
All | 31 | 36.521-3 - General | 38.521-3 | 7.3B.3.3.2 | ΔRIB,c for EN-DC in three bands | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For EN-DC in three bands inter-band EN-DC configurations add ΔRIB,c in relevant table in cclause 7,3B.3.3.2 |  | RAN5#95-e |  | DC_7_n28-n78 already included in 38.521-3. | 1 | 100% | 100%
All | 31 | 36.521-3 - General | 38.521-3 | 7.3B.3.3.3 | ΔRIB,c for EN-DC in four bands | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For EN-DC in four bands inter-band EN-DC configurations add ΔRIB,c in relevant table in cclause 7,3B.3.3.3 |  | RAN5#95-e |  | N/A | 1
All | 31 | 36.521-3 - General | 38.521-3 | 7.3B.3.3.4 | ΔRIB,c for EN-DC in five bands | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For EN-DC in five bands inter-band EN-DC configurations add ΔRIB,c in relevant table in cclause 7,3B.3.3.4 |  | RAN5#95-e |  | N/A | 1
All | 31 | 36.521-3 - General | 38.521-3 | 7.3B.3.3.5 | ΔRIB,c for EN-DC six bands | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For EN-DC in six bands inter-band EN-DC configurations add ΔRIB,c in relevant table in cclause 7,3B.3.3.5 |  | RAN5#95-e |  | N/A | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
UL | 9 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.1.1 | UE Maximum Output Power for Intra-Band Contiguous EN-DC Note! This WP item is dependent TP analysis (Step 2, WP item 2-1) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band contiguous EN-DC configurations within FR1: Update MOP for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.2B.1.1 based on TP analysis in 38.905 (WP item 2-1). |  | RAN5#95-e |  | N/A | 1
UL | 10 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.1.2 | UE Maximum Output Power for Intra-Band Non-Contiguous EN-DC Note! This WP item is dependent TP analysis (Step 2, WP item 2-1) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band non contiguous EN-DC configurations within FR1: Update MOP for intra band non contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.2B.1.12based on TP analysis in 38.905 (WP item 2-1). |  | RAN5#95-e |  | N/A | 1
UL | 11 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.1.3 | UE Maximum Output Power for Inter-Band EN-DC within FR1 Note! This WP item is dependent TP analysis (Step 2, WP item 2-1) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Inter-band configurations within FR1: Update maximum output power for inter-band EN-DC within FR1 to the relevant table in minimum conformance requirements/initial condition/test requirements in clause 6.2B.1.3 based on TP analysis in 38.905 (WP item 2-1). |  | RAN5#95-e | R5-220759 | Covered by the two band configurations | 1 | 100% | 100% |  | 100% |  | 100%
UL | 26 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.3.1 | UE Additional Maximum Output Power reduction for Intra-band contiguous EN-DC Note! This WP item is dependent TP analysis (Step 2, WP item 2-2) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band contiguous EN-DC configurations within FR1: Update A-MPR for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.2B.3.1 based on TP analysis in 38.905 (WP item 2-2). |  | RAN5#95-e |  |  | 1
UL | 30 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.3.2 | UE Additional Maximum Output Power reduction for Intra-Band Non-Contiguous EN-DC Note! This WP item is dependent TP analysis (Step 2, WP item 2-2) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band non-contiguous EN-DC configurations within FR1: Update A-MPR for intra band non-contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of in clause 6.2B.3.2 based on TP analysis in 38.905 (WP item 2-2). |  | RAN5#95-e |  | N/A | 1
UL | 10 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.1.2 | Spurious emission band UE co-existence for intra-band contiguous EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band contiguous EN-DC configurations within FR1: Update Spurious Emission band UE co-existence for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.5B.3.1.2. |  | RAN5#95-e |  | N/A | 1
UL | 11 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.2.2 | Spurious emission band UE co-existence for intra-band non-contiguous EN-DC | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band non-contiguous EN-DC configurations within FR1: Update Spurious Emission band UE co-existence for intra band non-contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.5B.3.2.2. |  | RAN5#95-e |  | N/A | 1
UL | 26 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.3.1 | General Spurious Emissions for Inter-band EN-DC within FR1 Note! This WP item is dependent TP analysis (Step 2, WP item 2-4) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Intra-band contiguous EN-DC configurations within FR1: Update General Spurious Emissions for inter-band EN-DC within FR1 to Table 6.5B.3.3.1.5-1 in Test Requirement in clause 6.5B.3.3.1 based on TP analysis in 38.905 (WP item 2-3). |  | RAN5#95-e |  |  | 1
UL | 30 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.3.2 | Spurious emission band UE co-existence for Inter-band within FR1 Note! This WP item is dependent TP analysis (Step 2, WP item 2-4) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Inter-band configurations within FR1: Update Spurious Emission band UE co-existence for Inter-band within FR1 (intra band contiguous) to the tables in minimum conformance requirements/initial condition/test requirements in clause 6.5B.3.3.2 based on TP analysis in 38.905 (WP item 2-3). |  | RAN5#95-e |  | N/A (3 bands) | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
All | 31 | 36.521-3-RF Rx | 38.521-3 | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 (2 CCs) Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 2-3) | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | For Inter-band configurations within FR1(2 CCs): Update the tables in initial condition/test requirements for inter-band EN-DC within FR1 (2 CCs) in clause 7.3B.2.3 based on TP analysis in 38.905 (WP item 2-3). |  | RAN5#95-e | R5-220390 |  | 1 | 100% | 100% |  | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
[6 empty] | - | No changes needed |  |  |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
[6 empty] | - | No changes needed |  |  |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
All | 45 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.1 | Declaration of EN_DC configurations completion | DC_7C_n28A-n78A/DC_7A_n28A DC_7C_n28A-n78A/DC_7A_n78A DC_7C_n28A-n78A/DC_7C_n28A DC_7C_n28A-n78A/DC_7C_n78A | Add configurations for inter-band EN-DC within FR1 to the relevant table in relevant clauses A.4.3.2B.2.1~A.4.3.2B.2.5. |  | RAN5#95-e | R5-223156 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N26: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N36: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N47: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N56: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N72: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N87: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N94: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N101: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N108: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.