## Cover sheet
3GPP TSG RAN WG5 Meeting #96-e | [8 empty] | R5-224365
Electronic Meeting, August 15th - 26th, 2022
Agenda Item: | 7.4.2
Source: | Verizon
Title: | WP for HPUE_PC1_5_n77_n78-UEConTest for RAN5#95-e
Work item code: | HPUE_PC1_5_n77_n78-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The core objectives of the WI is to introduce the support of UE conformance test specifications for UE power class 1.5 smart phone and FWA devices operations on NR bands n77 and n78, based upon the parent RAN4 work item RF requirements and specifications (HPUE_PC1_5_n77_n78, RAN4)
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 86% (+36%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 85.8% (+36%)
FR1 |  | 85.8% (+36%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx | 83.3% (+43.3%) |  |  | 83.3% (+43.3%)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100%
5 References
[1] RP-221242 | UE Conformance - High-power UE (power class 1.5) operation in NR bands n77 and n78
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - High-power UE (power class 1.5) operation in NR bands n77 and n78 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | HPUE_PC1_5_n77_n78-UEConTest
WP Scope: |  | The core objectives of the WI is to introduce the support of UE conformance test specifications for UE power class 1.5 smart phone and FWA devices operations on NR bands n77 and n78, based upon the parent RAN4 work item RF requirements and specifications (HPUE_PC1_5_n77_n78, RAN4)
WP Resp: |  | Jinwen Ma |  |  | jinwen.ma@verizonwireless.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
85.8% (+36%)
11 (+3)
2 (+0.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-2: Common ICS
1 |  | 38.508-2 |  | Addition of Power Class 1.5 implementation capability for n77 and n78 | UE Power Class 1.5 added - new Table A.4.3.1-4e: NR FR1 PC1.5 RF Baseline Implementation Capabilities - Rows for NR bands n77 and n78 added | Nokia | RAN5#93 (Nov-21) | R5-216554 |  | 0.1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.521-1 Tx | 6.2.1.3 | MOP Minimum conformance requirements | Include n77 n78 PC1.5 power class and tolerance values to Table 6.2.1.3-1: UE Power Class | Verizon, Nokia | RAN5#93 (Nov-21) | R5-218478 R5-223773 R5-223777 | Impacted by NR_RF_TxD-UEConTest feature. The content has been moved to 6.2G.1. Related CRs: R5-223773, R5-223777 | 0.1 | 100% | 100% |  | 100%
2 |  | 38.521-1 Tx | 6.2.1.5 | MOP Test requirement | Include n77 n78 to Table 6.2.1.5-2b: Maximum Output Power test requirement for Power Class 1.5 | Verizon, Nokia | RAN5#93 (Nov-21) | R5-218478 R5-223773 R5-223777 | Impacted by NR_RF_TxD-UEConTest feature. The content has been moved to 6.2G.1. Related CRs: R5-223773, R5-223777 | 0.1 | 100% | 100% |  | 100%
3 |  | 38.521-1 Tx | 6.2.2.3 (6.2G.2) | MPR Minimum conformance requirements | Update for PC1.5 and include new table Table 6.2.2.3-4a Maximum power reduction (MPR) for power class 1.5 with dual Tx | Verizon, Nokia | RAN5#93 (Nov-21) | R5-218477 R5-223774 R5-223778 | Impacted by NR_RF_TxD-UEConTest feature. The content has been moved to 6.2G.2. Related CRs: R5-223774, R5-223778 | 0.1 | 100% | 100% |  | 100%
4 |  | 38.521-1 Tx | 6.2.2.5 (6.2G.2) | MPR Test requirement | Include n77 n78 into Table title: Table 6.2.2.5-4b: UE Power Class test requirements (for Band n41, n77, n78) for Power Class 1.5 (contiguous allocation) | Verizon, Nokia, Google | RAN5#96 (Aug-22) | R5-218477 R5-223774 R5-223778 R5-225753 | The following aspects are either missing or not yet determined: The test requirements updates for n77 PC1.5 UE indicating modified MPR-Behavior in Table 6.2.2.3-4a Impacted by NR_RF_TxD-UEConTest feature. The content has been moved to 6.2G.2. Related CRs: R5-223774, R5-223778 | 1 | 100% (+70%) | 100% (+70%) |  | 100%
5 |  | 38.521-1 Tx | 6.2.3.3.1 (6.2G.3) | A-MPR Minimum conformance requirements | Include NS_55 into Table 6.2.3.3.1-1: Additional maximum power reduction (A-MPR) and Table 6.2.3.3.1-1A: Mapping of Network Signalling label | Verizon, Nokia | RAN5#93 (Nov-21) | R5-223775 R5-223779 | The work item code of CR has been changed to NR_RF_FR1-UEConTest. Due to the 3GU conflict and too late to asign a new T-Doc #, this CR was withdrawn Impacted by NR_RF_TxD-UEConTest feature. The content has been moved to 6.2G.3. Related CRs: R5-223775, R5-223779 | 0
6 |  | 38.521-1 Tx | 6.2.4.3 | Configured Tx Power Minimum conformance requirements | add the configured tx power requirements |  |  |  | Configured Tx Power test case for PC1.5 n79 will be addressed in TC 6.2G.4 of "NR_RF_TxD-UEConTest" WI at RAN5#96e. | 0.1 | 0% | 0% |  | 0%
7 |  | 38.521-1 Tx | 6.2.4.4.3 | Configured Tx Power message contents | update message contents, if needed |  |  |  |  | 0.1 | 0% | 0% |  | 0%
8 |  | 38.521-1 Tx | 6.2.4.5 | Configured Tx Power; Test Requirements | update test requirements |  |  |  |  | 0.1 | 0% | 0% |  | 0%
6 9 |  | 38.521-1 Tx | 6.2D.1.5, 6.2D.2 | Maximum Output Power for UL MIMO Test Requirement | Include n77 n78 into Table 6.2D.1.5-1: UE Power Class Include PC1.5 test configuration and requirement | Google, Verizon | RAN5#96 (Aug-22) | R5-223770 R5-225754 | 38.101-1 V17.4.0 still doesn't have the PC1.5 defined in Table 6.2D.1-1: UE Power Class for UL MIMO in closed loop spatial multiplexing scheme | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
7 10 |  | 38.521-1 Tx | 6.2D.1.3 | MOP for UL MIMO Minimum Conformance Requirements | Include n77 n78 into Table 6.2D.1.3-1: UE Power Class for UL MIMO in closed loop spatial multiplexing scheme | Google, Verizon | RAN5#95 (May-22) | R5-223770 | 38.101-1 V17.4.0 still doesn't have the PC1.5 defined in Table 6.2D.1-1: UE Power Class for UL MIMO in closed loop spatial multiplexing scheme | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
1 |  | 38.522 | 4.1.1 | Addition of Power Class 1.5 into applicability of RF SA FR1 conformance test cases | Add Power Class 1.5 in applicability of RF SA FR1 conformance test cases in table 4.1.1-1 for clauses 6.2.1 – 6.2.4. | Nokia | RAN5#93 (Nov-21) | R5-218390 |  | 0.1 | 100% | 100% |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.