## Cover sheet
3GPP TSG RAN WG5 Meeting #96-e | [8 empty] | R5-224394
Electronic Meeting, August 15 - 26, 2022
Agenda Item: | 7.4.2
Source: | CMCC, T-Mobile USA
Title: | WP B41 n41 PC1.5
Work item code: | LTE_NR_B41_Bn41_PC29dBm-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to the parent WID (LTE_NR_B41_Bn41_PC29dBm, RAN4), analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. Specific updates will be to MPR, A-MPR, ACLR, A-SEM and A-Spurious. This includes enabling single component carrier UL operation (no CA) for NR n41 UE Power Class 1.5 (29 dBm) to be utilized for LTE-NR Dual Connectivity, and NR 2x2 non-coherent UL MIMO and NR 29 dBm operation with transparent transmit diversity.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 82% (+15%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 82.1% (+14.8%)
82.1% (+14.8%)
NSA Option 3 (EN-DC)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
LTE
5GS
NR RF/RRM
Common Implementation Conformance Statement (ICS) | 38.508-2 ICS | 100% |  |  | 100%
FR1 RF Tx test cases | 38.521-1 Tx | 78.3% (-0%) |  |  | 78.3% (-0%)
Applicability for RF, Demod/QSI reporting and RRM test cases | 38.522 | 100% (+100%) |  |  | 100% (+100%)
Protocol | 38.523-1 | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] R5-224396 | Revised WID - UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41and NR Band n41, T-Mobile USA, CMCC
[2] R5-214476 | Addition of Configured Tx Power Minimum Conformance Requirements for n41 Power Class 1.5, CMCC
[3] R5-214477 | Addition of MOP for UL MIMO Minimum Conformance Requirements for n41 Power Class 1.5, CMCC
[4] R5-215999 | Addition of MOP for UL MIMO Test Requirements for n41 Power Class 1.5, CMCC
[5] R5-216000 | Adding Power Class 1.5 for LTE Band 41and NR Band n41 MOP, T-Mobile USA
[6] R5-216001 | Adding Power Class 1.5 for LTE Band 41and NR Band n41 MPR, T-Mobile USA
[7] R5-216002 | Adding Power Class 1.5 for LTE Band 41and NR Band n41 A-MPR, T-Mobile USA
[8] R5-217176 | Adding Power Class 1.5 for LTE Band 41and NR Band n41 to Annex N.1 Indication of modified MPR behaviour
[9] R5-218379 | Update of PC1.5 n41 MOP test requirement
[10] R5-220210 | Addition of NR FR1 PC1.5 RF Baseline Implementation Capabilities for n41, CMCC
[11] R5-221605 | Discussion on LTE_NR_B41_Bn41_PC29dBm-UEConTest Work plan review to include dependencies with NR_RF_TxD-UEConTest work plan, Keysight Technologies
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41and NR Band n41 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status
WI code |  | LTE_NR_B41_Bn41_PC29dBm-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to the parent WID, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. Specific updates will be to MPR, A-MPR, ACLR, A-SEM and A-Spurious. This includes enabling single component carrier UL operation (no CA) for NR n41 UE Power Class 1.5 (29 dBm) to be utilized for LTE-NR Dual Connectivity, and NR 2x2 non-coherent UL MIMO and NR 29 dBm operation with transparent transmit diversity.
WP Resp: |  | Dan Song |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
82.1% (+14.8%)
[15 empty] | 29 (-5) | 0
[15 empty] | 5.3 (-0.5) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
5GS
NR RF/RRM
TS 38.508-2: Common Implementation Conformance Statement (ICS)
|  | 38.508-2 ICS |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-2 ICS | A.4.3.1 | Baseline Implementation Capabilities PC1.5 | add the ICS table entry for PC1.5 n41 | Nokia, CMCC | RAN5#96 (Aug-22) | R5-220210,R5-225685 |  | 0.2 | 100% | 100% |  |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.521-1 Tx | 6.2.1.3 | MOP Minimum conformance requirements | add the power class and toleranxe values for the band, including descriptive text after the table | T-Mobile US | RAN5#92 (Aug-21) | R5-216000 R5-218379 R5-223773 R5-223777 | MOP test case for PC1.5 n41 has been removed into 6.2G.1 by R5-223773 and R5-223777 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
3 |  | 38.521-1 Tx | 6.2.1.4.2 | MOP test procedure | update the test procedure | T-Mobile US | RAN5#92 (Aug-21) | R5-216000 R5-223773 R5-223777 | MOP test case for PC1.5 n41 has been removed into 6.2G.1 by R5-223773 and R5-223777 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
4 |  | 38.521-1 Tx | 6.2.1.4.3 | MOP message contents | update the message contents, if needed | T-Mobile US | RAN5#92 (Aug-21) | R5-216000 R5-223773 R5-223777 | MOP test case for PC1.5 n41 has been removed into 6.2G.1 by R5-223773 and R5-223777 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
5 |  | 38.521-1 Tx | 6.2.1.5 | MOP test requirement | add the test requirement for PC1.5 | T-Mobile US | RAN5#92 (Aug-21) | R5-216000 R5-223773 R5-223777 | MOP test case for PC1.5 n41 has been removed into 6.2G.1 by R5-223773 and R5-223777 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
6 |  | 38.521-1 Tx | 6.2.2.3 | MPR Minimum conformance requirements | add the MPR for dual TX |  | RAN5#92 (Aug-21) | R5-223774 R5-223778 | already done MPR test case for PC1.5 n41 has been removed into 6.2G.2 by R5-223774 and R5-223778 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
7 |  | 38.521-1 Tx | 6.2.2.4.1 | MPR initial conditions | test configuration table for PC 1.5 | T-Mobile US | RAN5#92 (Aug-21) | R5-216001 R5-223774 R5-223778 | MPR test case for PC1.5 n41 has been removed into 6.2G.2 by R5-223774 and R5-223778 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
8 |  | 38.521-1 Tx | 6.2.2.4.2 | MPR test procedure | update test procedure for PC 1.5 | T-Mobile US | RAN5#92 (Aug-21) | R5-216001 R5-223774 R5-223778 | MPR test case for PC1.5 n41 has been removed into 6.2G.2 by R5-223774 and R5-223778 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
9 |  | 38.521-1 Tx | 6.2.2.4.2 | MPR message contents | update the message contents | T-Mobile US | RAN5#92 (Aug-21) | R5-216001 R5-223774 R5-223778 | MPR test case for PC1.5 n41 has been removed into 6.2G.2 by R5-223774 and R5-223778 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
10 |  | 38.521-1 Tx | 6.2.2.4.2 | MPR test requirements | update the test requirements for PC1.5 | T-Mobile US | RAN5#92 (Aug-21) | R5-216001 R5-223774 R5-223778 | MPR test case for PC1.5 n41 has been removed into 6.2G.2 by R5-223774 and R5-223778 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
11 |  | 38.521-1 Tx | 6.2.3.3.2 | A-MPR minimum conformance requirements for NS_04 | add the A-MPR for dual TX | T-Mobile US | RAN5#92 (Aug-21) | R5-216002 R5-223775 R5-223779 R5-224397 | A-MPR test case for PC1.5 n41 has been moved into 6.2G.3 by R5-223775, R5-223779 and R5-224397 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
12 |  | 38.521-1 Tx | 6.2.3.4.1 | A-MPR test configuration for NS_04 PC1.5 | test configuration table for PC 1.5 | T-Mobile US | RAN5#92 (Aug-21) | R5-216002 R5-223775 R5-223779 | A-MPR test case for PC1.5 n41 has been moved into 6.2G.3 by R5-223775 and R5-223779 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
13 |  | 38.521-1 Tx | 6.2.3.4.2 | A-MPR test procedure | update the test procedure | T-Mobile US | RAN5#92 (Aug-21) | R5-216002 R5-223775 R5-223779 | A-MPR test case for PC1.5 n41 has been moved into 6.2G.3 by R5-223775 and R5-223779 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
14 |  | 38.521-1 Tx | 6.2.3.4.3.4 | A-MPR message contents | update message contents exceptions for network signalling value "NS_04" | T-Mobile US | RAN5#92 (Aug-21) | R5-216002 R5-223775 R5-223779 | A-MPR test case for PC1.5 n41 has been moved into 6.2G.3 by R5-223775 and R5-223779 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 100% | 100% |  |  | 100%
15 |  | 38.521-1 Tx | 6.2.3.5 | A-MPR test requirements | update test requirements for network signalling value "NS_04" PC1.5 | T-Mobile US Google | RAN5#96 (Aug-22) | R5-224285 | A-MPR test case for PC1.5 n41 has been moved into 6.2G.3 by R5-224285 under "NR_RF_TxD-UEConTest" WI. | 0.2 | 0% | 0% |  |  | 0%
16 |  | 38.521-1 Tx | 6.2.4.3 | Configured Tx Power Minimum conformance requirements | add the configured tx power requirements | CMCC | RAN5#96 (Aug-22) | R5-214476 | Configured Tx Power test case for PC1.5 n79 has been moved by "NR_RF_TxD-UEConTest" WI and will be addressed in TC 6.2G.4 of "NR_RF_TxD-UEConTest" WI at RAN5#97e. | 0.2 | 100% | 100% |  |  | 100%
17 |  | 38.521-1 Tx | 6.2.4.4.3 | Configured Tx Power message contents | update message contents, if needed | CMCC | RAN5#96 (Aug-22) |  | Configured Tx Power test case for PC1.5 n79 will be addressed in TC 6.2G.4 of "NR_RF_TxD-UEConTest" WI at RAN5#97e. | 0.2 | 0% | 0% |  |  | 0%
18 |  | 38.521-1 Tx | 6.2.4.5 | Configured Tx Power; Test Requirements | update test requirements | CMCC | RAN5#96 (Aug-22) |  | Configured Tx Power test case for PC1.5 n79 will be addressed in TC 6.2G.4 of "NR_RF_TxD-UEConTest" WI at RAN5#97e. | 0.2 | 0% | 0% |  |  | 0%
19 |  | 38.521-1 Tx | 6.2D.1.3 | MOP for UL MIMO | add the minimum conformance requirements | CMCC | RAN5#92 (Aug-21) | R5-214477 |  | 0.2 | 100% | 100% |  |  | 100%
20 |  | 38.521-1 Tx | 6.2D.1.5 | MOP for UL MIMO | add the test requirements | CMCC | RAN5#92 (Aug-21) | R5-215999 |  | 0.2 | 100% | 100% |  |  | 100%
21 |  | 38.521-1 Tx | 6.5.2.4.1.3 | NR ACLR minimum conformance requirements | minimum conformance requirement | CMCC | RAN5#92 (Aug-21) |  | already done | 0.2 | 100% | 100% |  |  | 100%
22 |  | 38.521-1 Tx | 6.5.2.4.1.4.2 | NR ACLR test procedure | update test procedure for PC 1.5 | CMCC | RAN5#96 (Aug-22) |  |  | 0.2 | 0% | 0% |  |  | 0%
23 |  | 38.521-1 Tx | 6.5.2.4.1.4.3 | NR ACLR message contents | update message contents for PC 1.5 | CMCC | RAN5#96 (Aug-22) |  |  | 0.2 | 0% | 0% |  |  | 0%
24 |  | 38.521-1 Tx | 6.5.2.4.1.5 | NR ACLR test requirement | update test requirement for PC1.5 | CMCC | RAN5#92 (Aug-21) | R5-214479 |  | 0.2 | 100% | 100% |  |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0
25 |  | 38.522 | 4 | Test case conditions and selection criteria | set the conditions and selection criteria |  | RAN5#95 (May-22) | R5-223783 | R5-223783 has been submitted under "NR_RF_TxD-UEConTest" WI. | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
26 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the updated test cases introduced for 38.521-1 & 38.521-3. |  | RAN5#95 (May-22) | R5-223783 | R5-223783 has been submitted under "NR_RF_TxD-UEConTest" WI. | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TS 38.523-1: Protocol
|  | 38.523-1 | <Clause> | <Title> |  |  | TBD |  |  | 0
27 |  | 38.523-1 | 8.1.5.1.1 | Update RRC UE capability for PC1.5 duty cycle | Add UE capability “maxUplinkDutyCycle-PC1dot5-MPE-FR1-r16” |  | RAN5#96 (Aug-22) | R5-225323 | 2pc_nrBandx_maxUplinkDutyCycle_PC1dot5_MPE_FR1_r16 and Table A.4.3.1-4h to be added into TS 38.508 by R5-224209 | 0.1 | 100% | 100% |  |  | 100%
28 |  | 38.523-1 | 8.2.1.1.1 | Update RRC UE capability for PC1.5 duty cycle | Add UE capability “maxUplinkDutyCycle-PC1dot5-MPE-FR1-r16” |  | RAN5#96 (Aug-22) | R5-225323 | 2pc_nrBandx_maxUplinkDutyCycle_PC1dot5_MPE_FR1_r16 and Table A.4.3.1-4h to be added into TS 38.508 by R5-224209 | 0.1 | 100% | 100% |  |  | 100%
29 |  | 38.523-1 | 8.2.1.1.2 | Update RRC UE capability for PC1.5 duty cycle | Add UE capability “maxUplinkDutyCycle-PC1dot5-MPE-FR1-r16” |  | RAN5#96 (Aug-22) | R5-225323 | 2pc_nrBandx_maxUplinkDutyCycle_PC1dot5_MPE_FR1_r16 and Table A.4.3.1-4h to be added into TS 38.508 by R5-224209 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
0.1
TS 38.523-2: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.523-2 | <Clause> | <Title> |  |  | TBD |  |  | 0.1
0.1
0.1
TS 38.523-3: Protocol Test Suites
|  | 38.523-3 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.