## Cover sheet
3GPP TSG-RAN WG5 Meeting #96-e | [10 empty] | R5-224423
Electronic Meeting, 15th Aug - 26th Aug 2022
Agenda Item: | 7.4.2
Source: | CATT
Title: | WP UE Conformance Test Aspects - NR Uplink Data Compression (UDC)
Work item code: | NR_UDC-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
At the RAN#96-e meeting a Rel-17 RAN5 work item for NR Uplink Data Compression(NR_UDC-UEConTest) was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 7% (+7%) | 0 | 11 (+11)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 6.7% (+6.7%) | 0 | 11 (+11)
FR1 |  | 6.7% (+6.7%) | 0 | 11 (+11)
FR2 |  | 6.7% (+6.7%) | 0 | 11 (+11)
FR1 + FR2 |  | 6.7% (+6.7%) | 0 | 11 (+11)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0% |  |  | 0%
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 11 (+11) | 0% | 0 | 11 (+11) | 0% | 0 | 11 (+11) | 0% | 0 | 11 (+11)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-221449 | New WID on UE Conformance - NR Uplink Data Compression (UDC)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - NR Uplink Data Compression (UDC) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_UDC-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects - NR Uplink Compression comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Huiying Zhang, CATT |  |  | zhanghuiying@catt.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 6.7% (+6.7%) | 6.7% (+6.7%) | 6.7% (+6.7%)
[14 empty] | 15 (+15) | 15 (+15) | 15 (+15)
[14 empty] | 11.5 (+11.5) | 11.5 (+11.5) | 11.5 (+11.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | 4 | Common test environments | Definition of common test environment for Uplink Data Compression | CATT | RAN5#96 (Aug-22) | R5-225358 |  | 0.2 | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | A.4 | Common Implementation Conformance Statement (ICS) proforma | Introduction of common implementation conformance statement (ICS) for Uplink Data Compression |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
TBD |  | 38.523-1 | 7.1.3.6 | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 38.523-1 | 7.1.3.6.1 | PDCP UDC / No dictionary | To verify that UE correctly transmits PDCP PDU using UDC with pre-defined dictionary is not configured |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.2 | PDCP UDC / Pre-defined dictionary | To verify that UE correctly transmits PDCP PDU using UDC with pre-defined dictionary is configured |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.3 | PDCP UDC / checksum error / Reset | To verify that UE performs the reset procedure when receiving the UDC checksum error notification |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.4 | PDCP UDC/ Handover/ Intra-frequency | 1.To verify that UE resets UDC configuration when it performs Intra-frequency handover and drb-ContinueUDC was not configured. 2.To verify that UE continues UDC configuration when it performs Intra-frequency handover and drb-ContinueUDC was configured. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.5 | PDCP UDC/ Handover/ Inter-frequency | 1.To verify that UE resets UDC configuration when it performs Inter-frequency handover and drb-ContinueUDC was not configured. 2.To verify that UE continues UDC configuration when it performs Inter-frequency handover and drb-ContinueUDC was configured. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.6 | PDCP UDC/ RRC resume | 1. To verify that UE resets configured UDC when RRC resume and drb-ContinueUDC was not configured. 2. To verify that UE continues configured UDC when RRC resume and drb-ContinueUDC was configured. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.7 | PDCP UDC/ RRC reestablishment | 1. To verify that UE resets configured UDC when RRC reestablishment and drb-ContinueUDC was not configured. 2. To verify that UE continues configured UDC when RRC reestablishment and drb-ContinueUDC was configured. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.8 | PDCP UDC/ PSCell addition / SCG DRB with UDC configuration/ NR-DC | To verify that UE configures NR SCG DRB with UDC when it receives an RRCReconfiguration message to add an NR SCG DRB with UDC |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.9 | PDCP UDC/ PSCell addition / SCG DRB with UDC configuration/ NE-DC | To verify that UE configures E-UTRA SCG DRB with UDC when it receives an RRCReconfiguration message to add an E-UTRA SCG DRB with UDC |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.10 | PDCP UDC/ PSCell addition / Split DRB with UDC configuration/ NR-DC | To verify that UE configures NR Split DRB with UDC when it receives an RRCReconfiguration message to add an NR Split DRB with UDC |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TBD | Y | 38.523-1 | 7.1.3.6.11 | PDCP UDC/ PSCell addition / Split DRB with UDC configuration/ NE-DC | To verify that UE configures E-UTRA Split DRB with UDC when it receives an RRCReconfiguration message to add an E-UTRA Split DRB with UDC |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | 4.1 | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0% | 0%
TBD |  | 38.523-2 | 4.2 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.