## Cover sheet
RAN5 meeting #96e | [8 empty] | R5-224798
Electronic Meeting, 15th Aug 2022 – 26th Aug 2022
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Work item code: | NR_NTN_solutions_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 26
Completion Compensation |  | 6.939e-16%
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5% | 0 | 26
FR1 |  | 5% | 0 | 26
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0%
UE specific testing functions | 38.509
Conducted RF Transmitter Test cases | 38.101-5
5 References
[1] RP-221299 | New WID on UE Conformance - Further enhancement on NR demodulation performance
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance- Solutions for NR to support non-terrestrial networks (NTN) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_NTN_solutions_plus_CT-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for Solutions for NR to support non-terrestrial networks (NTN) Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
5%
51
36.1
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 5 | Introduction of General and RF Demod Test Environment for Rel17 NTN solutions | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-17 NTN solutions | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.509: UE specific testing functions
|  | 38.509 | TBD | TBD | [5 empty] | 1
TS 38.521-5: Conducted RF Transmitter Test cases
3 |  | 38.521-5 | 4 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
4 |  | 38.521-5 | 5 | Operating bands and channel arrangement |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
5 |  | 38.521-5 | 5.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
6 |  | 38.521-5 | 5.2 | Operating bands |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
7 |  | 38.521-5 | 5.3 | UE Channel Bandwidth |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
8 |  | 38.521-5 | 5.4 | Channel arrangment |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
9 |  | 38.521-5 | 6 | Conducted Transmitter characteristics |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
10 |  | 38.521-5 | 6.1 | General | [5 empty] | 0.5 | 0% | 0% |  | 0%
11 |  | 38.521-5 | 6.2 | Transmitter Power | [5 empty] | 0.5 | 0% | 0% |  | 0%
12 | Y | 38.521-5 | 6.2.1 | UE maximum output power | [5 empty] | 1 | 0% | 0% |  | 0%
13 | Y | 38.521-5 | 6.2.2 | UE maximum output power reduction | [5 empty] | 1 | 0% | 0% |  | 0%
14 | Y | 38.521-5 | 6.2.3 | UE additional maximum output power reduction | [5 empty] | 1 | 0% | 0% |  | 0%
15 | Y | 38.521-5 | 6.2.4 | Configured transmitted power | [5 empty] | 1 | 0% | 0% |  | 0%
16 |  | 38.521-5 | 6.3 | Output power dynamics | [9 empty] | 0%
17 | Y | 38.521-5 | 6.3.1 | Minimum output power | [5 empty] | 1 | 0% | 0% |  | 0%
18 | Y | 38.521-5 | 6.3.2 | Transmit off power | [5 empty] | 1 | 0% | 0% |  | 0%
19 | Y | 38.521-5 | 6.3.3 | Transmit on/off time mask | [5 empty] | 1 | 0% | 0% |  | 0%
20 | Y | 38.521-5 | 6.3.4 | Power control | [5 empty] | 1 | 0% | 0% |  | 0%
21 |  | 38.521-5 | 6.4 | Transmit signal quality | [9 empty] | 0%
22 | Y | 38.521-5 | 6.4.1 | Frequency error | [5 empty] | 1 | 0% | 0% |  | 0%
23 | Y | 38.521-5 | 6.4.2 | Transmit modulation quality | [5 empty] | 1 | 0% | 0% |  | 0%
24 |  | 38.521-5 | 6.5 | Output RF spectrum emissions | [9 empty] | 0%
25 | Y | 38.521-5 | 6.5.1 | Occupied Bandwidth | [5 empty] | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-5 | 6.5.2 | Out of band emissions | [9 empty] | 0%
27 |  | 38.521-5 | 6.5.2.1 | General | [5 empty] | 0.2 | 0% | 0% |  | 0%
28 | Y | 38.521-5 | 6.5.2.2 | Spectrum emission mask | [5 empty] | 1 | 0% | 0% |  | 0%
29 | Y | 38.521-5 | 6.5.2.4 | Adjacent channel leakage ratio | [5 empty] | 1 | 0% | 0% |  | 0%
30 |  | 38.521-5 | 6.5.3 | Spurious emission | [9 empty] | 0%
31 | Y | 38.521-5 | 6.5.3.1 | General spurious emission | [5 empty] | 1 | 0% | 0% |  | 0%
32 | Y | 38.521-5 | 6.5.3.2 | Spurious emissions for UE co-existence | [5 empty] | 1 | 0% | 0% |  | 0%
33 | Y | 38.521-5 | 6.5.3.3 | Additional spurious emissions | [5 empty] | 1 | 0% | 0% |  | 0%
34 | Y | 38.521-5 | 6.5.4 | Transmit intermodulation | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.521-5: Conducted RF Receiver Test cases
35 |  | 38.521-5 | 7.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
36 |  | 38.521-5 | 7.2 | Diversity Characteristics |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
37 |  | 38.521-5 | 7.3 | Reference sensitivity |  |  | RAN5#97 (Nov-22) | [6 empty] | 0%
38 |  | 38.521-5 | 7.3.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.2 | 0% | 0% |  | 0%
39 | Y | 38.521-5 | 7.3.2 | Reference sensitivity power level | [5 empty] | 1 | 0% | 0% |  | 0%
40 | Y | 38.521-5 | 7.4 | Maximum input level | [5 empty] | 1 | 0% | 0% |  | 0%
41 | Y | 38.521-5 | 7.5 | Adjacent channel selectivity | [5 empty] | 1 | 0% | 0% |  | 0%
42 |  | 38.521-5 | 7.6 | Blocking characteristics | [9 empty] | 0%
43 |  | 38.521-5 | 7.6.1 | General | [5 empty] | 0.2 | 0% | 0% |  | 0%
44 | Y | 38.521-5 | 7.6.2 | In-band blocking | [5 empty] | 1 | 0% | 0% |  | 0%
45 | Y | 38.521-5 | 7.6.3 | Out-of-band blocking | [5 empty] | 1 | 0% | 0% |  | 0%
45 | Y | 38.521-5 | 7.6.4 | Narrow band blocing | [5 empty] | 1 | 0% | 0% |  | 0%
46 | Y | 38.521-5 | 7.7 | Spurious response | [5 empty] | 1 | 0% | 0% |  | 0%
47 | Y | 38.521-5 | 7.8 | Intermodulation characteristics | [5 empty] | 1 | 0% | 0% |  | 0%
48 | Y | 38.521-5 | 7.9 | Spurious emissions | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.521-5: Annex
|  | 38.521-5 |  | Placeholder | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF Transmitter and Receiver Test cases
|  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-5 | [5 empty] | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.