## Cover sheet
3GPP TSG RAN WG5#96-e | [8 empty] | R5-224993
<Electronic meeting, 15th - 26th Aug 2022>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | UE Conformance - 4Rx support for NR band n8
Work item code: | NR_4Rx_Bn8_FWA-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
The objective of the UE Conformance - 4Rx support for NR band n8 work item is to define the UE conformance requirements, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications in Rel-17. At the RAN#96 meeting the Rel-17 RAN5 work item for UE Conformance - 4Rx support for NR band n8 was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+100%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 100% (+100%)
FR1 |  | 100% (+100%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%)
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx | 100% (+100%) |  |  | 100% (+100%)
5 References
1] RP-221159 | WID on UE Conformance - 4Rx support for NR band n8 for RAN#96e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP on UE Conformance - 4Rx support for NR band n8 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_4Rx_Bn8_FWA-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - 4Rx support for NR band n8 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID)
WP Resp: |  | Yu Shi, China Unicom |  |  | shiyu19@chinaunicom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
100% (+100%)
2 (+2)
2 (+2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-2: Common ICS
TBD |  | 38.508-2 | ICS proforma tables | RF baseline implementation capabilities for R17 4Rx UE on n8 | Introduction of common implementation conformance statement (ICS) for R17 4Rx UE on n8 | China Unicom | RAN5#96 (Aug-22) |  | R5-225055 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Rx
TBD |  | 38.521-1 Rx | 7.3 | Reference sensitivity for R17 4Rx UE on n8 | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions for R17 4Rx UE on n8 | China Unicom | RAN5#95 (May-22) |  | R5-225058 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.