## Cover sheet
3GPP TSG-RAN WG5 Meeting #96-e | [8 empty] | R5-225026
Electronic Meeting, 15th - 26th Aug. 2022
Agenda Item: | 7.4.2
Source: | Apple, Rohde & Schwarz, Vivo
Title: | UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC)
Work item code: | NR_FR1_TRP_TRS-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work plan is to track contributions towards the RAN5 test specifications enable UE conformance testing for the corresponding R17 NR FR1 TRP TRS Work Items
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 8
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5% | 0 | 6
FR1 |  | 5% | 0 | 6
NSA Option 3 (EN-DC) |  | 5% | 0 | 6
FR1 |  | 5% | 0 | 6
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
NR RF TRP and TRS requirements and test methodologies for FR1 (SA and EN-DC)
TS 38.561:Common Clauses 1-5 | 38.561
TS 38.561 Clause 6 - FR1 Tx: FR1 Transmitter (TRP) Performance | 38.561 | 0% | 0 | 4 | 0% |  | 4 |  |  | 0% |  | 4
TS 38.561 Clause 7 - FR1 Rx: FR1 Receiver (TRS) Performance | 38.561 |  | 0 | 4 |  |  | 4 |  |  |  |  | 4
TS 38.561 Annexes | 38.561
5 References
[1] RP-221690 | New WID on UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_FR1_TRP_TRS-UEConTest
WP Scope: |  | The purpose of this document is to create and track development of test requirements and procedures for FR1 OTA (TRP/TRS) for Standalone and EN-DC
WP Resp: |  | Ashwin Mohan, Jose Fortes, Ruixin Wang |  |  | ashwin_mohan@apple.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | Ashwin Mohan |  |  | ashwin_mohan@apple.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 5% | 5%
[15 empty] | 42 | 42
[15 empty] | 25.3 | 25.3
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
NR RF TRP and TRS requirements and test methodologies for FR1 (SA and EN-DC)
TS 38.561: Scope, References, Definitions, Frequency Bands
1 |  | 38.561 | 1 | Scope |  | Apple | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
2 |  | 38.561 | 2 | References |  |  | RAN5#97 (Nov-22) |  |  | 0.2 | 0% | 0% | 0% |  | 0% | 0%
3 |  | 38.561 | 3 | Definition of terms, symbols and abbreviations |  |  | RAN5#97 (Nov-22) |  |  | 0.2 | 0% | 0% | 0% |  | 0% | 0%
TS 38.561: General Information Clause
4 |  | 38.561 | 4 | General | Relationship between minimum conformance requirements and test requirements, Applicability Rules | Apple | RAN5#97 (Nov-22) |  |  | 0.7 | 0% | 0% | 0% |  | 0% | 0%
5 |  | 38.561 | 5 | Frequency Bands | Clause Header
6 |  | 38.561 | 5.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.7 | 0% | 0% | 0% |  | 0% | 0%
7 |  | 38.561 | 5.2 | Operating Bands | SA FR1 bands and EN-DC FR1 combinations |  | RAN5#98 (Feb-23) |  |  | 0.7 | 0% | 0% | 0% |  | 0% | 0%
TS 38.561 FR1 Tx: FR1 Transmitter (TRP) Performance
8 |  | 38.561 FR1 Tx | 6 | FR1 Transmitter TRP Performance | Clause Header |  |  |  | TC owner completes headers and introduction
9 |  | 38.561 FR1 Tx | 6.1 | General | Introductory Description |  |  |  | TC owner completes headers and introduction | 0.1 | 0% | 0% | 0% |  | 0% | 0%
10 |  | 38.561 FR1 Tx | 6.2 | TRP Performance for Handheld UE |  |  |  |  | TC owner completes headers and introduction | 0.1 | 0% | 0% | 0% |  | 0% | 0%
11 |  | 38.561 FR1 Tx | 6.2.1 | TRP Performance for Handheld UE for FR1 (NR SA and EN-DC) |  |  |  |  | TC owner completes headers and introduction | 0.1 | 0% | 0% | 0% |  | 0% | 0%
12 |  | 38.561 FR1 Tx | 6.2.1.1 | Total Radiated Power (TRP) in Browsing Mode with Hand Phantom |  |  |  |  | Includes full test structure including Test Requirements | 0.5 | 0% | 0% | 0% |  | 0% | 0%
13 | Y | 38.561 FR1 Tx | 6.2.1.1.1 | Total Radiated Power (TRP) for FR1 NR Standalone (SA) in Browsing Mode with Hand Phantom |  | Apple | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
14 | Y | 38.561 FR1 Tx | 6.2.1.1.2 | Total Radiated Power (TRP) for FR1 NR EN-DC in Browsing Mode with Hand Phantom |  | Apple | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
15 |  | 38.561 FR1 Tx | 6.2.1.2 | Total Radiated Power (TRP) with Beside the head and hand phantom |  |  | RAN5#99 (May-23) |  | Includes full test structure including Test Requirements | 0.5 | 0% | 0% | 0% |  | 0% | 0%
16 | Y | 38.561 FR1 Tx | 6.2.1.2.1 | Total Radiated Power (TRP) for FR1 NR Standalone (SA) with Beside the head and hand phantom |  | Apple | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0%
17 | Y | 38.561 FR1 Tx | 6.2.1.2.2 | Total Radiated Power (TRP) for FR1 NR EN-DC with Beside the head and hand phantom |  | Apple | RAN5#101 (Nov-23) |  |  | 1 | 0% |  | 0% |  |  | 0%
TS 38.561 FR1 Rx: FR1 Receiver (TRS) Performance
18 |  | 38.561 FR1 Rx | 7 | FR1 Receiver TRS Performance | Clause Header |  |  |  | TC owner completes headers and introduction
19 |  | 38.561 FR1 Rx | 7.1 | General | Introductory Description |  |  |  | TC owner completes headers and introduction | 0.5 | 0% | 0% | 0% |  | 0% | 0%
20 |  | 38.561 FR1 Rx | 7.2 | Total Radiated Sensitivity (TRS) Performance for Handheld UE |  |  |  |  | TC owner completes headers and introduction | 0.2 | 0% | 0% | 0% |  | 0% | 0%
21 |  | 38.561 FR1 Rx | 7.2.1 | Total Radiated Sensitivity (TRS) Performance for Handheld UE for FR1 (NR SA and EN-DC) |  |  |  |  | TC owner completes headers and introduction | 0.2 | 0% | 0% | 0% |  | 0% | 0%
22 |  | 38.561 FR1 Rx | 7.2.1.1 | Total Radiated Sensitivity (TRS) in Browsing Mode with Hand Phantom |  | Apple, Vivo | RAN5#99 (May-23) |  | Includes full test structure including Test Requirements | 0.5 | 0% | 0% | 0% |  | 0% | 0%
23 | Y | 38.561 FR1 Rx | 7.2.1.1.1 | Total Radiated Sensitivity (TRS) for FR1 NR Standalone (SA) in Browsing Mode with Hand Phantom |  | Apple, Vivo | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
24 | Y | 38.561 FR1 Rx | 7.2.1.1.2 | Total Radiated Sensitivity (TRS) for FR1 NR EN-DC in Browsing Mode with Hand Phantom |  | Apple, Vivo | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
25 |  | 38.561 FR1 Rx | 7.2.1.2 | Total Radiated Sensitivity (TRS) with Beside the head and hand phantom |  |  |  |  | Includes full test structure including Test Requirements | 0.2 | 0% | 0% | 0% |  | 0% | 0%
26 | Y | 38.561 FR1 Rx | 7.2.1.2.1 | Total Radiated Sensitivity (TRS) for FR1 NR Standalone (SA) with Beside the head and hand phantom |  | Vivo | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  |  | 0%
27 | Y | 38.561 FR1 Rx | 7.2.1.2.2 | Total Radiated Sensitivity (TRS) for FR1 NR EN-DC with Beside the head and hand phantom |  | Vivo | RAN5#101 (Nov-23) |  |  | 1 | 0% |  | 0% |  |  | 0%
38.561 Annex A : Test Methodology
28 |  | 38.561 Annex A | Annex A.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
29 |  | 38.561 Annex A | Annex A.2 | UE Configuration |  |  | RAN5#98 (Feb-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
30 |  | 38.561 Annex A | Annex A.3 | Test System - Anechoic Chamber Method | Add additional granurality from TR 38.834 after review | Apple | RAN5#98 (Feb-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
31 |  | 38.561 Annex A | Annex A.4 | Measurement Uncertainty of Test System and Test Tolerances | Annex Header |  |  |  | Clause owner(s) completes headers and introduction | 1 | 0% | 0% | 0% |  | 0% | 0%
32 |  | 38.561 Annex A | Annex A.4.1 | General | Definitions and description of section | R&S | RAN5#100 (Aug-23) |  |  | 0.5 |  | 0% | 0% |  | 0% | 0%
33 |  | 38.561 Annex A | Annex A.4.2 | Measurement Uncertainty of Test System | MU of Conformance Test System for FR1 TRP/TRS | R&S | RAN5#100 (Aug-23) |  |  | 1 |  | 0% | 0% |  | 0% | 0%
34 |  | 38.561 Annex A | Annex A.4.3 | Test Tolerances | TT across defined conformance tests for FR1 (SA and EN-DC) TRP and TRS | Apple | RAN5#101 (Nov-23) |  | Will be listed within the test case clause as well. This section is placeholder for summary within Annex | 1 |  | 0% | 0% |  | 0% | 0%
38.561 Annex B : Phantom Definitions and Positioning
35 |  | 38.561 Annex B | Annex B.1 | General |  |  | RAN5#98 (Feb-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
36 |  | 38.561 Annex B | Annex B.2 | Phantom Definitions |  |  | RAN5#98 (Feb-23) |  | Aligns with TR 38.834 and TS 38.161 | 1 | 0% | 0% | 0% |  | 0% | 0%
37 |  | 38.561 Annex B | Annex B.3 | UE positioning guidelines |  | Apple | RAN5#98 (Feb-23) |  | Aligns with TR 38.834 and TS 38.161 | 1 | 0% | 0% | 0% |  | 0% | 0%
38.561 Annex C : Environmental Requirements
38 |  | 38.561 Annex C | Annex C.1 | General |  |  | RAN5#98 (Feb-23) |  | Aligns with TR 38.834 and TS 38.161 | 1 | 0% | 0% | 0% |  | 0% | 0%
39 |  | 38.561 Annex C | Annex C.2 | Environmental |  |  | RAN5#98 (Feb-23) |  | Aligns with TR 38.834 and TS 38.161 | 1 | 0% | 0% | 0% |  | 0% | 0%
38.561 Annex D: Test Point analysis for FR1 (SA and EN-DC) TRP and TRS test cases
40 |  | 38.561 Annex D | Annex D.1 | Placeholder for FR1 SA TRP test point analysis |  | Apple | RAN5#100 (Aug-23) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
41 |  | 38.561 Annex D | Annex D.2 | Placeholder for FR1 SA TRS test point analysis |  | Apple | RAN5#100 (Aug-23) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
42 |  | 38.561 Annex D | Annex D.3 | Placeholder for FR1 EN-DC TRP test point analysis |  | Apple | RAN5#101 (Nov-23) |  |  | 0.5 |  |  |  |  | 0% | 0%
43 |  | 38.561 Annex D | Annex D.4 | Placeholder for FR1 EN-DC TRS test point analysis |  | Apple | RAN5#101 (Nov-23) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
38.561 Annex E: Test Case Applicability for FR1 (SA and EN-DC) TRP and TRS test cases
44 |  | 38.561 Annex E | Annex D.1 | Placeholder for FR1 SA TRP test case applicability |  | Vivo | RAN5#100 (Aug-23) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
45 |  | 38.561 Annex E | Annex D.2 | Placeholder for FR1 SA TRS test case applicability |  | Vivo | RAN5#100 (Aug-23) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
46 |  | 38.561 Annex E | Annex D.3 | Placeholder for FR1 EN-DC test case applicability |  | Vivo | RAN5#101 (Nov-23) |  |  | 0.1 |  |  |  |  | 0% | 0%
47 |  | 38.561 Annex E | Annex D.4 | Placeholder for FR1 EN-DC test case applicability |  | Vivo | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.