## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: SS: System Simulator
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-15:
    Endorsed clarification of NR ASP PdcpCount.
    Endorsed new test method for NR processing delay testing of RRC procedures with RACH.
    RRC connection re-establishment procedure: endorsed TTCN test sequence updates.
  Rel-16:
    NR IIoT: endorsed NR ASP updates for multiple DL SPS / multiple UL CG.
    NR IIoT: endorsed new test model and NR ASP updates for EHC.
    NR URLLC enh.: endorsed test model and NR ASP updates for PUSCH repetition type B.
    NR IMS eCall: endorsed new test model for NR/GERAN Inter-RAT.
  Prose CRs to TS 38.523-3 proposed at RAN5#96-e for the above.
Test Models – POS:
  Rel-16 NR positioning: endorsed test model & NR ASP updates for posSIBs broadcast.
  Prose CR to TS 38.523-3 proposed at RAN5#96-e for the above.
Test models & ASPs design Progress at TTCN Workshop #58 (6th Jul’22)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – LTE:
  IIoT: endorsed new test model and E-UTRA ASP updates for EHC.
  Prose CR to TS 36.523-3 proposed at RAN5#96-e for the above.
Test Models – WLAN:
  Endorsed correction to the definition of BeaconRSSI.
Test Models – MCX:
  Endorsed updates to absolute URL from MC Client in KMSInit and KeyProv.
  Endorsed various updates affecting MCPTT, MCVideo and MCData.
  Prose CRs to TS 36.579-x proposed at RAN5#96-e for the above.
Test models & ASPs design Progress at TTCN Workshop #58 (6th Jul’22)

## Slide 5: TTCN development Progress for period: Jun to Aug’22
Completed:
  5GS Rel-16:
    NR/5GC RACS
  LTE Rel-16:
    E-UTRA/EPS RACS
  IMS over NR/5GC:
    Supplementary services
Progressed:
  5GS Rel-15:
    NR/5GC single carrier
    NR/5GC NE-DC
  5GS Rel-16:
    5G private network
    NR IIoT
    NR SON/MDT
    NR UE power saving
  IMS over NR/5GC:
    IMS emergency
Started:
  5GS Rel-16:
    5G V2X
  IMS over NR/5GC:
    IMS eCall
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 4th May --> 10th Aug’22
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 90 / 102 | +1 | +1 under verification
NR/5GC access stratum | Rel-15 | 503 | 144 / 158 | = | Prio1: 88/96 ; Prio2: 56/62 +1 under verification
NR/5GC NR-DC | Rel-15 | 503 | 9 / 13 | = | Prio1: 8/11 ; Prio2: 1/2
NR/5GC NAS | Rel-15 | 504 | 70 / 73 | +1 | Prio1: 32/32 ; Prio2: 38/41
NR/5GC NR CA | Rel-15 | 510 | 30 / 32 | +3 | Prio1: 14/15 ; Prio2: 16/17
EN-DC NR CA | Rel-15 | 512 | 9 / 17 | = | Prio1: 9/13 ; Prio2: 0/4
Intra-NR SON/MDT | Rel-16 | 517_A | 27 / 31 | +1 | Prio1: 22/24 ; Prio2: 5/7 +3 under verification
NR RACS | Rel-16 | 520 | 4 / 8 | = | +1 under verification
NR mobility enhancements | Rel-16 | 522 | 4 / 10 | +2 | 
5G network slicing enhancements | Rel-16 | 523 | 3 / 5 | = | +1 under verification
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 4th May --> 10th Aug’22
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
VoLTE (GSMA IR.92) | Rel-8 | WI-103 | 45 / 51 | = | 
SMS over IMS | Rel-8 | WI-128 | 2 / 5 | = | 
IMS emergency over LTE | Rel-9 | WI-154 | 31 / 35 | = | 
LTE positioning | Rel-9+ | WI-166 | 15 / 27 | +1 | 
VoWiFi (GSMA IR.51) | Rel-11 | WI-267 | 18 / 22 | = | Prio1: 5/9 ; Prio2: 13/13
VoLTE over CAT-M1 (GSMA NG.108) | Rel-13 | WI-283 | 10 / 11 | = | Left: TC J.15.5(TIR)
SMS over CAT-M1 (GSMA NG.108) | Rel-13 | WI-128M | 1 / 2 | = | Left: TC J.18.1(MO SMS)
MCPTT over LTE | Rel-14 | WI-288, RFT-153 | 36 / 51 | +1 | Prio1: 31/42 ; Prio2: 5/9 +2 under verification
IMS eCall over LTE | Rel-14 | WI-298 | 5 / 12 | = | 
IMS over NR/5GC | Rel-15 | 505 | 83 / 96 | +25 | Prio1: 21/21 ; Prio2: 62/75 +2 under verification
5G Positioning | Rel-15 | 506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 4th May --> 10th Aug’22
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | WI-088 | 13 / 14 | = | Left: TC 8.4.5.4(LTE to HRPD HO)
LTE/UMTS Inter-RAT | Rel-9 | WI-167 | 11 / 12 | = | Left: TC 13.1.21(emergency call)
LTE/GERAN Inter-RAT | Rel-9 | WI-168 | 3 / 4 | = | Left: TC 13.1.21(emergency call)
LTE/C2K Inter-RAT | Rel-10 | WI-180 | 1 / 2 | = | Left: TC 8.6.5.3(MDT RLF logging)
LTE/GERAN Inter-RAT | Rel-10 | WI-182/184 | 1 / 2 | = | Left: TC 8.6.5.2(MDT RLF logging)
CA intra-band contiguous | Rel-11 | WI-162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | WI-245 | 6 / 9 | = | 
eDRX | Rel-13 | WI-253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | WI-254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | WI-254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | WI-257 | 71 / 73 | = | Left: TCs 22.1.1.M2, 22.4.26
LAA | Rel-13 | WI-272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | WI-295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
L2 latency reduction | Rel-14 | WI-306 | 1 / 4 | = | 
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 4th May --> 10th Aug’22
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
MCData over LTE | Rel-14 | WI-329 | 0 / 28 |  | +4 under verification
MCPTT enh. over LTE | Rel-15 | WI-330 | 0 / 22 |  | +3 under verification
Inter-RAT handover from NR/5GC to EN-DC | Rel-16 | 516_HO | 0 / 1 |  | +1 under verification
5G private network | Rel-16 | 519 | 0 / 6 |  | +5 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 10
2021 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of Aug’22) / Comments
MCX: PTT, Video, Data | Rel-14 | L | Q3’20 | 106 | Q3’17-Q4’22 | 4 | 73% (@iwd-22wk12)
LTE CA band combinations | R15to16 | L | Q4’22 | n/a | Q1’19-Q4’22 | 0.1 | 43% (@iwd-22wk23)
MTC (even) further enhanced | R14to15 | L | Q4’21 | 18 | Q1’18-Q4’22 | 1 | 11% (@iwd-21wk49)
NB-IoT further enhanced | Rel-15 | L | Q3’21 | 8 | Q2’20-Q3’22 | 0.5 | 60% (@iwd-21wk49)
MCX enhancements | Rel-15 | L | Q2’22 | 70 | Q3’21-Q4’22 | 6 | 34% (@iwd-22wk12)
LTE mobility even further enhancements | Rel-16 | L | Q2’22 | 12 | Q4’20-Q4’22 | 1 | Not started
5GS: NR/5GC (option 2) | Rel-15 | N,L | Q3’22 | 449 | Q3’18-Q3’22 | 1 | 98.6% (@iwd-22wk23)
UE RACS optimisations | Rel-16 | N,L | Q1’22 | 17 | Q4’20-Q2’22 | 1 | 100% (@iwd-22wk23)
NR UE power saving | Rel-16 | N | Q3’22 | 9 | Q4’20-Q3’22 | 0.5 | 80% (@iwd-22wk23)
NR industrial IoT | Rel-16 | N,L | Q1’22 | 7 | Q4’20-Q4’22 | 1 | 50% (@iwd-22wk23)
5G V2X with NR sidelink | Rel-16 | N,L | Q4’22 | 74 | Q4’20-Q1’23 | 6 | 10% (@iwd-22wk23)
5G private network | Rel-16 | N | Q4’22 | >14 | Q4’20-Q4’22 | 0.8 | 70% (@iwd-22wk23)
NR mobility enhancements | Rel-16 | N | Q2’22 | 13 | Q4’20-Q1’22 | 0.5 | 100% (@iwd-22wk12)
NR SON & MDT | Rel-16 | NLWB | Q2’22 | 47 | Q1’21-Q4’22 | 1 | 91% (@iwd-22wk23)
NR URLLC phy layer enhancements | Rel-16 | N | Q4’22 | 10 | Q2’21-Q4’22 | 1 | 40% (@iwd-22wk12)
NW slicing enhancements | Rel-16 | N | Q4’21 | 5 | Q3’21-Q1’22 | 0.1 | 100% (@iwd-22wk12)
IMS eCall over NR | Rel-16 | N | Q3’22 | 19 | Q3’21-Q3’22 | 2 | 6% (@iwd-22wk23)
NR positioning | Rel-16 | N | Q4’22 | 14 | Q2’21-Q4’22 | 0.5 | 50% (@iwd-22wk12)
NR MIMO enhancements | Rel-16 | N | Q4’22 | 1 | Q4’20-Q4’22 | 0.5 | Not started
NR new/extended bands | R16to17 | N | Q4’22 | n/a | Q1’21-Q4’22 | 0.2 | 54% (@iwd-22wk23)
5G CA/DC band combinations | R16to17 | N,L | Q4’22 | n/a | Q1’21-Q4’22 | 0.2 | 26% (@iwd-22wk23)
Total: |  |  |  | 893 |  | 28.9 | person-months
TTCN workplan 2022 Status of 2021 tasks carried over
Notes: Note: TTCN of some features initially started in 2021 will only be completed in 2022 due to availability of prose late in CY2021, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 11
2022 Tasks & Maintenance | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of Aug’22) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q4’22 | 35 | Q1’22-Q1’23 | 6 | 23% (@iwd-22wk23)
NR 2-step RACH | Rel-16 | N | Q4’22 | 8 | Q1’22-Q4’22 | 1 | Not started
MR-DC & NR CA enhancements | Rel-16 | N,L | Q4’22 | 29 | Q1’22-Q1’23 | 3 | Not started
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q4’22 | 13 | Q1’22-Q1’23 | 3 | Not started ; no prose
NR FR1 RF requirements | Rel-16 | N | Q4’22 | 6 | Q3’22-Q4’22 | 1 | Not started ; no prose
NB-IoT new band 103 | Rel-17 | L | Q4’22 | n/a | Q3’22-Q4’22 | 0.1 | Not started ; no prose
NW slicing enhancements - Phase2 | Rel-17 | N | Q4’22 | 13 | Q4’22-Q2’23 | 0.5 | Not started ; no prose
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q2’23 | ~20 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
Reduced capability NR UE (RedCap) | Rel-17 | N | Q2’23 | >9 | Q4’22-Q4’23 | 1 | Not started ; no prose
NR multi/broadcast services (MBS) | Rel-17 | N | Q2’23 | ~50 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR UE power saving enhancements | Rel-17 | N | Q3’23 | ~15 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR sidelink enhancements | Rel-17 | N | Q3’23 | <10 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q3’23 | ~10 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 20 | Q1’22-Q4’22 | 2 | 2022 total after RAN5#95-e: 2 TCs
TTCN maintenance & deliveries |  |  |  |  | Q1’22-Q4’22 | 45 | 
Release & configuration management |  |  |  |  | Q1’22-Q4’22 | 6 | 
Total: |  |  |  | ~260 |  | 72.1 | person-months
TTCN workplan 2022 Status of new 2022 tasks and maintenance tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2022 workload is estimated at 101 person-months, see previous slides.
PCG#47/OP#46 approved the 3GPP funding of 58 person-months for 2022 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2022.
Current commitments for 2022 are as follows:
3GPP companies / 3GPP MRPs committed to provide 17 person-months as voluntary contributions for 2022 TTCN development.
Total resources of 101 person-months  no estimated funding gap.
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#47/OP#46 approved (decision OP46/08)
CTIA/PTCRB | 12 | 5GS, MCX
GCF | 12 | 5GS, MCX
Qualcomm | 2 | RACS, NPN, IMSoNR eCall
Total: | 84 | person-months
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 5GS, V2X, NB-IoT, LCR TDD
Anritsu | 1 | 5GS
Keysight | 1 | 5GS
Rohde&Schwarz | 1 | 5GS
Total: | 17 | person-months
TTCN funding 2022 Status

## Slide 13
Course of action to secure funding for TF160 work in 2023:
  Prior to RAN5#96-e meeting (August), a request to identify the potential TTCN development tasks in 2023 has been made to 3GPP members.
  At RAN5#96-e, a provisional ‘TTCN Tasks List’ shall be endorsed by RAN5.
  The TTCN Tasks List will be presented at RAN#97-e (Sept) for TSG RAN initial endorsement.
  The RAN Chair will then present the List to 3GPP PCG/OP (Oct) in order to support TF160 request for the TTCN funding in 2023.
  The finalized TTCN Tasks List will be reviewed and endorsed at RAN5#97 (Nov) for TSG RAN approval at RAN#98-e (Dec).
Based on feedback from several RAN5 member companies and 3GPP MRPs, the list of TTCN tasks presented in the next slides has been produced by the TF160 Leader.
Preparing for 2023 TTCN Work
Overview

## Slide 14
2022 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | 3GPP related Work Item
5GS: NE-DC (option 4) | Rel-15 | N,L | Q4’22 | 35 | Q1’22-Q1’23 | 0.5 | 5GS_NR_LTE-UEConTest
5G V2X with NR sidelink | Rel-16 | N,L | Q4’22 | 74 | Q4’20-Q1’23 | 2 | 5G_V2X_NRSL_eV2XARC-UEConTest
MR-DC & NR CA enhancements | Rel-16 | N,L | Q4’22 | 29 | Q1’22-Q1’23 | 1 | LTE_NR_DC_CA_enh-UEConTest
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q4’22 | 13 | Q1’22-Q1’23 | 2 | NR_unlic-UEConTest
NW slicing enhancements - Phase2 | Rel-17 | N | Q4’22 | 13 | Q4’22-Q2’23 | 1 | eNS_Ph2-UEConTest
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q2’23 | ~20 | Q4’22-Q4’23 | 2 | NR_ENDC_SON_MDT_enh-UEConTest
Reduced capability NR UE (RedCap) | Rel-17 | N | Q2’23 | >9 | Q4’22-Q4’23 | 1.5 | NR_redcap_plus_ARCH-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q2’23 | ~50 | Q4’22-Q4’23 | 4 | NR_MBS_5MBS_5MBUSA-UEConTest
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q4’23 | 1.5 | LTE_NR_MUSIM-UEConTest
NR UE power saving enhancements | Rel-17 | N | Q3’23 | ~15 | Q4’22-Q4’23 | 1.5 | NR_UE_pow_sav_enh_plus_CT-UEConTest
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 1.5 | NR_slice-UEConTest
NR sidelink enhancements | Rel-17 | N | Q3’23 | <10 | Q4’22-Q4’23 | 1.5 | NR_SL_enh-UEConTest
NR sidelink relay | Rel-17 | N | Q3’23 | ~10 | Q4’22-Q4’23 | 1.5 | NR_SL_Relay-UEConTest
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’23-Q4’23 | 1 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | ~310 |  | 73.5 | person-months
Preparing for 2023 TTCN Work – Tasks List
2022 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2021 will only be completed in 2022 due to availability of prose late in CY2021, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 15
2023 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | 3GPP related Work Item
Inter-system mobility between untrusted non-3GPP and 3GPP | Rel-15 | L,N | Q2’23 | 8 | Q1’23-Q4’23 | 3 | TEI15_Test
NB-IoT/eMTC for non-terrestrial networks (NTN) | Rel-17 | L | Q3’23 | 14 | Q1’23-Q4’23 | 3 | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest
NR coverage enhancements | Rel-17 | N | Q2’23 | 5 | Q1’23-Q3’23 | 1.5 | NR_cov_enh-UEConTest
NR UL data compression (UDC) | Rel-17 | N | Q2’23 | 11 | Q1’23-Q3’23 | 2 | NR_UDC-UEConTest
NR industrial IoT and URLLC enhancements | Rel-17 | N | Q2’23 | >3 | Q1’23-Q3’23 | 1.5 | NR_IIoT_URLLC_enh-UEConTest
NR small data transmissions in INACTIVE state | Rel-17 | N | Q3’23 | 8 | Q1’23-Q4’23 | 1.5 | NR_SmallData_INACTIVE-UEConTest
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’23 | FFS | Q1’23-Q1’24 | 3 | NR_NTN_Solutions-UEConTest
5G private network enhancements | Rel-17 | N | Q4’23 | ~15 | Q1’23-Q1’24 | 2 | NG_RAN_PRN_enh-UEConTest
NR MIMO further enhancements | Rel-17 | N | Q4’23 | 3 | Q1’23-Q1’24 | 1 | NR_feMIMO-UEConTest
MCX Rel-16 enhancements | Rel-16 | L | Q3’24 | FFS | Q1’23-Q4’24 | 3 | MCProtoc16-UEConTest (new)
5G access traffic steering, switch and splitting | Rel-16 | N | Q4’23 | FFS | Q1’23-Q1’24 | 3 | NR_ATSSS-UEConTest (new)
User plane integrity protection for EPC | Rel-17 | L | Q2’23 | FFS | Q1’23-Q3’23 | 1 | UPIP_SEC_LTE-RAN-UEConTest (new)
NR QoE management and optimizations | Rel-17 | N | Q3’23 | FFS | Q1’23-Q4’23 | 2 | NR_QoE-UEConTest (new)
5G control plane steering of roaming for UE in connected mode enhancements (CP SOR) | Rel-17 | N | Q3’23 | FFS | Q1’23-Q4’23 | 1.5 | eCPSOR_CON-UEConTest (new)
NR positioning enhancements | Rel-17 | N | Q2’24 | FFS | Q1’23-Q3’24 | 1.5 | NR_pos_enh-UEConTest (new)
Total: |  |  |  | >67 |  | 30.5 | person-months
Preparing for 2023 TTCN Work – Tasks List
New 2023 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2023 Funding: 2023 workload is estimated at 104 person-months (mm), see previous slides.
  Funding will be requested to 3GPP PCG/OP.
    Typically, only part of necessary funding provided by PCG/OP
      example: 58 person-months in 2022
  Funding shall also be obtained through voluntary contributions from 3GPP companies and/or MRPs.
    Commitments received to date:
   RAN / RAN5 member companies and 3GPP MRPs are respectfully asked to consider providing funding support for the TTCN tasks in 2023.
Funding |  | 
Entity | Person-months | Comments
3GPP | TBD | 
TBD | TBD | 
Total: | TBD | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Keysight | 1 | 
Anritsu | 1 | 
Total: | 16 | 
Preparing for 2023 TTCN Work

## Slide 17
Question to RAN5: RAN5 is requested to endorse
  The 2023 TTCN Tasks List presented in the previous slides,
  The request from RAN5 to TSG RAN and PCG/OP for a 3GPP funding of 58 person-months in 2023.
  Note: Additional contributions of 46 person-months are expected to be found from other sources for 2023.
Preparing for 2023 TTCN Work
Funding

## Slide 18: Annexes

## Slide 19: TTCN deliveries and baseline 2022 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and five TTCN-3 full deliveries.
  Q4 dates confirmed: RAN5#97 meeting to be hosted F2F in Europe(TBC).
Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
  Rel-17 Stage3 freeze declared by 3GPP in March 2022.
  Rel-17 ASN.1 freeze declared by 3GPP in June 2022, with the following remark:
    Jun’22 Rel-17 ASN.1 is not recommended for Rel-17 implementation/deployment.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 21-Jan |  | 
wk12 | 25-Mar | 21-Mar | 25-Mar | TTCN-3 | 
wk16 |  |  | 14-Apr |  | GCF CAG#70 (19-22 Apr)
wk19 |  |  | 06-May |  | PTCRB PVG#97 (10-12 May)
wk23 | 10-Jun | 06-Jun | 10-Jun | TTCN-3 | 
wk30 |  |  | 22-Jul |  | GCF CAG#71 (26-29 Jul)
wk32 |  |  | 22-Jul |  | PTCRB PVG#98 (9-11 Aug)
wk37 | 16-Sep | 12-Sep | 16-Sep | TTCN-3 | 
wk42 |  |  | 14-Oct |  | GCF CAG#72 (18-21 Oct)
wk43 | 28-Oct | 19-Oct | 28-Oct | TTCN-3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk45 |  |  | 04-Nov |  | PTCRB PVG#99 (8-10 Nov)
wk48 | 01-Dec | 28-Nov |  | TTCN2 (FDD) | 
wk48 | 02-Dec | 28-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 09-Dec | 05-Dec | 09-Dec | TTCN-3 | 

## Slide 20: 5GS Rel-15 – Protocol test case numbers Before RAN5#96-e
5GS Rel-15 | TCs # | Details
NR/5GC (5G option 2) | Total: 449 | IdleMode: 60, NR L2: 81, NR RRC: 107, 5GC: 57, Multilayer: 33, IMS: 101, POS: 10.
EN-DC (5G option 3) | Total: 125 | NR L2: 71, RRC: 51, EPC: 3, IMS, POS: none.
NE-DC (5G option 4) | Total: 35 | NR L2: 2, NR RRC: 33, IdleMode, 5GC, Multilayer, IMS, POS: none.
TOTAL: | 609 | 
Notes: Legend:
Blue: changes from last MCC TF160 report.

## Slide 21: Minutes of TTCN Sidebar
Friday 19th August @11AM CEST.
Agenda and minutes:
  See RAN5#96-e_TTCN_Sidebar-v2.zip