## Cover sheet
3GPP TSG-RAN WG5 Meeting #96-e | [8 empty] | R5-225454
<Electronic meeting, 15th Aug - 26th Aug, 2022>
Agenda Item: | 7.4.2
Source: | Samsung
Title: | WP - UE Conformance - NR support for high speed train scenario in frequency range 2
Work item code: | NR_HST_FR2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_HST_FR2’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_HST_FR2.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 7%
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 7%
FR2 |  | 7%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0%
NR RF/RRM
FR2 RF common parts | 38.521-2 | 0% |  |  | 0%
FR2 RF Tx test cases | 38.521-2 Tx | 5.9% |  |  | 5.9%
FR2 RF Rx test cases | 38.521-2 Rx | 0% |  |  | 0%
RF Demod/QSI test cases | 38.521-4 | 0% |  |  | 0%
RRM test cases | 38.533 | 0% |  |  | 0%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-221402 | New WID on UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - NR support for high speed train scenario in frequency range 2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_HST_FR2-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_HST_FR2’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_HST_FR2.
WP Resp: |  | Sunlin Zhu |  |  | sunlin.zhu@samsung.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
7%
32
32
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
LTE RF/RRM
LTE RAN and CN protocols
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | adding release-17 PC6 HST FR2 radio resource control information element |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
2 |  | 38.508-1 | 4.6.4 | UE capability information elements | adding release-17 PC6 HST FR2 UE capability information element |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
3 |  | 38.508-2 | A.4 | High Speed Capabilities | adding release-17 PC6 HST FR2 capabilities |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
4 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for PC6 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
5 |  | 38.521-2 Tx | 6.1 | General | adding PC6 common uplink configuration |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
6 |  | 38.521-2 Tx | 6.2.1.0 | General | adding Release-17 FR2 PC6 UE Type |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
7 |  | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | adding RF requirement for Release-17 FR2 PC6 UE | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
8 |  | 38.521-2 Tx | 6.2.1.1_1 | UE maximum output power - EIRP and TRP (Rel16 and forward) | adding RF requirement for Release-17 FR2 PC6 UE with beam correspondence side condition | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
9 |  | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | adding UE spherical coverage for power class 6 | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
10 |  | 38.521-2 Tx | 6.2.1.2_1 | UE maximum output power - Spherical coverage (Rel16 and forward) | adding UE spherical coverage for power class 6 UE with beam correspondence side condition | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
11 |  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | adding Release-17 FR2 PC6 UE MPR | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
12 |  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | adding Release-17 FR2 PC6 UE MPR for NS_202 and NS_203 | Samsung | RAN5#101 (Nov-23) | R5-225771 | Harmonization with TS 38.101-2_6.2.3.3.6 & 6.2.3.4.6 Revised from: R5-224983r1. | 1 | 30% | 30% |  | 30%
13 |  | 38.521-2 Tx | 6.3.1 | Minimum output power | adding Release-17 FR2 PC6 Minimum output power | Samsung | RAN5#101 (Nov-23) | R5-225773 | Harmonization with TS 38.101-2_6.3.1.3 Revised from: R5-224985r1. | 0.1 | 30% | 30% |  | 30%
14 |  | 38.521-2 Tx | 6.4.2.2 | Carrier leakage | adding Release-17 FR2 PC6 Carrier leakage | Samsung | RAN5#101 (Nov-23) | R5-225774 | Harmonization with TS 38.101-2_6.4.2.2.7 Revised from: R5-224986r1. | 0.1 | 30% | 30% |  | 30%
15 |  | 38.521-2 Tx | 6.4.2.3 | In-band emissions | adding Release-17 FR2 PC6 In-band emissions | Samsung | RAN5#101 (Nov-23) | R5-225775 | Harmonization with TS 38.101-2_6.4.2.3.7 Revised from: R5-224987r1. | 0.1 | 30% | 30% |  | 30%
16 |  | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power for UL MIMO | Samsung | RAN5#101 (Nov-23) | R5-225772 | Harmonization with TS 38.101-2_6.2D.1.6 Revised from: R5-224984r1. | 1 | 30% | 30% |  | 30%
17 |  | 38.521-2 Tx | 6.2D.1.2 | UE maximum output power - Spherical coverage for UL MIMO | adding Release-17 FR2 PC6 UE spherical coverage for UL MIMO |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
18 |  | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power reduction for modulation / channel bandwidth for UL MIMO |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
19 |  | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power with additional requirements for UL MIMO |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
20 |  | 38.521-2 Tx | 6.3D.1 | Minimum output power for UL MIMO | adding Release-17 FR2 PC6 Minimum output power for UL MIMO |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
21 |  | 38.521-2 Tx | 6.6 | Beam correspondence | adding Release-17 FR2 PC6 Beam correspondence |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
22 |  | 38.521-2 Tx | Multi places | Multi sections | Checking all test cases and adding PC6 to configuration tables where 'inner full configuration' is used for testing |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Rx
23 |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | adding Release-17 FR2 PC6 Reference sensitivity power level |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
24 |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | adding Release-17 FR2 PC6 EIS spherical coverage |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
TBD |  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | RAN5#101 (Nov-23) |  |  | 10 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
25 |  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Adding applicability for test cases in 38.521-2 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
26 |  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
27 |  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.533: RRM test cases
TBD |  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
28 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
29 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
30 |  | 38.905 |  | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.