## Summary
Work plan summary:
Rel-15 NR Transmitter and Receiver Test Cases – SA Range 1 (TS 38.521-1)
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Rel-15 NR Transmitter and Receiver Test Cases – SA Range 1 (TS 38.521-1) | SA Option 2 (SA NR) | 99.47% | 99.47%
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)
|  | Area | SA Option 2 (SA NR) test case statistics
|  |  | Overall number of test cases |  | Number of FR independent test cases |  | Number of FR1 test cases |  | Number of FR2 test cases |  | Number of FR1+FR2 test cases
|  | Area | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| Rel-15 NR Transmitter and Receiver Test Cases – SA Range 1 (TS 38.521-1) | SA Option 2 (SA NR) | 121 | 120 |  |  | 121 | 120
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)

## RF Tx Rx Range 1
WP Title: | Rel-15 NR Transmitter and Receiver Test Cases – SA Range 1 (TS 38.521-1) | [11 empty] | WP item applicability | [5 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This part of the work plan covers NR transmitter and receiver test cases for SA range 1 (sub-6 GHz, TS 38.521-1) | [11 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Chunying Gu, Huawei |  |  |  | guchunying@huawei.com
TS Resp: | Yu Shi, China Unicom |  |  |  | shiyu19@chinaunicom.cn | [7 empty] | SA |  |  | NSA
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. |  | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7
[11 empty] | Overall |  | 99.47%
[7 empty] | Overall #WP items: Post WI close #WP items: | [5 empty] | 213 1
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
General
1 |  | 38.521-1 |  | Foreword |  |  | Opt 2: RAN5#83 (May-19) |  |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
2 |  | 38.521-1 |  | Introduction |  |  | Opt 2: RAN5#83 (May-19) |  |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
3 |  | 38.521-1 | 1 | Scope | define scope of TS |  | Opt 2: RAN5#83 (May-19) |  |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
4 |  | 38.521-1 | 2 | Reference | Define References made in TS | Bureau Veritas | Opt 2: RAN5#86 (Feb-20) | R5-181507 R5-182005 R5-190136 R5-190826 R5-191034 R5-193072 R5-194923 R5-194925 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
5 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Bureau Veritas | Opt 2: RAN5#86 (Feb-20) | R5-181507 R5-182005 R5-182768 R5-184572 R5-185866 R5-187150 R5-190055 R5-190293 R5-190826 R5-191035 R5-191156 R5-192426 R5-193072 R5-194922 R5-212839 R5-220273 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
6 |  | 38.521-1 | 4 | General | define categories of test requirements | Bureau Veritas | Opt 2: RAN5#86 (Feb-20) | R5-181507 R5-182005 R5-182768 R5-184572 R5-187150 R5-190351 R5-190984 R5-191506 R5-193072 R5-194923 R5-199493 R5-200908 R5-200924 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
7 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement | China unicom | Opt 2: RAN5#86 (Feb-20) | R5-181685 R5-181686 R5-182020 R5-183702 R5-185321 R5-186225 R5-186280 R5-187812 R5-187560 R5-190827 R5-193279 R5-193339 R5-193344 R5-193955 R5-194924 R5-196500 R5-199338 R5-198761 R5-200909 R5-201801 R5-204762 R5-205299 R5-211109 R5-211680 R5-211682 R5-213894 R5-221361 R5-222857 R5-225791 R5-224289 | 2019/6/24 Pending update according to 38.101 vf60 | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Transmitter characteristics (Clause 6)
8 |  | 38.521-1 | 6.1 | General | TS38.101-1 cl 6,1, provide general info for chapter 6. |  | Opt 2: RAN5#83 (May-19) | R5-181670 R5-184298 R5-186260 R5-187911 R5-187034 R5-190981 R5-191848 R5-198401 R5-200658 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Transmit power (Clause 6.2)
9 | Y | 38.521-1 | 6.2.1 | UE maximum output power | TS38.101-1 cl 6.2.1 measure the maximum output power of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#81 (Nov-18) | R5-180068 R5-181676 R5-183958 R5-183280 R5-185305 R5-184822 R5-186316 R5-187892 R5-187376 R5-190273 R5-192409 R5-193285 R5-201247 R5-201845 R5-203885 R5-204908 R5-206638 R5-211113 R5-212914 R5-215285 R5-216086 R5-220080 R5-220081 R5-225689 R5-225784 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
10 | Y | 38.521-1 | 6.2.2 | UE maximum output power reduction | TS38.101-1 cl 6.2.2 measure the UE MPR of 5G-NR SA Range1 | CATR | Opt 2: RAN5#82 (Feb-19) | R5-180070 R5-181676 R5-182021 R5-183957 R5-184822 R5-185411 R5-186274 R5-187804 R5-187892 R5-187893 R5-190400 R5-191465 R5-193435 R5-193574 R5-196191 R5-199503 R5-198398 R5-200640 R5-200664 R5-201247 R5-204908 R5-206863 R5-206638 R5-210291 R5-215285 R5-218417 R5-220080 R5-220081 R5-223809 | 2019/11/6, post RAN4#92 MPR requirement for PRACH,PUCCH is added Editor’s Note: The following aspects are either missing or not yet determined: - PC1 and PC4 requirements are not defined in RAN4 Rel-15 spec. | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
11 | Y | 38.521-1 | 6.2.3 | UE additional maximum output power reduction | TS38.101-1 cl 6.2.3 measure the UE AMPR of 5G-NR SA Range1 | Ericsson | Opt 2: RAN5#82 (Feb-19) | R5-180069 R5-185408 R5-185307 R5-187395 R5-187397 R5-187804 R5-186264 R5-186670 R5-187892 R5-193283 R5-193438 R5-193441 R5-194911 R5-194912 R5-193915 R5-194161 R5-195804 R5-199323 R5-199324 R5-199325 R5-199329 R5-198526 R5-199330 R5-199331 R5-199332 R5-200757 R5-200759 R5-200761 R5-200763 R5-200765 R5-200767 R5-201238 R5-200906 R5-200972 R5-201247 R5-201598 R5-202714 R5-202821 R5-202822 R5-202886 R5-202887 R5-202888 R5-202889 R5-204907 R5-204908 R5-204909 R5-206638 R5-206639 R5-211113 R5-212619 R5-212668 R5-213891 R5-212671 R5-213892 R5-213015 R5-215846 R5-215165 R5-215285 R5-215334 R5-216085 R5-216034 R5-216514 R5-216515 R5-218418 R5-217427 R5-218421 R5-221675 R5-220080 R5-220081 R5-220254 R5-220899 R5-220900 R5-221109 R5-222335 R5-223806 R5-223875 R5-222808 R5-223812 R5-225786 R5-225068 | 2019/11/6, post RAN4#92 AMPR requirement updated for several NSs Editor’s note: The following aspects are either missing or not yet determined: - Tests for network signalling values NS_10, NS_07, NS_40 and NS_49 not complete. | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
12 | Y | 38.521-1 | 6.2.4 | Configured transmitted power | TS38.101-1 cl 6.2.4 measure the configured transmitted power of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-185322 R5-184303 R5-186261 R5-187804 R5-187892 R5-187888 R5-190272 R5-192402 R5-198546 [38.905]R5-190274 R5-200976 R5-201247 R5-204906 R5-204908 R5-203967 R5-206638 R5-211113 R5-213015 R5-215285 R5-220080 R5-221679 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Transmitter power for CA（Clause 6.2A）
228 |  | 38.521-1 | 6.2A.1 | UE maximum output power for CA | TS38.101-1 cl 6.2A.1, provide general info for chapter 6.2A.1 UE maximum output power for CA | Huawei |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
229 |  | 38.521-1 | 6.2A.1.0 | Minimum conformance requirements | TS38.101-1 cl 6.2A.1, provide Minimum conformance requirements on UE maximum output power for CA. | Huawei | Opt 2: RAN5#83 (May-19) | R5-195403 R5-215214 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
230 | Y | 38.521-1 | 6.2A.1.1 | UE maximum output power for CA (2UL CA) | Test case for TS38.101-1 cl 6.2A.1.1 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-195403 R5-196402 R5-202217 R5-206638 R5-213883 R5-215286 R5-220080 R5-221107 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
88 |  | 38.521-1 | 6.2A.2 | UE maximum output power reduction for CA | TS38.101-1 cl 6.2A.2, provide general info for chapter 6.2A.2 UE maximum output power reduction for CA | Huawei |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.2A.2.0 | Minimum conformance requirement |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-197519 R5-215286 R5-218224 |  | 0.1 | 100% |  | 4 | 100%
89 | Y | 38.521-1 | 6.2A.2.1 | UE maximum output power reduction for CA (2UL CA) | TS38.101-1 cl 6.2A.2.1, provide Minimum conformance requirements on UE maximum output power reduction for CA. | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-197519 R5-202217 R5-213884 R5-216032 R5-220080 R5-221052 R5-222336 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s Note: Initial Conditions and test requirement for Intra-band UL CA non-contiguous RB allocation is incomplete. | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
92 |  | 38.521-1 | 6.2A.3 | UE additional maximum output power reduction for CA | TS38.101-1 cl 6.2A.3, provide general info for chapter 6.2A.3 UE maximum output power reduction for CA | Huawei |  |  |  | 0 |  |  | 4 |  | 1 | 1 | 1 | 1
93 |  | 38.521-1 | 6.2A.3.0 | Minimum conformance requirement | TS38.101-1 cl 6.2A.3.1, provide Minimum conformance requirements on UE maximum output power reduction for CA. | Huawei | Opt 2: RAN5#85 (Nov-19) | R5-197316 R5-218416 |  | 0.1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
94 | Y | 38.521-1 | 6.2A.3.1 | UE additional maximum output power reduction for CA (2UL CA) | Test case for TS38.101-1 cl 6.2A.3.2 | Huawei | Opt 2: RAN5#88 (Aug-20) | R5-197316 R5-202217 R5-202710 R5-202888 R5-204711 R5-213015 R5-218416 R5-220080 R5-223804 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s note: This clause is incomplete. The following aspects are either missing for not yet determined: FFS is left in Test applicability since there are no requirements for 6.5A.2.3 Additional Spectrum Emission mask for CA and 6.5A.3.3 Additional Spurious Emissions for CA in In Release-15. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
96 |  | 38.521-1 | 6.2A.4 | Configured output power for CA | Test case for TS38.101-1 cl 6.2A.4 | Huawei |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
98 |  | 38.521-1 | 6.2A.4.0 | Minimum conformance requirements |  | Huawei |  |  |  | 0 |  |  | 3
99 |  | 38.521-1 | 6.2A.4.0.1 | Configured transmitted power level |  | Huawei |  |  | Information copy from RAN4 for reference | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.2A.4.0.1.1 | FFS |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-195403 |  | 0 | 100% |  | 3 | 100%
|  | 38.521-1 | 6.2A.4.0.1.2 | FFS |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-195403 |  | 0 | 100% |  | 3 | 100%
|  | 38.521-1 | 6.2A.4.0.1.3 | Configured transmitted power for Inter-band CA | TS38.101-1 cl 6.2A.4.1.3, provide Minimum conformance requirements on configured transmitted output power for CA. | Huawei | Opt 2: RAN5#83 (May-19) | R5-195403 R5-200971 R5-206638 |  | 1 | 100% |  | 3 | 100%
102 |  | 38.521-1 | 6.2A.4.0.2 | ΔTIB,c for CA | TS38.101-1 cl 6.2A.4.2, provide ΔTIB,c for CA of the requirements on configured transmitted output power for CA. | Huawei | Opt 2: RAN5#83 (May-19) | R5-194910 | Information copy from RAN4 for reference | 0.1 | 100% |  | 3 | 100%
103 |  | 38.521-1 | 6.2A.4.0.2.1 | FFS |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-194910 R5-195732 |  | 0.1 | 100% |  | 3 | 100%
104 |  | 38.521-1 | 6.2A.4.0.2.2 | FFS |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-194910 R5-195732 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
105 |  | 38.521-1 | 6.2A.4.0.2.3 | ΔTIB,c for Inter-band CA | TS38.101-1 cl 6.2A.4.2.3, provide ΔTIB,c for CA of the requirements on configured transmitted output power for Inter-band CA. | Huawei | Opt 2: RAN5#83 (May-19) | R5-194910 | Information copy from RAN4 for reference | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.2A.4.1 | Configured transmitted power for CA (2UL CA) | Test case for TS38.101-1 cl 6.2A.4.1.1 in case of 2UL CA | Huawei |  | R5-197318 R5-211677 R5-213888 R5-213015 R5-220080 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 4 | 100%
Transmitter power for SUL（Clause 6.2C）
80 | Y | 38.521-1 | 6.2C.1 | Configured transmitted power for SUL | TS38.101-1 cl 6.2C.1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-185446 R5-185309 R5-186266 R5-187892 R5-199313 R5-200975 R5-203679 R5-215284 R5-220080 R5-225064 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
106 |  | 38.521-1 | 6.2C.2 | ΔTIB,c | TS38.101-1 cl 6.2C.2 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-185446 | Information copy from RAN4 for reference | 0.1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.2C.3 | UE maximum output power for SUL | TS38.101-1 cl 6.2.1, SUL bands | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199314 R5-200975 R5-203679 R5-206638 R5-211113 R5-215284 R5-220080 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.2C.4 | UE maximum output power reduction for SUL | TS38.101-1 cl 6.2.2, SUL bands | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199315 R5-200975 R5-203679 R5-215284 R5-220080 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.2C.5 | UE additional maximum output power reduction for SUL | ， | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-197917 R5-200975 R5-203679 R5-212969 R5-215284 R5-220080 | Editor’s notes: - Tests for network signalling values NS_05, NS_17, NS_18, NS_43 and NS_100 not complete. | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Transmitter power for UL MIMO（Clause 6.2D）
107 | Y | 38.521-1 | 6.2D.1 | UE maximum output power for UL MIMO | Test case for TS38.101-1 cl 6.2D.1 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-186205 R5-190813 [38.905]R5-190440 R5-192547 R5-197520 R5-202891 R5-204905 R5-206638 R5-213015 R5-220080 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
108 | Y | 38.521-1 | 6.2D.2 | UE maximum output power reduction for UL MIMO | Test case for TS38.101-1 cl 6.2D.2 | Huawei | Opt 2: RAN5#83 (May-19) | R5-186206 R5-190950 [38.905] R5-190442 R5-195142 R5-203881 R5-213882 R5-213015 R5-220073 R5-220080 R5-220252 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
109 | Y | 38.521-1 | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Test case for TS38.101-1 cl 6.2D.3 | Huawei | Opt 2: RAN5#83 (May-19) | R5-193436 R5-193930 R5-211676 R5-211678 R5-211113 R5-220080 R5-223804 R5-225790 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.2D.4 | Configured transmitted power for UL MIMO | Test case for TS38.101-1 cl 6.2D.4 | Huawei | Opt 2: RAN5#83 (May-19) | R5-186263 R5-190814 [38.905]R5-190444 R5-192548 R5-195142 R5-198546 R5-215043 R5-220080 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
|  | Output power dynamics (Clause 6.3) | [6 empty] | referenced by 521-3
13 | Y | 38.521-1 | 6.3.1 | Minimum output power | Test case for TS38.101-1 cl 6.3.1 measure the minimum output power of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#81 (Nov-18) | R5-180071 R5-181676 R5-181833 R5-182973 R5-183958 R5-183280 R5-185323 R5-186204 R5-187892 R5-187378 R5-192411 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
14 |  | 38.521-1 | 6.3.2 | Transmit OFF power | Test case for TS38.101-1 cl 6.3.2 measure the minimum output power of 5G-NR SA Range1 | CATR | Opt 2: RAN5#81 (Nov-18) | R5-180077 R5-181842 R5-183280 R5-186736 R5-196699 R5-210485 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
Transmit ON/OFF time mask (Clause 6.3.3)
15 |  | 38.521-1 | 6.3.3.1 | General | TS38.101-1 cl 6.3.3.1 measure the general ON/OFF time mask of 5G-NR SA Range1 |  | Opt 2: RAN5#83 (May-19) |  |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
16 | Y | 38.521-1 | 6.3.3.2 | General ON/OFF time mask | TS38.101-1 cl 6.3.3.2 measure the general ON/OFF time mask of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#81 (Nov-18) | R5-180072 R5-181676 R5-181833 R5-182973 R5-183958 R5-183280 R5-185495 R5-186262 R5-187379 R5-187892 R5-193488 R5-194307 R5-197492 R5-197493 R5-216029 R5-223805 R5-225071 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
17 |  | 38.521-1 | 6.3.3.3 | Transmit power time mask for slot and short or subslot boundaries | TS38.101-1 cl 6.3.3.3 measure the Transmit power time mask for slot and [mini-slot] boundariesof 5G-NR SA Range1 | LGE | Opt 2: RAN5#83 (May-19) | R5-195090 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
18 | Y | 38.521-1 | 6.3.3.4 | PRACH time mask | TS38.101-1 cl 6.3.3.4 measure the PRACH time mask of 5G-NR SA Range1 | KTL | Opt 2: RAN5#81 (Nov-18) | R5-183956 R5-188035 R5-187818 R5-190205 R5-194228 R5-197314 R5-200397 R5-205852 R5-206160 R5-218223 R5-217553 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
110 |  | 38.521-1 | 6.3.3.5 | void |  | CATR |  |  | 2018/12/25: The requirement is removed in 38.101-1 | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
21 | Y | 38.521-1 | 6.3.3.6 | SRS time mask | TS38.101-1 cl 6.3.3.6 measure the SRS time mask of 5G-NR SA Range1 | MTCC | Opt 2: RAN5#82 (Feb-19) | R5-187895 R5-191526 R5-194915 R5-197492 R5-206641 R5-216030 R5-218227 R5-220893 R5-220919 R5-221267 R5-223805 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
22 |  | 38.521-1 | 6.3.3.7 | PUSCH-PUCCH and PUSCH-SRS time mask | TS38.101-1 cl 6.3.3.7 measure the PUSCH-PUCCH and PUSCH-SRS time mask of 5G-NR SA Range1 | MTCC | Opt 2: RAN5#83 (May-19) | R5-188206 R5-190997 R5-195090 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
111 |  | 38.521-1 | 6.3.3.8 | Transmit power time mask for consecutive slot or long subslot transmission and short subslot transmission boundaries |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-195090 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
112 |  | 38.521-1 | 6.3.3.9 | Transmit power time mask for consecutive short subslot transmissions boundaries |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-195090 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Power control(Clause 6.3.4)
23 |  | 38.521-1 | 6.3.4.1 | General | introduction of power control |  | Opt 2: RAN5#83 (May-19) | R5-181677 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
24 | Y | 38.521-1 | 6.3.4.2 | Absolute power tolerance | TS38.101-1 cl 6.3.4.2 measure the absolute power tolerance of 5G-NR SA Range1 | Intel | Opt 2: RAN5#84 (Aug-19) | R5-181677 R5-186318 R5-187455 R5-195198 R5-197517 R5-197492 R5-220537 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
25 | Y | 38.521-1 | 6.3.4.3 | Relative power tolerance | TS38.101-1 cl 6.3.4.3 measure the relative power tolerance of 5G-NR SA Range1 | Ericsson | Opt 2: RAN5#82 (Feb-19) | R5-181677 R5-186318 R5-187455 R5-195198 R5-197517 R5-196233 R5-198237 R5-199322 R5-200440 R5-200659 R5-201847 R5-202715 R5-203748 R5-213015 R5-220537 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
26 | Y | 38.521-1 | 6.3.4.4 | Aggregate power tolerance | TS38.101-1 cl 6.3.4.4 measure the aggregate power tolerance of 5G-NR SA Range1 | Intel | Opt 2: RAN5#85 (Nov-19) | R5-181678 R5-186277 R5-188036 R5-187456 R5-195140 R5-195198 R5-200443 R5-202715 |  | 1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
Output power dynamics for CA(Clause 6.3A)
113 |  | 38.521-1 | 6.3A.1 | Minimum output power for CA |  | China unicom |  | R5-192412 |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
114 |  | 38.521-1 | 6.3A.1.0 | Minimum conformance requirements | 38.101-1 cl 6.3A.1 | China unicom | Opt 2: RAN5#83 (May-19) |  |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
115 | Y | 38.521-1 | 6.3A.1.1 | Minimum output power for CA (2UL CA) | 38.101-1 cl 6.3A.1.1 ,cl 6.3A.1.2 and cl 6.3A.1.3 2UL CA | China unicom | Opt 2: RAN5#84 (Aug-19) | R5-194910 R5-196396 R5-199311 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
118 |  | 38.521-1 | 6.3A.2 | Transmit OFF power for CA |  | China unicom |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
119 |  | 38.521-1 | 6.3A.2.0 | Minimum conformance requirements | 38.101-1 cl 6.3A.2 | China unicom | Opt 2: RAN5#83 (May-19) | R5-195145 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
120 |  | 38.521-1 | 6.3A.2.1 | Transmit OFF power for CA (2UL CA) | 38.101-1 cl 6.3A.2.1, cl 6.3A.2.2 and cl 6.3A.2.3 | China unicom | Opt 2: RAN5#83 (May-19) | R5-192685 R5-195145 R5-220071 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
123 |  | 38.521-1 | 6.3A.3 | Transmit ON/OFF time mask for CA |  | China unicom |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
124 |  | 38.521-1 | 6.3A.3.0 | Minimum conformance requirements | 38.101-1 cl 6.3A.3 | China unicom | Opt 2: RAN5#83 (May-19) |  |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
125 | Y | 38.521-1 | 6.3A.3.1 | Transmit ON/OFF time mask for CA (2UL CA) | 38.101-1 cl 6.3A.3.1, cl 6.3A.3.2 and cl 6.3A.3.3 | China unicom | Opt 2: RAN5#84 (Aug-19) | R5-192561 R5-194908 R5-197518 R5-200962 R5-218232 R5-220253 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
|  |  | 6.3A.4 Power control for CA | [5 empty] | No requirements unique to CA operation are defined.Only chapter title needs to be added.
|  | 38.521-1 | 6.3A.4.1 | Absolute power tolerance for CA | [8 empty] | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.1.0 | Minimum conformance requirements | 38.101-1 cl 6.3A.4 |  |  |  | No inter-band requirements defined |  |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.1.1 | Absolute power tolerance for CA (2UL CA) | 38.101-1 cl 6.3A.4 |  |  | R5-220072 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. |  |  |  | 4 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.2 | Relative power tolerance for CA | [8 empty] | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.2.0 | Minimum conformance requirements | 38.101-1 cl 6.3A.4 |  |  |  | No inter-band requirements defined |  |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.2.1 | Relative power tolerance for CA (2UL CA) | 38.101-1 cl 6.3A.4 |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. |  |  |  | 4 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.3 | Aggregate power tolerance for CA | [8 empty] | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.3.0 | Minimum conformance requirements | 38.101-1 cl 6.3A.4 |  |  |  | No inter-band requirements defined |  |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3A.4.3.1 | Aggregat power tolerance for CA (2UL CA) | 38.101-1 cl 6.3A.4 |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. |  |  |  | 4 |  | 1 | 1 | 1 | 1
Output power dynamics for SUL (Clause 6.3C)
| Y | 38.521-1 | 6.3C.1 | Minimum output power for SUL | 38.101-1 cl 6.3.1 | Huawei | Opt 2: RAN5#87 (May-20) | R5-201734 R5-203679 R5-215284 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3C.2 | Transmit OFF power for SUL | 38.101-1 cl 6.3.2 | Huawei | Opt 2: RAN5#87 (May-20) | R5-201735 R5-215373 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3C.3 | Transmit ON/OFF time mask for SUL | 38.101-1 cl 6.3.4 |  |  |  |  | 1 |  |  | 7 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3C.3.0 | Minimum conformance requirements | 38.101-1 cl 6.3.3.2 | Huawei | Opt 2: RAN5#87 (May-20) | R5-225069 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.3C.3.1 | General transmit ON/OFF time mask for SUL | 38.101-1 cl 6.3.3.2 | Huawei | Opt 2: RAN5#87 (May-20) | R5-201736 R5-203679 R5-215284 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.3C.4 | Power control for SUL | 38.101-1 cl 6.3.4 |  |  |  |  | 1 |  |  | 7 |  | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.3C.4,1 | Absolute power tolerance for SUL | 38.101-1 cl 6.3.4.1 | Huawei | Opt 2: RAN5#87 (May-20) | R5-202711 R5-203679 R5-215284 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.3C.4.2 | Relative power tolerance for SUL | 38.101-1 cl 6.3.4.2 | Huawei | Opt 2: RAN5#87 (May-20) | R5-202712 R5-203679 R5-205535 R5-215284 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.3C.4.3 | Aggregate power tolerance for SUL | 38.101-1 cl 6.3.4.3 | Huawei | Opt 2: RAN5#87 (May-20) | R5-201739 R5-203679 R5-215284 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
Output power dynamics for UL MIMO(Clause 6.3D)
133 | Y | 38.521-1 | 6.3D.1 | Minimum output power for UL MIMO | 38.101-1 cl 6.3D.1 | China Telecom | Opt 2: RAN5#84 (Aug-19) | R5-186209 R5-186774 R5-192549 R5-193282 R5-193753 R5-197313 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
134 |  | 38.521-1 | 6.3D.2 | Transmit OFF power for UL MIMO | 38.101-1 cl 6.3D.2 | China Telecom | Opt 2: RAN5#83 (May-19) | R5-186210 R5-186776 R5-193282 R5-193753 R5-210485 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
135 | Y | 38.521-1 | 6.3D.3 | Transmit ON/OFF time mask for UL MIMO | 38.101-1 cl 6.3D.3 | China Telecom | Opt 2: RAN5#83 (May-19) | R5-186211 R5-186781 R5-193282 R5-193753 R5-199308 R5-216512 R5-218419 R5-224293 R5-225788 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
|  |  | 6.3D.4 | Power control for UL MIMO | [5 empty] | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
233 | Y | 38.521-1 | 6.3D.4.1 | Absolute power tolerance for UL MIMO | 38.101-1 cl 6.3D.4 | China Telecom | Opt 2: RAN5#84 (Aug-19) | R5-188032 R5-194905 R5-196653 R5-198134 R5-199309 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
234 | Y | 38.521-1 | 6.3D.4.2 | Relative power tolerance for UL MIMO | 38.101-1 cl 6.3D.4 | China Telecom | Opt 2: RAN5#84 (Aug-19) | R5-188033 R5-194906 R5-196711 R5-198134 R5-199310 R5-211679 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
235 | Y | 38.521-1 | 6.3D.4.3 | Aggregate power tolerance for UL MIMO | 38.101-1 cl 6.3D.4 | China Telecom | Opt 2: RAN5#84 (Aug-19) | R5-188034 R5-185140 R5-196726 R5-198134 R5-223811 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
|  | Transmit signal quality(Clause 6.4) | [6 empty] | referenced by 521-3
27 | Y | 38.521-1 | 6.4.1 | Frequency error | TS38.101-1 cl 6.4.1 measure the frequency error of 5G-NR SA Range1 | Rohde & Schwarz | Opt 2: RAN5#82 (Feb-19) | R5-182026 R5-183959 R5-185317 R5-185316 R5-186223 R5-187585 R5-187892 R5-190947 R5-192413 R5-198399 R5-200438 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Transmit modulation quality(Clause 6.4.2)
28 | Y | 38.521-1 | 6.4.2.1 | Error Vector Magnitude | TS38.101-1 cl 6.4.2.1 measure the EVM of 5G-NR SA Range1 | Rohde & Schwarz | Opt 2: RAN5#83 (May-19) | R5-183959 R5-184822 R5-185326 R5-185412 R5-186223 R5-187585 R5-187892 R5-190947 R5-192413 R5-193440 R5-193489 R5-194228 R5-194916 R5-194918 R5-197514 R5-197314 R5-196234 R5-198134 R5-199322 R5-202715 R5-203291 R5-205852 R5-218226 R5-220914 R5-223807 | 2019/11/6, post RAN4#92 Measurement period is updated | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
29 | Y | 38.521-1 | 6.4.2.2 | Carrier leakage | TS38.101-1 cl 6.4.2.2 measure the carrier leakge of 5G-NR SA Range1 | Rohde & Schwarz | Opt 2: RAN5#82 (Feb-19) | R5-183959 R5-185312 R5-185311 R5-186223 R5-187585 R5-187892 R5-190947 R5-192413 R5-193502 R5-194308 R5-197514 R5-199321 R5-202715 R5-202890 R5-213015 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
30 | Y | 38.521-1 | 6.4.2.3 | In-band emissions | TS38.101-1 cl 6.4.2.3 measure the in-band emissions of 5G-NR SA Range1 | Rohde & Schwarz | Opt 2: RAN5#82 (Feb-19) | R5-183959 R5-185320 R5-185319 R5-186223 R5-187585 R5-187892 R5-190947 R5-192413 R5-193440 R5-193502 R5-194226 R5-194916 R5-194308 R5-197514 R5-196234 R5-199321 R5-198134 R5-198397 R5-199322 R5-202715 R5-202890 R5-203291 R5-218226 R5-218228 R5-220914 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
31 | Y | 38.521-1 | 6.4.2.4 | EVM equalizer spectrum flatness | TS38.101-1 cl 6.4.2.4 measure the EVM equalizer spectrum flatness of 5G-NR SA Range1 | Rohde & Schwarz | Opt 2: RAN5#82 (Feb-19) | R5-183959 R5-185315 R5-185314 R5-186223 R5-187585 R5-187892 R5-190947 R5-192413 R5-198134 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
237 | Y | 38.521-1 | 6.4.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK | 6.4.2.5 Requirements for pi/2 BPSK modulation | Rohde & Schwarz | Opt 2: RAN5#83 (May-19) | R5-187898 R5-190947 R5-192413 R5-193489 R5-194918 R5-204054 R5-222203 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Transmit signal quality for CA(Clause 6.4A)
137 |  | 38.521-1 | 6.4A.1 | Frequency error for CA |  | Samsung |  | R5-187899 |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.4A.1.0 | Minimum conformance requirements |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187899 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
138 | Y | 38.521-1 | 6.4A.1.1 | Frequency error for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187899 R5-192567 R5-200438 R5-204760 R5-211677 R5-218229 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
141 |  | 38.521-1 | 6.4A.2 | Transmit modulation quality for CA |  | Samsung |  |  |  | 0 |  |  | 4 |  | 1 | 1 | 1 | 1
142 |  | 38.521-1 | 6.4A.2.1 | Error Vector Magnitude for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.4A.2.1.0 | Minimum conformance requirements | 38.101-1 Clause 6.4A.2 | Samsung | Opt 2: RAN5#83 (May-19) | R5-187900 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4A.2.1.1 | Error Vector Magnitude for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187900 R5-190807 R5-191039 R5-192570 R5-197514 R5-202715 R5-204760 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
143 |  | 38.521-1 | 6.4A.2.2 | Carrier leakage for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 2 | 1 | 1 | 1
|  | 38.521-1 | 6.4A.2.2.0 | Minimum conformance requirements |  | Samsung | Opt 2: RAN5#83 (May-19) | R5-187900 R5-194308 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4A.2.2.1 | Carrier leakage for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187900 R5-190808 R5-192544 R5-192570 R5-193502 R5-194308 R5-197514 R5-199321 R5-202715 R5-204760 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
144 |  | 38.521-1 | 6.4A.2.3 | In-band emissions for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.4A.2.3.0 | Minimum conformance requirements |  | Samsung | Opt 2: RAN5#83 (May-19) | R5-187900 R5-194308 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4A.2.3.1 | In-band emissions for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187900 R5-192570 R5-193502 R5-194308 R5-197514 R5-199321 R5-202715 R5-204760 R5-217479 R5-221266 | Inter-band 2UL CA tracked in current WP. Intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
|  | Transmit signal quality for SUL(Clause 6.4C) | [6 empty] | referenced by 521-3
| Y | 38.521-1 | 6.4C.1 | Frequency error for SUL | TS38.101-1 cl 6.4.1 measure the frequency error of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199316 R5-200438 R5-200975 R5-203679 R5-215284 R5-220249 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Transmit modulation quality for SUL(Clause 6.4C.2)
| Y | 38.521-1 | 6.4C.2.1 | Error Vector Magnitude for SUL | TS38.101-1 cl 6.4.2.1 measure the EVM of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199317 R5-200975 R5-203679 R5-215284 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4C.2.2 | Carrier leakage for SUL | TS38.101-1 cl 6.4.2.2 measure the carrier leakge of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199318 R5-200975 R5-203679 R5-210793 R5-215284 R5-220905 R5-220915 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4C.2.3 | In-band emissions for SUL | TS38.101-1 cl 6.4.2.3 measure the in-band emissions of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199319 R5-200975 R5-203679 R5-215284 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4C.2.4 | EVM equalizer spectrum flatness for SUL | TS38.101-1 cl 6.4.2.4 measure the EVM equalizer spectrum flatness of 5G-NR SA Range1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-199320 R5-200975 R5-203679 R5-215284 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Transmit signal quality for UL MIMO(Clause 6.4D)
145 | Y | 38.521-1 | 6.4D.1 | Frequency error for UL MIMO |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-186317 R5-196413 R5-200438 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
146 |  | 38.521-1 | 6.4D.2 | Transmit modulation quality for UL MIMO |  | Huawei |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.4D.2.1 | Error Vector Magnitude for UL MIMO |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-185685 R5-197514 R5-197319 R5-197923 R5-202715 R5-204854 R5-204010 |  | 1 | 100% |  | 4 | 100%
| Y | 38.521-1 | 6.4D.2.2 | Carrier leakage for UL MIMO |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-186207 R5-193502 R5-194308 R5-197514 R5-197321 R5-202715 R5-204854 R5-204010 |  | 1 | 100% |  | 4 | 100%
| Y | 38.521-1 | 6.4D.2.3 | In-band emissions for UL MIMO |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-186208 R5-193502 R5-194308 R5-197514 R5-197324 R5-202715 R5-204854 R5-204010 R5-221266 |  | 1 | 100% |  | 4 | 100%
| Y | 38.521-1 | 6.4D.2.4 | EVM equalizer spectrum flatness for UL MIMO |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-185688 R5-196421 |  | 1 | 100% |  | 4 | 100%
147 | Y | 38.521-1 | 6.4D.3 | Time alignment error for UL MIMO |  | China Unicom | Opt 2: RAN5#83 (May-19) | R5-187894 R5-192407 R5-195144 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
148 | Y | 38.521-1 | 6.4D.4 | Requirements for coherent UL MIMO |  | Huawei | Opt 2: Post WI close | R5-192408 R5-216033 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - Test config table is still FFS. - SA Generic procedures with condition NR in TS 38.508-1 is FFS. - SA message contents in TS 38.508-1[5] subclause 4.6 is FFS - The test procedure is FFS. - TT value is still FFS | 1 | 20% |  | 16 | 20% | 1 | 1 | 1 | 1
Output RF spectrum emissions(Clause 6.5)
32 | Y | 38.521-1 | 6.5.1 | Occupied bandwidth | TS38.101-1 cl 6.5.1 measure the occupied bandwidth of 5G-NR SA Range1 | Keysight | Opt 2: RAN5#81 (Nov-18) | R5-180075 R5-181670 R5-183960 R5-185414 R5-187892 R5-190964 R5-191815 R5-192598 R5-213885 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
Out of band emission(Clause 6.5.2)
33 |  | 38.521-1 | 6.5.2.1 | General | TS38.101-1 cl 6.5.2.1 general info introudction for chapter 7 | Keysight | Opt 2: RAN5#82 (Feb-19) | R5-190551 R5-191244 |  | 0.1 | 100% |  | 2 | 100%
34 | Y | 38.521-1 | 6.5.2.2 | Spectrum emission mask | TS38.101-1 cl 6.5.2.2 measure the spectrum emission mask of 5G-NR SA Range1 | Keysight | Opt 2: RAN5#81 (Nov-18) | R5-180078 R5-181671 R5-183960 R5-184822 R5-185414 R5-186226 R5-186257 R5-187038 R5-187892 R5-187804 R5-186901 R5-187892 R5-192598 R5-193287 R5-194125 R5-200441 R5-202765 R5-203880 R5-211092 R5-215472 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
35 | Y | 38.521-1 | 6.5.2.3 | Additional spectrum emission mask | TS38.101-1 cl 6.5.2.3 measure the additional spectrum emission mask of 5G-NR SA Range1 | Ericsson | Opt 2: RAN5#84 (Aug-19) | R5-180076 R5-186265 R5-187399 R5-187892 R5-186671 R5-190997 R5-191090 R5-193284 R5-194162 R5-197312 R5-196231 R5-199333 R5-200755 R5-202888 R5-206088 R5-215287 R5-225789 |  | 1 | 100% |  | 4 | 100% |  | 1 | 1 | 1
Adjacent channel leakage ratio(Clause 6.5.2.4)
36 | Y | 38.521-1 | 6.5.2.4.1 | NR ACLR | TS38.101-1 cl 6.5.2.4.1 measure the NR ACLR of 5G-NR SA Range1 | Keysight | Opt 2: RAN5#81 (Nov-18) | R5-180079 R5-181672 R5-183960 R5-183280 R5-184822 R5-185414 R5-186257 R5-187804 R5-187892 R5-192598 R5-193285 R5-200441 R5-201247 R5-202713 R5-202940 R5-203880 R5-206863 R5-221676 |  | 1 | 100% |  | 1 | 100% |  | 1 | 1 | 1
37 | Y | 38.521-1 | 6.5.2.4.2 | UTRA ACLR | TS38.101-1 cl 6.5.2.4.2 measure the UTRA ACLR of 5G-NR SA Range1 | Ericsson | Opt 2: RAN5#82 (Feb-19) | R5-185858 R5-186680 R5-190948 R5-192545 R5-192986 R5-193535 R5-199485 R5-200441 R5-202713 R5-204905 R5-215845 R5-215285 R5-225003 |  | 1 | 100% |  | 2 | 100% |  | 1 | 1 | 1
Spurious emissions(Clause 6.5.3)
38 | Y | 38.521-1 | 6.5.3.1 | General spurious emissions | TS38.101-1 cl 6.5.3.1 measure the general spurious emissions of 5G-NR SA Range1 | Qualcomm | Opt 2: RAN5#81 (Nov-18) | R5-181699 R5-183705 R5-183280 R5-185413 R5-186276 R5-186605 R5-187892 R5-190810 [38.905] R5-190811 R5-191846 R5-197308 R5-199484 R5-202716 R5-218225 R5-221678 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
39 | Y | 38.521-1 | 6.5.3.2 | Spurious emissions for UE co-existence | TS38.101-1 cl 6.5.3.2 measure the spurious emissions for UE co-existence of 5G-NR SA Range1 | Qualcomm | Opt 2: RAN5#81 (Nov-18) | R5-181700 R5-182000 R5-183703 R5-185496 R5-186275 R5-186606 R5-187892 R5-190812 R5-191852 R5-193281 R5-194316 R5-197521 R5-199486 R5-200570 R5-200693 R5-202887 R5-202888 R5-204195 R5-206640 R5-206642 R5-211677 R5-210995 R5-211613 R5-213889 R5-212340 R5-216031 R5-221682 R5-222745 | 2019/11/6, post RAN4#92 Protected band list is updated | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
40 | Y | 38.521-1 | 6.5.3.3 | Additional spurious emissions | TS38.101-1 cl 6.5.3.3 Additional spurious emissions | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-180044 R5-183955 R5-185501 R5-187892 R5-187896 R5-193439 R5-194377 R5-197309 R5-199334 R5-200725 R5-200892 R5-202823 R5-202888 R5-202889 R5-203572 R5-215335 R5-216085 R5-216034 R5-218418 R5-225785 R5-225789 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined Initial conditions for NS_17, NS_18, NS_37, NS_38, NS_39, NS_40, NS_41, NS_42, and NS_45 are incomplete. Test point analysis for NS_05 and NS_43 are TBD. | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
41 | Y | 38.521-1 | 6.5.4 | Transmit intermodulation | TS38.101-1 cl 6.5.4 measure the transmit intermodulation of 5G-NR SA Range1 | KTL | Opt 2: RAN5#82 (Feb-19) | R5-183906 R5-185445 R5-187892 R5-190809 R5-191258 R5-200666 R5-213015 R5-215573 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Output RF spectrum emissions for CA(Clause 6.5A )
149 |  | 38.521-1 | 6.5A.1 | Occupied bandwidth for CA |  | LGE |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
150 |  |  | 6.5A.1.0 | Minimum conformance requirements | TS38.101-1 cl 6.5A.1 | LGE | Opt 2: RAN5#83 (May-19) | R5-195143 R5-197522 R5-205736 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
151 | Y | 38.521-1 | 6.5A.1.1 | Occupied bandwidth for CA (2UL CA) | TS38.101-1 cl 6.5A.1.1,cl 6.5A.1.2 and cl 6.5A.1.3 | LGE | Opt 2: RAN5#84 (Aug-19) | R5-195143 R5-197522 R5-211677 R5-213885 R5-216084 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
154 |  | 38.521-1 | 6.5A.2 | Out of band emission for CA | TS38.101-1 cl 6.5A.2 |  |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
155 |  | 38.521-1 | 6.5A.2.1 | General | TS38.101-1 cl 6.5A.2.1 |  | Opt 2: RAN5#93 (Nov-21) | R5-217476 |  | 0.1 | 100% |  | 13 | 100% | 1 | 1 | 1 | 1
156 |  | 38.521-1 | 6.5A.2.2 | Spectrum emission mask for CA | TS38.101-1 cl 6.5A.2.2 |  |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
157 |  | 38.521-1 | 6.5A.2.2.0 | Minimum conformance requirements |  |  | Opt 2: RAN5#88 (Aug-20) | R5-187901 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
158 | Y | 38.521-1 | 6.5A.2.2.1 | Spectrum emission mask for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187901 R5-192576 R5-204760 R5-213886 R5-224831 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
192 |  | 38.521-1 | 6.5A.2.3 | Additional spectrum emission mask for CA | TS38.101-1 cl 6.5A.2.3 | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
191 |  | 38.521-1 | 6.5A.2.3.0 | Minimum conformance requirements |  | Samsung | Opt 2: RAN5#88 (Aug-20) |  |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
189 |  | 38.521-1 | 6.5A.2.3.1 | Additional spectrum emission mask for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) |  | No requirement in Rel-15. Only chapter title needs to be added. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
187 |  | 38.521-1 | 6.5A.2.4 | Adjacent channel leakage ratio for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
186 |  | 38.521-1 | 6.5A.2.4.1 | NR ACLR for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
185 |  | 38.521-1 | 6.5A.2.4.1.0 | Minimum conformance requirements | TS38.101-1 cl 6.5A.2.4.1 | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187902 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
184 | Y | 38.521-1 | 6.5A.2.4.1.1 | NR ACLR for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187902 R5-192577 R5-204760 R5-203682 R5-213886 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s note: The following aspects are either missing or not yet determined: - Extending the coverage of the TCs with intra-band CA scenarios is FFS | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
181 |  | 38.521-1 | 6.5A.2.4.2 | UTRA ACLR for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
180 |  | 38.521-1 | 6.5A.2.4.2.0 | Minimum conformance requirements | TS38.101-1 cl 6.5A.2.4.1 | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187903 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
179 | Y | 38.521-1 | 6.5A.2.4.2.1 | UTRA ACLR for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187903 R5-192578 R5-204760 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s note: The following aspects are either missing or not yet determined: - Extending the coverage of the TCs with intra-band CA scenarios is FFS | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
176 |  | 38.521-1 | 6.5A.3 | Spurious emission for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
174 |  | 38.521-1 | 6.5A.3.1 | General spurious emissions for CA | TS38.101-1 cl 6.5A.3.1 | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.5A.3.1.0 | Minimum conformance requirements | TS38.101-1 cl 6.5A.3.1 | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187904 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5A.3.1.1 | General spurious emissions for CA (2UL CA) | TS38.101-1 cl 6.5A.3.1 | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187904 R5-192579 R5-204760 R5-210899 R5-213887 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s Note: The following aspects are either missing or not yet determined: - Extending the coverage of the TCs with intra-band CA scenarios is FFS | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
175 |  | 38.521-1 | 6.5A.3.2 | Spurious emissions for UE co-existence for CA |  | Samsung |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
173 |  | 38.521-1 | 6.5A.3.2.0 | Minimum conformance requirements |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187905 R5-204761 R5-206901 R5-213890 R5-216031 R5-215332 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
172 | Y | 38.521-1 | 6.5A.3.2.1 | Spurious emissions for UE co-existence for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187905 R5-192580 R5-193344 R5-204760 R5-206901 R5-210899 R5-213887 R5-213890 R5-214603 R5-215332 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s note: The following aspects are either missing or not yet determined: - Extending the coverage of the TCs with intra-band CA scenarios is FFS. | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
170 |  | 38.521-1 | 6.5A.4 | Transmit intermodulation for CA | [5 empty] | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
168 |  | 38.521-1 | 6.5A.4.0 | Minimum conformance requirements | TS38.101-1 cl 6.5A.4 |  | Opt 2: RAN5#88 (Aug-20) | R5-187906 |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
167 | Y | 38.521-1 | 6.5A.4.1 | Transmit intermodulation for CA (2UL CA) |  | Samsung | Opt 2: RAN5#88 (Aug-20) | R5-187906 R5-192581 R5-204760 R5-211677 | Inter-band 2UL CA tracked in current WP; intra-band contiguous/non-contiguous 2UL CA are tracked in Rel16 NR_RF_FR1-UEConTest WP. Editor’s Note: The following aspects are either missing or not yet determined: - Extending the coverage of the TCs with intra-band CA scenarios is FFS | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
Output RF spectrum emissions for SUL(Clause 6.5C)
| Y | 38.521-1 | 6.5C.1 | Occupied bandwidth for SUL | TS38.101-1 cl 6.5.1 measure the occupied bandwidth of 5G-NR SA Range1 | huawei | Opt 2: RAN5#86 (Feb-20) | R5-186342 R5-200975 R5-203679 R5-215284 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Out of band emission for SUL(Clause 6.5C.2)
|  | 38.521-1 | 6.5C.2.1 | General | TS38.101-1 cl 6.5.2.1 general info introudction for chapter 7 | huawei | Opt 2: RAN5#93 (Nov-21) |  |  | 0.1 | 100% |  | 13 | 100%
| Y | 38.521-1 | 6.5C.2.2 | Spectrum emission mask for SUL | TS38.101-1 cl 6.5.2.2 measure the spectrum emission mask of 5G-NR SA Range1 | huawei | Opt 2: RAN5#86 (Feb-20) | R5-186343 R5-200975 R5-203679 R5-215284 R5-224832 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5C.2.3 | Additional spectrum emission mask for SUL | TS38.101-1 cl 6.5.2.3 measure the additional spectrum emission mask of 5G-NR SA Range1 | huawei | Opt 2: RAN5#86 (Feb-20) | R5-186267 R5-200975 R5-202888 R5-215284 |  | 1 | 100% |  | 6 | 100% |  | 1 | 1 | 1
Adjacent channel leakage ratio for SUL(Clause 6.5C.2.4)
| Y | 38.521-1 | 6.5C.2.4.1 | NR ACLR for SUL | TS38.101-1 cl 6.5.2.4.1 measure the NR ACLR of 5G-NR SA Range1 | huawei | Opt 2: RAN5#86 (Feb-20) | R5-186268 R5-200975 R5-203679 R5-215284 R5-221676 |  | 1 | 100% |  | 6 | 100% |  | 1 | 1 | 1
| Y | 38.521-1 | 6.5C.2.4.2 | UTRA ACLR for SUL | TS38.101-1 cl 6.5.2.4.2 measure the UTRA ACLR of 5G-NR SA Range1 | huawei | Opt 2: RAN5#86 (Feb-20) | R5-186269 R5-200975 R5-203679 R5-212970 R5-215284 |  | 1 | 100% |  | 6 | 100% |  | 1 | 1 | 1
Spurious emissions for SUL(Clause 6.5C.3)
| Y | 38.521-1 | 6.5C.3.1 | General spurious emissions for SUL | TS38.101-1 cl 6.5.3.1 measure the general spurious emissions of 5G-NR SA Range1 |  | Opt 2: RAN5#86 (Feb-20) | R5-186270 R5-200975 R5-203679 R5-215284 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5C.3.2 | Spurious emissions for UE co-existence for SUL | TS38.101-1 cl 6.5.3.2 measure the spurious emissions for UE co-existence of 5G-NR SA Range1 |  | Opt 2: RAN5#86 (Feb-20) | R5-186271 R5-200975 R5-203679 R5-215284 R5-220906 R5-220915 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5C.3.3 | Additional spurious emissions for SUL | TS38.101-1 cl 6.5.3.3 Additional spurious emissions |  | Opt 2: RAN5#87 (May-20) | R5-186272 R5-194377 R5-200975 R5-201741 R5-203679 R5-215284 R5-221322 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5C.4 | Transmit intermodulation for SUL | TS38.101-1 cl 6.5.4 measure the transmit intermodulation of 5G-NR SA Range1 |  | Opt 2: RAN5#86 (Feb-20) | R5-186273 R5-200975 R5-203679 R5-215284 R5-222334 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Output RF spectrum emissions for UL MIMO(Clause 6.5D)
164 | Y | 38.521-1 | 6.5D.1 | Occupied bandwidth for UL MIMO | TS38.101-1 cl 6.5D.1 | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186212 R5-192550 R5-212856 R5-225787 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
163 |  | 38.521-1 | 6.5D.2 | Out of band emission for UL MIMO | TS38.101-1 cl 6.5D.2 | Huawei |  |  |  | 0 |  | 1 | 3 |  | 1 | 1 | 1 | 1
236 |  | 38.521-1 | 6.5D.2.1 | General | TS38.101-1 cl 6.5D.2 | Huawei | Opt 2: RAN5#83 (May-19) | R5-186213 |  | 0.1 | 100% |  | 3 | 100% | 1
| Y | 38.521-1 | 6.5D.2.2 | Spectrum emission mask for UL MIMO | TS38.101-1 cl 6.5D.2 | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186213 R5-192551 R5-200974 R5-222201 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5D.2.3 | Additional spectrum emission mask for UL MIMO | TS38.101-1 cl 6.5D.2 | Huawei | Opt 2: RAN5#83 (May-19) | R5-186214 R5-192553 R5-193443 R5-193917 R5-210906 R5-222201 R5-224830 |  | 1 | 100% | 3 | 3 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 6.5D.2.4 | Adjacent channel leakage ratio for UL MIMO | TS38.101-1 cl 6.5D.2 | Huawei |  |  |  | 0 |  | 3 | 3 |  | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5D.2.4.1 | NR ACLR for UL MIMO |  | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186215 R5-192554 R5-200974 R5-214603 R5-221676 R5-221106 |  | 1 | 100% |  | 2 | 100%
| Y | 38.521-1 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO |  | Huawei | Opt 2: RAN5#83 (May-19) | R5-186216 R5-192555 R5-193289 R5-193918 R5-199502 R5-200974 R5-210908 R5-221106 |  | 1 | 100% |  | 3 | 100%
162 |  | 38.521-1 | 6.5D.3 | Spurious emission for UL MIMO | TS38.101-1 cl 6.5D.3 | Huawei |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5D.3.1 | General spurious emissions for UL MIMO | TS38.101-1 cl 6.5D.3 | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186217 R5-192556 R5-193285 R5-205790 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5D.3.2 | Spurious emissions for UE co-existence for UL MIMO | TS38.101-1 cl 6.5D.3 | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186218 R5-192557 R5-205790 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 6.5D.3.3 | Additional spurious emissions for UL MIMO | TS38.101-1 cl 6.5D.3 | Huawei | Opt 2: RAN5#83 (May-19) | R5-186219 R5-192558 R5-193248 R5-193920 R5-202888 R5-205790 R5-210911 |  | 1 | 100% |  | 3 | 100%
161 | Y | 38.521-1 | 6.5D.4 | Transmit intermodulation for UL MIMO | TS38.101-1 cl 6.5D.4 | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186220 R5-192559 R5-211176 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Receiver characteristics(Clause 7)
42 |  | 38.521-1 | 7.1 | General | TS38.101-1 cl 7.1 general info introudction for chapter 7 | China unicom | Opt 2: RAN5#83 (May-19) | R5-181771 R5-187911 R5-214598 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
43 |  | 38.521-1 | 7.2 | Diversity characteristics | TS38.101-1 cl 7.2 diveristy characteristics intrdocution | China unicom | Opt 2: RAN5#83 (May-19) | R5-181771 R5-202719 R5-203879 R5-205493 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Reference sensitivity power level(Clause 7.3)
44 |  | 38.521-1 | 7.3.1 | General | TS38.101-1 cl 7.3.1 general info introudction for reference sensiticity | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-186278 R5-186604 R5-210903 |  | 0.1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
45 | Y | 38.521-1 | 7.3.2 | Reference sensitivity power level | TS38.101-1 cl 7.3.2 measure the reference sensitivity power level of 5G-NR SA Range1 including both 2Rx and 4 Rx ports. | Qualcomm | Opt 2: RAN5#81 (Nov-18) | R5-181698 R5-183953 R5-185477 R5-186278 R5-186604 R5-187892 R5-190820 R5-191854 R5-193149 R5-193303 R5-193445 R5-193259 R5-194921 R5-194256 R5-194313 R5-194314 R5-197609 R5-201833 R5-201597 R5-202718 R5-202941 R5-204912 R5-210991 R5-213102 R5-222200 R5-222338 R5-222540 R5-224243 R5-224300 | 2019/11/6, post RAN4#92 REFSENS requirements are updated for some bands | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 7.3.3 | ΔRIB,c | TS38.101-1 cl 7.3.3 | Qualcomm | Opt 2: RAN5#81 (Nov-18) | R5-198747 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
Reference sensitivity for CA(Clause 7.3A)
|  | 38.521-1 | 7.3A.0 | Minimum conformance requirements | TS38.101-1 Clause 7.3A.1 General is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-197328 |  | 0.1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 7.3A.0.1 | General | TS38.101-1 7.3A.2.1 Reference sensitivity power level for Intra-band contiguous CA is copied under this subtitle |  | Opt 2: RAN5#84 (Aug-19) | R5-193021 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.2 | Reference sensitivity power level for CA |  |  | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-204202 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.2.1 | Reference sensitivity power level for Intra-band contiguous CA | TS38.101-1 7.3A.2.1 Reference sensitivity power level for Intra-band contiguous CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-194312 R5-205872 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.2.2 | Reference sensitivity power level for Intra-band non-contiguous CA | TS38.101-1 7.3A.2.2 Reference sensitivity power level for Intra-band contiguous CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-205872 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.2.3 | Reference sensitivity power level for Inter-band CA | TS38.101-1 7.3A.2.3 Reference sensitivity power level for Intra-band contiguous CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-194312 R5-205872 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.3 | ΔRIB,c for CA | TS38.101-1 7.3A.3 ΔRIB,c for CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.3.1 | General | TS38.101-1 7.3A.3.1 General is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.3.2 | ΔRIB,c for Inter-band CA | TS38.101-1 7.3A.3.2 ΔRIB,c for Inter-band CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-193344 R5-194312 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.3.2.1 | ΔRIB,c for two bands | TS38.101-1 7.3A.3.2.1 ΔRIB,c for two bands is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 |  |  | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
|  | 38.521-1 | 7.3A.0.3.2.2 | ΔRIB,c for three bands | TS38.101-1 7.3A.3.2.2 ΔRIB,c for two bands is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.4 | Reference sensitivity exceptions due to UL harmonic interference for CA | TS38.101-1 7.3A.4 Reference sensitivity exceptions due to UL harmonic interference for CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-194312 | 2019/6/24 Minor update in minimum requirements |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.5 | Reference sensitivity exceptions due to intermodulation interference due to 2UL CA | TS38.101-1 7.3A.5 Reference sensitivity exceptions due to intermodulation interference due to 2UL CA is copied under this subtitle | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 |  |  | 100% |  | 4 | 100%
|  | 38.521-1 | 7.3A.0.6 | Reference sensitivity exceptions due to cross band isolation for CA | TS38.101-1 7.3A.6 Reference sensitivity exceptions due to cross band isolation for CA | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-193021 R5-194312 |  |  | 100% |  | 4 | 100%
48 | Y | 38.521-1 | 7.3A.1 | Reference sensitivity power level for 2DL CA without exception | TS38.101-1 cl 7.3A.2 for CA including intra-band contiguous, intra-band non-contiguous, and inter-band CA with 2 DL CC | Qualcomm | Opt 2: RAN5#86 (Feb-20) | R5-183704 R5-186279 R5-186603 R5-190952 R5-197525 R5-200924 R5-202942 R5-204912 R5-213101 R5-214603 R5-216035 R5-220255 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 7.3A.1_1 | Reference sensitivity power level for 2DL CA exceptions | TS38.101-1 cl 7.3A.4 ~ 7.3A.5 for inter-band CA exceptional requirements | Ericsson | Opt 2: RAN5#87 (May-20) | R5-200924 R5-202942 R5-204912 R5-210902 R5-214603 R5-221108r1 | Inter-band CA without UL CA Inter-band CA with UL CA | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
193 |  | 38.521-1 | 7.3A.2 | Reference sensitivity level for 3DL CA | TS38.101-1 cl 7.3A.2 ~ 7.3A.5 for CA including intra-band contiguous, intra-band non-contiguous, and inter-band CA with 3 DL CC | Qualcomm |  | R5-200924 R5-202942 R5-214603 R5-218423 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
82 |  | 38.521-1 | 7.3A.3 | Reference sensitivity level for 4DL CA | TS38.101-1 cl 7.3A.2 ~ 7.3A.5 for CA including intra-band contiguous, intra-band non-contiguous, and inter-band CA with 4 DL CC | Qualcomm |  | R5-214603 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Reference sensitivity for SUL(Clause 7.3C)
new |  | 38.521-1 | 7.3C.0 | Minimum conformance requirements | 38.101-1 cl 7.3C.2, 7.3C.3 |  | Opt 2: RAN5#83 (May-19) | R5-193446 R5-194315 R5-197327 R5-199491 | 7.3C.0 Minimum Conformance Requirements 7.3C.0.1 void 7.3C.0.2 Requirements for Reference sensitivity power level 7.3C.0.3 ΔRIB,c for SUL 7.3C.0.3.1 General 7.3C.0.3.2 SUL band combination 7.3C.0.3.2.1 ΔRIB,c for two bands | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
52 |  | 38.521-1 | 7.3C.1 | General |  | Qualcomm | Opt 2: RAN5#88 (Aug-20) |  |  | 0.1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
53 | Y | 38.521-1 | 7.3C.2 | Reference sensitivity power level for SUL | 38.101-1 cl 7.3C.2, 7.3C.3 | Qualcomm | Opt 2: RAN5#90 (Feb-21) | R5-182004 R5-183954 R5-185325 R5-187892 R5-190951 R5-191849 R5-193306 R5-194315 R5-197608 R5-202941 R5-203679 R5-211681 R5-215284 R5-220076 | 2019/11/6, post RAN4#92 Minor updates in minimum requirements Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Test point analysis and selection are FFS. - Initial condition is FFS - Test configuration for exceptional test points is FFS | 1 | 100% |  | 10 | 100% | 1 | 1 | 1 | 1
Reference sensitivity for UL MIMO(Clause 7.3D)
new | Y | 38.521-1 | 7.3D.2 | Reference sensitivity power level for UL MIMO | TS38.101-1 cl 7.3D | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186221 R5-187811 R5-202941 R5-210723 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Maximum input level(Clause 7.4)
56 | Y | 38.521-1 | 7.4 | Maximum input level | TS38.101-1 cl 7.4 | CATR | Opt 2: RAN5#81 (Nov-18) | R5-187915 R5-197515 R5-197329 R5-196696 R5-202109 R5-202941 R5-204912 R5-204913 R5-224628 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
Maximum input level for CA (7.4A)
57 |  | 38.521-1 | 7.4A | Maximum input level for CA |  | Huawei |  |  |  | 0 |  |  | 3 |  | 1 | 1 | 1 | 1
194 |  | 38.521-1 | 7.4A.0 | Minimum conformance requirements | TS38.101-1 cl 7.4A | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-197523 R5-200977 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
195 | Y | 38.521-1 | 7.4A.1 | Maximum input level for CA (2DL CA) |  | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-197523 R5-200977 R5-200979 R5-200924 R5-202941 R5-204913 R5-217111 R5-223813 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
196 |  | 38.521-1 | 7.4A.2 | Maximum input level for CA (3DL CA) |  | Huawei |  | R5-224941 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
197 |  | 38.521-1 | 7.4A.3 | Maximum input level for CA (4DL CA) |  | Huawei |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Maximum input level for UL MIMO (7.4D)
198 | Y | 38.521-1 | 7.4D | Maximum input level for UL MIMO | TS38.101-1 cl 7.4D | Huawei | Opt 2: RAN5#82 (Feb-19) | R5-186222 R5-197515 R5-202941 R5-204912 R5-204913 R5-210723 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Adjacent channel selectivity(Clause 7.5)
58 | Y | 38.521-1 | 7.5 | Adjacent channel selectivity | TS38.101-1 cl 7.5 | Keysight | Opt 2: RAN5#84 (Aug-19) | R5-182003 R5-183923 R5-185415 R5-186224 R5-187892 R5-186902 R5-190953 R5-191245 R5-193192 R5-194126 R5-195431 R5-197515 R5-202109 R5-202718 R5-202941 |  | 1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
Adjacent channel selectivity for CA(Clause 7.5A)
199 |  | 38.521-1 | 7.5A.0 | Minimum conformance requirements | TS38.101-1 cl 7.5A | China Telecom | Opt 2: RAN5#83 (May-19) | R5-194268 R5-197330 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
59 | Y | 38.521-1 | 7.5A.1 | Adjacent channel selectivity for CA (2DL CA) | TS38.101-1 cl 7.5A.1 | China Telecom | Opt 2: RAN5#86 (Feb-20) | R5-195092 R5-197515 R5-200979 R5-200393 R5-200924 R5-202941 R5-204913 R5-217112 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
200 |  | 38.521-1 | 7.5A.2 | Adjacent channel selectivity for CA (3DL CA) | TS38.101-1 cl 7.5A.2 | China Telecom |  | R5-194383 R5-198481 R5-200393 R5-200924 R5-202941 R5-222337 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
201 |  | 38.521-1 | 7.5A.3 | Adjacent channel selectivity for CA (4DL CA) | TS38.101-1 cl 7.5A.3 | China Telecom |  | R5-194920 R5-200393 R5-200924 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Adjacent channel selectivity for UL MIMO(Clause 7.5D)
202 | Y | 38.521-1 | 7.5D | Adjacent channel selectivity for UL MIMO | TS38.101-1 cl 7.5D | Huawei | Opt 2: RAN5#85 (Nov-19) | R5-202941 R5-210723 |  | 1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
Blocking charateristics(Clause 7.6)
60 |  | 38.521-1 | 7.6.1 | General | TS38.101-1 cl 7.6 |  | Opt 2: RAN5#84 (Aug-19) |  |  | 0.1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
61 | Y | 38.521-1 | 7.6.2 | In-band blocking | TS38.101-1 cl 7.6.2 | Keysight | Opt 2: RAN5#83 (May-19) | R5-181679 R5-182002 R5-183923 R5-185415 R5-186224 R5-187892 R5-186902 R5-190953 R5-191245 R5-194126 R5-197515 R5-200700 R5-202109 R5-202718 R5-202941 R5-203290 R5-204913 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
62 | Y | 38.521-1 | 7.6.3 | Out-of-band blocking | TS38.101-1 cl 7.6.3 | CATR | Opt 2: RAN5#82 (Feb-19) | R5-185524 R5-185301 R5-187892 R5-190968 R5-191262 R5-197515 R5-197329 R5-199336 R5-200700 R5-200893 R5-201742 R5-202109 R5-202941 R5-204910 R5-204911 R5-204913 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
63 | Y | 38.521-1 | 7.6.4 | Narrow band blocking | TS38.101-1 cl 7.6.4 | CATR | Opt 2: RAN5#82 (Feb-19) | R5-190969 [38.905]R5-190966 R5-191264 R5-197515 R5-197329 R5-199335 R5-200700 R5-202109 R5-202941 R5-204911 R5-204913 R5-210487 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Blocking characteristics for CA(Clause 7.6A)
64 |  | 38.521-1 | 7.6A.1 | General | TS38.101-1 cl 7.6A.1 |  | Opt 2: RAN5#93 (Nov-21) |  |  | 0.1 | 100% |  | 13 | 100% | 1 | 1 | 1 | 1
Inband blocking for CA(Clause 7.6A.2)
204 |  | 38.521-1 | 7.6A.2.0 | Minimum conformance requirements | TS38.101-1 cl 7.6A.2.1-3 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-200978 |  | 0.1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
65 | Y | 38.521-1 | 7.6A.2.1 | In-band blocking for CA (2DL CA) | TS38.101-1 cl 7.6A.2.1 | Huawei | Opt 2: RAN5#86 (Feb-20) | R5-200978 R5-200393 R5-200924 R5-202941 R5-204913 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
203 |  | 38.521-1 | 7.6A.2.2 | In-band blocking for CA (3DL CA) | TS38.101-1 cl 7.6A.2.2 | Huawei |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
227 |  | 38.521-1 | 7.6A.2.3 | In-band blocking for CA (4DL CA) | TS38.101-1 cl 7.6A.2.3 | Huawei |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Out-of-band blocking for CA(Clause 7.6A.3)
226 |  | 38.521-1 | 7.6A.3.0 | Minimum conformance requirements | TS38.101-1 cl 7.6A.3.1-3 | CAICT | Opt 2: RAN5#85 (Nov-19) | R5-199563 R5-200461 R5-204855 R5-204910 R5-223124 |  | 0.1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
66 | Y | 38.521-1 | 7.6A.3.1 | Out-of-band blocking for CA (2DL CA) | TS38.101-1 cl 7.6A.3.1 | CAICT | Opt 2: RAN5#86 (Feb-20) | R5-199563 R5-200461 R5-200393 R5-200924 R5-202941 R5-204855 R5-204910 R5-204913 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
205 |  | 38.521-1 | 7.6A.3.2 | Out-of-band blocking for CA (3DL CA) | TS38.101-1 cl 7.6A.3.2 | CAICT |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
206 |  | 38.521-1 | 7.6A.3.3 | Out-of-band blocking for CA (4DL CA) | TS38.101-1 cl 7.6A.3.3 | CAICT |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Narrow band blocking for CA(Clause 7.6A.4)
207 |  | 38.521-1 | 7.6A.4.0 | Minimum conformance requirements | TS38.101-1 cl 7.6A.4.1-3 | CAICT | Opt 2: RAN5#85 (Nov-19) | R5-199564 R5-200462 R5-205494 |  | 0.1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
208 | Y | 38.521-1 | 7.6A.4.1 | Narrow band blocking for CA (2DL CA) | TS38.101-1 cl 7.6A.4.1 | CAICT | Opt 2: RAN5#86 (Feb-20) | R5-199564 R5-200462 R5-200393 R5-200924 R5-202941 R5-204913 R5-205494 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
209 |  | 38.521-1 | 7.6A.4.2 | Narrow band blocking for CA (3DL CA) | TS38.101-1 cl 7.6A.4.2 | CAICT |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
210 |  | 38.521-1 | 7.6A.4.3 | Narrow band blocking for CA (4DL CA) | TS38.101-1 cl 7.6A.4.3 | CAICT |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Blocking characteristics for SUL (7.6C)
|  | 38.521-1 | 7.6C.1 | General | TS38.101-1 cl 7.6C |  | Opt 2: RAN5#93 (Nov-21) |  |  | 0.1 | 100% |  | 13 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 7.6C.2 | In-band blocking for SUL | TS38.101-1 cl 7.6C |  | Opt 2: RAN5#87 (May-20) | R5-202717 R5-203679 R5-204912 R5-212971 R5-215284 R5-214599 R5-220082 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
| Y | 38.521-1 | 7.6C.3 | Out-of-band blocking for SUL | TS38.101-1 cl 7.6C |  | Opt 2: RAN5#87 (May-20) | R5-201744 R5-203679 R5-204912 R5-212972 R5-215284 R5-214600 R5-220078 R5-220082 |  | 1 | 100% |  | 7 | 100% | 1 | 1 | 1 | 1
Blocking characteristics for UL MIMO (7.6D)
211 |  | 38.521-1 | 7.6D.1 | General | TS38.101-1 cl 7.6D | CAICT | Opt 2: RAN5#83 (May-19) | R5-190821 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
212 | Y | 38.521-1 | 7.6D.2 | In-band blocking for UL MIMO | TS38.101-1 cl 7.6D | CAICT | Opt 2: RAN5#83 (May-19) | R5-190821 R5-193296 R5-193567 R5-197515 R5-202941 R5-210723 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
213 | Y | 38.521-1 | 7.6D.3 | Out-of-band blocking for UL MIMO | TS38.101-1 cl 7.6D | CAICT | Opt 2: RAN5#83 (May-19) | R5-190822 R5-193300 R5-193569 R5-197515 R5-202941 R5-210723 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
214 | Y | 38.521-1 | 7.6D.4 | Narrow band blocking for UL MIMO |  | CAICT | Opt 2: RAN5#83 (May-19) | R5-190823 R5-193301 R5-193571 R5-197515 R5-202941 R5-210723 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Spurious response(Clause 7.7)
67 | Y | 38.521-1 | 7.7 | Spurious response | TS38.101-1 cl 7.7 measure the spurious response for SC of 5G-NR SA Range1 | CATR | Opt 2: RAN5#82 (Feb-19) | R5-190970 [39.905]R5-190967 R5-191265 R5-197515 R5-197329 R5-199336 R5-200700 R5-204913 |  | 1 | 100% |  | 2 | 100% | 1 | 1 | 1 | 1
Spurious response for CA(Clause 7.7A)
215 |  | 38.521-1 | 7.7A.0 | Minimum conformance requirements | 7.7A | CMCC | Opt 2: RAN5#83 (May-19) | R5-190815 R5-193039 R5-193585 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
68 | Y | 38.521-1 | 7.7A.1 | Spurious response for CA (2DL CA) | TS38.101-1 cl 7.7A.1 | CMCC | Opt 2: RAN5#86 (Feb-20) | R5-190816 R5-200907 R5-200393 R5-200924 R5-204913 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
216 |  | 38.521-1 | 7.7A.2 | Spurious response for CA (3DL CA) | TS38.101-1 cl 7.7A.2 | CMCC |  | R5-190817 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
217 |  | 38.521-1 | 7.7A.3 | Spurious response for CA (4DL CA) | TS38.101-1 cl 7.7A.3 | CMCC |  | R5-190818 | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Spurious response for UL MIMO(Clause 7.7D)
| Y | 38.521-1 | 7.7D | Spurious response for UL MIMO |  | CMCC | Opt 2: RAN5#83 (May-19) | R5-187805 R5-193047 R5-194974 R5-210723 R5-220250 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Intermodulation characteristic(Clause 7.8)
69 |  | 38.521-1 | 7.8.1 | General | TS38.101-1 cl 7.8.1 |  | Opt 2: RAN5#84 (Aug-19) | R5-187810 R5-200893 |  | 0.1 | 100% |  | 4 | 100% | 1 | 1 | 1 | 1
70 | Y | 38.521-1 | 7.8.2 | Wide band Intermodulation | TS38.101-1 cl 7.8.2 | Anritus | Opt 2: RAN5#83 (May-19) | R5-187810 R5-190997 R5-191090 R5-193305 R5-194305 R5-197515 R5-202109 R5-202941 R5-204913 R5-214601 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Intermodulation characteristics for CA(Clause 7.8A)
71 |  | 38.521-1 | 7.8A.1 | General | TS38.101-1 cl 7.8A.1 | CAICT | Opt 2: RAN5#85 (Nov-19) | R5-199565 R5-200893 |  | 0.1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
218 |  | 38.521-1 | 7.8A.1.0 | Minimum conformance requirements | TS38.101-1 cl 7.8A minimum Requirements for Intermodulation characteristics for CA | CAICT | Opt 2: RAN5#85 (Nov-19) | R5-199565 |  | 0.1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
Wide band Intermodulation for CA(Clause 7.8A.2)
72 | Y | 38.521-1 | 7.8A.2.1 | Wide band Intermodulation for CA (2DL CA) | TS38.101-1 cl 7.8A.2.1 measure the intra-band contiguous CA of 5G-NR SA Range1 | CAICT | Opt 2: RAN5#86 (Feb-20) | R5-199565 R5-200463 R5-200393 R5-200924 R5-202941 R5-204913 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
219 |  | 38.521-1 | 7.8A.2.2 | Wide band Intermodulation for CA (3DL CA) | TS38.101-1 cl 7.8A.2.2 | CAICT |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
220 |  | 38.521-1 | 7.8A.2.3 | Wide band Intermodulation for CA (4DL CA) | TS38.101-1 cl 7.8A.2.3 | CAICT |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_CADC_NR_LTE_DC_R16-UEConTest WP. | 0 |  |  | 7 |  | 1 | 1 | 1 | 1
Wide band Intermodulation for CA(Clause 7.8D)
221 | Y | 38.521-1 | 7.8D.2 | Wide band Intermodulation for UL MIMO | TS38.101-1 cl 7.8D | CAICT | Opt 2: RAN5#83 (May-19) | R5-190824 R5-193302 R5-193573 R5-197515 R5-202941 R5-210723 |  | 1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
Spurious emissions (Clause 7.9)
73 | Y | 38.521-1 | 7.9 | Spurious emissions | TS38.101-1 cl 7.9 measure the spurious emission of 5G-NR SA range1 | CATR | Opt 2: RAN5#81 (Nov-18) | R5-187807 R5-198103 R5-199336 R5-202109 R5-202941 |  | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
Spurious emissions for CA(Clause 7.9A)
223 |  | 38.521-1 | 7.9A.0 | Minimum conformance requirements |  | CMCC | Opt 2: RAN5#83 (May-19) | R5-194973 |  | 0.1 | 100% |  | 3 | 100% | 1 | 1 | 1 | 1
74 | Y | 38.521-1 | 7.9A.1 | Suprious emissions for CA (2DL CA) | TS38.101-1 cl 7.9A.3 measure the inter-band contiguous CA of 5G-NR SA Range1 | CMCC | Opt 2: RAN5#86 (Feb-20) | R5-193304 R5-194919 R5-198044 R5-200393 R5-202941 |  | 1 | 100% |  | 6 | 100% | 1 | 1 | 1 | 1
Annex
75 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels | Bureau Veritas | Opt 2: RAN5#88 (Aug-20) | R5-181506 R5-182768 R5-185390 R5-185865 R5-187149 R5-196499 R5-198479 R5-198635 R5-204103 R5-204263 R5-205495 R5-206643 R5-215847 R5-220251 R5-221684 |  | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
76 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions | Bureau Veritas/QUALCOMM | Opt 2: RAN5#85 (Nov-19) | R5-183955 |  | 1 | 100% |  | 5 | 100% | 1 | 1 | 1 | 1
77 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels | Bureau Veritas | Opt 2: RAN5#88 (Aug-20) | R5-184574 R5-185521 R5-185500 R5-187149 R5-196425 R5-197526 R5-199339 R5-202892 R5-204712 |  | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
78 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal | Samsung | Opt 2: RAN5#88 (Aug-20) |  |  | 1 | 100% | 1 | 8 | 100% | 1 | 1 | 1 | 1
86 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-185327 R5-186000 R5-190828 R5-192121 R5-193440 R5-193491 R5-194916 R5-194926 R5-200438 R5-202890 R5-201834 R5-202503 |  | 1 | 100% |  | 7 | 100%
79 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT | NTT DOCOMO, INC. Anritsu Rohde & Schwarz HUAWEI CATR MTCC KTL Ericsson Keysight Qualcomm Intel | Opt 2: RAN5#88 (Aug-20) | R5-183280 R5-185444 R5-185565 R5-184394 R5-186336 R5-186337 R5-187908 R5-187909 R5-190956 R5-191675 R5-193490 R5-195430 R5-194957 R5-196481 R5-197610 R5-196291 R5-199085 R5-199337 R5-200022 R5-200393 R5-201745 R5-202422 R5-203678 R5-210290 R5-211048 R5-222339 R5-224301 R5-225070 |  | 1 | 100% |  | 8 | 100% | 1 | 1 | 1 | 1
225 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels | Huawei | Opt 2: RAN5#88 (Aug-20) | R5-185324 R5-186332 R5-187149 R5-193052 R5-194304 |  | 1 | 100% |  | 8 | 100%
87 |  | 38.521-1 | Annex H | Statistical Testing |  | Qualcomm | Opt 2: RAN5#88 (Aug-20) | R5-183936 R5-200924 R5-202807 R5-212974 R5-221683 |  | 1 | 100% |  | 8 | 100%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Y = the WP Pitem is a test case.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.
Note on G337: LocalAccount: Confirmation from RD?