## WP scope
Work plan for introduction of NR PC3 CA FR2 configurations into 3GPP UE conformance test specifications
| WP template: | WP NR CA PC3 FR2 v1.2.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | DRAFT WP NR band and CBW FR1 v1.2.0 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | TBD | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 0%
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version
|  |  |  | CA_x | -
|  |  |  | CA_x | CA_x
Draft:
- CA_x/- and CA_x/CA_x used in the draft to force all WP items in teh WP to be visible
- Changes highlighted by Yellow highlighted cells and strike through of deleted text

## WP NR CA PC3 FR2
Work plan for introduction of NR PC3 CA FR2 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR CA PC3 FR2 v1.2.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | FR2 NR CA configuration(s) without UL CA |  |  |  | DL/- | CA_x/-
|  | FR2 NR CA configurations with UL CA |  |  |  | DL/UL | CA_x/CA_x
|  | All configurations |  |  |  | All | CA_x/-, CA_x/CA_x
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 0%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 0%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations |  |  |  |  | 0%
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 0%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-2) |  |  |  |  | 0%
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-2, clause 6) |  |  |  |  | 0%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-2, clause 7) |  |  |  |  | 0%
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 0%
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Bands completed | TCs available
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands within the WP scope are completed | CA_x/-, CA_x/CA_x | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in PRD21 worksheet "NR bands". |  | TBD |  |  | 1 | 0% |  | 0%
All | 1-2 | Pre-requisite | 38.521-2 | 6, 7 | All applicable Transmitter (clause 6), Receiver (clause 7) for the type of NR CA configuration completed | CA_x/-, CA_x/CA_x | Set status in column "TCs available" to 100% when all applicable test cases in 38.521-2 are completed for at least one of the same NR CA type of CA configuraion. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. |  | TBD |  |  | 1 | 0% |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
DL/UL | 2-1 | TP Analysis | 38.905 | 4.2 | Test point (TP) analysis for UE-coexistance spurious emissions test case for FR2 intra-band contiguous and non contiguous UL CA | CA_x/CA_x | For each UL contiguous and non-contiguous CA configuration perform UE co-existence spurious emission TP analysis for UE co-exstence as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
All | 3.1-1 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1 | Test frequencies | CA_x/-, CA_x/CA_x | - Add the NR CA configuration to the relevant test frequency table in clause 4.3.1.2.2 to 4.3.1.1.4. - Check that the involved bands have single carrier test frequencies specified in 4.3.1.x - For NR CA configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in in clause A.4.3.2A. |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.1-2 | 38.508-1 - (4) Common | 38.508-1 | 4.6.3 | Radio resource control information elements | CA_x/-, CA_x/CA_x | Add Radio resource control information elements for new type of CA combination configurations |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.4 | Test frequencies for CA signalling test | CA_x/-, CA_x/CA_x | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.4 (protocol testing limited to 2CC NR CA configurations) |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-2)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Clause 5 | Discussion paper
[15 empty] | 1 | 1
All | 3.2-0 | 38.521-2 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. | CA_x/-, CA_x/CA_x | If it is thought there are no configuration specific changes needed for Chapter 6/7 or only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7 or why only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | TBD |  |  | 1 | 0% |  |  | 0%
All | 3.2-1 | 38.521-2 - General | 38.521-2 | 5.2A.1 | FR1 /FR2 Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. | CA_x/-, CA_x/CA_x | For intra-band contiguous and non-contiguos CA configrurations add the CA operating bands to the relevant table in clause 5.2A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-2 | 38.521-2 - General | 38.521-2 | 5.5A.1 | FR1/FR2 configurations for intra-band contiguous CCs | CA_x/-, CA_x/CA_x | For intra-band contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
All | 3.2-3 | 38.521-2 - General | 38.521-2 | 5.5A.2 | FR1/FR2 configurations for intra-band non-contiguous CCs | CA_x/-, CA_x/CA_x | For intra-band non-contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.2. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-2, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
DL/UL | 3.3-1 | 38.521-2 - RF Tx | 38.521-2 (FR1) | 6.2A.1 | UE maximum output power for CA | CA_x/CA_x | For configurations including any intra-band contiguous UL CA CCs add the UE maximum output power for intra-band contiguous UL CA to the relevant table in clause 6.2A.1. |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
DL/UL | 3.3-2 | 38.521-2 - RF Tx | 38.521-2 (FR1) | 6.5A.3.2 | Spurious emission for UE co-existence for Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 2-1) | CA_x/CA_x | For configurations including any intra-band contiguous UL CA CCs: - Add the minimum conformance requirements, initial condition and test requirements for intra-band contiguous UL CA to the relevant table in clause 6.5A.3.2 bsed on TP analysis in Step 2 (WP item 2-1). |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-2, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.4-1 | 38.521-2- RF Rx | 38.521-2 | 7.3A.x, x dependent on number of DL CCs | Reference sensitivity power level for 2DL to 5DL CA Note! This WP item is dependent on Reference TP analysis (Step 2, WP item 4) | CA_x/-, CA_x/CA_x | For intra-band contiguous and intra-band non-contiguous CA: - Add test configuration and test requirements for the involved NR band. For inter-band CA: - Add test configuration for the involved NR bands - Add ΔRIB for the inter-band CA configuration. - Add test requirement for the involved NR bands Add test configuration and test requirements for any exceptional requirements based on TR 38.905 reference sensitivity TP analysis in Step 2 (WP item 4). |  | TBD |  |  | 1 | 0% |  | 0% |  | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.2.2 | NR CA Intra-band contiguous | CA_x/-, CA_x/CA_x | Add configurations for Intra-band contiguous CA within FR2 to the relevant table in Column F |  | TBD |  |  | 1 | 0% |  | 0%
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.3.2 | NR CA Intra-band non-contiguous | CA_x/-, CA_x/CA_x | Add configurations for NR Intra-band non-contiguous CA within FR2 to the relevant table in Column F |  | TBD |  |  | 1 | 0% |  | 0%
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.5 | NR Inter-band CA | CA_x/-, CA_x/CA_x | Add CA configurations for NR Inter-band CA within FR2 to the relevant table in Column F |  | TBD |  |  | 1 | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N27: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N35: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N43: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N52: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N62: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N70: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N77: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N84: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N91: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.2.0 | RAN5#96-e | 1. Extended the number of rows in the input table to cope with the case when multiple cut and paste of configurations from PRD21 CADC list are done. 2. WP item 3.4-1 (ref sense TC): - Removed reference to TP analysis WP item as the existing TP analsysis in TR 38.905 is generic for FR2 NR CA configurations. - Updated text to reflect for what need to be added in test case 7.3A.x. 3. WP item 3.2-0: Adding missing formula to cell in column
v1.1.0 | RAN5#95-e | 1. Updated WP template version in WP scope worksheet to get version number from cell A3 in the "Revision History WP template" worksheet. 2. Correcting TS for WP item 1-2. 3. Correcting clause reference for WP item 3.1-3 from 6.2.3.2 to 6.2.3.4. 5. Correcting TS reference in "area" and "TS" columns from 36.521-2/38.521-1 to 38.521-2. 6. Added a note to WP items 3.2-1 to 3.2-3 to remind about merge with "jumbo" CR. 7. Added WP item 3.2-0 about need for discussion paper to add configuration information to chapter 5.
v1.0.0 | RAN5#94-e | Initial version