## Common Test Env
WP Title: | Rel-15 5GS Common Test Environment (TS 38.508-1 and TS 36.508) | [9 empty] | WP item applicability | [7 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers tasks for all SA and NSA options. NR aspects for SA (Stand-Alone) will be part of TS 38.508-1, while LTE aspects of NSA (Non Stand-Alone) will also impact TS 36.508 (see work plan items below for details). | [9 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Bo Jönsson, Ericsson |  |  | bo.jonsson@ericsson.com
TS Resp: | Bo Jönsson, Ericsson |  |  | bo.jonsson@ericsson.com | [6 empty] | SA |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 |  | Opt. 4 |  | Opt. 7
[10 empty] | Overall | 98.18% |  |  | 98.25% |  | 100%
[6 empty] | Overall #WP items: Post WI close #WP items: |  |  |  |  | 55 1 |  |  | 57 1 |  | 2 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [9 empty] | Phase number (1,2 etc) and completion (%) per option
TS 38.508 work tasks - Claus 1 - 4: Common part
| 38.508-1 | 1,2,3 | Scope, References, Definitions
1 | 38.508-1 | 1,2,3 | Scope, References, Definitions |  | Ericsson 1 | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#79 (May-18) | R5-176779, R5-184087 |  | 1 | 100% | 2 | 100% | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 4.1 - 4.2 | Common test environment
3 | 38.508-1 | 4.1 | Environmental conditions |  | NTT DoCoMo | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#80 (Aug-18) | R5-181697, R5-183920 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
4 | 38.508-1 | 4.2 | Common requirements of test equipment |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-176995, R5-182792 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 4.3.1 | Test frequencies (General info and skeleton tables. Specific test frequency values for the different NR band and NR/MR-DC band combinations are handled by the NR band/band-combination work plan)
| 38.508-1 | 4.3.1.1 | Test frequencies for NR operating bands in FR1
5 | 38.508-1 | 4.3.1.1.1 | Operating bands in FR1 |  | Sprint | Opt 2: RAN5#81 (Nov-18) | R5-180577, R5-182108, R5-181973, R5-183256, R5-185250-R5-185270, R5-184471 - R5-184477 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
6 | 38.508-1 | 4.3.1.1.2, 4.3.1.1.3 | NR CA in FR1 |  | Sprint | Opt 2: RAN5#83 (May-19) | R5-191274 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
60 | 38.508-1 | 4.3.1.1.4 | Operating bands for NR DC in FR1 |  | Sprint | Opt 2: RAN5#83 (May-19) | R5-191274 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
61 | 38.508-1 | 4.3.1.1.5 | Operating band combination for SUL in FR1 |  | Sprint | Opt 2: RAN5#83 (May-19) | R5-191274 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
| 38.508-1 | 4.3.1.2 | Test frequencies for NR operating bands in FR2
62 | 38.508-1 | 4.3.1.2.1 | Operating bands in FR2 | Create general info and skeleton tables for NR bands. | Sprint | Opt 2: RAN5#81 (Nov-18) | R5-180577, R5-182108, R5-181973, R5-184474 - R5-184477 |  | 1 | 100% | 1 | 100% | 1 | 2 |  | 1 |  | 1
63 | 38.508-1 | 4.3.1.1.2, 4.3.1.1.3 | NR CA in FR2 |  | Ericsson 4 | Opt 2: RAN5#83 (May-19) | R5-194881, R5-194882, R5-194884 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
Test frequencies NR Inter-band CA FR1+FR2
58 | 38.508-1 | 4.3.1.3.1 | Test frequencies NR CA band combinations | Create general info and skeleton tables for SA NR CA band combinations. | Ericsson 4 | Opt 2: RAN5#84 (Aug-19) | R5-196874, R5-196875, R5-196159, R5-196468, R5-196469, R5-196873 |  | 1 | 100% | 4 | 100% | 1 | 4 |  | 1 |  | 1
Test frequencies MR-DC
57 | 38.508-1 | 4.3.1.3.2 | Test frequencies for NR operation with other radios (MR-DC with 2 bands) | Create general info and skeleton tables for DC LTE-NR band combinations with one LTE and one NR band for EN-DC, NE-DC and NGEN-DC. | Sprint | Opt 3: RAN5#79 (May-18) | R5-180577, R5-182108, R5-181973, R5-183218, R5-185173 R5-191302 | Test freqeuncy details for MR DC configurations is handled by the NR band & CA/DC configuration work plan. | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
59 | 38.508-1 | 4.3.1.3.3 - 4.3.1.3.x | Test frequencies for NR operation with other radios (MR-DC with 3 or more bands) | Create general info and skeleton tables for DC LTE-NR band combinations with > 2 bands. | Sprint | Opt 3: RAN5#81 (Nov-18) | R5-191302 | Test frequency details for MR DC configurations is handled by the NR band & CA/DC configuration work plan. | 1 | 100% | 1 |  | 1 | 2 | 100% | 1 |  | 1
55 | 38.508-1 | 4.3.1.3.3 - 4.3.1.3.x | Test frequencies for E-UTRA (MR-DC) |  | Sprint | Opt 3: RAN5#79 (May-18) | R5-183218, R5-185173 | Legacy E-UTRA test frequencies are re-used. Specific needs handled by the NR band and MR DC configuration work plan. | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 4.3.2 | Radio conditions
8 | 38.508-1 | 4.3.2.1 | Radio conditions conducted testing | Definition of radio conditions for NR and DC LTE-NR band combination conducted testing (sub-6GHz) |  | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-182063 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
9 | 38.508-1 | 4.3.2.2 | Radio conditions OTA testing | Definition of radio conditions for NR and DC LTE-NR band combination Over The Air (OTA) testing (mmWave) | FFS | Opt 2: Post WI close Opt 3: Post WI close |  |  | 1 | 0% | 16 | 0% | 1 | 16 | 0% | 1 |  | 16
| 38.508-1 | 4.3.3 | Physical channel allocations
10 | 38.508-1 | 4.3.3.1 | Physical channel allocations E-UTRA | Definition of physical channel allocations for E-UTRA | Ericsson 2 | Opt 3: RAN5#79 (May-18) | R5-182067 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
45 | 38.508-1 | 4.3.3.2 | Physical channel allocations NR for protocol testing | Definition of physical channel allocations for NR and protocol testing | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-182067, R5-183234 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
46 | 38.508-1 | 4.3.3.2 | Physical channel allocations NR for RF testing | Definition of physical channel allocations for NR and RF testing | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#80 (Aug-18) | R5-182067, R5-185133 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
| 38.508-1 | 4.3.4 | Signal levels
12 | 38.508-1 | 4.3.4.1 | Signal levels conducted testing | Definition of signal levels for NR for conducted testing (sub-6GHz) | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-182091, R5-183255 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
13 | 38.508-1 | 4.3.4.2 | Signal levels OTA testing | Definition of signal levels for NR for Other The Air (OTA) testing (mmWave) | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-182091 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 4.3.6 | Physical layer parameters
| 38.508-1 | 4.3.6.1 | Downlink physical layer parameters
14 | 38.508-1 | 4.3.6.1.1.1, 4.3.6.1.1.2 | Physical layer parameters for scheduling of PUSCH | Definition of DCI Formats 0_0 and 0_1 | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-180066, R5-181972, R5-182288 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
82 | 38.508-1 | 4.3.6.1.2.1, 4.3.6.1.2.2 | Physical layer parameters for scheduling of PDSCH | Definition of NR DCI Formats 1_0 and 1_1 | Ericsson 2 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-180066, R5-181972, R5-182288 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
83 | 38.508-1 | 4.3.6.1.3.x | Physical layer parameters for other purposes | Definition of physical layer parameters for NR DCI Format 2_0, 2_1, 2_2, 2_3 | Ericsson 2 | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) | R5-180066, R5-181972 | Chapter void. | 1 | 100% | 4 | 100% | 1 | 5 | 100% | 1 |  | 1
| 38.508-1 | 4.4 | Reference system configurations
15 | 38.508-1, 36.508 | 4.4 | Reference system configurations | Definition of reference system configurations for NSA LTE-NR testing | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-182110, R5-182349 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
100 | 38.508-1 | 4.4.3.1.2 | Combinations of system information blocks for NE-DC |  |  | Opt 4: Post WI close | R5-222464 |  | 1 | 100% | 1 |  | 1 | 1 |  | 16 | 100% | 1
| 38.508-1 | 4.5 | Generic procedures
19 | 38.508-1 | 4.5 | Generic procedures EN-DC | Definition of generic procedures for NSA LTE-NR testing of option 3 | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-176917, R5-176918, R5-181311, R5-180966, R5-181035, R5-182065, R5-181813, R5-182066, R5-182312, R5-182313, R5-183264 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
20 | 38.508-1 | 4.5 | Generic procedures SA NR | Definition of generic procedures for SA NR testing of option 2 | Ericsson 1 | Opt 2: RAN5#81 (Nov-18) | R5-188122, R5-188123, R5-187753 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
99 | 38.508-1 | 4.5 | Generic procedures NR-DC | Definition of generic procedures for NR-DC | Ericsson 1 | Opt 2: RAN5#87 (May-20) | R5-200956, R5-201222, R5-200957, R5-200958, R5-200959, R5-200960, R5-200961, R5-202024, R5-203079 |  | 1 | 100% | 7 | 100% | 1 | 1 |  | 1 |  | 1
95 | 38.508-1 | 4.5 | Generic procedures SA E-UTRA | Definition of generic procedures for SA NR testing of option 5 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
21 | 38.508-1 | 4.5 | Generic procedures NGEN-DC | Definition of generic procedures for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
22 | 38.508-1 | 4.5 | Generic procedures NE-DC | Definition of generic procedures for NSA LTE-NR testing of option 4 |  | Opt 4: RAN5#93 (Nov-21) | R5-217792, R5-217793, R5-217794, R5-217799, R5-217801, R5-217095, R5-217867 |  | 1 | 100% | 1 |  | 1 | 1 |  | 1 | 100% | 1
94 | 38.508-1 | 4.5 | IMS registration | Definition of IMS registration in generic procedures for NR testing of option 2. | Ericsson 1, Qualcomm | Opt 2: RAN5#82 (Feb-19) | R5-192740 |  | 1 | 100% | 2 | 100% | 1 | 1 |  | 1 |  | 1
97 | 38.508-1 | 4.5 | Generic procedures and environment for 0 and > 2 multi PDUs/PDNs. | Definition of multi PDUs/PDNs environment (default messages) and enhance generic procedures for the case when number of PDUs/PDNs =0 or > 2 | MediaTek | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) | R5-196035 |  | 1 | 100% | 4 | 100% | 1 | 5 | 100% | 1 |  | 1
| 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents
43 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3. | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-176920, R5-180382, R5-180383, R5-180709, R5-180773, R5-180775, R5-181812, R5-182109, R5-182064, R5-182062, R5-181786, R5-181971, R5-182249, R5-182263, R5-182381, R5-183082, R5-183083, R5-183084, R5-183087, R5-183210, R5-183211, R5-183212, R5-183214, R5-183215, R5-183216, R5-183249 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
47 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents. Measurement. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3. Measurement. | NTT DoCoMo | Opt 3: RAN5#81 (Nov-18) | R5-182068, R5-183086, R5-183090, R5-183260 |  | 1 | 100% | 1 |  | 1 | 2 | 100% | 1 |  | 1
48 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents SRB3. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3. SRB3. | Ericsson 3 | Opt 3: RAN5#81 (Nov-18) | R5-181974 |  | 1 | 100% | 1 |  | 1 | 2 | 100% | 1 |  | 1
53 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents. PSCell Add, Mod and Release conditions. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.PSCell Add, Mod and Release conditions. | Qualcomm | Opt 3: RAN5#79 (May-18) |  |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
49 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents MCG PDCP condition. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.MCG PDCP condition. | Ericsson 1 | Opt 3: RAN5#79 (May-18) |  |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
84 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents SRB1 and SRB2 NR PDCP condition. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.SRB1 and SRB 2 NR PDCP condition. | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-185028 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
54 | 38.508-1 | 4.6.4 | Default NG-RAN RRC message and information elements contents.Default structure, UE capability information elements A to L. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.Default structure, UE capability.information elements A to L. | InterTek | Opt 3: RAN5#79 (May-18) | R5-181893, R5-183250 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
50 | 38.508-1 | 4.6.4 | Default NG-RAN RRC message and information elements contents.Default structure, UE capability information elements M to U. | Definition of NG-RAN RRC default messages for NSA1 NR testing of option 3.Default structure, UE capability.information elements M to U. | Ericsson 3 | Opt 3: RAN5#79 (May-18) | R5-181893, R5-183088 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
23 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for SA NR testing of option 2 and 5 | Ericsson 1 | Opt 2: RAN5#81 (Nov-18) | R5-185030, R5-185032, R5-185033, R5-185038, R5-187745, R5-187661, R5-187750, R5-187754, R5-187755, R5-187756, R5-187757, R5-187680, R5-187762, R5-187764, R5-186575, R5-186612, R5-186613, R5-186641, R5-186665, R5-186666, R5-186682, R5-186691, R5-186692, R5-186714, R5-186734, R5-186744, R5-186911, R5-186912, R5-186913, R5-186918, R5-186920, R5-186921, R5-186922, R5-186923, R5-186925, R5-187172, R5-187175 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
93 | 38.508-1 | 4.6.2 | Default NG-RAN RRC message and information elements contents.System information blocks | Definition of NG-RAN RRC default messages for SA NR testing of option 2 and 5.System information blocks. | Huawei, Hisilicon | Opt 2: RAN5#81 (Nov-18) | R5-187673, R5-186987, R5-186988, R5-186989, R5-186990 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
90 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for SA NR testing of option 2 and 5 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
24 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
25 | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Definition of NG-RAN RRC default messages for NSA LTE-NR testing of option 4 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
| 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents
26 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for SA NR testing option 2 and 5 | Ericsson 1 | Opt 2: RAN5#81 (Nov-18) | R5-184783, R5-184785, R5-187677, R5-188107, R5-187166, R5-187678, R5-187759, R5-187679, R5-187760, R5-187761, R5-186916, R5-187159, R5-187160, R5-187161, R5-187162 R5-187163, R5-187164 |  | 1 | 100% | 1 | 100% | 1 | 1 |  | 1 |  | 1
91 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for SA NR testing option 2 and 5 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
27 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
28 | 38.508-1 | 4.7 | Default 5GC NAS message and information elements contents | Definition of 5GC NAS default messages for NSA LTE-NR testing of option 4 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
| 38.508-1 | 4.8 | Reference configurations
42 | 38.508-1 | 4.8 | Reference configurations | Definition of reference configurations for specific test case purposes. |  |  | R5-180265 |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
52 | 38.508-1 | 4.8 | Reference configurations. To configure m+n SCG bearers where m are AM RLC and n UM RLC. | Definition of reference configurations for specific test case purposes.To configure m+n SCG bearers where m are AM RLC and n UM RLC | Ericsson 3 | Opt 3: RAN5#79 (May-18) |  |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 4.9 | Test procedures
87 | 38.508-1 | 4.9 | Test procedures | Definition of test procedures for specific test case purposes. |  | Opt 3: RAN5#79 (May-18) | R5-185037 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
96 | 38.508-1 | 4.9 | Test procedure to configure SCC for CA RF test cases. | Definition of common procedure used by RF CA test cases to configur SCC | Ericsson 4 | Opt 2: RAN5#83 (May-19) | R5-194367 |  | 1 | 100% | 3 | 100% | 1 | 1 |  | 1 |  | 1
98 | 38.508-1 | 4.9 | Test procedure to configure SCC for EN-DC RF test cases. | Definition of common procedure used by RF CA test cases to configur SCC | Ericsson 4 | Opt 3: RAN5#85 (Nov-19) | R5-194367, R5-198956 |  | 1 | 100% |  |  | 1 | 6 | 100% | 1 |  | 1
TS 38.508 work tasks - Clause 5: Test environment for RF test
| 38.508-1 | 5.1 | Requirements of test equipment
| 38.508-1 | 5.1.1 | Requirements for transmission and reception tests
31 | 38.508-1 | 5.1.1.1 | Requirements common for conducted and OTA tests | Describe the test equipment requirements which are specific to transmission and reception tests and common for conducted and OTA tests. | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-187271 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
64 | 38.508-1 | 5.1.1.2 | Requirements for conducted tests | Describe the test equipment requirements which are specific to conducted test environment for transmission and reception tests. | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-187271 | No specific needs for this sub-clause identified for NSA Opt.3 Phase 1.5 | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
65 | 38.508-1 | 5.1.1.3 | Requirements for OTA tests | Describe the test equipment requirements which are specific to OTA test environment for transmission and reception tests. | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-187271 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 5.1.2 | Requirements for performance tests
66 | 38.508-1 | 5.1.2.1 | Requirements common for conducted and OTA performance tests | Describe the test equipment requirements which are specific to performance tests and common for conducted and OTA tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206112 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
67 | 38.508-1 | 5.1.2.2 | Requirements for conducted for performance conducted tests | Describe the test equipment requirements which are specific to conducted test environment for performance tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206112 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
68 | 38.508-1 | 5.1.2.3 | Requirements for OTA tests | Describe the test equipment requirements which are specific to OTA test environment for performance tests. | Anritsu | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#82 (Feb-19) | R5-176995, R5-177271 |  | 1 | 100% | 2 | 100% | 1 | 3 | 100% | 1 |  | 1
| 38.508-1 | 5.2 | Reference test conditions
| 38.508-1 | 5.2.1 | Signal levels
69 | 38.508-1 | 5.2.1.1 | Signal levels for conducted testing |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#80 (Aug-18) | R5-176995, R5-183255 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
70 | 38.508-1 | 5.2.1.2 | Signal levels for OTA |  | Anritsu | Opt 2: RAN5#82 (Feb-19) Opt 3: RAN5#82 (Feb-19) | R5-176995, R5-182091, R5-187272, R5-187802 |  | 1 | 100% | 2 | 100% | 1 | 3 | 100% | 1 |  | 1
TS 38.508 work tasks - Clause 6: Test environment for Signalling test
| 38.508-1 | 6.1 | Requirements of test equipment
33 | 38.508-1 | 6.1.1 | Requirements common for conducted and OTA tests | Describe the test equipment requirements which are specific to signalling tests and common for conducted and OTA tests. | Anritsu 2 | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
71 | 38.508-1 | 6.1.2 | Requirements for conducted test method | Describe the test equipment requirements which are specific to conducted test environment for signalling tests. | Anritsu 2 | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206308 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
72 | 38.508-1 | 6.1.3 | Requirements for OTA test method | Describe the test equipment requirements which are specific to OTA test environment for signalling tests. | Anritsu, Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-185168, R5-187681 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
85 | 38.508-1 | 6.1.4 | Requirements for timer tolerances | Describe the test equipment requirements which are specific to timer tolerances for signalling tests. |  | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-185040 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 6.2 | Reference test conditions
| 38.508-1 | 6.2.1 | Physical Channel Allocations
73 | 38.508-1 | 6.2.1.1 | Antennas |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-183255, R5-187747 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
78 | 38.508-1 | 6.2.1.2 | Downlink physical channels and physical signals |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-183255, R5-187747 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
| 38.508-1 | 6.2.2 | Signal levels
79 | 38.508-1 | 6.2.2.1 | Signal Levels for conducted testing |  | Anritsu | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#79 (May-18) | R5-176995, R5-183255, R5-187747 |  | 1 | 100% | 1 | 100% | 1 | 1 | 100% | 1 |  | 1
80 | 38.508-1 | 6.2.2.2 | Signal Levels for OTA testing |  | Anritsu 2, Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) | R5-176995, R5-185168, R5-184893 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 |  | 1
| 38.508-1 | 6.2.3 | Defaul test frequencies
81 | 38.508-1 | 6.2.3 | Default test frequencies |  | Ericsson 4 | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#82 (Feb-19) | R5-185177 R5-187752 R5-191301 |  | 1 | 100% | 1 | 100% | 1 | 3 | 100% | 1 |  | 1
| 38.508-1 | 6.3 | Reference system configurations
86 | 38.508-1 | 6.3.1 | Cell configurations | Describe different types of SS cell configurations. | FFS | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-185040 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
89 | 38.508-1 | 6.3 | Configurations for 5GC | Describe different types of configurations for 5GC. | CATT, Rohde-Schwarz | Opt 2: RAN5#82 (Feb-19) | R5-187660 |  | 1 | 100% | 2 | 100% | 1 | 2 |  | 1 |  | 1
88 | 38.508-1 | 6.3.9.1 | Test procedures 5GC | Definition of test procedures for 5GC specific test case purposes. | CATT | Opt 2: RAN5#82 (Feb-19) | R5-187763, R5-187676 R5-192744 R5-192745 |  | 1 | 100% | 2 | 100% | 1 | 1 |  | 1 |  | 1
TS 38.508 work tasks - Clause 7: Test environment for RRM tests
| 38.508-1 | 7.1 | Requirements of test equipment
34 | 38.508-1 | 7.1.1 | Requirements common for conducted and OTA tests | Describe the test equipment requirements which are specific to RRM tests and common for conducted and OTA tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206113 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
35 | 38.508-1 | 7.1.2 | Requirements for conducted test method | Describe the test equipment requirements which are specific to conducted test environment for RRM tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206113 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
75 | 38.508-1 | 7.1.3 | Requirements for OTA test method | Describe the test equipment requirements which are specific to OTA test environment for RRM tests. | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
| 38.508-1 | 7.2 | Reference test conditions
76 | 38.508-1 | 7.2.1.1 | Signal Levels for conducted testing |  | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206115 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
77 | 38.508-1 | 7.2.1.1 | Signal Levels for OTA testing |  | Anritsu | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-176995, R5-206115 | Closed. No contributions in latest meetings. | 1 | 100% | 8 | 100% | 1 | 9 | 100% | 1 |  | 1
TS 38.508 work tasks - Annexes
| 38.508-1 | Annex A | Connection Diagrams
36 | 38.508-1 | Annex A | Connection Diagrams, General part | Introduction clause etc | Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#80 (Aug-18) | R5-183916 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
37 | 38.508-1 | Annex A.3.1 | Connection Diagrams, Test equipment part | Connection diagram for test equipment part | Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#80 (Aug-18) | R5-183916 | Remains: connection diagrams for transmitter tests using Spectrum Analyser and Signal Generator (cl A.3.1.3). Specific details for test case authors to decide. | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
38 | 38.508-1 | Annex A.3.2 | Connection Diagrams, UE part | Connection diagram for UE part | Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#80 (Aug-18) | R5-183916 | Remains: connection diagrams for 3 and 4 antenna ports.Specific details for test case authors to decide. | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 |  | 1
TS 36.508 work tasks
| 36.508 | 4.6 | Default RRC message and information elements contents
40 | 36.508 | 4.6 | Default RRC message and information elements contents | Definition of E-UTRA RAN RRC default messages for NSA LTE-NR testing of option 3 | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-176919, R5-182073 |  | 1 | 100% | 1 |  | 1 | 1 | 100% | 1 |  | 1
92 | 36.508 | 4.6 | Default RRC message and information elements contents | Definition of E-UTRA RAN RRC default messages for NSA LTE-NR testing of option 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.