## Cover sheet
3GPP TSG-RAN WG5 meeting#97 | [10 empty] | R5-226007
Toulouse, France, November 14 - 18 2022
Agenda Item: | 7.4.2
Source: | Rapporteur (Ericsson)
Title: | UE Conformance Test Aspects – UE Conformance Test Aspects – Rel-16 CA configurations Work Plan
Work item code: | LTE_CA_R16-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
At the RAN#80 meeting in August 2018 the Rel-16 RAN5 work item for UE Conformance Test Aspects of Rel-16 LTE CA configurations was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items for Rel-16 CA configurations. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'Summary Work Plan' shows the status for each Rel-16 CA configuration. For each company assigned CA configurations that is ongoing and not yet completed a specific work sheet with the detailed work plan is provided. Note: This work plan is limited to the addition of new and update of existing LTE CA test cases for the new types of CA configuration introduced by this basket work item as endorsed by RAN5 in R5-215708 at RAN5#92-e. Completed CA configuration are listed in TS 36.521-2 clause A.4.6. Tracking of the responsible companies and guidlines for introducing new LTE CA configurations can be found in the RAN5 Permanent Reference Document [2] PRD20 . Introducing new LTE CA Configuration shall be in accordance to the guidelines in [2] PRD20.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 7% | 0 | 33
Completion Compensation |  | 2%
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 5% | 0 | 33
FDD |  | 5% | 0 | 17
TDD |  | 5% | 0 | 15
FDD + TDD |  | 5% | 0 | 19
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE RF/RRM
8DL RF Rx test cases | 36.521-1 Rx 8DL | 0% | 0 | 9 | 0% | 0 | 9 | 0% | 0 | 9 | 0% | 0 | 9
8DL RF Rx test cases Demod/QSI reporting | 36.521-1 Perf 8DL | 0% | 0 | 24 | 0% | 0 | 8 | 0% | 0 | 6 | 0% | 0 | 10
8DL RRM test cases | 36.521-3 RRM 8DL
5 References
[1] RP-181605 | New Work Item Proposal: UE Conformance Test Aspects – Rel-16 LTE CA configurations; Supporting companies: Bureau Veritas, CAICT, China Unicom, CMCC, Ericsson, Huawei, Korea Testing Laboratory, NTT DOCOMO, INC., Sprint, SRTC, Tejet, Telecom Italia, Verizon
[2] RAN5 PRD20 | E-UTRA CA configuration handling in RAN5 (Release 10 and later releases)
Download PRD20 from here: ftp://ftp.3gpp.org/TSG_RAN/WG5_Test_ex-T1/PRD/
WP closed without introducing any new
8DL LTE CA test cases due to low industry interest
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects – Rel-16 CA configurations | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_CA_R16-UEConTest
WP Scope: |  | This work plan is limited to the addition of new and update of existing Rel-16 LTE CA test cases for the new types of CA configuration introduced by this basket work item as endorsed by RAN5 in R5-215708 at RAN5#92-e. Completed CA configuration are listed in TS 36.521-2 clause A.4.6. Tracking of the responsible companies and guidlines for introducing new LTE CA configurations can be found in the RAN5 Permanent Reference Document [2] PRD20 . Introducing new LTE CA Configuration shall be in accordance to the guidelines in [2] PRD20. | [12 empty] | vs Area
WP Resp: |  | Leif Mattisson, Ericsson |  |  | leif.mattisson@ericsson.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD | FDD + TDD
[14 empty] | 5% | 5% | 5%
[14 empty] | 17 | 15 | 19
[14 empty] | 17 | 15 | 19
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
8DL LTE CA test cases
TS 36.521-1: 8DL RF Rx test cases
1 | Y | 36.521-1 Rx 8DL | [7.3A.13] | Reference sensitivity level for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
2 | Y | 36.521-1 Rx 8DL | [7.4A.11] | Maximum input level for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
3 | Y | 36.521-1 Rx 8DL | [7.4A.11_H] | Maximum input level for 8DL CA for 256QAM in DL | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
4 | Y | 36.521-1 Rx 8DL | [7.5A.11] | Adjacent Channel Selectivity (ACS) for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
5 | Y | 36.521-1 Rx 8DL | [7.6.1A.11] | In-band blocking for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
6 | Y | 36.521-1 Rx 8DL | [7.6.2A.11] | Out-of-band blocking for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
7 | Y | 36.521-1 Rx 8DL | [7.6.3A.11] | Narrow band blocking for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
8 | Y | 36.521-1 Rx 8DL | [7.7A.11] | Spurious response for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
9 | Y | 36.521-1 Rx 8DL | [7.8.1A.11] | Wideband intermodulation for 8DL CA | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0%
TS 36.521-1: 8DL Demod/QSI reporting test cases
10 | Y | 36.521-1 Perf 8DL | [8.2.1.1.1_A.8] | FDD PDSCH Single Antenna Port Performance for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
11 | Y | 36.521-1 Perf 8DL | [8.2.1.3.1_A.8] | FDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
12 | Y | 36.521-1 Perf 8DL | [8.2.1.4.2_A.7] | FDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
13 | Y | 36.521-1 Perf 8DL | [8.2.2.1.1_A.7] | TDD PDSCH Single Antenna Port Performance for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
14 | Y | 36.521-1 Perf 8DL | [8.2.2.3.1_A.7] | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
15 | Y | 36.521-1 Perf 8DL | [8.2.2.4.2_A.8] | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
16 | Y | 36.521-1 Perf 8DL | [8.2.3.1.1.7] | TDD FDD CA PDSCH Single Antenna Port Performance for FDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
17 | Y | 36.521-1 Perf 8DL | [8.2.3.1.2.7] | TDD FDD CA PDSCH Single Antenna Port Performance for TDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
18 | Y | 36.521-1 Perf 8DL | [8.2.3.2.1.7] | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for FDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
19 | Y | 36.521-1 Perf 8DL | [8.2.3.2.2.7] | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for TDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
20 | Y | 36.521-1 Perf 8DL | [8.2.3.3.1.7] | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for FDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
21 | Y | 36.521-1 Perf 8DL | [8.2.3.3.2.7] | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for TDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
22 | Y | 36.521-1 Perf 8DL | [8.7.1.1_A.8] | FDD Sustained data rate performance for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
23 | Y | 36.521-1 Perf 8DL | [8.7.1.1_H.8] | FDD Sustained data rate performance for CA (8DL CA) for 256QAM in DL | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
24 | Y | 36.521-1 Perf 8DL | [8.7.2.1_A.8] | TDD sustained data rate performance for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
25 | Y | 36.521-1 Perf 8DL | [8.7.2.1_H.8] | TDD sustained data rate performance for CA (8DL CA) for 256QAM in DL | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
26 | Y | 36.521-1 Perf 8DL | [8.7.5.1.7] | TDD FDD CA Sustained data rate performance for FDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
27 | Y | 36.521-1 Perf 8DL | [8.7.5.1_H.7] | TDD FDD CA Sustained data rate performance for FDD PCell (8DL CA) for 256QAM in DL | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
28 | Y | 36.521-1 Perf 8DL | [8.7.5.2.7] | TDD FDD CA Sustained data rate performance for TDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
29 | Y | 36.521-1 Perf 8DL | [8.7.5.2_H.7] | TDD FDD CA Sustained data rate performance for TDD PCell (8DL CA) for 256QAM in DL | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
30 | Y | 36.521-1 Perf 8DL | [9.6.1.1_A.7] | FDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
31 | Y | 36.521-1 Perf 8DL | [9.6.1.2_A.7] | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
32 | Y | 36.521-1 Perf 8DL | [9.6.1.3.7] | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for FDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
33 | Y | 36.521-1 Perf 8DL | [9.6.1.4.7] | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for TDD PCell (8DL CA) | Add test case variant for 8DL |  | TBD |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.