## Cover sheet
3GPP TSG-RAN WG5 Meeting #97 | [10 empty] | R5-226034
Toulouse, France, 14th Nov 2022 - 18th Nov 2022
Agenda Item: | 7.4.2
Source: | MediaTek Inc.
Title: | WP UE Conformance Test Aspects - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects
Work item code: | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
The objective of this work item is to provide conformance tests for the protocol aspects of the NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects core requirement: At the RAN#96-emeeting in Jun 2022,Rel-17 RAN5 work item for UE Conformance Test Aspects- NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects [1] was approved. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 95% (+50%) | 14 (+7) | 14
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Applications) |  | 95% (+50%) | 14 (+7) | 14
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
EPS
EPS Common
Common test environment | 36.508 | 90% (+10%) |  |  | 90% (+10%)
Common ICS | 36.523-2 | 100% |  |  | 100%
EPS RAN and CN protocols
Protocol test cases | 36.523-1 | 100% (+50%) | 14 (+7) | 14 | 100% (+50%) | 14 (+7) | 14
Applicability Protocol test cases | 36.523-2 | 100% (+50%) |  |  | 100% (+50%)
Test suites (TTCN) | 36.523-3 | 0%
5 References
[1] RP-221548 | New WID on UE Conformance Test Aspects – NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects；MediaTek Inc.
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest
WP Scope: |  | The purpose of present document is to provide a work plan for the RAN5 work item UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Daiwei Zhou, MediaTek Inc. |  |  | daiwei.zhou@mediatek.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD
[12 empty] | Overall |  | 95% (+50%)
[12 empty] | Number of WP items |  | 21
[12 empty] | Sum weight of WP items |  | 20.5
Contribution by work plan analysis
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
NTN IoT
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
1 |  | 36.508 | 3.3 | Abbreviation of NTN |  | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225359 |  | 0.5 | 100% | 100% |  | 100%
EPS - RAN and CN
EPS Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
2 |  | 36.508 | 4.4.3 | Common parameters for simulated E-UTRA cells | Common parameters for eMTC | MediaTek Inc. | RAN5#97 (Nov-22) | R5-225359 R5-226377 R5-227490 | NTN bands and test frequency need to be added into TS 36.508. | 1 | 90% (+10%) | 90% (+10%) |  | 90%
3 |  | 36.508 | 8.1.4.3 | NB-IoT Common parameters for simulated cells | Common parameters for NB-IoT | MediaTek Inc. | RAN5#97 (Nov-22) | R5-225359 R5-227490 | NTN bands and test frequency need to be added into TS 36.508. | 1 | 90% (+10%) | 90% (+10%) |  | 90%
TS 36.523-2: Common ICS
|  | 36.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
4 |  | 36.523-2 | A.4.4 | General Capabilities of IoT NTN |  | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225015 R5-226032 |  | 1 | 100% | 100% |  | 100%
RAN and CN protocol
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
eMTC
5 | Y | 36.523-1 | 6.1.1.10 | eMTC / NTN / GSO | **** TP1: [TS 36.300 clauses 4.12, 23.21.1 and 23.21.6, TS 36.331 clauses 5.2.2.3, 5.2.2.4, 5.3.3.1a and 5.3.3.4] with { UE in EMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by E-UTRA RAT } ensure that { when { Cell broadcasts systemInformationBlockType31 and UE has a valid GNSS position } then { UE establishes RRC connection, and includes gnss-validityDuration in RRCConnectionSetupComplete message, and successfully performs an attach procedure } } | MediaTek Inc. | RAN5#97 (Nov-22) | R5-227491 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6 | Y | 36.523-1 | 6.1.1.11 | eMTC / NTN / MultiTAC | **** TP1: [TS 36.331 clause 5.2.2.7 and 6.2.2] with { UE in EMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by E-UTRA RAT } ensure that { when { systemInformationBlockType1 broadcast more than one TAC per PLMN } then { UE forwards the trackingAreaList to upper layers for mobility management procedure } } | Qualcomm Inc. | RAN5#97 (Nov-22) | R5-227266 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
7 | Y | 36.523-1 | 7.1.6.6 | eMTC / NTN / DRX / (UL)HARQ RTT | **** TP1: [TS 36.321 clauses 3.1, 5.7, 7.7 and Annex C] (1) with { UE in E-UTRA RRC_CONNECTED state with DRX cycle configured and a new DL transmission is indicated on the PDCCH during Active Time} ensure that { when { After expiry of the HARQ RTT timer with the consideration of UE-eNB RTT } then { UE starts or restarts the Drx-InactivityTimer-r13 and monitors the PDCCH for Drx-InactivityTimer-r13 PDCCH periods } } (2) with { UE in E-UTRA RRC_CONNECTED state and DRX cycle is configured } ensure that { when { when a HARQ RTT Timer expires with the consideration of UE-eNB RTT and the data in the soft buffer of the corresponding HARQ process has not been successfully decoded } then { UE starts the drx-RetransmissionTimer-r13 for the corresponding HARQ process and monitors the PDCCH for drx-RetransmissionTimer-r13 consecutive PDCCH periods } } | MediaTek Inc. | RAN5#97 (Nov-22) | R5-227492 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
8 | Y | 36.523-1 | 7.1.4.43 | eMTC / NTN / UE specific TA report / UE specific Koffset | **** TP1: [TS 36.331 clauses 5.3.3.2, TS 36.321 clauses 5.4.9, 5.26, 6.1.3.20 and 6.3.1.21] (1) with { UE in RRC_IDLE state and ta-Report is configured with value enabled in SystemInformationBlockType2-NB } ensure that { when { during the Random Access procedure } then { UE performs the Timing Advance reporting procedure } } (2) with { UE in RRC_CONNECTED state and k-Offset-r17 is broadcasted in SystemInformationBlockType31-NB } ensure that { when { Differential Koffset MAC CE is received } then { UE indicates to lower layers the Differential Koffset for TA reporting } } | MediaTek Inc. | RAN5#97 (Nov-22) | R5-227493 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
9 | Y | 36.523-1 | 7.2.2.12 | eMTC / NTN / AM RLC / Receiver status triggers / extended t-Reordering configured | **** TP1: [TS 36.322 clause 5.1.3.2.3, 5.1.3.2.4, 7.1 and TS 36.331 clause 6.3.2] (1) with { UE in RRC_CONNECTED state } ensure that { when { t-ReorderingExt-r17 is configured } then { UE ignores the value signaled by t-Reordering-r14 and uses the extended value t-ReorderingExt-r17 } } | MediaTek Inc. | RAN5#97 (Nov-22) | R5-227494 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
10 | Y | 36.523-1 | 8.5.6.1 | eMTC / NTN / Ephemeris information update / T317 Expiry / T318 Expiry | **** TP1: [TS 36.331 clauses 5.2.1.3, 5.2.2.4, 5.2.2.39, 5.3.18 and 5.3.11.3] (1) with { UE has acquired SystemInformationBlockType31 and starts timer T317 with the duration ul-SyncValidityDuration } ensure that { when { T317 expires in RRC_CONNECTED state } then { UE informs lower layers that the UL synchronisation is lost and start T318 } } (2) with { UE has starts T318 in RRC_CONNECTED state } ensure that { when { T318 expires } then { UE considerx radio link failure and initiates the connection re-establishment procedure } } | MediaTek Inc. | RAN5#97 (Nov-22) | R5-227495 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
11 | Y | 36.523-1 | 9.2.1.1.34 | eMTC TC NB-IoT / NTN / GNSS position reporting / reject cause #78 "PLMN not allowed to operate at the present UE location" | **** TP1: [TS 24.301 clauses 4.11.2, 5.5.1.2.5 and 5.5.1.2.6] (1) with { UE has sent an ATTACH REQUEST message } ensure that { when { UE receives an ATTACH REJECT message with the reject cause set to "PLMN not allowed to operate at the present UE location" } then { UE sets the EPS update status to EU3 ROAMING NOT ALLOWED, UE deletes the GUTI, last visited registered TAI, TAI list and eKSI, UE resets the registration attempt counter, UE enters the state EMM-DEREGISTERED.PLMN-SEARCH and perform a PLMN selection } } | Qualcomm Inc. | RAN5#97 (Nov-22) | R5-227269 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
NB-IoT
12 | Y | 36.523-1 | 22.1.2 | NB-IoT/ NTN / GSO | **** TP1: [TS 36.300 clauses 4.12, 23.21.1 and 23.21.6, TS 36.331 clauses 5.2.2.3, 5.2.2.4, 5.3.3.1a and 5.3.3.4] with { UE in EMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by NB-IoT RAT } ensure that { when { Cell broadcasts systemInformationBlockType31-NB and UE has a valid GNSS position } then { UE establishes RRC connection, and includes gnss-validityDuration in RRCConnectionSetupComplete-NB message, and successfully performs an attach procedure } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225360 |  | 1 | 100% | 100% |  | 100%
13 | Y | 36.523-1 | 22.2.13 | NB-IoT / NTN / Multi-TAC | **** TP1: [TS 36.331 clauses 5.2.2.7 and 6.7.2] with { UE in EMM-REGISTERED/RRC-IDLE and UE finds a cell which provides access by NB-IoT RAT } ensure that { when { systemInformationBlockType1-NB broadcast more than one TAC per PLMN } then { UE forwards the trackingAreaList to upper layers for mobility management procedure } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225361 R5-226797 |  | 1 | 100% | 100% |  | 100%
14 | Y | 36.523-1 | 22.3.1.5a | NB-IoT / NTN / DRX / (UL)HARQ RTT | **** TP1: [TS 36.321 clauses 3.1, 5.7, 7.7 and Annex C] (1) with { UE in E-UTRA RRC_CONNECTED state with DRX cycle configured and a new DL transmission is indicated on the NPDCCH during Active Time } ensure that { when { After expiry of the HARQ RTT timer with the consideration of UE-eNB RTT } then { UE starts or restarts the Drx-InactivityTimer-r13 and monitors the NPDCCH for Drx-InactivityTimer-r13 NPDCCH periods } } (2) with { UE in E-UTRA RRC_CONNECTED state and DRX cycle is configured } ensure that { when { when a HARQ RTT Timer expires with the consideration of UE-eNB RTT and the data in the soft buffer of the corresponding HARQ process has not been successfully decoded } then { UE starts the drx-RetransmissionTimer-r13 for the corresponding HARQ process and monitors the NPDCCH for drx-RetransmissionTimer-r13 consecutive NPDCCH periods } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225133 R5-226458 |  | 1 | 100% | 100% |  | 100%
15 | Y | 36.523-1 | 22.3.1.13 | NB-IoT / NTN / UE specific TA report / UE specific Koffset | **** TP1: [TS 36.331 clauses 5.3.3.2, TS 36.321 clauses 5.4.9, 5.26, 6.1.3.20 and 6.3.1.21] (1) with { UE in RRC_IDLE state and ta-Report is configured with value enabled in SystemInformationBlockType2-NB } ensure that { when { during the Random Access procedure } then { UE performs the Timing Advance reporting procedure } } (2) with { UE in RRC_CONNECTED state and k-Offset-r17 is broadcasted in SystemInformationBlockType31-NB } ensure that { when { Differential Koffset MAC CE is received } then { UE indicates to lower layers the Differential Koffset for TA reporting } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225134 R5-226445 |  | 1 | 100% | 100% |  | 100%
16 | Y | 36.523-1 | 22.3.2.7a | NB-IoT / NTN / AM RLC / Receiver status triggers / extended t-Reordering configured | **** TP1: [TS 36.322 clause 5.1.3.2.3, 5.1.3.2.4, 7.1 and TS 36.331 clause 6.7.3] (1) with { UE in RRC_CONNECTED state and twoHARQ-ProcessesConfig is set to TRUE } ensure that { when { t-ReorderingExt-r17 is configured } then { UE ignores the value signalled by t-Reordering-r14 and uses the extended value t-ReorderingExt-r17 } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225135 R5-226458 |  | 1 | 100% | 100% |  | 100%
17 | Y | 36.523-1 | 22.4.30 | NB-IoT / NTN / Ephemeris information update / T317 Expiry / T318 Expiry | **** TP1: [TS 36.331 clauses 5.2.1.3, 5.2.2.4, 5.2.2.39, 5.3.18 and 5.3.11.3] (1) with { UE has acquired SystemInformationBlockType31-NB and starts timer T317 with the duration ul-SyncValidityDuration } ensure that { when { T317 expires in RRC_CONNECTED state } then { UE informs lower layers that the UL synchronisation is lost and start T318 } } (2) with { UE has starts T318 in RRC_CONNECTED state } ensure that { when { T318 expires } then { UE considers radio link failure and initiates the connection re-establishment procedure } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225165 |  | 1 | 100% | 100% |  | 100%
18 | Y | 36.523-1 | 22.5.23 | NB-IoT / NTN / GNSS position reporting / reject cause #78 "PLMN not allowed to operate at the present UE location" | **** TP1: [TS 24.301 clauses 4.11.2, 5.5.1.2.5 and 5.5.1.2.6] (1) with { UE has sent an ATTACH REQUEST message } ensure that { when { UE receives an ATTACH REJECT message with the reject cause set to "PLMN not allowed to operate at the present UE location" } then { UE sets the EPS update status to EU3 ROAMING NOT ALLOWED, UE deletes the GUTI, last visited registered TAI, TAI list and eKSI, UE resets the registration attempt counter, UE enters the state EMM-DEREGISTERED.PLMN-SEARCH and perform a PLMN selection } } | MediaTek Inc. | RAN5#96 (Aug-22) | R5-225166 |  | 1 | 100% | 100% |  | 100%
TS 36.523-2: Applicability for Protocol test cases
19 |  | 36.523-2 | 4.1 | Applicability for protocal test case |  |  | RAN5#97 (Nov-22) | R5-225020 R5-226032 |  | 1 | 100% (+50%) | 100% (+50%) |  | 100%
20 |  | 36.523-2 | 4.2 | Applicability of Protocol conformance test cases Conditions |  |  | RAN5#97 (Nov-22) | R5-225020 R5-226033 R5-227270 |  | 1 | 100% (+50%) | 100% (+50%) |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
21 |  | 36.523-3 | <Clause> | Addition of NTN IoT Test Model |  |  | RAN5#98 (Feb-23) |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.