## Cover sheet
3GPP TSG-RAN WG5 Meeting #97 | [10 empty] | R5-226450
Toulouse, France, 14th Nov - 18th Nov 2022
Agenda Item: | 7.4.2
Source: | CATT
Title: | WP UE Conformance Test Aspects - UE Power Saving in NR
Work item code: | NR_UE_pow_sav-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#88-e meeting a Rel-16 RAN5 work item for UE power saving in NR (NR_UE_pow_sav-UEConTest) was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+1%) | 20 (+4) | 20
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+0.5%) | 20 (+4) | 20
FR1 |  | 100% (+0.9%) | 15 (+4) | 15
FR2 |  | 100% | 10 | 10
FR1 + FR2 |  | 100% | 1 | 1
NSA Option 3 (EN-DC) |  | 100% (+1.3%) | 9 (+4) | 9
FR1 |  | 100% (+2.3%) | 8 (+4) | 8
FR2 |  | 100% | 5 | 5
FR1 + FR2 |  | 100% | 1 | 1
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  | 100%
Common ICS | 38.508-2
UE specific test functions | 38.509 | 100% |  |  | 100% |  |  | 100%
NR RF/RRM
RF Demod/QSI test cases | 38.521-4 | 100% (+2.6%) | 5 (+4) | 5 | 100% (+4.7%) | 4 (+4) | 4 | 100% | 1 | 1 |  |  |  | 100% (+5%) | 4 (+4) | 4 | 100% | 1 | 1
RRM test cases | 38.533 | 100% | 10 | 10 | 100% | 6 | 6 | 100% | 4 | 4
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100% |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% |  |  | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% | 5 | 5 | 100% | 5 | 5 | 100% | 5 | 5 | 100% | 1 | 1 | 100% | 4 | 4 | 100% | 4 | 4 | 100% | 1 | 1
Applicability Protocol test cases | 38.523-2 | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200930 | New WI Proposal: UE Conformance Test Aspects – UE Power Saving in NR – CATT
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - UE power saving in NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_UE_pow_sav-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects - UE power saving in NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Huiying Zhang, CATT |  |  | zhanghuiying@catt.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 100% (+0.9%) | 100% | 100% | 100% (+2.3%) | 100% | 100%
[15 empty] | 31 | 26 | 1 | 12 | 10 | 1
[15 empty] | 22 | 16.6 | 1 | 8.3 | 5.6 | 1
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | Common test environments | Definition of common test environment for the UE power saving | CATT, Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-205288 R5-215936 R5-216761 |  | 0.5 | 100% | 100% |  |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | A.4 | ICS proforma tables | Common Implementation Conformance Statement (ICS) proforma | Introduction of common implementation conformance statement (ICS) for the UE power saving | CATT, Huawei, Hisilicon,Qualcomm | RAN5#92 (Aug-21) | R5-205612 R5-211463 R5-214565 R5-215161 R5-220750 |  | 0.5 | 100% | 100% |  |  | 100% | 100%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.509 | 5.8, 6.8 | UAI test function | Special Test Function to test UE Assistance Information | Qualcomm | RAN5#90-e (Feb-21) | R5-211549 |  | 1 | 100% | 100% |  |  | 100% | 100%
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
31 | Y | 38.521-4 | 5.3.2.1.3 | 2Rx FDD FR1 PDCCH 1 Tx antenna performance for power saving | Verifying UE can perform PDCCH-WUS feature/function designed in RAN1/RAN2 correctly for FDD UE in FR1. | Huawei, Hisilicon Anritsu, Keysight | RAN5#97 (Nov-22) | R5-216112 R5-218328 R5-220751 R5-222499 R5-224537 R5-225726 R5-226461 R5-227090 R5-227333 |  | 1 | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% |  |  | 100%
32 | Y | 38.521-4 | 5.3.3.1.3 | 4Rx FDD FR1 PDCCH 1 Tx antenna performance for power saving | Verifying UE can perform PDCCH-WUS feature/function designed in RAN1/RAN2 correctly for FDD UE in FR1. | Huawei, Hisilicon Anritsu, Keysight | RAN5#97 (Nov-22) | R5-216113 R5-218329 R5-220936 R5-225726 R5-226461 R5-227090 R5-227333 |  | 1 | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% |  |  | 100%
33 | Y | 38.521-4 | 5.3.2.2.3 | 2Rx TDD FR1 PDCCH 1 Tx antenna performance for power saving | Verifying UE can perform PDCCH-WUS feature/function designed in RAN1/RAN2 correctly for TDD UE in FR1. | CATT, Anritsu, Keysight | RAN5#97 (Nov-22) | R5-216072 R5-218465 R5-225727 R5-226461 R5-227090 R5-227333 |  | 1 | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% |  |  | 100%
34 | Y | 38.521-4 | 5.3.3.2.3 | 4Rx TDD FR1 PDCCH 1 Tx antenna performance for power saving | Verifying UE can perform PDCCH-WUS feature/function designed in RAN1/RAN2 correctly for TDD UE in FR1. | CATT Anritsu, Keysight | RAN5#97 (Nov-22) | R5-216073 R5-218465 R5-220936 R5-225727 R5-227991 R5-227090 R5-227333 |  | 1 | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% |  |  | 100%
35 |  | 38.521-4 | 7.1.1_1 | Applicability of test requirements due to maximum achievable SNR |  | CATT | RAN5#92 (Aug-21) | R5-216074 |  | 0.1 | 100% | 100% |  |  |  | 100%
36 | Y | 38.521-4 | 7.3.2.2.3 | 2Rx TDD FR2 PDCCH 1 Tx antenna performance for power saving | Verifying UE can perform PDCCH-WUS feature/function designed in RAN1/RAN2 correctly for TDD UE in FR2. | CATT, Anritsu | RAN5#93 (Nov-21) | R5-216074 R5-218465 R5-227090 |  | 1 | 100% | 100% | 100% |  |  | 100% |  |  | 100%
37 |  | 38.521-4 | Annex F，G | Measurement of Demod Performance requirements |  | CATT, Huawei, Hisilicon, Anritsu | RAN5#97 (Nov-22) | R5-215937 R5-226461 |  | 0.3 | 100% | 100% | 100% |  | 100% | 100% |  |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
4 |  | 38.522 | 4.1.4 | Performance conformance test cases | Introduction of test applicability for UE power saving Performance conformance test cases | CATT, Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-214571 |  | 0.3 | 100% | 100% |  |  | 100% | 100%
5 |  | 38.522 | 4.2 | RRM conformance test cases | Introduction of test applicability for UE power saving RRM conformance test cases | CATT, Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-214571 |  | 0.3 | 100% | 100% |  |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.533 | 6.1.1.0.3 | Minimum conformance requirement for intra-frequency NR cells for UE configured with relaxed measurement criterion |  | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-215020 |  | 0.5 | 100% | 100% |  |  | 100%
7 |  | 38.533 | 6.1.1.0.4 | Minimum conformance requirement for inter-frequency NR cells for UE configured with relaxed measurement criterion |  | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-215022 |  | 0.5 | 100% | 100% |  |  | 100%
8 | Y | 38.533 | 6.1.1.3 | NR SA FR1 cell re-selection for UE fulfilling low mobility relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for intra-frequency measurement correctly for UE fulfilling low mobility criterion | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215023 R5-216886 |  | 1 | 100% | 100% |  |  | 100%
9 | Y | 38.533 | 6.1.1.4 | NR SA FR1 cell re-selection for UE fulfilling not-at-cell edge relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for intra-frequency measurement correctly for UE fulfilling not-at-cell edge criterion | Huawei, Hisilicon, keysight | RAN5#93 (Nov-21) | R5-215024 R5-216887 R5-227335 |  | 1 | 100% | 100% |  |  | 100%
10 | Y | 38.533 | 6.1.1.5 | NR SA FR1-FR1 cell re-selection for UE fulfilling low mobility relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for inter-frequency measurement correctly for UE fulfilling low mobility relaxed measurement criterion | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215025 R5-216888 |  | 1 | 100% | 100% |  |  | 100%
11 | Y | 38.533 | 6.1.1.6 | NR SA FR1-FR1 cell re-selection for UE fulfilling not-at-cell edge relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for inter-frequency measurement correctly for UE fulfilling not-at-cell edge relaxed measurement criterion | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215026 R5-216889 |  | 1 | 100% | 100% |  |  | 100%
12 |  | 38.533 | 6.1.2.0.2 | Minimum conformance requirement for inter-RAT E-UTRAN cells for UE configured with relaxed measurement criterion |  | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-215940 |  | 0.5 | 100% | 100% |  |  | 100%
13 | Y | 38.533 | 6.1.2.3 | NR SA FR1 – E-UTRA cell re-selection to lower priority E-UTRAN for UE fulfilling low mobility relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for inter-RAT measurement correctly in Low mobility state | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-216143 R5-217395 |  | 1 | 100% | 100% |  |  | 100%
14 | Y | 38.533 | 6.1.2.4 | NR SA FR1 – E-UTRA cell re-selection to lower priority E-UTRAN for UE fulfilling not-at-cell edge relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for inter-RAT measurement correctly in Not-at-cell-edge | Huawei, Hisilicon, keysight | RAN5#93 (Nov-21) | R5-216144 R5-217395 R5-227337 |  | 1 | 100% | 100% |  |  | 100%
15 |  | 38.533 | 7.1.1.0.3 | Minimum conformance requirement for intra-frequency NR cells for UE configured with relaxed measurement criterion |  | CATT | RAN5#92 (Aug-21) | R5-215368 |  | 0.5 | 100% | 100% |  |  |  | 100%
16 |  | 38.533 | 7.1.1.0.4 | Minimum conformance requirement for inter-frequency NR cells for UE configured with relaxed measurement criterion |  | CATT | RAN5#92 (Aug-21) | R5-215368 |  | 0.5 | 100% | 100% |  |  |  | 100%
17 | Y | 38.533 | 7.1.1.3 | NR SA FR2 cell re-selection for UE fulfilling low mobility relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for FR2 intra-frequency measurement correctly for UE fulfilling low mobility criterion | CATT, Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-216364 R5-225855 |  | 1 | 100% | 100% |  |  |  | 100%
18 | Y | 38.533 | 7.1.1.4 | NR SA FR2 cell re-selection for UE fulfilling not-at-cell edge relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for FR2 intra-frequency measurement correctly for UE fulfilling not-at-cell edge criterion | CATT, Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-216365 R5-225856 |  | 1 | 100% | 100% |  |  |  | 100%
19 | Y | 38.533 | 7.1.1.5 | NR SA FR2-FR2 cell re-selection for UE fulfilling low mobility relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for FR2 inter-frequency measurement correctly for UE fulfilling low mobility criterion | CATT, Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-215938 R5-225857 |  | 1 | 100% | 100% |  |  |  | 100%
20 | Y | 38.533 | 7.1.1.6 | NR SA FR2-FR2 cell re-selection for UE fulfilling not-at-cell edge relaxed measurement criterion | Verifying UE can perform relaxed RRM requirements for FR2 inter-frequency measurement correctly for UE fulfilling not-at-cell edge criterion | CATT, Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-216366 R5-225858 |  | 1 | 100% | 100% |  |  |  | 100%
21 |  | 38.533 | Annex E,F | Cell configuration mapping and Measurement of RRM requirements |  | Huawei, Hisilicon, CATT | RAN5#96 (Aug-22) | R5-215939 R5-215941 R5-216890 R5-217396 R5-225859 |  | 0.3 | 100% | 100% |  |  | 100% | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
38 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 |  | Huawei, Hisilicon, CATT | RAN5#96 (Aug-22) | R5-218330 R5-218331 R5-218332 R5-218333 R5-218334 R5-225860 R5-225861 R5-225862 R5-225863 |  | 2 | 100% | 100% |  |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
|  | 38.523-1 | 7.1.1.12 | UE power saving | New sub-section title |  |  |  |  | 0 | 100% | 100% |  |  | 100% | 100%
22 | Y | 38.523-1 | 7.1.1.12.1 | Void |  | CATT | RAN5#91-e (May-21) | R5-212538 |  | 0 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
23 | Y | 38.523-1 | 7.1.1.12.2 | Void |  | CATT | RAN5#91-e (May-21) | R5-212538 |  | 0 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
24 | Y | 38.523-1 | 7.1.1.12.3 | DRX adaptation / UE wakeup indication | 1. Verifying wakeup-indication can wake up UE correctly when DCP is configured 2. Verifying RRC parameter ps-wakeup can wake up UE when DCP is configured but not detected 3. Verifying UE performs normal DRX operations when all DCP occasions occur in DRX active time 4. Verifying UE performs normal DRX operations when all DCP occasions occur during measurement gap 5. Verifying UE does not enter DRX active state and skips monitoring the PDCCH when reveived the value of wake-up indication is 0 | CATT | RAN5#89-e (Nov-20) | R5-206418 R5-221530 R5-222362 |  | 1 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
25 |  | 38.523-1 | 7.1.1.12.4 | SCell dormancy indication | [5 empty] | 0 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
26 | Y | 38.523-1 | 7.1.1.12.4.1 | DRX adaptation / SCell dormancy indication / Intra-band Contiguous CA | 1. Verifying the DCI 2_6 can instruct the UE to enter or leave the dormant BWP of SCell outside DRX active time1. Verifying the DCI 2_6 can instruct the UE to enter or leave the dormant BWP of SCell outside DRX active time | CATT | RAN5#90-e (Feb-21) | R5-211358 R5-225297 |  | 1 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
27 | Y | 38.523-1 | 7.1.1.12.4.2 | DRX adaptation / SCell dormancy indication / Intra-band non Contiguous CA | 1. Verifying the DCI 2_6 can instruct the UE to enter or leave the dormant BWP of SCell outside DRX active time | CATT | RAN5#90-e (Feb-21) | R5-211358 R5-225297 |  | 1 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
28 | Y | 38.523-1 | 7.1.1.12.4.3 | DRX adaptation / SCell dormancy indication / Inter-band CA | 1. Verifying the DCI 2_6 can instruct the UE to enter or leave the dormant BWP of SCell outside DRX active time | CATT | RAN5#90-e (Feb-21) | R5-211358 R5-225297 |  | 1 | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100%
RRC
|  | 38.523-1 | 8.1.5.10 | UE Assistance Information | New sub-section title |  |  |  |  | 0
29 | Y | 38.523-1 | 8.1.5.10.1 | UE Assistance Information/ Release Preference | TS38.331 Cl 5.7.4 | Qualcomm | RAN5#92 (Aug-21) | R5-216272 |  | 1 | 100% | 100% |  |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
30 |  | 38.523-2 | 4.1, 4.2 | Protocol conformance test cases applicability | Addition of test applicabilities of test cases for UE power saving in NR | CATT,Qualcomm | RAN5#92 (Aug-21) | R5-205287 R5-211464 R5-214758 R5-225298 |  | 0.3 | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.