## Cover sheet
RAN5 meeting #97 | [8 empty] | R5-226631
Toulouse, France, Nov 14 - 18, 2022
Agenda Item: | 7.4.2
Source: | Qualcomm Incorporated
Title: | WP - UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum
Work item code: | NR_unlic-UEConTest-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 28% (+3%) | 5 | 249 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 34.3% (+3.2%) | 5 | 172 (+2)
FR1 |  | 34.3% (+3.2%) | 5 | 172 (+2)
NSA Option 3 (EN-DC) |  | 8.1% (+2.5%) | 0 | 85
FR1 |  | 8.1% (+2.8%) | 0 | 85
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
5GS
5GS Common
Common test environment | 38.508-1 | 50% (+13.2%) |  |  | 50% (+10%) |  |  |  |  | 50% (+20%)
Common ICS | 38.508-2 | 26.6% (+19.1%) |  |  | 16% (+8.5%) |  |  |  |  | 50% (+50%)
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 60.1% (+2.7%) | 2 | 34 (+2) | 60.1% (+2.7%) | 2 | 34 (+2)
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 7.5% (+7.5%) | 0 | 8 | 7.5% (+7.5%) | 0 | 8 |  |  | 7.5% (+7.5%) | 0 | 8
RRM test cases | 38.533 | 0.6% (+0.6%) | 0 | 185 | 0% | 0 | 109 |  |  | 2% (+2%) | 0 | 76
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 10% (+10%) |  |  | 10% (+10%) |  |  |  |  | 10% (+10%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 12.5% (+0%) | 3 | 22 | 18.2% | 3 | 21 |  |  | 0% | 0 | 1
Applicability Protocol test cases | 38.523-2 | 10.3% (+0.1%) |  |  | 15% |  |  |  |  | 0%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0%
5 References
[2] R5-224796 | WP - UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | NR-based access to unlicensed spectrum - (TS 38.533) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_unlic-UEConTest-UEConTest
WP Scope: |  | This part of the work plan covers Radio Resource Management test cases for NR based access to unlicensed spectrum for range 1 (sub-6 GHz)
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 34.3% (+3.2%) | 8.1% (+2.8%)
[15 empty] | 195 (+4) | 90 (+2)
[15 empty] | 280.6 (+18) | 88 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). XXXXDX | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
1 |  | 38.508-1 | 4, 5 | Introduction of General and RF Demod Test Environment for Rel-16 NR-U | [5 empty] | 1
2 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-16 NR-U |  |  | RAN5#97 (Nov-22) | R5-217949 R5-217950 R5-217951 R5-216773 R5-224033 R5-224034 R5-224909 R5-225321 R5-224912 R5-224913 R5-224914 R5-224915 R5-224916 R5-224917 R5-226718 R5-226731 | Addition of IEs to default messages. Bands and frequencies addition to 38.508-1 | 1 | 42.5% (+7.5%) | 45% (+5%) | 40% (+10%) |  | 50% | 50%
TS 38.508-2: Common ICS
TBD |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-16 NR-U | [5 empty] | 1 | 15% | 15% |  |  | 15%
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
382 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-16 NR-U |  |  |  |  | Addition of PICS parameters | 1 | 0% | 0% |  |  | 0%
3 |  | 38.508-2 | 4 |  | Introduction of common implementation conformance statements for Rel-16 NR-U | Ericsson | RAN5#97 (Nov-22) | R5-214334 R5-227707 R5-227585 |  | 0.5 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TBD |  | 38.509 | TBD | TBD | [5 empty] | 1
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
4 |  | 38.521-1 | 4 | General | define categories of test requirements for NR-U |  | RAN5#97 (Nov-22) | R5-215984 |  | 0.1
5 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement for NR-U |  | RAN5#97 (Nov-22) | R5-215984 R5-222174 |  | 0.1
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 90 | 75% | 75% |  |  | 75%
TBD |  | 38.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
6 |  | 38.521-1 | 6.1 | General | TS38.101-1 cl 6,1, provide general info for chapter 6. |  | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  |  | 0%
7 | Y | 38.521-1 | 6.2F.1 | UE maximum output power |  | Ericsson | RAN5#97 (Nov-22) | R5-215983 R5-224241 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - No test points are defined since there is no configuration satisfying MPR=0dB requirements in RAN4. Testing with 1.5dB MPR has been covered in [6.2F.2]. - MU and TT for >6GHz (band n96). - RMC in Annex A. - Test coverage for UL-MIMO - Message exceptions - Test state and generic procedure are TBD in 38.508-1 | 1 | 70% | 70% |  |  | 70%
8 | Y | 38.521-1 | 6.2F.2 | UE maximum output power reduction |  |  | RAN5#97 (Nov-22) |  | FFS | 1 | 0% | 0% |  |  | 0%
9 | Y | 38.521-1 | 6.2F.3 | UE additional maximum output power reduction |  | Ericsson | RAN5#97 (Nov-22) | R5-218411 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - Test points are TBD - MU and TT for >6GHz (band n96). - RMC in Annex A. - Test coverage for UL-MIMO - Message exceptions - Test state and generic procedure are TBD in 38.508-1 | 1 | 60% | 60% |  |  | 60%
10 | Y | 38.521-1 | 6.2F.4 | Configured transmitted power |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
11 | Y | 38.521-1 | 6.3F.1 | Minimum output power |  | TTA | RAN5#97 (Nov-22) | R5-224811 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - Test configuration table is FFS - MU and TT for >6GHz (band n96). - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
12 | Y | 38.521-1 | 6.3F.2 | Transmit OFF power |  | Ericsson | RAN5#93 (Nov-21) | R5-221894 |  | 1 | 100% | 100% |  |  | 100%
13 | Y | 38.521-1 | 6.3F.3 | Transmit ON/OFF time mask |  | Ericsson | RAN5#97 (Nov-22) | R5-221895 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - Test points are TBD - MU and TT for >6GHz (band n96). - RMC in Annex A. - Test coverage for UL-MIMO - Message exceptions - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
14 |  | 38.521-1 | 6.3F.4 | Power control
15 | Y | 38.521-1 | 6.3F.4.2 | Absolute power tolerance |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
16 | Y | 38.521-1 | 6.3F.4.3 | Relative power tolerance |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
17 | Y | 38.521-1 | 6.3F.4.4 | Aggregate power tolerance |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
18 | Y | 38.521-1 | 6.4F.1 | Frequency Error |  | TTA | RAN5#97 (Nov-22) | R5-224812 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - Test configuration table is FFS - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
19 | Y | 38.521-1 | 6.4F.2.1 | Error Vector Magnitude |  | TTA | RAN5#97 (Nov-22) | R5-227741 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - Test configuration table is FFS - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
65 | Y | 38.521-1 | 6.4F.2.2 | Carrier leakage |  | Qualcomm | RAN5#97 (Nov-22) | R5-227923 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - RB allocation in Test configuration table is TBD - Test state and generic procedure are TBD in 38.508-1 - MU and TT for 5.925GHz < f ≤ 7.125GHz is TBD. | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
20 | Y | 38.521-1 | 6.4F.2.3 | In-band emissions |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
21 | Y | 38.521-1 | 6.4F.2.4 | EVM equalizer spectrum flatness |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
22 | Y | 38.521-1 | 6.5F.1 | Occupied bandwidth |  | TTA | RAN5#97 (Nov-22) | R5-227921 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - Test configuration table is FFS - Test state and generic procedure are TBD in 38.508-1 - MU and TT for > 6GHz (band n96) - Message exception for NR-U | 1 | 60% (+60%) | 60% (+60%) |  |  | 60%
23 |  | 38.521-1 | 6.5F.2.1 | Out of band Emission | [5 empty] | 0.1 | 0% | 0% |  |  | 0%
24 | Y | 38.521-1 | 6.5F.2.2 | Spectrum emission mask for operation with shared spectrum channel access |  | Qualcomm | RAN5#97 (Nov-22) | R5-215564 | Test config table is FFS TP analysis is TBD Message content is TBD | 1 | 60% | 60% |  |  | 60%
25 | Y | 38.521-1 | 6.5F.2.3 | Additional spectrum emission mask |  | Ericsson | RAN5#97 (Nov-22) |  | No requirements yet in 38.101-1 but will come | 1 | 0% | 0% |  |  | 0%
26 | Y | 38.521-1 | 6.5F.2.4.1 | Shared spectrum channel access ACLR |  | Qualcomm | RAN5#97 (Nov-22) | R5-217234 | Editor’s Note: The following aspects are not yet determined: - Test configuration and TP analysis are TBD - MU and TT for >6GHz (band n96) are TBD. - RMC in Annex A. - Test coverage for UL-MIMO - Message exceptions - Test state and generic procedure are TBD in 38.508-1 | 1 | 60% | 60% |  |  | 60%
27 | Y | 38.521-1 | 6.5F.2.4.2 | Additional requirements for network signaled value "NS_29" |  | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
28 | Y | 38.521-1 | 6.5F.3.1 | General spurious emissions |  | Qualcomm | RAN5#97 (Nov-22) | R5-215985 R5-227924 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined - Test state and generic procedure are TBD in 38.508-1 - RB allocation in Test configuration table is TBD - Message exceptions for NR-U is TBD - MU and TT for frequency > 5.925 GHz is TBD | 1 | 60% | 60% |  |  | 60%
29 |  | 38.521-1 | 6.5F.3.2 | Spurious emissions for UE co-existence |  | Qualcomm | RAN5#93 (Nov-21) | R5-215985 | not applicable | 1 | 100% | 100% |  |  | 100%
30 |  | 38.521-1 | 6.5F.3.3 | Additional spurious emissions | [5 empty] | 1 | 0% | 0% |  |  | 0%
31 | Y | 38.521-1 | 6.5F.3.3.1 | Requirements for network signaled value "NS_28" |  | Ericsson | RAN5#97 (Nov-22) |  | Combine all NS values into one test case, 6.5F.3.3 Additional spurious emissions. | 1 | 0% | 0% |  |  | 0%
32 | Y | 38.521-1 | 6.5F.3.3.2 | Requirements for network signaled value "NS_29" |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
33 | Y | 38.521-1 | 6.5F.3.3.3 | Requirements for network signaled value "NS_30" |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
34 | Y | 38.521-1 | 6.5F.3.3.4 | Requirements for network signaled value "NS_31" |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
35 | Y | 38.521-1 | 6.5F.3.3.5 | Requirements for network signaled value "NS_53" or "NS_54" |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
36 | Y | 38.521-1 | 6.5F.4 | Transmit intermodulation |  | Qualcomm | RAN5#93 (Nov-21) | R5-227922 | Editor’s Note: This test is incomplete. The following aspects are not yet determined: - RB allocation in Test configuration table is TBD - Message contents and test procedure specific for NR-U is TBD - MU and TT for frequency > 5.925 GHz is TBD | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
37 |  | 38.521-1 | 7.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  |  | 0%
38 | Y | 38.521-1 | 7.2 | Diversity characteristics |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
39 |  | 38.521-1 | 7.3.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  |  | 0%
40 | Y | 38.521-1 | 7.3F.2 | Reference sensitivity power level for shared spectrum channel access |  | Qualcomm | RAN5#97 (Nov-22) | R5-215562 R5-222738 R5-224244 R5-227926 | Message content for NS_53 is FFS TT for 5.925GHz < f ≤ 7.125GHz is TBD | 1 | 80% | 80% |  |  | 80%
41 | Y | 38.521-1 | 7.3F.3 | ΔRIB,c |  | Qualcomm | RAN5#93 (Nov-21) | R5-217235 |  | 1 | 100% | 100% |  |  | 100%
42 | Y | 38.521-1 | 7.4F | Maximum input level |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
42 | Y | 38.521-1 | 7.5F | Adjacent channel selectivity | TS38.101-1 cl 7.5 | Qualcomm | RAN5#97 (Nov-22) | R5-222746 R5-227925 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - Test Configuration Table is FFS - Message content for NS_53 is FFS - TP analysis is TBD - TT for 5.925GHz < f ≤ 7.125GHz is TBD | 1 | 60% | 60% |  |  | 60%
37 |  | 38.521-1 | 7.6F.1 | General |  |  | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  |  | 0%
38 | Y | 38.521-1 | 7.6F.2.1 | Inband blocking |  | Qualcomm | RAN5#97 (Nov-22) | R5-222739 R5-224899 | Test configuration table is FFS TP analysis is pending | 1 | 70% | 70% |  |  | 70%
39 | Y | 38.521-1 | 7.6F.3 | Out of band blocking |  | Qualcomm | RAN5#97 (Nov-22) | R5-224900 |  | 0 | 90% | 90% |  |  | 90%
40 | Y | 38.521-1 | 7.7F.1 | Spurious response for shared spectrum channel access |  | Qualcomm | RAN5#97 (Nov-22) | R5-224902 R5-227751 |  | 0 | 90% | 90% |  |  | 90%
41 | Y | 38.521-1 | 7.7F.2 | Intra-band contiguous shared spectrum channel access CA |  | Qualcomm | RAN5#97 (Nov-22) | R5-227927 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - TT for 5.925GHz < f ≤ 7.125GHz is TBD - Message contents and test procedure specific for NR-U is TBD | 0 | 65% (+65%) | 65% (+65%) |  |  | 65%
42 |  | 38.521-1 | 7.8F.1 | General |  |  | RAN5#97 (Nov-22) |  | R5-224904 | 0.1 | 100% | 100% |  |  | 100%
43 | Y | 38.521-1 | 7.8F.2 | Wide band Intermodulation |  |  | RAN5#97 (Nov-22) | R5-224904 R5-226763 |  | 1 | 90% | 90% |  |  | 90%
44 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
45 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
46 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
47 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  |  |  |  | 1 | 0% | 0% |  |  | 0%
48 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
49 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#97 (Nov-22) | R5-218411 R5-221894 R5-223754 R5-224905 R5-227741 R5-227928 |  | 1 | 50% (+10%) | 50% (+10%) |  |  | 50%
50 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#97 (Nov-22) | R5-215893 |  | 1 | 10% | 10% |  |  | 10%
51 |  | 38.521-1 | Annex H | Statistical Testing |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-2 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-2 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-3 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-3 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-4: Demodulation performance requirements (conducted requirements)
56 |  | 38.521-4 | 5.1 | General | Exisiting sub-clause header |  |  |  |  | 0.5
57 | Y | 38.521-4 | 5.2.2.2.15.1 | 2Rx TDD FR1 PDSCH performance of Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header | Qualcomm |  | R5-227808 | Editor’s Note: This test case is incomplete. Following aspects are either missing or TBD - Use of PDCCH DCI format 1_1 pending further check - Message contents may need additional NR-U specific IE - Minimum test time analysis FFS - MU/TT is TBD | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
58 | Y | 38.521-4 | 5.2.3.2.15.1 | 4Rx TDD FR1 PDSCH performance of Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
59 | Y | 38.521-4 | 5.2A.2.3.1 | 2Rx FR1 PDSCH performance of Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
60 | Y | 38.521-4 | 5.2A.3.3.1 | 4Rx FR1 PDSCH performance of Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 38.521-4: CSI reporting requirements (conducted requirements)
61 |  | 38.521-4 | 6.1 | General | Exisiting sub-clause header |  |  |  |  | 0.5
62 | Y | 38.521-4 | 6.2.2.2.1.3.1 | 2Rx TDD FR1 CQI reporting under AWGN for Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
63 | Y | 38.521-4 | 6.2.3.2.1.3.1 | 4Rx TDD FR1 CQI reporting under AWGN for Pcell on band with shared spectrum access for both SA and NSA | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
64 | Y | 38.521-4 | 6.2A.3.1.2.1 | 2Rx FR1 CQI reporting under AWGN for Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
65 | Y | 38.521-4 | 6.2A.4.1.1.1 | 4Rx FR1 CQI reporting under AWGN for Scell on band with shared spectrum access for CA (2DLCA) | New sub-clause header |  |  |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 38.521-4: Annex
66 |  | 38.521-4 | Annex A | Measurements Channels | [5 empty] | 1
67 |  | 38.521-4 | Annex B | Propagation conditions | [5 empty] | 1
68 |  | 38.521-4 | Annex C | Downlink physical channels | [5 empty] | 1
69 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | [5 empty] | 1
70 |  | 38.521-4 | Annex G | Statistical testing | [5 empty] | 1
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
71 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-4 | [5 empty] | 1
72 |  | 38.522 |  |  | Introduction of common implementation conformance statements for Rel-16 NR-U | Qualcomm, Ericsson | RAN5#97 (Nov-22) | R5-214334 R5-218371 R5-222736 R5-224903 R5-227302 |  | 0.5 | 10% (+10%) | 10% (+10%) | 10% (+10%) |  | 10% | 10%
TS 38.533: RRM test cases
73 |  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
74 |  | 38.533 | 10 | EN-DC Tests with NR PSCell under CCA and Other NR Cells in FR1 | New sub-clause header |  | TBD |  |  | 0
75 |  | 38.533 | 10.1 | RRC_CONNECTED state mobility | New sub-clause header |  | TBD |  |  | 0
76 |  | 38.533 | 10.1.1 | RRC connection mobility control | New sub-clause header |  | TBD |  |  | 0
77 |  | 38.533 | 10.1.1.1 | Random Access | New sub-clause header |  | TBD |  |  | 0
78 | Y | 38.533 | 10.1.1.1.1 | EN-DC FR1 4-step RA type contention-based random access for NR PSCell with CCA | 38.133 Requirements in Annex A.10.1.1.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
79 | Y | 38.533 | 10.1.1.1.2 | EN-DC FR1 4-step RA type non-contention based random access for NR PSCell with CCA | 38.133 Requirements in Annex A.10.1.1.1.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
80 | Y | 38.533 | 10.1.1.1.3 | EN-DC FR1 2-step RA type contention-based random access for NR PSCell with CCA | 38.133 Requirements in Annex A.10.1.1.1.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
81 | Y | 38.533 | 10.1.1.1.4 | EN-DC FR1 2-step RA type non-contention based random access for NR PSCell with CCA | 38.133 Requirements in Annex A.10.1.1.1.4 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
82 | Y | 38.533 | 10.1.2 | EN-DC FR1 Handover with PSCell from EN-DC to EN-DC with known target PSCell using CCA | 38.133 Requirements in Annex A.10.1.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
83 |  | 38.533 | 10.2 | Timing | New sub-clause header |  | TBD |  |  | 0
84 |  | 38.533 | 10.2.1 | UE transmit timing | New sub-clause header |  | TBD |  |  | 0
85 | Y | 38.533 | 10.2.1.1 | EN-DC FR1 UE Transmit Timing Test with PSCell under DL CCA | 38.133 Requirements in Annex A.10.2.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
86 |  | 38.533 | 10.2.2 | UE timing advance | New sub-clause header |  | TBD |  |  | 0
87 | Y | 38.533 | 10.2.2.1 | EN-DC FR1 UE Timing Advance Adjustment Accuracy with PSCell under DL CCA | 38.133 Requirements in Annex A.10.2.2.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
88 |  | 38.533 | 10.3 | Signalling characteristics | New sub-clause header |  | TBD |  |  | 0
89 |  | 38.533 | 10.3.1 | Radio link monitoring | New sub-clause header |  | TBD |  |  | 0
90 | Y | 38.533 | 10.3.1.2 | EN-DC FR1 Radio link monitoring out-of-sync test for PSCell under CCA configured with SSB-based RLM RS in non-DRX mode | 38.133 Requirements in Annex A.10.3.1.2 | Qualcomm | TBD | R5-227993 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure may need to be updated - Applicability may need to be updated - Statistical analysis to determine test case verdict is FFS | 1 | 50% (+50%) |  | 50% (+50%) |  |  | 50%
91 | Y | 38.533 | 10.3.1.3 | EN-DC FR1 Radio link monitoring in-sync test for PSCell under CCAconfigured with SSB-based RLM RS in non-DRX mode | 38.133 Requirements in Annex A.10.3.1.3 | Qualcomm | TBD | R5-227993 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure may need to be updated - Applicability may need to be updated - Statistical analysis to determine test case verdict is FFS | 1 | 50% (+50%) |  | 50% (+50%) |  |  | 50%
92 | Y | 38.533 | 10.3.1.4 | EN-DC FR1 Radio link monitoring out-of-sync test for PSCell under CCA configured with SSB-based RLM RS in DRX mode | 38.133 Requirements in Annex A.10.3.1.4 | Qualcomm | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
93 | Y | 38.533 | 10.3.1.5 | EN-DC FR1 Radio link monitoring in-sync test for PSCell under CCA configured with SSB-based RLM RS in DRX mode | 38.133 Requirements in Annex A.10.3.1.5 | Qualcomm | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
94 |  | 38.533 | 10.3.2 | Interruption | New sub-clause header |  | TBD |  |  | 0
95 | Y | 38.533 | 10.3.2.1 | EN-DC FR1 E-UTRAN – NR interruptions during SCell operations with CCA | 38.133 Requirements in Annex A.10.3.2.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
96 |  | 38.533 | 10.3.3 | SCell activation and deactivation delay | New sub-clause header |  | TBD |  |  | 0
97 | Y | 38.533 | 10.3.3.1 | EN-DC FR1 SCell Activation and Deactivation of known NR SCell with NR PSCell and NR SCell under CCA, 160 ms SCell measurement cycle | 38.133 Requirements in Annex A.10.3.3.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
98 | Y | 38.533 | 10.3.3.2 | EN-DC FR1 SCell Activation and Deactivation of known NR SCell with NR PSCell and NR SCell under CCA, 640 ms SCell measurement cycle | 38.133 Requirements in Annex A.10.3.3.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
99 | Y | 38.533 | 10.3.3.3 | EN-DC FR1 SCell Activation and Deactivation of unknown NR SCell with NR PSCell and NR SCell under CCA | 38.133 Requirements in Annex A.10.3.3.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
100 |  | 38.533 | 10.3.4 | Beam failure detection and link recovery procedures | New sub-clause header |  | TBD |  |  | 0
101 | Y | 38.533 | 10.3.4.1 | EN-DC FR1 EN-DC Beam Failure Detection and Link Recovery Test for FR1 PSCell under CCA configured with SSB-based BFD and LR in non-DRX mode | 38.133 Requirements in Annex A.10.3.4.1 | Qualcomm | TBD | R5-227992 | Editor's Note: - MU and TT analysis is incomplete - Message contents may need to be updated - Call setup and test procedure may need to be updated - Applicability may need to be updated - Statistical analysis to determine test case verdict is FFS | 1 | 50% (+50%) |  | 50% (+50%) |  |  | 50%
102 | Y | 38.533 | 10.3.4.2 | EN-DC FR1 EN-DC Beam Failure Detection and Link Recovery Test for FR1 PSCell under CCA configured with SSB-based BFD and LR in DRX mode | 38.133 Requirements in Annex A.10.3.4.2 | Qualcomm | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
103 |  | 38.533 | 10.3.5 | Active BWP switching | New sub-clause header |  | TBD |  |  | 0
104 | Y | 38.533 | 10.3.5.1 | EN-DC FR1 UL active BWP switch delay with consistent UL LBT failure on PSCell subject to UL CCA in EN-DC | 38.133 Requirements in Annex A.10.3.5.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
105 |  | 38.533 | 10.3.5.2 | DCI-based and Timer-based Active BWP Switch | New sub-clause header |  | TBD |  |  | 0
106 | Y | 38.533 | 10.3.5.2.1 | EN-DC FR1 E-UTRAN – NR PSCell under CCA FR1 DL active BWP switch in non-DRX in synchronous EN-DC | 38.133 Requirements in Annex A.10.3.5.2.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
107 | Y | 38.533 | 10.3.5.2.2 | EN-DC FR1 E-UTRAN – NR PSCell under CCA FR1 DL active BWP switch with FR1 SCell in non-DRX in synchronous EN-DC | 38.133 Requirements in Annex A.10.3.5.2.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
108 |  | 38.533 | 10.3.5.3 | RRC-based Active BWP Switch | New sub-clause header |  | TBD |  |  | 0
109 | Y | 38.533 | 10.3.5.3.1 | EN-DC FR1 E-UTRAN – NR PSCell under CCA FR1 DL active BWP switch in non-DRX in synchronous EN-DC | 38.133 Requirements in Annex A.10.3.5.3.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
110 |  | 38.533 | 10.3.6 | PSCell addition and release delay | New sub-clause header |  | TBD |  |  | 0
111 | Y | 38.533 | 10.3.6.1 | EN-DC FR1 Addition and Release Delay of known NR PSCell on the carrier under CCA | 38.133 Requirements in Annex A.10.3.6.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
112 |  | 38.533 | 10.4 | Measurement procedure | New sub-clause header |  | TBD |  |  | 0
113 |  | 38.533 | 10.4.1 | Intra-frequency measurements | New sub-clause header |  | TBD |  |  | 0
114 | Y | 38.533 | 10.4.1.1 | EN-DC FR1 Event-triggered reporting tests on PSCC under CCA without gaps under non-DRX | 38.133 Requirements in Annex A.10.4.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
115 | Y | 38.533 | 10.4.1.2 | EN-DC FR1 Event-triggered reporting tests on PSCC under CCA without gaps under DRX | 38.133 Requirements in Annex A.10.4.1.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
116 | Y | 38.533 | 10.4.1.3 | EN-DC FR1 Event-triggered reporting tests on PSCC under CCA with per-UE gaps under non-DRX | 38.133 Requirements in Annex A.10.4.1.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
117 | Y | 38.533 | 10.4.1.4 | EN-DC FR1 Event-triggered reporting tests on PSCC under CCA with per-UE gaps under DRX | 38.133 Requirements in Annex A.10.4.1.4 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
118 | Y | 38.533 | 10.4.1.5 | EN-DC FR1 Event-triggered reporting tests on SCC under CCA without gaps under non-DRX | 38.133 Requirements in Annex A.10.4.1.5 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
119 | Y | 38.533 | 10.4.1.6 | EN-DC FR1 Event-triggered reporting tests on SCC under CCA without gaps under DRX | 38.133 Requirements in Annex A.10.4.1.6 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
120 | Y | 38.533 | 10.4.1.7 | EN-DC FR1 Event-triggered reporting tests on SCC under CCA with per-UE gaps under non-DRX | 38.133 Requirements in Annex A.10.4.1.7 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
121 | Y | 38.533 | 10.4.1.8 | EN-DC FR1 Event-triggered reporting tests on SCC under CCA with per-UE gaps under DRX | 38.133 Requirements in Annex A.10.4.1.8 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
122 | Y | 38.533 | 10.4.1.9 | EN-DC FR1 RSSI measurement reporting on PSCC under CCA | 38.133 Requirements in Annex A.10.4.1.9 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
123 | Y | 38.533 | 10.4.1.10 | EN-DC FR1 Channel occupancy measurement reporting on PSCC under CCA | 38.133 Requirements in Annex A.10.4.1.10 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
124 | Y | 38.533 | 10.4.1.11 | EN-DC FR1 RSSI measurement reporting on SCC under CCA | 38.133 Requirements in Annex A.10.4.1.11 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
125 | Y | 38.533 | 10.4.1.12 | EN-DC FR1 Channel occupancy measurement reporting on SCC under CCA | 38.133 Requirements in Annex A.10.4.1.12 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
126 |  | 38.533 | 10.4.2 | Inter-frequency measurements | New sub-clause header |  | TBD |  |  | 0
127 | Y | 38.533 | 10.4.2.1 | EN-DC FR1 RSSI measurement reporting | 38.133 Requirements in Annex A.10.4.2.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
128 | Y | 38.533 | 10.4.2.2 | EN-DC FR1 Channel occupancy measurement reporting | 38.133 Requirements in Annex A.10.4.2.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
129 | Y | 38.533 | 10.4.2.3 | EN-DC FR1 event triggered reporting tests for FR1 with CCA cell without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.10.4.2.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
130 | Y | 38.533 | 10.4.2.4 | EN-DC FR1 event triggered reporting tests for FR1 cell with CCA without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.10.4.2.4 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
131 | Y | 38.533 | 10.4.2.5 | EN-DC FR1 event triggered reporting tests for FR1 cell with CCA with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.10.4.2.5 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
132 | Y | 38.533 | 10.4.2.6 | EN-DC FR1 event triggered reporting tests for FR1 cell with CCA with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.10.4.2.6 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
133 | Y | 38.533 | 10.4.2.7 | EN-DC FR1 event triggered reporting tests for FR1 cell without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.10.4.2.7 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
134 | Y | 38.533 | 10.4.2.8 | EN-DC FR1 event triggered reporting tests for FR1 cell without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.10.4.2.8 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
135 | Y | 38.533 | 10.4.2.9 | EN-DC FR1 event triggered reporting tests for FR1 cell with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.10.4.2.9 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
136 | Y | 38.533 | 10.4.2.10 | EN-DC FR1 event triggered reporting tests for FR1 cell with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.10.4.2.10 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
137 |  | 38.533 | 10.4.3 | L1-RSRP measurements for beam reporting | New sub-clause header |  | TBD |  |  | 0
138 | Y | 38.533 | 10.4.3.1 | EN-DC FR1 SSB based L1-RSRP measurement on PSCC under CCA when DRX is not used | 38.133 Requirements in Annex A.10.4.3.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
139 | Y | 38.533 | 10.4.3.2 | EN-DC FR1 SSB based L1-RSRP measurement on PSCC under CCA when DRX is used | 38.133 Requirements in Annex A.10.4.3.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
140 | Y | 38.533 | 10.4.3.3 | EN-DC FR1 SSB based L1-RSRP measurement on SCC under CCA when DRX is not used | 38.133 Requirements in Annex A.10.4.3.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
141 | Y | 38.533 | 10.4.3.4 | EN-DC FR1 SSB based L1-RSRP measurement on SCC under CCA when DRX is used | 38.133 Requirements in Annex A.10.4.3.4 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
142 |  | 38.533 | 10.4.4 | E-UTRAN-NR inter-RAT measurements on NR carrier frequency under CCA | New sub-clause header |  | TBD |  |  | 0
143 | Y | 38.533 | 10.4.4.1 | EN-DC FR1 E-UTRA-NR inter-RAT event triggered reporting tests for FR1 without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.10.4.4.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
144 | Y | 38.533 | 10.4.4.2 | EN-DC FR1 E-UTRA-NR inter-RAT event triggered reporting tests for FR1 without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.10.4.4.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
145 | Y | 38.533 | 10.4.4.3 | EN-DC FR1 NR Inter-RAT event triggered reporting tests for FR1 with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.10.4.4.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
146 | Y | 38.533 | 10.4.4.4 | EN-DC FR1 NR Inter-RAT event triggered reporting tests for FR1 with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.10.4.4.4 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
147 |  | 38.533 | 10.5 | Measurement performance | New sub-clause header |  | TBD |  |  | 0
148 |  | 38.533 | 10.5.1 | SS-RSRP | New sub-clause header |  | TBD |  |  | 0
149 | Y | 38.533 | 10.5.1.1 | EN-DC FR1 Intra-frequency measurement accuracy on a CCA serving cell | 38.133 Requirements in Annex A.10.5.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
150 | Y | 38.533 | 10.5.1.2 | EN-DC FR1 Inter-frequency measurement accuracy with FR1 CCA serving cell and FR1 CCA target cell | 38.133 Requirements in Annex A.10.5.1.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
151 |  | 38.533 | 10.5.2 | SS-RSRQ | New sub-clause header |  | TBD |  |  | 0
152 | Y | 38.533 | 10.5.2.1 | EN-DC FR1 Intra-frequency measurement accuracy with FR1 CCA serving cell and FR1 CCA target cell | 38.133 Requirements in Annex A.10.5.2.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
153 | Y | 38.533 | 10.5.2.2 | EN-DC FR1 Inter-frequency measurement accuracy with FR1 CCA serving cell and FR1 CCA target cell | 38.133 Requirements in Annex A.10.5.2.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
154 |  | 38.533 | 10.5.3 | SS-SINR | New sub-clause header |  | TBD |  |  | 0
155 | Y | 38.533 | 10.5.3.1 | EN-DC FR1 Intra-frequency measurement accuracy on PSCC under CCA | 38.133 Requirements in Annex A.10.5.3.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
156 | Y | 38.533 | 10.5.3.2 | EN-DC FR1 Inter-frequency measurement accuracy on PSCC under CCA | 38.133 Requirements in Annex A.10.5.3.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
157 | Y | 38.533 | 10.5.3.3 | EN-DC FR1 Intra-frequency measurement accuracy on SCC under CCA | 38.133 Requirements in Annex A.10.5.3.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
158 |  | 38.533 | 10.5.4 | L1-RSRP measurement for beam reporting with CCA serving cell | New sub-clause header |  | TBD |  |  | 0
159 | Y | 38.533 | 10.5.4.1 | EN-DC FR1 SSB based L1-RSRP measurement | 38.133 Requirements in Annex A.10.5.4.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
160 |  | 38.533 | 10.5.5 | RSSI | New sub-clause header |  | TBD |  |  | 0
161 | Y | 38.533 | 10.5.5.1 | EN-DC FR1 RSSI measurement accuracy on PSCC with CCA | 38.133 Requirements in Annex A.10.5.5.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
162 | Y | 38.533 | 10.5.5.2 | EN-DC FR1 RSSI measurement accuracy on SCC with CCA | 38.133 Requirements in Annex A.10.5.5.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
163 | Y | 38.533 | 10.5.5.3 | EN-DC FR1 Inter-frequency RSSI measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.10.5.5.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
164 |  | 38.533 | 10.5.6 | Channel occupancy | New sub-clause header |  | TBD |  |  | 0
165 | Y | 38.533 | 10.5.6.1 | EN-DC FR1 Channel occupancy measurement accuracy on PSCC with CCA | 38.133 Requirements in Annex A.10.5.6.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
166 | Y | 38.533 | 10.5.6.2 | EN-DC FR1 Channel occupancy measurement accuracy on SCC with CCA | 38.133 Requirements in Annex A.10.5.6.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
167 | Y | 38.533 | 10.5.6.3 | EN-DC FR1 Inter-frequency channel occupancy measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.10.5.6.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
168 |  | 38.533 | 11 | NR Standalone Tests with NR PCell under CCA and Other NR Cells in FR1 | New sub-clause header |  | TBD |  |  | 0
169 |  | 38.533 | 11.1 | RRC_IDLE state mobility | New sub-clause header |  | TBD |  |  | 0
170 |  | 38.533 | 11.1.1 | Cell re-selection with both source and target NR carrier frequencies under CCA | New sub-clause header |  | TBD |  |  | 0
171 | Y | 38.533 | 11.1.1.1 | NR SA FR1 Cell reselection to FR1 intra-frequency NR cells when subject to CCA on the serving and target cell | 38.133 Requirements in Annex A.11.1.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
172 | Y | 38.533 | 11.1.1.2 | NR SA FR1 Cell reselection to FR1 inter-frequency NR case when subject to CCA on the serving and target cell | 38.133 Requirements in Annex A.11.1.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
173 | Y | 38.533 | 11.1.2 | NR SA FR1 Cell re-selection to NR with source NR carrier frequency under CCA | 38.133 Requirements in Annex A.11.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
174 | Y | 38.533 | 11.1.3 | NR SA FR1 Cell re-selection from NR carrier with target NR carrier frequency under CCA | 38.133 Requirements in Annex A.11.1.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
175 |  | 38.533 | 11.1.4 | Inter-RAT cell re-selection to E-UTRAN with source NR carrier frequency under CCA | New sub-clause header |  | TBD |  |  | 0
176 | Y | 38.533 | 11.1.4.1 | NR SA FR1 Cell reselection to higher priority E-UTRAN when serving cell is subject to CCA | 38.133 Requirements in Annex A.11.1.4.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
177 | Y | 38.533 | 11.1.4.2 | NR SA FR1 Cell reselection to lower priority E-UTRAN when serving cell is subject to CCA | 38.133 Requirements in Annex A.11.1.4.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
178 |  | 38.533 | 11.2 | RRC_CONNECTED state mobility | New sub-clause header |  | TBD |  |  | 0
179 |  | 38.533 | 11.2.1 | Handover | New sub-clause header |  | TBD |  |  | 0
180 | Y | 38.533 | 11.2.1.1 | NR SA FR1 Intra-frequency handover from FR1 carrier under CCA to FR1 carrier under CCA; known target cell | 38.133 Requirements in Annex A.11.2.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
181 | Y | 38.533 | 11.2.1.2 | NR SA FR1 Intra-frequency handover from FR1 carrier under CCA to FR1 carrier under CCA; unknown target cell | 38.133 Requirements in Annex A.11.2.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
182 | Y | 38.533 | 11.2.1.3 | NR SA FR1 Inter-frequency handover from FR1 carrier under CCA to FR1 carrier under CCA; unknown target cell | 38.133 Requirements in Annex A.11.2.1.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
183 | Y | 38.533 | 11.2.1.4 | NR SA FR1 Inter-frequency handover from FR1 carrier under CCA to FR1; known target cell | 38.133 Requirements in Annex A.11.2.1.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
184 | Y | 38.533 | 11.2.1.5 | NR SA FR1 Inter-frequency handover from FR1 carrier under CCA to FR1; unknown target cell | 38.133 Requirements in Annex A.11.2.1.5 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
185 | Y | 38.533 | 11.2.1.6 | NR SA FR1 Inter-frequency handover from FR1 to FR1 carrier under CCA; unknown target cell | 38.133 Requirements in Annex A.11.2.1.6 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
186 | Y | 38.533 | 11.2.1.7 | NR SA FR1 carrier under CCA - E-UTRAN handover with known target cell | 38.133 Requirements in Annex A.11.2.1.7 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
187 | Y | 38.533 | 11.2.1.8 | NR SA FR1 carrier under CCA - E-UTRAN handover with unknown target cell | 38.133 Requirements in Annex A.11.2.1.8 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
188 | Y | 38.533 | 11.2.1.9 | NR SA FR1 Handover with PSCell from NR SA to EN-DC with known target PSCell using CCA | 38.133 Requirements in Annex A.11.2.1.9 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
189 |  | 38.533 | 11.2.2 | RRC connection mobility control | New sub-clause header |  | TBD |  |  | 0
190 |  | 38.533 | 11.2.2.1 | RRC re-establishment | New sub-clause header |  | TBD |  |  | 0
191 | Y | 38.533 | 11.2.2.1.1 | NR SA FR1 Intra-frequency RRC Re-establishment with CCA in FR1 | 38.133 Requirements in Annex A.11.2.2.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
192 | Y | 38.533 | 11.2.2.1.2 | NR SA FR1 Inter-frequency RRC Re-establishment with CCA in FR1 | 38.133 Requirements in Annex A.11.2.2.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
193 | Y | 38.533 | 11.2.2.1.4 | NR SA FR1 Inter-frequency RRC Re-establishment from NR FR1 carrier without CCA to NR FR1 carrier under CCA | 38.133 Requirements in Annex A.11.2.2.1.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
194 |  | 38.533 | 11.2.2.2 | Random Access | New sub-clause header |  | TBD |  |  | 0
195 | Y | 38.533 | 11.2.2.2.1 | NR SA FR1 4-step RA type contention-based random access for NR PCell with CCA | 38.133 Requirements in Annex A.11.2.2.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
196 | Y | 38.533 | 11.2.2.2.2 | NR SA FR1 4-step RA type non-contention based random access for NR PSCell with CCA | 38.133 Requirements in Annex A.11.2.2.2.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
197 | Y | 38.533 | 11.2.2.2.3 | NR SA FR1 2-step RA type contention-based random access for NR PCell with CCA | 38.133 Requirements in Annex A.11.2.2.2.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
198 | Y | 38.533 | 11.2.2.2.4 | NR SA FR1 2-step RA type non-contention-based random access for NR PCell with CCA | 38.133 Requirements in Annex A.11.2.2.2.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
199 |  | 38.533 | 11.2.2.3 | RRC connection release with redirection | New sub-clause header |  | TBD |  |  | 0
200 | Y | 38.533 | 11.2.2.3.1 | NR SA FR1 Redirection from NR FR1 carrier under CCA to NR FR1 carrier under CCA | 38.133 Requirements in Annex A.11.2.2.3.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
201 | Y | 38.533 | 11.2.2.3.2 | NR SA FR1 Redirection from NR FR1 carrier without CCA to NR FR1 carrier with CCA | 38.133 Requirements in Annex A.11.2.2.3.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
202 |  | 38.533 | 11.3 | Timing | New sub-clause header |  | TBD |  |  | 0
203 |  | 38.533 | 11.3.1 | UE transmit timing | New sub-clause header |  | TBD |  |  | 0
204 | Y | 38.533 | 11.3.1.1 | NR SA FR1 UE Transmit Timing Test with PCell under DL CCA | 38.133 Requirements in Annex A.11.3.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
205 |  | 38.533 | 11.3.2 | UE timing advance | New sub-clause header |  | TBD |  |  | 0
206 | Y | 38.533 | 11.3.2.1 | NR SA FR1 UE Timing Advance Adjustment Accuracy with PCell under DL CCA | 38.133 Requirements in Annex A.11.3.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
207 |  | 38.533 | 11.4 | Signalling characteristics | New sub-clause header |  | TBD |  |  | 0
208 |  | 38.533 | 11.4.1 | Radio link monitoring | New sub-clause header |  | TBD |  |  | 0
209 | Y | 38.533 | 11.4.1.2 | NR SA FR1 Radio link monitoring out-of-sync test for PCell under CCA configured with SSB-based RLM RS in non-DRX mode | 38.133 Requirements in Annex A.11.4.1.2 | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0%
210 | Y | 38.533 | 11.4.1.3 | NR SA FR1 Radio link monitoring in-sync test for PCell under CCA configured with SSB-based RLM RS in non-DRX mode | 38.133 Requirements in Annex A.11.4.1.3 | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0%
211 | Y | 38.533 | 11.4.1.4 | NR SA FR1 Radio link monitoring out-of-sync test for PCell under CCA configured with SSB-based RLM RS in DRX mode | 38.133 Requirements in Annex A.11.4.1.4 | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0%
212 | Y | 38.533 | 11.4.1.5 | NR SA FR1 Radio link monitoring in-sync test for PCell under CCA configured with SSB-based RLM RS in DRX mode | 38.133 Requirements in Annex A.11.4.1.5 | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0%
213 | Y | 38.533 | 11.4.2.1 | NR SA FR1 NR interruptions during Scell operations with CCA on PCell and SCell | 38.133 Requirements in Annex A.11.4.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
214 |  | 38.533 | 11.4.3 | SCell activation and deactivation delay | New sub-clause header |  | TBD |  |  | 0
215 | Y | 38.533 | 11.4.3.1 | NR SA FR1 SCell Activation and Deactivation of known SCell with PCell and SCell under CCA, 160 ms SCell measurement cycle | 38.133 Requirements in Annex A.11.4.3.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
216 | Y | 38.533 | 11.4.3.2 | NR SA FR1 SCell Activation and Deactivation of known SCell with PCell and SCell under CCA, 640 ms SCell measurement cycle | 38.133 Requirements in Annex A.11.4.3.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
217 | Y | 38.533 | 11.4.3.3 | NR SA FR1 SCell Activation and Deactivation of unknown SCell with PCell and SCell under CCA | 38.133 Requirements in Annex A.11.4.3.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
218 |  | 38.533 | 11.4.4 | Beam failure detection and link recovery procedures | New sub-clause header |  | TBD |  |  | 0
219 | Y | 38.533 | 11.4.4.1 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell under CCA configured with SSB-based BFD and LR in non-DRX mode | 38.133 Requirements in Annex A.11.4.4.1 | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0%
220 | Y | 38.533 | 11.4.4.2 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell under CCA configured with SSB-based BFD and LR in DRX mode | 38.133 Requirements in Annex A.11.4.4.2 | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0%
221 |  | 38.533 | 11.4.5 | Active BWP switching | New sub-clause header |  | TBD |  |  | 0
222 | Y | 38.533 | 11.4.5.1 | NR SA FR1 UL active BWP switch delay with consistent UL LBT failure on PCell subject to UL CCA | 38.133 Requirements in Annex A.11.4.5.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
223 |  | 38.533 | 11.4.5.2 | DCI-based and Timer-based Active BWP Switch | New sub-clause header |  | TBD |  |  | 0
224 | Y | 38.533 | 11.4.5.2.1 | NR SA FR1 - NR FR1 DL active BWP switch of PCell under CCA with non-DRX in SA | 38.133 Requirements in Annex A.11.4.5.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
225 | Y | 38.533 | 11.4.5.2.2 | NR SA FR1 DL active BWP switch with non-DRX in SA | 38.133 Requirements in Annex A.11.4.5.2.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
226 |  | 38.533 | 11.4.5.3 | RRC-based Active BWP Switch | New sub-clause header |  | TBD |  |  | 0
227 | Y | 38.533 | 11.4.5.3.1 | NR SA FR1 DL active BWP switch of Cell with non-DRX in SA | 38.133 Requirements in Annex A.11.4.5.3.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
228 |  | 38.533 | 11.5 | Measurement procedure | New sub-clause header |  | TBD |  |  | 0
229 |  | 38.533 | 11.5.1 | Intra-frequency measurements | New sub-clause header |  | TBD |  |  | 0
230 | Y | 38.533 | 11.5.1.1 | NR SA FR1 Event-triggered reporting tests on PCC under CCA without gaps under non-DRX | 38.133 Requirements in Annex A.11.5.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
231 | Y | 38.533 | 11.5.1.2 | NR SA FR1 Event-triggered reporting tests on PCC under CCA without gaps under DRX | 38.133 Requirements in Annex A.11.5.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
232 | Y | 38.533 | 11.5.1.3 | NR SA FR1 Event-triggered reporting tests on PCC under CCA with per-UE gaps under non-DRX | 38.133 Requirements in Annex A.11.5.1.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
233 | Y | 38.533 | 11.5.1.4 | NR SA FR1 Event-triggered reporting tests on PCC under CCA with per-UE gaps under DRX | 38.133 Requirements in Annex A.11.5.1.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
234 | Y | 38.533 | 11.5.1.5 | NR SA FR1 Event-triggered reporting tests on SCC under CCA without gaps under non-DRX | 38.133 Requirements in Annex A.11.5.1.5 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
235 | Y | 38.533 | 11.5.1.6 | NR SA FR1 Event-triggered reporting tests on SCC under CCA without gaps under DRX | 38.133 Requirements in Annex A.11.5.1.6 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
236 | Y | 38.533 | 11.5.1.7 | NR SA FR1 Event-triggered reporting tests on SCC under CCA with per-UE gaps under non-DRX | 38.133 Requirements in Annex A.11.5.1.7 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
237 | Y | 38.533 | 11.5.1.8 | NR SA FR1 Event-triggered reporting tests on SCC under CCA with per-UE gaps under DRX | 38.133 Requirements in Annex A.11.5.1.8 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
238 | Y | 38.533 | 11.5.1.9 | NR SA FR1 RSSI measurement reporting on PCC | 38.133 Requirements in Annex A.11.5.1.9 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
239 | Y | 38.533 | 11.5.1.10 | NR SA FR1 Channel occupancy measurement reporting on PCC | 38.133 Requirements in Annex A.11.5.1.10 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
240 | Y | 38.533 | 11.5.1.11 | NR SA FR1 RSSI measurement reporting on SCC | 38.133 Requirements in Annex A.11.5.1.11 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
241 | Y | 38.533 | 11.5.1.12 | NR SA FR1 Channel occupancy measurement reporting on SCC | 38.133 Requirements in Annex A.11.5.1.12 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
242 |  | 38.533 | 11.5.2 | Inter-frequency measurements | New sub-clause header |  | TBD |  |  | 0
243 | Y | 38.533 | 11.5.2.1 | NR SA FR1 RSSI measurement reporting | 38.133 Requirements in Annex A.11.5.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
244 | Y | 38.533 | 11.5.2.2 | NR SA FR1 Channel occupancy measurement reporting | 38.133 Requirements in Annex A.11.5.2.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
245 | Y | 38.533 | 11.5.2.3 | NR SA FR1 Event triggered reporting tests for FR1 with CCA without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.11.5.2.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
246 | Y | 38.533 | 11.5.2.4 | NR SA FR1 Event triggered reporting tests for FR1 with CCA without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.11.5.2.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
247 | Y | 38.533 | 11.5.2.5 | NR SA FR1 Event triggered reporting tests for FR1 with CCA with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.11.5.2.5 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
248 | Y | 38.533 | 11.5.2.6 | NR SA FR1 Event triggered reporting tests for FR1 with CCA with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.11.5.2.6 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
249 | Y | 38.533 | 11.5.2.7 | NR SA FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.11.5.2.7 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
250 | Y | 38.533 | 11.5.2.8 | NR SA FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.11.5.2.8 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
251 | Y | 38.533 | 11.5.2.9 | NR SA FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.11.5.2.9 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
252 | Y | 38.533 | 11.5.2.10 | NR SA FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.11.5.2.10 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
253 |  | 38.533 | 11.5.3 | Inter-RAT E-UTRAN measurements | New sub-clause header |  | TBD |  |  | 0
254 |  | 38.533 | 11.5.4 | L1-RSRP measurements for beam reporting | New sub-clause header |  | TBD |  |  | 0
255 | Y | 38.533 | 11.5.4.1 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used | 38.133 Requirements in Annex A.11.5.4.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
256 | Y | 38.533 | 11.5.4.2 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used | 38.133 Requirements in Annex A.11.5.4.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
257 | Y | 38.533 | 11.5.4.3 | NR SA FR1 SSB based L1-RSRP measurement on SCC under CCA when DRX is not used | 38.133 Requirements in Annex A.11.5.4.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
258 | Y | 38.533 | 11.5.4.4 | NR SA FR1 SSB based L1-RSRP measurement on SCC under CCA when DRX is used | 38.133 Requirements in Annex A.11.5.4.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
259 |  | 38.533 | 11.6 | Measurement performance | New sub-clause header |  | TBD |  |  | 0
260 |  | 38.533 | 11.6.1 | SS-RSRP | New sub-clause header |  | TBD |  |  | 0
261 | Y | 38.533 | 11.6.1.1 | NR SA FR1 Intra-frequency measurement accuracy on a carrier frequency with CCA | 38.133 Requirements in Annex A.11.6.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
262 | Y | 38.533 | 11.6.1.2 | NR SA FR1 Intra-frequency measurement accuracy on SCC on a carrier frequency with CCA | 38.133 Requirements in Annex A.11.6.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
263 |  | 38.533 | 11.6.2 | SS-RSRQ | New sub-clause header |  | TBD |  |  | 0
264 | Y | 38.533 | 11.6.2.1 | NR SA FR1 Intra-frequency measurement accuracy | 38.133 Requirements in Annex A.11.6.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
265 | Y | 38.533 | 11.6.2.2 | NR SA FR1 Inter-frequency measurement accuracy | 38.133 Requirements in Annex A.11.6.2.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
266 | Y | 38.533 | 11.6.2.3 | NR SA FR1 Intra-frequency measurement accuracy on SCC | 38.133 Requirements in Annex A.11.6.2.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
267 | Y | 38.533 | 11.6.2.4 | NR SA FR1 Inter-frequency measurement accuracy | 38.133 Requirements in Annex A.11.6.2.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
268 |  | 38.533 | 11.6.3 | SS-SINR | New sub-clause header |  | TBD |  |  | 0
269 | Y | 38.533 | 11.6.3.1 | NR SA FR1 Intra-frequency measurement accuracy | 38.133 Requirements in Annex A.11.6.3.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
270 | Y | 38.533 | 11.6.3.2 | NR SA FR1 Inter-frequency measurement accuracy | 38.133 Requirements in Annex A.11.6.3.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
271 | Y | 38.533 | 11.6.3.3 | NR SA FR1 Intra-frequency measurement accuracy on SCC | 38.133 Requirements in Annex A.11.6.3.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
272 | Y | 38.533 | 11.6.3.4 | NR SA FR1 Inter-frequency measurement accuracy | 38.133 Requirements in Annex A.11.6.3.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
273 |  | 38.533 | 11.6.4 | L1-RSRP measurement for beam reporting with CCA serving cell | New sub-clause header |  | TBD |  |  | 0
274 | Y | 38.533 | 11.6.4.1 | NR SA FR1 SSB based L1-RSRP measurement | 38.133 Requirements in Annex A.11.6.4.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
275 |  | 38.533 | 11.6.5 | RSSI | New sub-clause header |  | TBD |  |  | 0
276 | Y | 38.533 | 11.6.5.1 | NR SA FR1 Intra-frequency RSSI measurement accuracy on PCC with CCA | 38.133 Requirements in Annex A.11.6.5.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
277 | Y | 38.533 | 11.6.5.2 | NR SA FR1 Intra-frequency RSSI measurement accuracy on SCC with CCA | 38.133 Requirements in Annex A.11.6.5.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
278 | Y | 38.533 | 11.6.5.3 | NR SA FR1 Inter-frequency RSSI measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.11.6.5.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
279 |  | 38.533 | 11.6.6 | Channel occupancy | New sub-clause header |  | TBD |  |  | 0
280 | Y | 38.533 | 11.6.6.1 | NR SA FR1 Intra-frequency channel occupancy measurement accuracy on PCC with CCA | 38.133 Requirements in Annex A.11.6.6.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
281 | Y | 38.533 | 11.6.6.2 | NR SA FR1 Intra-frequency channel occupancy measurement accuracy on SCC with CCA | 38.133 Requirements in Annex A.11.6.6.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
282 | Y | 38.533 | 11.6.6.3 | NR SA FR1 Inter-frequency channel occupancy measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.11.6.6.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
283 |  | 38.533 | 11.6.7 | E-UTRAN RSRP | New sub-clause header |  | TBD |  |  | 0
284 |  | 38.533 | 11.6.8 | E-UTRAN RSRQ | New sub-clause header |  | TBD |  |  | 0
285 |  | 38.533 | 11.6.9 | E-UTRAN SINR | New sub-clause header |  | TBD |  |  | 0
286 |  | 38.533 | 12 | E-UTRA Standalone Tests with at Least One NR Cell under CCA | New sub-clause header |  | TBD |  |  | 0
287 |  | 38.533 | 12.1 | RRC_IDLE state mobility | New sub-clause header |  | TBD |  |  | 0
288 |  | 38.533 | 12.1.1 | Inter-RAT cell re-selection to NR on a carrier frequency with CCA | New sub-clause header |  | TBD |  |  | 0
289 | Y | 38.533 | 12.1.1.1 | E-UTRA Cell reselection to higher priority NR target Cell in FR1 when target cell is subject to CCA | 38.133 Requirements in Annex A.12.1.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
290 |  | 38.533 | 12.2 | RRC_CONNECTED state mobility | New sub-clause header |  | TBD |  |  | 0
291 |  | 38.533 | 12.2.1 | Handover | New sub-clause header |  | TBD |  |  | 0
292 | Y | 38.533 | 12.2.1.1 | E-UTRAN - NR with CCA handover | 38.133 Requirements in Annex A.12.2.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
293 |  | 38.533 | 12.3 | Signalling characteristics | New sub-clause header |  | TBD |  |  | 0
294 |  | 38.533 | 12.3.1 | Interruptions | New sub-clause header |  | TBD |  |  | 0
295 |  | 38.533 | 12.4 | Measurement procedure | New sub-clause header |  | TBD |  |  | 0
296 |  | 38.533 | 12.4.1 | E-UTRAN-NR inter-RAT SFTD measurements | New sub-clause header |  | TBD |  |  | 0
297 | Y | 38.533 | 12.4.1.1 | E-UTRA – NR Inter-RAT SFTD Measurement Delay with NR under CCA in non-DRX | 38.133 Requirements in Annex A.12.4.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
298 |  | 38.533 | 12.4.2 | E-UTRAN-NR inter-RAT measurements on NR carrier frequency under CCA | New sub-clause header |  | TBD |  |  | 0
299 | Y | 38.533 | 12.4.2.1 | E-UTRA-NR inter-RAT event triggered reporting tests for FR1 without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.12.4.2.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
300 | Y | 38.533 | 12.4.2.2 | E-UTRA-NR inter-RAT event triggered reporting tests for FR1 without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.12.4.2.2 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
301 | Y | 38.533 | 12.4.2.3 | NR Inter-RAT event triggered reporting tests for FR1 with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.12.4.2.3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
302 | Y | 38.533 | 12.4.2.4 | NR Inter-RAT event triggered reporting tests for FR1 with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.12.4.2.4 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
303 | Y | 38.533 | 12.4.2.5 | RSSI measurement reporting | 38.133 Requirements in Annex A.12.4.2.5 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
304 | Y | 38.533 | 12.4.2.6 | Channel occupancy measurement reporting | 38.133 Requirements in Annex A.12.4.2.6 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
305 |  | 38.533 | 12.5 | Measurement performance | New sub-clause header |  | TBD |  |  | 0
306 |  | 38.533 | 12.5.1 | E-UTRAN-NR SFTD | New sub-clause header |  | TBD |  |  | 0
307 | Y | 38.533 | 12.5.1.1 | Inter-RAT SFTD accuracy with NR target cell under CCA | 38.133 Requirements in Annex A.12.5.1.1 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
308 |  | 38.533 | 12.5.2 | E-UTRAN-NR SS-RSRP | New sub-clause header |  | TBD |  |  | 0
309 |  | 38.533 | 12.5.3 | E-UTRAN-NR SS-RSRQ | New sub-clause header |  | TBD |  |  | 0
310 |  | 38.533 | 12.5.4 | E-UTRAN-NR SS-SINR | New sub-clause header |  | TBD |  |  | 0
311 |  | 38.533 | 12.5.5 | E-UTRAN-NR RSSI | New sub-clause header |  | TBD |  |  | 0
312 |  | 38.533 | 12.5.6 | E-UTRAN-NR channel occupancy | New sub-clause header |  | TBD |  |  | 0
313 |  | 38.533 | 13 | NR Standalone Tests with NR SCell under CCA and All Other NR Cells in FR1 | New sub-clause header |  | TBD |  |  | 0
314 |  | 38.533 | 13.1 | Timing | New sub-clause header |  | TBD |  |  | 0
315 |  | 38.533 | 13.1.1 | UE transmit timing | New sub-clause header |  | TBD |  |  | 0
316 |  | 38.533 | 13.1.2 | Timing advance | New sub-clause header |  | TBD |  |  | 0
317 |  | 38.533 | 13.2 | Signalling characteristics | New sub-clause header |  | TBD |  |  | 0
318 |  | 38.533 | 13.2.1 | Interruption | New sub-clause header |  | TBD |  |  | 0
319 | Y | 38.533 | 13.2.1.1 | NR SA FR1 interruptions during SCell operations with CCA on SCell | 38.133 Requirements in Annex A.13.2.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
320 |  | 38.533 | 13.2.2 | SCell activation and deactivation delay | New sub-clause header |  | TBD |  |  | 0
321 | Y | 38.533 | 13.2.2.1 | NR SA FR1 SCell Activation and Deactivation of known SCell under CCA, 160 ms SCell measurement cycle | 38.133 Requirements in Annex A.13.2.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
322 | Y | 38.533 | 13.2.2.2 | NR SA FR1 SCell Activation and Deactivation of known SCell under CCA, 640 ms SCell measurement cycle | 38.133 Requirements in Annex A.13.2.2.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
323 | Y | 38.533 | 13.2.2.3 | NR SA FR1 SCell Activation and Deactivation of unknown SCell under CCA | 38.133 Requirements in Annex A.13.2.2.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
324 |  | 38.533 | 13.3 | Measurement procedure | New sub-clause header |  | TBD |  |  | 0
325 |  | 38.533 | 13.3.1 | Intra-frequency measurements | New sub-clause header |  | TBD |  |  | 0
326 | Y | 38.533 | 13.3.1.1 | NR SA FR1 Event-triggered reporting tests on SCC under CCA without gaps under non-DRX | 38.133 Requirements in Annex A.13.3.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
327 | Y | 38.533 | 13.3.1.2 | NR SA FR1 Event-triggered reporting tests on SCC under CCA without gaps under DRX | 38.133 Requirements in Annex A.13.3.1.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
328 | Y | 38.533 | 13.3.1.3 | NR SA FR1 Event-triggered reporting tests on SCC under CCA with per-UE gaps under non-DRX | 38.133 Requirements in Annex A.13.3.1.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
329 | Y | 38.533 | 13.3.1.4 | NR SA FR1 Event-triggered reporting tests on SCC under CCA with per-UE gaps under DRX | 38.133 Requirements in Annex A.13.3.1.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
330 | Y | 38.533 | 13.3.1.5 | NR SA FR1 RSSI measurement reporting on SCC under CCA | 38.133 Requirements in Annex A.13.3.1.5 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
331 | Y | 38.533 | 13.3.1.6 | NR SA FR1 Channel occupancy measurement reporting on SCCunder CCA | 38.133 Requirements in Annex A.13.3.1.6 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
332 |  | 38.533 | 13.3.2 | Inter-frequency measurements | New sub-clause header |  | TBD |  |  | 0
333 | Y | 38.533 | 13.3.2.1 | NR SA FR1 RSSI measurement reporting | 38.133 Requirements in Annex A.13.3.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
334 | Y | 38.533 | 13.3.2.2 | NR SA FR1 Channel occupancy measurement reporting | 38.133 Requirements in Annex A.13.3.2.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
335 | Y | 38.533 | 13.3.2.3 | NR SA FR1 Event triggered reporting tests for FR1 with CCA without SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.13.3.2.3 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
336 | Y | 38.533 | 13.3.2.4 | NR SA FR1 Event triggered reporting tests for FR1 with CCA without SSB time index detection when DRX is used | 38.133 Requirements in Annex A.13.3.2.4 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
337 | Y | 38.533 | 13.3.2.5 | NR SA FR1 Event triggered reporting tests for FR1 with CCA with SSB time index detection when DRX is not used | 38.133 Requirements in Annex A.13.3.2.5 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
338 | Y | 38.533 | 13.3.2.6 | NR SA FR1 Event triggered reporting tests for FR1 with CCA with SSB time index detection when DRX is used | 38.133 Requirements in Annex A.13.3.2.6 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
339 |  | 38.533 | 13.3.3 | L1-RSRP measurements for beam reporting | New sub-clause header |  | TBD |  |  | 0
340 | Y | 38.533 | 13.3.3.1 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used | 38.133 Requirements in Annex A.13.3.3.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
341 | Y | 38.533 | 13.3.3.2 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used | 38.133 Requirements in Annex A.13.3.3.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
342 |  | 38.533 | 13.4 | Measurement performance | New sub-clause header |  | TBD |  |  | 0
343 |  | 38.533 | 13.4.1 | SS-RSRP | New sub-clause header |  | TBD |  |  | 0
344 | Y | 38.533 | 13.4.1.1 | NR SA FR1 Intra-frequency measurement accuracy on a carrier frequency with CCA | 38.133 Requirements in Annex A.13.4.1.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
345 |  | 38.533 | 13.4.2 | SS-RSRQ | New sub-clause header |  | TBD |  |  | 0
346 | Y | 38.533 | 13.4.2.1 | NR SA FR1 Intra-frequency measurement accuracy on SCC under CCA | 38.133 Requirements in Annex A.13.4.2.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
347 |  | 38.533 | 13.4.3 | SS-SINR | New sub-clause header |  | TBD |  |  | 0
348 | Y | 38.533 | 13.4.3.1 | NR SA FR1 Intra-frequency measurement accuracy on SCC under CCA | 38.133 Requirements in Annex A.13.4.3.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
349 |  | 38.533 | 13.4.4 | L1-RSRP measurement for beam reporting with CCA serving cell | New sub-clause header |  | TBD |  |  | 0
350 | Y | 38.533 | 13.4.4.1 | NR SA FR1 SSB based L1-RSRP measurement | 38.133 Requirements in Annex A.13.4.4.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
351 |  | 38.533 | 13.4.5 | RSSI | New sub-clause header |  | TBD |  |  | 0
352 | Y | 38.533 | 13.4.5.1 | NR SA FR1 Intra-frequency RSSI measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.13.4.5.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
353 | Y | 38.533 | 13.4.5.2 | NR SA FR1 Inter-frequency RSSI measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.13.4.5.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
354 |  | 38.533 | 13.4.6 | Channel occupancy | New sub-clause header |  | TBD |  |  | 0
355 | Y | 38.533 | 13.4.6.1 | NR SA FR1 Intra-frequency channel occupancy measurement accuracy on SCC with CCA | 38.133 Requirements in Annex A.13.4.6.1 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
356 | Y | 38.533 | 13.4.6.2 | NR SA FR1 Inter-frequency channel occupancy measurement accuracy on a carrier with CCA | 38.133 Requirements in Annex A.13.4.6.2 |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
TBD |  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
TBD |  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TBD |  | 38.905 |  | Derivation of test points for radio transmission and reception test cases | Introduce TP analysis for RF test cases | All Companies | RAN5#97 (Nov-22) | R5-222733 R5-224901 |  | 0.5
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
357 |  | 38.523-1 | 6.6 | NR unlicensed idle mode operations | New sub-clause header |  |  |  | Sub tasks to be identified
358 |  | 38.523-1 | 6.6.1 | NR unlicensed cell selection | New sub-clause header |  |  |  | Sub tasks to be identified
359 | Y | 38.523-1 | 6.6.1.1 | Cell selection / next strongest cell | TS 38.304, clause 5.2.3 | Qualcomm |  | R5-227461 | Merged earlier 6.6.1.2 with this test case 6.6.1.1 | 1 | 100% | 100% |  |  | 100%
360 | Y | 38.523-1 | 6.6.1.2 | Cell selection / Intra frequency reselection not allowed | TS 38.331, clause 5.2.2.5 |  |  |  | Sub tasks to be identified | 1 | 0% | 0% |  |  | 0%
361 |  | 38.523-1 | 6.6.2 | NR unlicensed cell reselection | New sub-clause header |  |  |  | Sub tasks to be identified | 1 | 0% | 0% |  |  | 0%
362 | Y | 38.523-1 | 6.6.2.1 | Cell reselection / next best cell / intra frequency | TS 38.304, clause 5.2.4.4 |  |  |  | Sub tasks to be identified | 1 | 0% | 0% |  |  | 0%
363 | Y | 38.523-1 | 6.6.2.2 | Cell reselection / next best cell / inter frequency | TS 38.304, clause 5.2.4.4 |  |  |  | Sub tasks to be identified | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 6.6.2.3 | Cell reselection / next best cell / intra frequency / RRC Inactive | TS 38.304 clause 5.2.4.1 (1) with { UE in NR RRC_INACTIVE state } ensure that { when { UE detects the cell re-selection criteria are met for the next best cell on the same frequency } then { the UE reselects the new cell } } |  |  |  |  | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 6.6.2.4 | Cell reselection / next best cell / inter frequency / RRC Inactive | TS 38.304 clause 5.2.4.1 (1) with { UE in NR RRC_INACTIVE state } ensure that { when { UE detects the cell re-selection criteria are met for the next best cell on different frequency } then { the UE reselects the new cell } } |  |  |  |  | 1 | 0% | 0% |  |  | 0%
MAC/RLC/PDCP
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
364 | Y | 38.523-1 | 7.1.1.10.3 | NR CA / LBT failure on Scell / MAC CE indication |  |  |  |  | Sub tasks to be identified | 6 | 0% | 0% |  |  | 0%
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
365 |  | 38.523-1 | 8.2.5 | Reconfiguration Failure / Radio link failure | Exisiting sub-clause header
366 |  | 38.523-1 | 8.2.5.7 | Radio link failure / Shared spectrum / LBT Failure | New sub-clause header
367 | Y | 38.523-1 | 8.2.5.7.1 | Radio link failure / LBT Failure / EN-DC | TS 36.331, clause 5.6.13a.3, TS 38.331, clauses 5.3.5.3, 5.3.5.5.1, 5.3.5.5.2, 5.3.5.8.3, 5.7.3.2 and 5.7.3.3 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% |  |  | 0%
368 | Y | 38.523-1 | 8.2.5.7.2 | Radio link failure / LBT Failure / NR-DC | TS 38.331, clauses 5.3.5.5.1, 5.3.5.5.2, 5.3.5.8.3, 5.3.10.3, 5.7.3.2, 5.7.3.5 | Ericsson | RAN5#97 (Nov-22) |  |  | 1
369 | Y | 38.523-1 | 8.2.5.7.3 | Radio link failure / LBT Failure | TS 38.331, clauses 5.3.5.5.1, 5.3.5.5.2, 5.3.5.8.3, 5.3.10.3, 5.7.3.2, 5.7.3.5 |  | RAN5#97 (Nov-22) |  |  | 1 | 20% | 20% |  |  | 20%
367 |  | 38.523-1 | 8.1.5.6 | Radio link failure | [6 empty] | 0% |  | 0% |  |  | 0%
368 |  | 38.523-1 | 8.1.5.6.6 | Radio link failure / Shared spectrum / LBT Failure
369 | Y | 38.523-1 | 8.1.5.6.6.1 | Radio link failure / LBT Failure | TS 38.331, clauses 5.3.5.5.1, 5.3.5.5.2, 5.3.5.8.3, 5.3.10.3, 5.7.3.2, 5.7.3.5 | Qualcomm | RAN5#97 (Nov-22) | R5-227462 | LBT failures on Pcell, trigger RLF. 20% kept open for any issues in UL consistent LBT failure updates based on test model. | 1 | 80% | 80% |  |  | 80%
370 |  | 38.523-1 | 8.1.8 | Shared spectrum access | New sub-clause header
371 |  | 38.523-1 | 8.1.8.1 | Measurement configuration control and reporting for Shared spectrum | New sub-clause header
372 | Y | 38.523-1 | 8.1.8.1.1 | Measurement configuration control and reporting for Shared spectrum / RMTC / RSSI measurements / intra-frequency | TS 38.331 | Ericsson | RAN5#97 (Nov-22) | R5-227586 | Merged earlier 8.1.8.1.3 with 8.1.8.1.1 | 1 | 100% | 100% |  |  | 100%
373 | Y | 38.523-1 | 8.1.8.1.2 | Measurement configuration control and reporting for Shared spectrum / RMTC / RSSI measurements / inter-frequency | TS 38.331 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
374 | Y | 38.523-1 | 8.1.8.1.3 | Measurement configuration control and reporting for Shared spectrum / RMTC / Channel Occupancy reporting / intra-frequency | TS 38.331 |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
375 | Y | 38.523-1 | 8.1.8.1.4 | Measurement configuration control and reporting for Shared spectrum / RMTC / Channel Occupancy reporting / inter-frequency | TS 38.331 |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
376 | Y | 38.523-1 | 8.1.8.1.5 | Measurement configuration control and reporting for Shared spectrum / RMTC / Event A2 / inter-frequency | TS 38.331 |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
377 |  | 38.523-1 | 8.1.8.2 | Paging monitoring
378 | Y | 38.523-1 | 8.1.8.2.1 | Paging monitoring / Short message indication / stopPagingMonitoring | TS 38.331 clause 5.2.2.2.2 |  | RAN5#97 (Nov-22) | R5-227280 |  | 1 | 100% | 100% |  |  | 100%
379 | Y | 38.523-1 | 8.1.8.2.2 | Paging monitoring / multiple PDCCH monitoring occasions | TS 38.304 clause 7.1 |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
380 |  | 38.523-1 | 8.1.8.3 | CAPC | TS 38.300 5.7.1, 5.3.3, 5.X.2, |  |  |  | Sub tasks to be identified
TBD |  | 38.523-1 | FFS | CG (Configured grant) | TS 37.213 4.2.3, TS 38.212 7.3.1 |  |  |  | Sub tasks to be identified
TBD |  | 38.523-1 | FFS | Study of legacy test cases to be made applicable to NR-U |  |  |  |  | Sub tasks to be identified
TBD |  | 38.523-1 | FFS | Test cases to be identified for CA Scenario A: Carrier aggregation between licensed band NR (PCell) and NR-U (SCell) o NR-U SCell may have both DL and UL, or DL-only. - Scenario D: A stand-alone NR cell in unlicensed band and UL in licensed band |  |  |  |  | Sub tasks to be identified
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
381 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | [5 empty] | 1 | 5% | 15% | 0% |  | 15% | 0%
TS 38.523-3: Protocol test suites (TTCN)
TBD |  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | TBD | Introduction of General and Signaling Test Environment for NR-U in NR | [5 empty] | 2 | 0% | 0% |  |  | 0%
UE Positioning
TS 37.571-1: UE Positioning -Performance
|  | 37.571-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 37.571-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 37.571-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 37.571-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 37.571-2: UE Positioning -Protocol
|  | 37.571-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 37.571-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 37.571-2 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 37.571-2 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 37.571-3: Applicability and ICS UE Positioning test cases
TBD |  | 37.571-3 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 37.571-3 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 37.571-1 and 37.571-2. |  | TBD |  |  | 0.1
TS 37.571-4: UE Positioning test suites (TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 37.571-4 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 37.571-5: UE Positioning test scenarios and assistance data
|  | 37.571-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 37.571-5 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.