## Cover sheet
3GPP TSG-RAN5 Meeting # 98 | [7 empty] | R5-230088
Athens, Greece, Feb 27th – March 3rd 2023
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP for UE Conformance – Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink RAN5#98
Work item code: | DL_intrpt_combos_TxSW_R17-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to introduce DL interruption clarifications for the specific CA combinations while UE conducting Tx Switching, in corresponding to the objectives of the RAN4 WID on ‘Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink’. Note: The DL interruption clarifications are not introduced for the CA configurations with PC3 status ‘pending’ in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5% (+5%)
FR1 |  | 5% (+5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common ICS | 38.508-2
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-222948 | New WID on UE Conformance – Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for UE Conformance – Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | DL_intrpt_combos_TxSW_R17-UEConTest
WP Scope: |  | The objective of this work item is to introduce DL interruption clarifications for the specific CA combinations while UE conducting Tx Switching, in corresponding to the objectives of the RAN4 WID on ‘Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink’. Note: The DL interruption clarifications are not introduced for the CA configurations with PC3 status ‘pending’ in RAN5.
WP Resp: |  | Jingzhou Wu (China Telecom) |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title (CA Configuration) | Test purpose / Task (UL CA Configuration) | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
5% (+5%)
1 (+1)
1 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Test of 'No DL interruption' requirements for the following band combinitions
1 |  | 38.521-1 | 5.2A.2.2 | CA_n1-n3-n78 | CA_n1-n78, CA_n3-n78 | China Telecom | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
The DL interruption requirements are not introduced for the following configurations with PC3 status ‘pending’ in RAN5 (PRD21)
|  | 38.521-1 | 5.2A.2.2 | CA_n3-n40-n41 | CA n3-n40, CA n3-n41 |  |  |  |  | 0
|  | 38.521-1 | 5.2A.2.2 | CA_n3-n41-n79 | CA n3-n41, CA n3-n79, CA n41-n49 |  |  |  |  | 0
|  | 38.521-1 | 5.2A.2.2 | CA_n39-n41-n79 | CA n39-n79, CA n41-n79, CA n39-n41 |  |  |  |  | 0
|  | 38.521-1 | 5.2A.2.2 | CA_n40-n41-n79 | CA n40-n79, CA n41-n79 |  |  |  |  | 0
|  | 38.521-1 | 5.2A.2.2 | CA_n8-n39-n41 | CA n8-n39, CA n8-n41, CA n39-n41 |  |  |  |  | 0
|  | 38.521-1 | 5.2A.2.2 | CA_n8-n41-n79 | CA n8-n41, CA n8-n79, CA n41-n79 |  |  |  |  | 0
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.