## Cover sheet
3GPP TSG RAN WG5 Meeting #98 | [8 empty] | R5-230386
Athens, Greece, Feb 27th - Mar 3rd, 2023
Agenda Item: | 7.4.2
Source: | Rapporteur (CMCC)
Title: | WP UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations
Work item code: | NR_CADC_NR_LTE_DC_R16-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
At the [RAN#83 meeting in March 2019 the Rel-16 RAN5 work item for UE Conformance Test Aspects of Rel-16 NR CA and DC; and NR and LTE DC Configurations was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the introducing the Rel-16 NR CA and DC; and NR and LTE DC Configurations into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'NR CA, NR DC and EN-DC configs' shows the status for each configuration. Note: This work plan is limited to the addition of new and update of existing NR CA, NR-DC and EN-DC test cases for the new types of configurations introduced by this basket work item. Tracking of status, interested operator and responsible companies for configurations can be found in the RAN5 Permanent Reference Document [2] PRD21. Introducing new Rel-16 NR CA, NR-DC and EN-DC shall be in accordance to the guidelines in [2] PRD21.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 42% | 11 | 110 (+7)
Completion Compensation |  | 7.376%
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 50% (+5.6%) | 5 | 19 (+3)
FR1 |  | 50% (+5.6%) | 5 | 16
NSA Option 3 (EN-DC) |  | 32.2% (+4.4%) | 6 | 94 (+7)
FR1 |  | 100%
FR2 |  | 31.6% (+4.4%) | 6 | 122 (+3)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
Rel-16 New CADC test cases
TS 38.521-1
NR CA FR1 Tx test cases | 38.521-1: NR CA Tx
NR CA FR1 Rx test cases | 38.521-1: NR CA Rx | 44.1% | 5 | 16 | 44.1% | 5 | 16
TS 38.521-2
NR CA FR2 Tx test cases | 38.521-2: NR CA Tx
NR CA FR2 Rx test cases | 38.521-2: NR CA Rx
TS 38.521-3
EN-DC FR1 tx test cases | 38.521-3: EN-DC FR1 Tx
EN-DC FR2 tx test cases | 38.521-3: EN-DC FR2 Tx | 27.5% (+4.1%) | 6 | 91 (+4) | [8 empty] | 27.5% (+4.1%) | 6 | 119
EN-DC FR1 Rx test cases | 38.521-3: EN-DC FR1 Rx | 50% (+50%) | 0 | 3 (+3) | [8 empty] | 50% (+50%) | 0 | 3 (+3)
EN-DC FR2 Rx test cases | 38.521-3: EN-DC FR2 Rx
5 References
[1] RP-190321 | New WID on: UE Conformance Test Aspects - Rel-16 NR CA_DC Configurations; Supporting companies: CMCC, China Unicom, Ericsson, Huawei, Hisilicon, Keysight, R&S, China Telecom, AT&T, CAICT, KTL NTT DOCOMO, Nokia, Nokia Shanghai Bell, Bureau Veritas, Orange, Dish
[2] RAN5 PRD21 | NR bands and 5G NR CADC configuration handling in RAN5 (Release 15 and later releases)
Download PRD21 from here: ftp://ftp.3gpp.org/TSG_RAN/WG5_Test_ex-T1/PRD/
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_CADC_NR_LTE_DC_R16-UEConTest
WP Scope: |  | <WP Scope description>
WP Resp: |  | Dan Song |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1 | FR2
[15 empty] | 50% (+5.6%) | 100% | 31.6% (+4.4%)
[15 empty] | 17 | 2 | 122 (+3)
[15 empty] | 17 | 1 | 122 (+3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Rel-16 New CADC test cases
TS 38.521-1: NR CA FR1
TS 38.521-1: NR CA Transmitter Characterstics (Section 6)
TS 38.521-1: NR CA Receiver Characterstics (section 7)
|  | 38.521-1 | 7.3A.2 | Reference sensitivity power level for CA (3DL CA) without exceptions | TS38.101-1 cl 7.3A.2 ~ 7.3A.5 for CA including intra-band contiguous, intra-band non-contiguous, and inter-band CA with 3 DL CC | Qualcomm |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 NR_RF_FR1-UEConTest WP. | 0 |  |  | 7 | 1 |  | 1
133 |  | 38.521-1 | 7.3A.2_1 | Reference sensitivity power level for 3DL CA exceptions |  | Verizon | RAN5#98 (Feb-23) | 38.521-1: R5-230282 | Ma, Jinwen<jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  |  | 100% | 1
1 | Y | 38.521-1: NR CA Rx | 7.3A.3 | Reference sensitivity level for CA (4DL CA) |  | Qualcomm | RAN5#95 (May-22) | 38.521-1: R5-210539 38.522: R5-231809 | Kevin Wang (QMC)<kevinw@qti.qualcomm.com> | 1 | 50% | 50% |  |  | 50%
TBD | Y | 38.521-1: NR CA Rx | 7.3A.4 | Reference sensitivity level for CA (5DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
2 | Y | 38.521-1: NR CA Rx | 7.4A.3 | Maximum input level for CA (4DL CA) |  | WE Certification Oy | RAN5#95 (May-22) | 38.521-1： R5-210540 38.522： for further input | aleksi.heino@wecertification.com | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-1: NR CA Rx | 7.4A.4 | Maximum input level for CA (5DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
3 | Y | 38.521-1: NR CA Rx | 7.5A.3 | Adjacent channel selectivity for 4DL CA |  | China Telecom | RAN5#95 (May-22) | 38.521-1： R5-192586, R5-194920, R5-200393, R5-200924, R5-206719, R5-211764, R5-217746 38.522： R5-195444 | Jing ZHAO<zhaoj16@chinatelecom.cn> | 1 | 95% | 95% |  |  | 95%
TBD | Y | 38.521-1: NR CA Rx | 7.5A.4 | Adjacent channel selectivity for 5DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
4 | Y | 38.521-1: NR CA Rx | 7.6A.2.3 | In-band blocking for CA (4DL CA) |  | WE Certification Oy | RAN5#89 (Nov-20) | 38.521-1： R5-210541 38.522： No need to change | aleksi.heino@wecertification.com | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-1: NR CA Rx | 7.6A.2.4 | In-band blocking for CA (5DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
5 | Y | 38.521-1: NR CA Rx | 7.6A.3.3 | Out-of-band blocking for CA (4DL CA) |  | CAICT | RAN5#89 (Nov-20) | 38.521-1： R5-202035 38.522： R5-195444, R5-197650, R5-203114 | Yufeng ZHANG<zhangyufeng@caict.ac.cn> | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-1: NR CA Rx | 7.6A.3.4 | Out-of-band blocking for CA (5DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
6 | Y | 38.521-1: NR CA Rx | 7.6A.4.3 | Narrow band blocking for CA (4DL CA) |  | CAICT | RAN5#89 (Nov-20) | R5-202037, R5-223656 | Yufeng ZHANG<zhangyufeng@caict.ac.cn> | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-1: NR CA Rx | 7.6A.4.4 | Narrow band blocking for CA (5DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
7 | Y | 38.521-1: NR CA Rx | 7.7A.3 | Spurious response for 4DL CA |  | CMCC | RAN5#98 (Feb-27) | 38.521-1： R5-192565, R5-197329 38.522： R5-195444 | songdan<songdan@chinamobile.com> | 1 | 60% | 60% |  |  | 60%
TBD | Y | 38.521-1: NR CA Rx | 7.7A.4 | Spurious response for 5DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
8 | Y | 38.521-1: NR CA Rx | 7.8A.2.3 | Wide band Intermodulation for CA (4DL CA) |  | CAICT | RAN5#89 (Nov-20) | 38.521-1： R5-202039 38.522： R5-203114 | Yufeng ZHANG<zhangyufeng@caict.ac.cn> | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-1: NR CA Rx | 7.8A.2.4 | Wide band Intermodulation for CA (5DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-2: NR CA FR2
TS 38.521-2: NR CA Transmitter Characterstics (Section 6)
TS 38.521-2: NR CA Receiver Characterstics (Section 7)
TS 38.521-3: NR CA FR1+FR2, NR-DC FR1+FR2, EN-DC
TS 38.521-3: EN-DC FR1 Transmitter Characterstics (Section 6)
TS 38.521-3: EN-DC FR2 Transmitter Characterstics (Section 6)
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (2 NR CCs) | Sub-heading |  |  |  |  | 0
13 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.1.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (2 NR CCs) - EIRP and TRP |  | Intertek | RAN5#98 (Feb-27) | 38.521-3： R5-199377, R5-204924, R5-204925 | Test case for PC3 and BW<=400MHz under normal conditions is completed. Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
14 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.1.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (2 NR CCs) - Spherical Coverage |  | Intertek | RAN5#98 (Feb-27) | 38.521-3： R5-199377, R5-204924, R5-204925 | Test case for PC3 and BW<=400MHz is completed. Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (3 NR CCs) | Sub-heading |  |  |  |  | 0
15 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.2.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (3 NR CCs) - EIRP and TRP |  | Intertek | RAN5#98 (Feb-27) | 38.521-3： R5-199377, R5-204924, R5-204925 | Test case for PC3 and BW<=400MHz under normal conditions is completed. Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
16 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.2.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (3 NR CCs) - Spherical Coverage |  | Intertek | RAN5#98 (Feb-27) | 38.521-3： R5-199377, R5-204924, R5-204925 | Test case for PC3 and BW<=400MHz is completed. Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.3 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (4 NR CCs) | Sub-heading |  |  |  |  | 0
17 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.3.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (4 NR CCs) - EIRP and TRP |  | Intertek | RAN5#98 (Feb-27) | 38.521-3： R5-199377, R5-204924, R5-204925 | Test case for PC3 and BW<=400MHz under normal conditions is completed. Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
18 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.3.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (4 NR CCs) - Spherical Coverage |  | Intertek | RAN5#98 (Feb-27) | 38.521-3： R5-199377, R5-204924, R5-204925 | Test case for PC3 and BW<=400MHz is completed. Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.4 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (5 NR CCs) | Sub-heading |  |  |  |  | 0
66 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.4.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (5 NR CCs) - EIRP and TRP |  | Intertek | RAN5#98 (Feb-27) | 38.521-3: R5-223664 38522: R5-222562 | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 60% |  | 60% |  |  |  | 60%
67 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.4.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (5 NR CCs) - Spherical Coverage |  | Intertek | RAN5#98 (Feb-27) | 38.521-3: R5-223664 38522: R5-222562 | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 60% |  | 60% |  |  |  | 60%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.5 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (6 NR CCs) | Sub-heading |  |  |  |  | 0
68 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.5.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (6 NR CCs) - EIRP and TRP | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) | 38.521-3: R5-224437 38522: R5-224438 | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 60% |  | 60% |  |  |  | 60%
69 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.5.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (6 NR CCs) - Spherical Coverage | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) | 38.521-3: R5-224437 38522: R5-224438 | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 60% |  | 60% |  |  |  | 60%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.6 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (7 NR CCs) | Sub-heading |  |  |  |  | 0
70 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.6.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (7 NR CCs) - EIRP and TRP | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
71 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.6.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (7 NR CCs) - Spherical Coverage | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.7 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (8 NR CCs) | Sub-heading |  |  |  |  | 0
72 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.7.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (8 NR CCs) - EIRP and TRP | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
73 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.1.4_1.7.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (8 NR CCs) - Spherical Coverage | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh Intertek<bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
19 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.1 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (2 NR CCs) |  | Intertek | RAN5#98 (Feb-27) | 38.521-3: R5-221772 38.522: R5-221213 | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 80% |  | 80% |  |  |  | 80%
20 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.2 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
24 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.3 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
74 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.4 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
75 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.5 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
76 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.6 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
77 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.2.4_1.7 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (> 1 NR CC) | Sub-heading |  |  |  |  | 0
21 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.1 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
22 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.2 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
23 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.3 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
78 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.4 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
79 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.5 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
80 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.6 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
81 | Y | 38.521-3: EN-DC FR2 Tx | 6.2B.3.4_1.7 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#98 (Feb-27) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1 | Minimum output power for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
25 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.1 | Minimum output power for inter-band EN-DC including FR2 (2 NR CCs) |  | KTL | RAN5#98 (Feb-27) | 38.521-3： R5-206720 | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 60% |  | 60% |  |  |  | 60%
26 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.2 | Minimum output power for inter-band EN-DC including FR2 (3 NR CCs) |  | KTL | RAN5#98 (Feb-27) | 38.521-3： R5-206721 | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 60% |  | 60% |  |  |  | 60%
27 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.3 | Minimum output power for inter-band EN-DC including FR2 (4 NR CCs) |  | KTL | RAN5#98 (Feb-27) | 38.521-3： R5-206722 | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 60% |  | 60% |  |  |  | 60%
82 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.4 | Minimum output power for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
83 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.5 | Minimum output power for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
84 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.6 | Minimum output power for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
85 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.1.4_1.7 | Minimum output power for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1 | Transmit OFF Power for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  | As per the agreed CR R5-213909,the test cases in section 6.3B.2.4_1 have been removed assuming testing is enough in single CC test. | 0
31 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.1 | Transmit OFF Power for inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) | 38.521-2： R5-204948, R5-210489 |  | 1 | 0% |  | 0% |  |  |  | 0%
32 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.2 | Transmit OFF Power for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) | 38.521-2： R5-204948, R5-210489 |  | 1 | 0% |  | 0% |  |  |  | 0%
33 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.3 | Transmit OFF Power for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) | 38.521-2： R5-204948, R5-210489 |  | 1 | 0% |  | 0% |  |  |  | 0%
86 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.4 | Transmit OFF Power for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
87 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.5 | Transmit OFF Power for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
88 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.6 | Transmit OFF Power for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
89 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.2.4_1.7 | Transmit OFF Power for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  | RAN5#98 (Feb-27) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
28 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.1 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
29 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.2 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
30 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.3 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
90 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.4 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
91 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.5 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
92 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.6 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
93 | Y | 38.521-3: EN-DC FR2 Tx | 6.3B.3.4_1.7 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Intertek | RAN5#99 (May-23) |  | Bruce Hsueh <bruce.hsueh@intertek.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1 | Frequency Error for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
34 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.1 | Frequency Error for inter-band EN-DC including FR2 (2 NR CCs) |  | DCM | RAN5#97 (Nov-22) | 38.521-2： R5-202918 38.521-3： R5-202959 R5-213912 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 100% |  | 100% |  |  |  | 100%
35 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.2 | Frequency Error for inter-band EN-DC including FR2 (3 NR CCs) |  | DCM | RAN5#97 (Nov-22) | 38.521-2： R5-202918 38.521-3： R5-202959 R5-213912 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 100% |  | 100% |  |  |  | 100%
36 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.3 | Frequency Error for inter-band EN-DC including FR2 (4 NR CCs) |  | DCM | RAN5#97 (Nov-22) | 38.521-2： R5-202918 38.521-3： R5-202959 R5-213912 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 100% |  | 100% |  |  |  | 100%
94 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.4 | Frequency Error for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
95 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.5 | Frequency Error for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
96 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.6 | Frequency Error for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
97 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.1.4_1.7 | Frequency Error for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1 | Error Vector Magnitude for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
37 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.1 | Error Vector Magnitude for inter-band EN-DC including FR2 (2 NR CCs) |  | KTL | RAN5#98 (Feb-27) | 38.521-3： R5-206723 | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 50% |  | 50% |  |  |  | 50%
38 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.2 | Error Vector Magnitude for inter-band EN-DC including FR2 (3 NR CCs) |  | KTL | RAN5#98 (Feb-27) | 38.521-3： R5-206724 | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 50% |  | 50% |  |  |  | 50%
39 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.3 | Error Vector Magnitude for inter-band EN-DC including FR2 (4 NR CCs) |  | KTL | RAN5#98 (Feb-27) | 38.521-3： R5-206725 | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 50% |  | 50% |  |  |  | 50%
98 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.4 | Error Vector Magnitude for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
99 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.5 | Error Vector Magnitude for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
100 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.6 | Error Vector Magnitude for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
101 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.1_1.7 | Error Vector Magnitude for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
|  |  | 6.4B.2.4.2_1 | Carrier Leakage for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
40 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.1 | Carrier Leakage for inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
41 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.2 | Carrier Leakage for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
42 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.3 | Carrier Leakage for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
102 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.4 | Carrier Leakage for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
103 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.5 | Carrier Leakage for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
104 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.6 | Carrier Leakage for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
105 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.2_1.7 | Carrier Leakage for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
|  |  | 6.4B.2.4.3_1 | In-band Emissions for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
43 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.1 | In-band Emissions for inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
44 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.2 | In-band Emissions for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
45 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.3 | In-band Emissions for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
106 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.4 | In-band Emissions for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
107 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.5 | In-band Emissions for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
108 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.6 | In-band Emissions for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
109 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.3_1.7 | In-band Emissions for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL | RAN5#98 (Feb-27) |  | Phil Kwak <pkkwak@ktl.re.kr> | 1 | 0% |  | 0% |  |  |  | 0%
|  |  | 6.4B.2.4.4_1 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
46 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.1 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
47 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.2 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
48 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.3 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
110 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.4 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
111 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.5 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
112 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.6 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
113 | Y | 38.521-3: EN-DC FR2 Tx | 6.4B.2.4.4_1.7 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1 | Occupied bandwidth for inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
49 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.1 | Occupied bandwidth for inter-band EN-DC including FR2 (2 NR CCs) |  | DCM | RAN5#98 (Feb-27) | 38.521-2： R5-211946 38.521-3： R5-195157 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 70% |  | 70% |  |  |  | 70%
50 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.2 | Occupied bandwidth for inter-band EN-DC including FR2 (3 NR CCs) |  | DCM | RAN5#98 (Feb-27) | 38.521-2： R5-211946 38.521-3： R5-195157 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 70% |  | 70% |  |  |  | 70%
51 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.3 | Occupied bandwidth for inter-band EN-DC including FR2 (4 NR CCs) |  | DCM | RAN5#98 (Feb-27) | 38.521-2： R5-211946 38.521-3： R5-195157 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 70% |  | 70% |  |  |  | 70%
114 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.4 | Occupied bandwidth for inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
115 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.5 | Occupied bandwidth for inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
116 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.6 | Occupied bandwidth for inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
117 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.1.4_1.7 | Occupied bandwidth for inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1 | Spectrum emissions mask for Inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
52 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.1 | Spectrum emissions mask for Inter-band EN-DC including FR2 (2 NR CCs) |  | DCM | RAN5#93 (Nov-21) | 38.521-3： R5-202135, R5-204925 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 100% |  | 100% |  |  |  | 100%
53 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.2 | Spectrum emissions mask for Inter-band EN-DC including FR2 (3 NR CCs) |  | DCM | RAN5#93 (Nov-21) | 38.521-3： R5-202135, R5-204925 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 100% |  | 100% |  |  |  | 100%
54 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.3 | Spectrum emissions mask for Inter-band EN-DC including FR2 (4 NR CCs) |  | DCM | RAN5#93 (Nov-21) | 38.521-3： R5-202135, R5-204925 | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 100% |  | 100% |  |  |  | 100%
124 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.4 | Spectrum emissions mask for Inter-band EN-DC including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
125 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.5 | Spectrum emissions mask for Inter-band EN-DC including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
126 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.6 | Spectrum emissions mask for Inter-band EN-DC including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
127 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.1_1.7 | Spectrum emissions mask for Inter-band EN-DC including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | DCM | RAN5#98 (Feb-27) |  | Takashi Akao <takashi.akao.wa@nttdocomo.com> | 1 | 0% |  | 0% |  |  |  | 0%
|  |  | 6.5B.2.4.3_1 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
55 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.1 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.1 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
56 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.2 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.2 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
57 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.3 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.3 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
128 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.4 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (5 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223665, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.4 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
129 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.5 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (6 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223666, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.5 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
130 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.6 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (7 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223667, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.6 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
131 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.2.4.3_1.7 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (8 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223668, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.2.2.7 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
|  |  | 6.5B.3.4.1_1 | General Spurious Emissions for Inter-band including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
59 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.1 | General Spurious Emissions for Inter-band including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.1 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
60 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.2 | General Spurious Emissions for Inter-band including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.2 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
61 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.3 | General Spurious Emissions for Inter-band including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Sporton | RAN5#98 (Feb-27) |  | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.3 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
132 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.4 | General Spurious Emissions for Inter-band including FR2 (5 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223669, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.4 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
12 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.5 | General Spurious Emissions for Inter-band including FR2 (6 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223670, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.5 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
11 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.6 | General Spurious Emissions for Inter-band including FR2 (7 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223671, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.6 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
10 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.1_1.7 | General Spurious Emissions for Inter-band including FR2 (8 NR CCs) |  | Sporton | RAN5#98 (Feb-27) | 38.521-3: R5-223671, R5-225678 38.522: R5-225710 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> The referred test case 6.5A.3.1.7 in TS 38.521-2 [9] is incomplete for intra-band contiguous CA supporting aggregated BW > 400MHz are TBD. | 1 | 60% |  | 60% |  |  |  | 60%
|  |  | 6.5B.3.4.2_1 | Spurious emission band UE co-existence for Inter-band including FR2 (>1 NR CC) | Sub-heading |  |  |  |  | 0
62 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.1 | Spurious emission band UE co-existence for Inter-band including FR2 (2 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-218211 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
63 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.2 | Spurious emission band UE co-existence for Inter-band including FR2 (3 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-218211 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
64 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.3 | Spurious emission band UE co-existence for Inter-band including FR2 (4 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-218211 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
9 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.4 | Spurious emission band UE co-existence for Inter-band including FR2 (5 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-231675 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
123 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.5 | Spurious emission band UE co-existence for Inter-band including FR2 (6 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-231675 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
123 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.6 | Spurious emission band UE co-existence for Inter-band including FR2 (7 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-231675 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
122 | Y | 38.521-3: EN-DC FR2 Tx | 6.5B.3.4.2_1.7 | Spurious emission band UE co-existence for Inter-band including FR2 (8 NR CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) | 38.521-3: R5-231675 | Hemish Parikh<hparikh@qti.qualcomm.com> | 1 | 70% (+70%) |  | 70% (+70%) |  |  |  | 70%
TS 38.521-3: EN-DC FR1 Receiver Characterstics (Section 7)
|  | 38.521-3: EN-DC FR1 Rx | 7.3B.2.3_1 | Reference sensitivity for EN-DC within FR1 (>2 CCs) | [5 empty] | 0
121 | Y | 38.521-3: EN-DC FR1 Rx | 7.3B.2.3_1.1 | Reference sensitivity for EN-DC within FR1 (3 CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) |  | Kevin Wang (QMC)<kevinw@qti.qualcomm.com> | 1 | 50% (+50%) |  | 50% (+50%) |  |  |  | 50%
120 | Y | 38.521-3: EN-DC FR1 Rx | 7.3B.2.3_1.2 | Reference sensitivity for EN-DC within FR1 (4 CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) |  | Kevin Wang (QMC)<kevinw@qti.qualcomm.com> | 1 | 50% (+50%) |  | 50% (+50%) |  |  |  | 50%
119 | Y | 38.521-3: EN-DC FR1 Rx | 7.3B.2.3_1.3 | Reference sensitivity for EN-DC within FR1 (5 CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) |  | Kevin Wang (QMC)<kevinw@qti.qualcomm.com> | 1 | 50% (+50%) |  | 50% (+50%) |  |  |  | 50%
118 | Y | 38.521-3: EN-DC FR1 Rx | 7.3B.2.3_1.4 | Reference sensitivity for EN-DC within FR1 (6 CCs) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | Qualcomm | RAN5#98 (Feb-27) |  | Kevin Wang (QMC)<kevinw@qti.qualcomm.com> | 1
TS 38.521-3: EN-DC FR2 Receiver Characterstics (Section 7)
TBD |  | 38.521-3: EN-DC FR2 Rx | [7 empty] | 0
TS 38.522: Applicability
TS 38.522: Recommended test case applicability (Section 4)
|  | 38.522: Applicaiblity for the R16 CADC test cases | 4 | [5 empty] | The corresponding Tdocs have been captured in the specific test cases. | 0
TS 38.905: Derivation of test points for radio transmission and reception
TS 38.905: Test coverage analysis (Section 4)
|  | 38.905: TP analysis for R16 CADC configurations | 4 | [5 empty] | The corresponding Tdocs have been captured in the specific test cases. | 0
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.