## Cover sheet
3GPP TSG-RAN WG5 Meeting #98 | [7 empty] | R5-230392
Athens, Greece, Feb 27th - Mar 3rd, 2023
Agenda Item: | 7.4.2
Source: | CMCC, MediaTek Inc.
Title: | WP UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN)
Work item code: | LTE_NBIOT_eMTC_NTN_req-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 30% (+30%) | 6.9 (+6.9) | 64.9 (+64.9)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD) |  | 29.6% (+29.6%) | 6.9 (+6.9) | 64.9 (+64.9)
FDD |  | 29.6% (+29.6%) | 6.9 (+6.9) | 64.9 (+64.9)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 54.5% (+54.5%) | 0.4 (+0.4) | 0.4 (+0.4) | 54.5% (+54.5%) | 0.4 (+0.4) | 0.4 (+0.4)
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-4 | 95.7% (+95.7%) | 6 (+6) | 8 (+8) | 95.7% (+95.7%) | 6 (+6) | 8 (+8)
RF Rx test cases | 36.521-4 Rx | 10.3% (+10.3%) | 0 | 17 (+17) | 10.3% (+10.3%) | 0 | 17 (+17)
RF Tx test cases | 36.521-4 Tx | 0% | 0 | 37 (+37) | 0% | 0 | 37 (+37)
RF Demod test cases | 36.521-4 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 40% (+40%) |  |  | 40% (+40%)
RRM test cases | 36.521-3 | 9.8% (+9.8%) | 0.5 (+0.5) | 1 (+1) | 9.8% (+9.8%) | 0.5 (+0.5) | 1 (+1)
Test Tolerances analysis RRM test cases | 36.903 | 0% |  |  | 0%
Test Tolerances analysis receiver test cases | 36.904 | 17.6% (+17.6%) | 0 | 0.5 (+0.5) | 17.6% (+17.6%) | 0 | 0.5 (+0.5)
Test Point analysis receiver and transmitter test cases | 36.905 | 16.7% (+16.7%) | 0 | 1 (+1) | 16.7% (+16.7%) | 0 | 1 (+1)
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2 | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NBIOT_eMTC_NTN_req-UEConTest
WP Scope: |  | This work plan covers the tasks needed to include NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN)
WP Resp: |  | Danni Song (CMCC); Danbo Fu (MediaTek) |  |  | songdan@chinamobile.com; Danbo.Fu@mediatek.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | Danni Song (CMCC) |  |  | songdan@chinamobile.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
29.6% (+29.6%)
140 (+140)
107.5 (+107.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 36.508 | 2 | References | Add TS 36.521-4. | CMCC | RAN5#99 (May-23) | R5-230397 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.508 | 4 | Common test environment | Clause header |  |  |  |  | TBD
2 |  | 36.508 | 4.2 | Common requirements of test equipment | Update common requirements of test equipment for RF/RRM/Demod test cases impacted by Rel-18 eMTC core & performance requirements for NTN |  | RAN5#99 (May-23) |  |  | TBD | 0% | 0% |  | 0%
|  | 36.508 | 4.3 | Reference test conditions | Sub-clause header |  |  |  |  | TBD
|  | 36.508 | 4.3.1.1 | FDD Mode Test frequencies | Sub-clause header |  |  |  |  | TBD
3 | Y | 36.508 | 4.3.1.1.255 | FDD reference test frequencies for operating band 255 | Update FDD Mode Test frequencies for operating band 255 for Rel-18 eMTC core & performance requirements for NTN | CMCC | RAN5#99 (May-23) | R5-230395 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
4 | Y | 36.508 | 4.3.1.1.256 | FDD reference test frequencies for operating band 256 | Update FDD Mode Test frequencies for operating band 256 for Rel-18 eMTC core & performance requirements for NTN | CMCC | RAN5#99 (May-23) | R5-230395 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.508 | 5 | Test environment for RF test | Clause header |  |  |  |  | TBD
|  | 36.508 | 5.2 | RF Reference system configurations | Sub-clause header |  |  |  |  | TBD
5 |  | 36.508 | 5.2.1 | Common parameters for simulated E-UTRA cells | Update common parameters for eMTC NTN RF testing |  | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  | 0%
|  | 36.508 | 6 | Test environment for Signalling test | Clause header |  |  |  |  | TBD
|  | 36.508 | 6.2 | Reference test conditions | Sub-clause header |  |  |  |  | TBD
6 |  | 36.508 | 6.2.3 | Default test frequencies | Update the general wording for default test frequencies for eMTC NTN SIG testing | CMCC | RAN5#99 (May-23) | R5-231561 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
7 |  | 36.508 | 6.2.3.1 | Test frequencies for signalling test | Update test frequencies for eMTC NTN SIG testing | CMCC | RAN5#99 (May-23) | R5-231561 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.508 | 7 | Test environment for RRM tests | Clause header |  |  |  |  | TBD
|  | 36.508 | 7.2 | RRM Reference system configurations | Sub-clause header |  |  |  |  | TBD
8 |  | 36.508 | 7.2.1 | Common parameters for simulated E-UTRA cells | Update common parameters for eMTC NTN RRM testing |  | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  | 0%
|  | 36.508 | 8 | NB-IoT test environment | Clause header |  |  |  |  | TBD
|  | 36.508 | 8.1 | NB-IoT Common test environment | Sub-clause header |  |  |  |  | TBD
9 |  | 36.508 | 8.1.2 | NB-IoT Common requirements of test equipment | Update common requirements of test equipment for RF/RRM/Demod test cases impacted by Rel-18 NB-IoT core & performance requirements for NTN | Mediatek | RAN5#99 (May-23) | R5-231027（under LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest WI） | Danbo Fu<danbo.fu@mediatek.com> | 0 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.508 | 8.1.3.1.1 | NB-IoT FDD Mode Test frequencies | Sub-clause header |  |  |  |  | TBD
10 | Y | 36.508 | 8.1.3.1.1.255 | NB-IoT FDD reference test frequencies for operating band 255 | Update FDD Mode Test frequencies for operating band 255 for Rel-18 NB-IoT core & performance requirements for NTN | CMCC | RAN5#99 (May-23) | R5-232011 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
11 | Y | 36.508 | 8.1.3.1.1.256 | NB-IoT FDD reference test frequencies for operating band 256 | Update FDD Mode Test frequencies for operating band 256 for Rel-18 NB-IoT core & performance requirements for NTN | CMCC | RAN5#99 (May-23) | R5-232011 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
12 |  | 36.508 | 8.2 | NB-IoT Test environment for RF test | Update Test environment parameters for NB-IoT NTN RF testing |  | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  | 0%
13 |  | 36.508 | 8.3.2.3 | NB-IoT Default test frequencies | Update the general wording for default test frequencies for NB-IoT NTN SIG testing | CMCC | RAN5#99 (May-23) | R5-231562 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
14 |  | 36.508 | 8.3.2.3.1 | NB-IoT FDD Mode Test frequencies for signalling test | Update test frequencies for NB-IoT NTN SIG testing | CMCC | RAN5#99 (May-23) | R5-231562 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
15 |  | 36.508 | 8.4 | NB-IoT Test environment for RRM tests | Update Test environment parameters for NB-IoT NTN RRM testing |  | RAN5#99 (May-23) |  |  | 0.5 | 0% | 0% |  | 0%
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.509 | <Clause> | TBD | TBD |  |  |  |  | 0
LTE RF/RRM
TS 36.521-4: RF test cases - Common parts (general clauses, Annexes)
|  | 36.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 |  | 36.521-4 |  | Foreword | Add Foreword for TS 36.521-4 | CMCC | RAN5#99 (May-23) | R5-230406 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
17 |  | 36.521-4 |  | Introduction | Add Introduction for TS 36.521-4 | CMCC | RAN5#99 (May-23) | R5-230406 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
18 |  | 36.521-4 | 1 | Scope | Add Scope for TS 36.521-4 | CMCC | RAN5#99 (May-23) | R5-230407 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
19 |  | 36.521-4 | 2 | References | Add References for TS 36.521-4 | CMCC | RAN5#99 (May-23) | R5-230407 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
20 |  | 36.521-4 | 3 | Definitions, symbols and abbreviations | Add Definitions, symbols and abbreviations for TS 36.521-4 | CMCC | RAN5#99 (May-23) | R5-230407 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
21 |  | 36.521-4 | 4 | General | Add General for TS 36.521-4 | CMCC | RAN5#99 (May-23) | R5-230408 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.521-4 | 5 | Operating bands and channel arrangement | New clause header |  |  |  |  | TBD
22 |  | 36.521-4 | 5.1 | General |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
23 |  | 36.521-4 | 5.2 | Operating bands |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
24 |  | 36.521-4 | 5.2A | Operating bands for UE category M1 |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
25 |  | 36.521-4 | 5.2B | Operating bands for category NB1 and NB2 |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.521-4 | 5.3 | Channel bandwidth | New clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
26 |  | 36.521-4 | 5.3A | Channel bandwidth for category M1 |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
27 |  | 36.521-4 | 5.3B | Channel bandwidth for category NB1 and NB2 |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.521-4 | 5.4 | Channel arrangement | New clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
28 |  | 36.521-4 | 5.4A | Channel arrangement for category M1 |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
29 |  | 36.521-4 | 5.4B | Channel arrangement for category NB1 and NB2 |  | CMCC | RAN5#99 (May-23) | R5-230409 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-4: RF test cases - Tx
|  | 36.521-4 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 36.521-4 | 6 | Transmitter characteristics | New clause header |  |  |  |  | TBD
30 |  | 36.521-4 | 6.1 | General |  | Mediatek | RAN5#99 (May-23) | R5-231868 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.521-4 | 6.2 | Transmit power | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
|  | 36.521-4 | 6.2A | Transmit power for category M1 | New Sub-clause header |  |  |  |  | TBD
31 | Y | 36.521-4 | 6.2A.1 | UE maximum output power for category M1 |  | Mediatek | RAN5#99 (May-23) | R5-231868 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
32 | Y | 36.521-4 | 6.2A.2 | UE maximum output power reduction for category M1 |  | Mediatek | RAN5#99 (May-23) | R5-231868 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
33 | Y | 36.521-4 | 6.2A.3 | UE additional maximum output power reduction for category M1 UE |  | Mediatek | RAN5#99 (May-23) | R5-231868 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
34 | Y | 36.521-4 | 6.2A.4 | Configured transmitted Power for category M1 |  | Mediatek | RAN5#99 (May-23) | R5-231868 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 36.521-4 | 6.2B | Transmit power for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
35 | Y | 36.521-4 | 6.2B.1 | UE maximum output power for category NB1 and NB2 |  | Mediatek | RAN5#99 (May-23) | R5-231869 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
36 | Y | 36.521-4 | 6.2B.2 | UE maximum output power reduction for category NB1 and NB2 |  | Mediatek | RAN5#99 (May-23) | R5-231869 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
37 | Y | 36.521-4 | 6.2B.3 | UE additional maximum output power reduction for category NB1 and NB2 UE |  | Mediatek | RAN5#99 (May-23) | R5-231869 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
38 | Y | 36.521-4 | 6.2B.4 | Configured transmitted Power for category NB1 and NB2 |  | Mediatek | RAN5#99 (May-23) | R5-231869 | Danbo Fu<danbo.fu@mediatek.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.521-4 | 6.3 | Output power dynamics | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
|  | 36.521-4 | 6.3A | Output power dynamics for category M1 | New Sub-clause header |  |  |  |  | TBD
39 | Y | 36.521-4 Tx | 6.3A.1 | UE Minimum output power for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
40 | Y | 36.521-4 Tx | 6.3A.2 | Transmit OFF power for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.3A.3 | ON/OFF time mask for category M1 | New Sub-clause header |  |  |  |  | TBD
41 | Y | 36.521-4 Tx | 6.3A.3.1 | General ON/OFF time mask for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.3A.3.2 | PRACH and SRS time mask for category M1 | New Sub-clause header |  |  |  |  | TBD
42 | Y | 36.521-4 Tx | 6.3A.3.2.1 | PRACH time mask for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
43 | Y | 36.521-4 Tx | 6.3A.3.2.2 | SRS time mask for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.3A.4 | Power control for category M1 | New Sub-clause header |  |  |  |  | TBD
44 | Y | 36.521-4 Tx | 6.3A.4.1 | Power Control Absolute power tolerance for UE category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
45 | Y | 36.521-4 Tx | 6.3A.4.2 | Power Control Relative power tolerance for UE category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
46 | Y | 36.521-4 Tx | 6.3A.4.3 | Aggregate power control tolerance for UE category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.3B | Output power dynamics for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
47 | Y | 36.521-4 Tx | 6.3B.1 | UE Minimum output power for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
48 | Y | 36.521-4 Tx | 6.3B.2 | Transmit OFF power for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.3B.3 | ON/OFF time mask for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
49 | Y | 36.521-4 Tx | 6.3B.3.1 | General ON/OFF time mask for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
50 | Y | 36.521-4 Tx | 6.3B.3.2 | NPRACH time mask for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.3B.4 | Power Control for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
51 | Y | 36.521-4 Tx | 6.3B.4.1 | Power Control Absolute power tolerance for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
52 | Y | 36.521-4 Tx | 6.3B.4.2 | Power Control Relative power tolerance for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
53 | Y | 36.521-4 Tx | 6.3B.4.3 | Aggregate power control tolerance for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.4 | Transmit signal quality | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
|  | 36.521-4 | 6.4A | Transmit signal quality for category M1 | New Sub-clause header |  |  |  |  | TBD
54 | Y | 36.521-4 Tx | 6.4A.1 | Frequency error for UE category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.4A.2 | Transmit modulation quality for category M1 | New Sub-clause header |  |  |  |  | TBD
55 | Y | 36.521-4 Tx | 6.4A.2.1 | Error Vector Magnitude (EVM) for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
56 | Y | 36.521-4 Tx | 6.4A.2.2 | Carrier leakage for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
57 | Y | 36.521-4 Tx | 6.4A.2.3 | In-band emissions for non allocated RB for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
58 | Y | 36.521-4 Tx | 6.4A.2.4 | EVM equalizer spectrum flatness for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.4B | Transmit signal quality for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
59 | Y | 36.521-4 Tx | 6.4B.1 | Frequency error for UE category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.4B.2 | Transmit modulation quality for Category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
60 | Y | 36.521-4 Tx | 6.4B.2.1 | Error Vector Magnitude (EVM) for Category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
61 | Y | 36.521-4 Tx | 6.4B.2.2 | Carrier leakage for Category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
62 | Y | 36.521-4 Tx | 6.4B.2.3 | In-band emissions for Category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
63 | Y | 36.521-4 Tx | 6.4B.2.4 | EVM equalizer spectrum flatness for Category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
64 |  | 36.521-4 Tx | 6.5 | Output RF spectrum emissions | Add general descriptions for UE output RF spectrum emissions | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5A | Output RF spectrum emissions for category M1 | New Sub-clause header |  |  |  |  | TBD
65 |  | 36.521-4 Tx | 6.5A.1 | General | Add general descriptions for UE output RF spectrum emissions for category M1 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
66 | Y | 36.521-4 Tx | 6.5A.2 | Occupied bandwidth for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5A.3 | Out of band emission for category M1 | New Sub-clause header |  |  |  |  | TBD
67 |  | 36.521-4 Tx | 6.5A.3.1 | General | Add general descriptions for UE out of band emission for category M1 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
68 | Y | 36.521-4 Tx | 6.5A.3.2 | Spectrum emission mask |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
69 | Y | 36.521-4 Tx | 6.5A.3.3 | Additional Spectrum Emission Mask for category M1 |  |  | RAN5#100 (Aug-23) |  | The additional spectrum emission mask is not applicable. | 1 | 0% | 0% |  | 0%
70 | Y | 36.521-4 Tx | 6.5A.3.4 | Adjacent Channel Leakage Ratio for category M1 |  | Mediatek | RAN5#99 (May-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5A.4 | Spurious emission for category M1 | New Sub-clause header |  |  |  |  | TBD
71 |  | 36.521-4 Tx | 6.5A.4.1 | General | Add general descriptions for UE spurious emission for category M1 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
72 |  | 36.521-4 Tx | 6.5A.4.2 | Minimum requirements |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
73 | Y | 36.521-4 Tx | 6.5A.4.3 | Spurious emission band UE co-existence |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 Tx | 6.5A.4.4 | Additional spurious emissions | New Sub-clause header |  |  |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5A.4.4.0 | Minimum conformance requirements | New Sub-clause header. |  |  |  |  | TBD
74 |  | 36.521-4 Tx | 6.5A.4.4.0.1 | General | Add general descriptions for UE additional spurious emission for category M1 as per sub-clause 6.5A.4.4.1 in TS 36.102 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
75 |  | 36.521-4 Tx | 6.5A.4.4.0.2 | Minimum requirement (network signalled value "NS_02N") | Add Minimum requirement (network signalled value "NS_02N") for category M1 as per sub-clause 6.5A.4.4.2 in TS 36.102 | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
76 |  | 36.521-4 Tx | 6.5A.4.4.0.3 | Minimum requirement (network signalled value "NS_24") | Add Minimum requirement (network signalled value "NS_24") for category M1 as per sub-clause 6.5A.4.4.3 in TS 36.102 | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
77 | Y | 36.521-4 Tx | 6.5A.4.4.1 | Additional spurious emissions for category M1 |  | Mediatek | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5B | Output RF spectrum emissions for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
78 |  | 36.521-4 Tx | 6.5B.1 | General | Add general descriptions for UE Output RF spectrum emissions for category NB1 and NB2 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
79 | Y | 36.521-4 Tx | 6.5B.2 | Occupied bandwidth for category NB1 and NB2 |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5B.3 | Out of band emission for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
80 |  | 36.521-4 Tx | 6.5B.3.1 | General | Add general descriptions for UE Out of band emission for category NB1 and NB2 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
81 | Y | 36.521-4 Tx | 6.5B.3.2 | Spectrum emission mask |  | Mediatek | RAN5#99 (May-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
82 | Y | 36.521-4 Tx | 6.5B.3.3 | Additional Spectrum Emission Mask for category NB1 and NB2 |  | TBD |  |  | The additional spectrum emission mask for category NB1 and NB2 is not applicable. | 0 | 0% | 0% |  | 0%
83 | Y | 36.521-4 Tx | 6.5B.3.4 | Adjacent Channel Leakage Ratio for category NB1 and NB2 |  | Mediatek | RAN5#99 (May-23) |  | Danbo Fu<danbo.fu@mediatek.com> | TBD
|  | 36.521-4 | 6.5B.4 | Spurious emission for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
84 |  | 36.521-4 Tx | 6.5B.4.1 | General | Add general descriptions for UE Spurious emission for category NB1 and NB2 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
85 |  | 36.521-4 Tx | 6.5B.4.2 | Minimum requirements |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
86 | Y | 36.521-4 Tx | 6.5B.4.3 | Spurious emission band UE co-existence |  | Mediatek | RAN5#100 (Aug-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 Tx | 6.5B.4.4 | Additional spurious emissions | New Sub-clause header |  |  |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.5B.4.4.0 | Minimum conformance requirements | New Sub-clause header. |  |  |  |  | TBD
87 |  | 36.521-4 Tx | 6.5B.4.4.0.1 | General | Add general descriptions for UE Additional spurious emissions for category NB1 and NB2 as per sub-clause 6.5B.4.4.1 in TS 36.102 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
88 |  | 36.521-4 Tx | 6.5B.4.4.0.2 | Minimum requirement (network signalled value "NS_02N") | Add Minimum requirement (network signalled value "NS_02N") for category NB1 and NB2 as per sub-clause 6.5B.4.4.2 in TS 36.102 | Mediatek | RAN5#99 (May-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
89 |  | 36.521-4 Tx | 6.5B.4.4.0.3 | Minimum requirement (network signalled value "NS_24") | Add Minimum requirement (network signalled value "NS_24") for category NB1 and NB2 as per sub-clause 6.5B.4.4.3 in TS 36.102 | Mediatek | RAN5#99 (May-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
90 | Y | 36.521-4 Tx | 6.5B.4.4.1 | Additional spurious emissions for category NB1 and NB2 |  | Mediatek | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-4 | 6.6 | Transmit intermodulation | New Sub-clause header. "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
91 | Y | 36.521-4 Tx | 6.6A | Transmit intermodulation for category M1 |  |  | TBD |  | For category M1 UE, Tx intermodulation requirements are not applicable. | 1 | 0% | 0% |  | 0%
92 | Y | 36.521-4 Tx | 6.6B | Transmit intermodulation for category NB1 and NB2 |  | Mediatek | RAN5#99 (May-23) |  | Danbo Fu<danbo.fu@mediatek.com> | 1 | 0% | 0% |  | 0%
TS 36.521-4: RF test cases - Rx
|  | 36.521-4 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 36.521-4 Rx | 7 | Receiver characteristics | New clause header |  |  |  |  | TBD
93 |  | 36.521-4 Rx | 7.1 | General | Add general descriptions for Receiver characteristics | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
94 |  | 36.521-4 Rx | 7.2 | Diversity characteristics | Add general descriptions for Diversity characteristics | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 36.521-4 Rx | 7.3 | Reference sensitivity power level | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
95 | Y | 36.521-4 Rx | 7.3A | Reference sensitivity power level for UE category M1 | [5 empty] | 1 | 0% | 0% |  | 0%
96 | Y | 36.521-4 Rx | 7.3B | Reference sensitivity power level for UE category NB1 and NB2 | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 36.521-4 Rx | 7.4 | Maximum input level | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
97 | Y | 36.521-4 Rx | 7.4A | Maximum input level for category M1 |  | Sporton | RAN5#99 (May-23) | R5-231824 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
98 | Y | 36.521-4 Rx | 7.4B | Maximum input level for category NB1 and NB2 |  | Sporton | RAN5#99 (May-23) | R5-231825 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 36.521-4 Rx | 7.5 | Adjacent Channel Selectivity (ACS) | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
99 | Y | 36.521-4 Rx | 7.5A | Adjacent Channel Selectivity for category M1 |  | Sporton | RAN5#99 (May-23) | R5-231826 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
100 | Y | 36.521-4 Rx | 7.5B | Adjacent Channel Selectivity for category NB1 and NB2 |  | Sporton | RAN5#99 (May-23) | R5-231827 | Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 36.521-4 Rx | 7.6 | Blocking characteristics | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
|  | 36.521-4 Rx | 7.6A | Blocking characteristics for category M1 | New Sub-clause header |  |  |  |  | TBD
101 |  | 36.521-4 Rx | 7.6A.1 | General | Add general descriptions for UE Blocking characteristics for category M1 as per sub-clause 7.6A.1 in TS 36.102 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
102 | Y | 36.521-4 Rx | 7.6A.2 | In-band blocking for category M1 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
103 | Y | 36.521-4 Rx | 7.6A.3 | Out-of-band blocking for category M1 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
104 | Y | 36.521-4 Rx | 7.6A.4 | Narrow band blocking for category M1 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 Rx | 7.6B | Blocking characteristics for category NB1 and NB2 | New Sub-clause header |  |  |  |  | TBD
105 |  | 36.521-4 Rx | 7.6B.1 | General | Add general descriptions for UE Blocking characteristics for category NB1 and NB2 as per sub-clause 7.6B.1 in TS 36.102 | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
106 | Y | 36.521-4 Rx | 7.6B.2 | In-band blocking for category NB1 and NB2 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
107 | Y | 36.521-4 Rx | 7.6B.3 | Out-of-band blocking for category NB1 and NB2 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
108 | Y | 36.521-4 Rx | 7.6B.4 | Narrow band blocking for category NB1 and NB2 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
|  | 36.521-4 Rx | 7.7 | Spurious response | New Sub-clause header "This clause is reserved." as indicated in TS 36.102 v0.3.0 |  |  |  |  | TBD
109 | Y | 36.521-4 Rx | 7.7A | Spurious response for category M1 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
110 | Y | 36.521-4 Rx | 7.7B | Spurious response for category NB1 and NB2 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
111 |  | 36.521-4 Rx | 7.8 | Intermodulation characteristics | Add general descriptions for Intermodulation characteristics | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
112 | Y | 36.521-4 Rx | 7.8A | Wideband intermodulation for category M1 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
113 | Y | 36.521-4 Rx | 7.8B | Wideband intermodulation for category NB1 and NB2 |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
114 | Y | 36.521-4 Rx | 7.9 | Spurious emissions |  | CAICT | RAN5#99 (May-23) |  | CAICT 张玉凤<zhangyufeng@caict.ac.cn> | 1 | 0% | 0% |  | 0%
TS 36.521-4: Demod/CSI reporting test cases
|  | 36.521-4 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-4 Demod | 8 | Performance requirement | New Clause header | Mediatek | RAN5#101 (Nov-23) |  | allen.zhang@mediatek.com | TBD
TBD |  | 36.521-4 Demod | <Clause> | <Title of new sub-clause header> | New sub-clause header | Mediatek | RAN5#101 (Nov-23) |  | allen.zhang@mediatek.com | TBD
TBD |  | 36.521-4 Demod | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> | Mediatek | RAN5#101 (Nov-23) |  | allen.zhang@mediatek.com | TBD
TBD | Y | 36.521-4 Demod | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> | Mediatek | RAN5#101 (Nov-23) |  | allen.zhang@mediatek.com | TBD
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
115 |  | 36.521-2 | 1 | Scope | Extend the scope to include the test cases described in TS 36.521-4 also. | CMCC | RAN5#99 (May-23) | R5-230398 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
116 |  | 36.521-2 | 2 | References | Add TS 36.521-4. | CMCC | RAN5#99 (May-23) | R5-230398 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
117 |  | 36.521-2 | Annex A | ICS proforma for E-UTRA User Equipment | Add ICS for RF/RRM/Demod test cases impacted by Rel-18 NB-IoT/eMTC core & performance requirements for NTN |  |  |  |  | 0.1 | 0% | 0% |  | 0%
118 |  | 36.521-2 | 4.1 | RF conformance test cases | Add test applicability for RF/Demod test cases impacted by Rel-18 NB-IoT/eMTC core & performance requirements for NTN |  |  |  |  | 0.1 | 0% | 0% |  | 0%
119 |  | 36.521-2 | 4.2 | RRM conformance test cases | Add test applicability for RRM test cases impacted by Rel-18 NB-IoT/eMTC core & performance requirements for NTN |  |  |  |  | 0.1 | 0% | 0% |  | 0%
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
120 |  | 36.521-3 | 3.3 | Abbreviations | Add abbreviation for "NTN" , "SAB", "SAN" as per R4-2220412 | CMCC | RAN5#99 (May-23) | R5-230399 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
121 | Y | 36.521-3 | 3.5.1A | Groups of bands for satellite access | Add groups of bands for satellite access | CMCC | RAN5#99 (May-23) | R5-230400 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 36.521-3 | 3A | Requirements for support of RRM | Clause header |  |  |  |  | TBD
|  | 36.521-3 | 3A.3 | RRM Test Configurations | Sub-clause header |  |  |  |  | TBD
123 | Y | 36.521-3 | 3A.3.8 (TBD) | Test configuration for NB-IoT/eMTC test cases | Add test configuration for NB-IoT/eMTC RRM testing |  | RAN5#101 (Nov-23) |  |  | 0.5 | 0% | 0% |  | 0%
|  | 36.521-3 | 4 | E-UTRAN RRC_IDLE State Mobility | Clause header |  |  |  |  | TBD
TBD |  | 36.521-3 | TBD | TBD | TBD |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-3 | 5 | E-UTRAN RRC_CONNECTED State Mobility | Clause header |  |  |  |  | TBD
TBD |  | 36.521-3 | TBD | TBD | TBD |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-3 | 6 | RRC Connection Mobility Control | Clause header |  |  |  |  | TBD
TBD |  | 36.521-3 | TBD | TBD | TBD |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-3 | 7 | Timing and Signalling Characteristic | Clause header |  |  |  |  | TBD
TBD |  | 36.521-3 | TBD | TBD | TBD |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 36.521-3 | 8 | UE Measurements Procedures | Clause header |  |  |  |  | TBD
TBD |  | 36.521-3 | TBD | TBD | TBD |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
124 |  | 36.903 | 5 | Grouping of test cases defined in TS 36.521-3 | Update grouping of RRM test cases for Rel-18 NB-IoT/eMTC NTN defined in TS 36.521-3. |  | RAN5#101 (Nov-23) |  |  | 0.5 | 0% | 0% |  | 0%
125 |  | 36.903 | 7 | Determination of Test Tolerances | Add the zip files into the attachments. The RRM test cases which have been analysed to determine Test Tolerances are included as .zip files. The name of the zip file indicates the test cases covered in TS 36.521-3. |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TR 36.904: Test Tolerances analysis receiver test cases
|  | 36.904 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
126 |  | 36.904 | 1 | Scope | Extend the scope of TR 36.905 to include the test cases described in TS 36.521-4 also. | CMCC | RAN5#99 (May-23) | R5-230401 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
127 |  | 36.904 | 2 | References | Add TS 36.521-4. | CMCC | RAN5#99 (May-23) | R5-230401 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
128 | Y | 36.904 | 5A | Grouping of test cases defined in TS 36.521-4 | Add grouping of RF test cases for Rel-18 NB-IoT/eMTC NTN defined in TS 36.521-4 |  | RAN5#101 (Nov-23) | R5-230402 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.5 | 20% (+20%) | 20% (+20%) |  | 20%
129 |  | 36.904 | 7 | Determination of Test Tolerances | Add the zip files into the attachments. The RF test cases which have been analysed to determine Test Tolerances are included as .zip files. The name of the zip file indicates the test cases covered in TS 36.521-4. |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TR 36.905: Test Point analysis receiver and transmitter test cases
|  | 36.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
130 |  | 36.905 | 1 | Scope | Extend the scope of TR 36.905 to include the test cases described in TS 36.521-4 also. | CMCC | RAN5#99 (May-23) | R5-230403 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
131 |  | 36.905 | 2 | References | Add TS 36.521-4. | CMCC | RAN5#99 (May-23) | R5-230403 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
132 | Y | 36.905 | 4.5 (TBD) | Test point analysis for test cases in TS 36.521-4 | Test point analysis for test cases in TS 36.521-4, and documented as .zip files. | CMCC | RAN5#99 (May-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 1 | 0% | 0% |  | 0%
LTE RAN and CN protocols
TS 36.523-2: Applicability for Protocol test cases
133 |  | 36.523-2 | 2 | References | Add TS 36.521-4. | CMCC | RAN5#99 (May-23) |  | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> No need to add TS 36.521-4 since TS 36.521-4 will not be referenced in TS 36.523-2. | 0 | 0% | 0% |  | 0%
134 |  | 36.523-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Add NTN frequency bands into “RF Baseline Implementation Capabilities” Table A.4.3.1-1 for SIG test cases impacted by Rel-18 NB-IoT/eMTC core & performance requirements for NTN | CMCC | RAN5#99 (May-23) | R5-231563 | CMCC 赵鲁阳<zhaoluyang@chinamobile.com> | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | Assess and update of the test case execution guidelines for new NTN frequency bands |  | RAN5#101 (Nov-23) |  |  | TBD | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.