## Cover sheet
3GPP TSG-RAN5 Meeting #98 | [8 empty] | R5-231104
Athens,Greece, 27th Feb – 3rd Mar. 2023
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon, China Unicom
Title: | UE Conformance - Additional NR bands for UL-MIMO in Rel-17
Work item code: | NR_bands_UL_MIMO_PC3_R17-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define corresponding UE conformance requirements for PU3 UE for SUL bands, and PC3, PC2 and PC1.5 UE for NR bands with UL MIMO configuration in FR1 covered in RAN4 work item in Rel-17
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 73% (+25%) | 23 (+9) | 33 (-1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 73% (+25.5%) | 23 (+9) | 33 (-1)
FR1 |  | 73% (+25.5%) | 23 (+9) | 33 (-1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 40% (+3.3%) |  |  | 40% (+3.3%)
FR1 RF Tx test cases | 38.521-1 Tx | 62.8% (+42.1%) | 14 (+9) | 24 (-1) | 62.8% (+42.1%) | 14 (+9) | 24 (-1)
FR1 RF Rx test cases | 38.521-1 Rx | 100% | 9 | 9 | 100% | 9 | 9
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 75% |  |  | 75%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-213227 | New WID on UE Conformance - Additional NR bands for UL-MIMO in Rel-17
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Additional NR bands for UL-MIMO in Rel-17 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_bands_UL_MIMO_PC3_R17-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Additional NR bands for UL-MIMO in Rel-17 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Yuxin Hao |  |  | haoyuxin@huawei.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | - |  |  | -
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
73% (+25.5%)
45 (-1)
44.5 (-1.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
NR RF/RRM
TS 38.508-1: Common test environment
1 |  | 38.508-1 | A.3.1 | Test Equipment Parts for Conducted Measurements | Adding TE connection diagram for SUL with MIMO configuration | Huawei | RAN5#96 (Aug-22) | R5-225092 |  | 1 | 100% | 100% |  | 100%
2 |  | 38.508-1 | A.3.2 | User Equipment Parts for Conducted Measurements | Adding UE connection diagram for SUL with MIMO configuration | Huawei | RAN5#96 (Aug-22) | R5-225092 |  | 1 | 100% | 100% |  | 100%
TS 38.508-2: PICS
|  | 38.508-2 | A.4.3 | Baseline Implementation Capabilities | Adding SUL bands into table 4.3.9-12 | Huawei | RAN5#97 (Nov-22) | R5-226847 |  | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
3 |  | 38.521-1 | 5.2D | Operating bands for UL MIMO | Adding NR bands n84 n95 n97 n98 n24 n99 n77 n78 into table 5.2D-1 | Chinatelecom | RAN5#96 (Aug-22) | R5-220349 |  | 1 | 100% | 100% |  | 100%
47 |  | 38.521-1 | 4.3 | Specification suffix information | Updaitng clause content to align with core specification |  | RAN5#100 (Aug-23) | R5-231080 |  | 0.5 | 0% | 0% |  | 0%
36 |  | 38.521-1 | Annex.F.1.2 | Measurement of transmitter | Adding MU for newly added TCs |  | RAN5#101 (Nov-23) | R5-225091 R5-226937 R5-231090 |  | 1 | 20% (+15%) | 20% (+15%) |  | 20%
37 |  | 38.521-1 | Annex.F.3.2 | Measurement of transmitter | Adding TT for newly added TCs |  | RAN5#101 (Nov-23) | R5-225091 R5-226937 R5-231090 |  | 1 | 20% (+15%) | 20% (+15%) |  | 20%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx | 6.2D | Transmitter power for UL MIMO | [5 empty] | 0
8 |  | 38.521-1 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Updating minimum requirement for band n84 n95(PC3,PC2) n97(PC3,PC2) n98(PC3,PC2) n24 n99 n77(PC 1.5) n78(PC 1.5) Updating TC for n77(PC 1.5) n78(PC 1.5) | Huawei | RAN5#96 (Aug-22) | R5-223770 R5-231081 | PC1.5 done in R5-223770 for n77 n78 | 1 | 100% (+75%) | 100% (+75%) |  | 100%
5 | Y | 38.521-1 Tx | 6.2D.1_1 | UE maximum output power for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-227759 |  | 1 | 100% | 100% |  | 100%
33 |  | 38.521-1 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Udating TC for n24, n77(PC 1.5) n78(PC 1.5) | Google | RAN5#96 (Aug-22) | R5-225754 R5-231082 | PC1.5 done in R5-225754 for n77 n78 | 1 | 100% (+25%) | 100% (+25%) |  | 100%
6 | Y | 38.521-1 Tx | 6.2D.2_1 | UE maximum output power reduction for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Chinatelecom | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
34 |  | 38.521-1 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating TC for n24(NS_56) | Huawei | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0%
7 | Y | 38.521-1 Tx | 6.2D.3_1 | UE additional maximum output power reduction for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for n84 (NS_05/05U) n99(NS_56 ) | Chinatelecom | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
4 | Y | 38.521-1 Tx | 6.2D.4_1 | Configured transmitted power for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226849 |  | 1 | 100% | 100% |  | 100%
|  | 38.521-2 Tx | 6.3D | Output power dynamics for UL MIMO | [5 empty] | 0
9 | Y | 38.521-1 Tx | 6.3D.1_1 | Minimum output power for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-226850 |  | 1 | 100% | 100% |  | 100%
10 | Y | 38.521-1 Tx | 6.3D.2_1 | Transmit OFF power for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-226851 |  | 1 | 100% | 100% |  | 100%
11 | Y | 38.521-1 Tx | 6.3D.3_1 | Transmit ON/OFF time mask for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-227931 |  | 1 | 100% | 100% |  | 100%
12 | Y | 38.521-1 Tx | 6.3D.4.1_1 | Absolute power tolerance for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231083 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
13 | Y | 38.521-1 Tx | 6.3D.4.2_1 | Relative power tolerance for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231650 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
14 | Y | 38.521-1 Tx | 6.3D.4.3_1 | Aggregate power tolerance for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231085 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.4D | Transmit signal quality for UL MIMO | [5 empty] | 0
15 | Y | 38.521-1 Tx | 6.4D.1_1 | Frequency error for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231087 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
16 | Y | 38.521-1 Tx | 6.4D.2.1_1 | Error Vector Magnitude for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231651 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
17 | Y | 38.521-1 Tx | 6.4D.2.2_1 | Carrier leakage for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Chinatelecom | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
18 | Y | 38.521-1 Tx | 6.4D.2.3_1 | In-band emissions for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
19 | Y | 38.521-1 Tx | 6.4D.2.4_1 | EVM equalizer spectrum flatness for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231097 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
38 | Y | 38.521-1 Tx | 6.4D.3_1 | Time alignment error for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231098 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.5D | Output RF spectrum emissions for UL MIMO | [5 empty] | 0
20 | Y | 38.521-1 Tx | 6.5D.1_2 | Occupied bandwidth for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231086 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
21 | Y | 38.521-1 Tx | 6.5D.2.2_1 | Spectrum emission mask for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231089 | TC MPR for SUL with UL MIMO is absent | 1 | 95% (+95%) | 95% (+95%) |  | 95%
22 | Y | 38.521-1 Tx | 6.5D.2.4.1_1 | NR ACLR for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Chinatelecom | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
23 | Y | 38.521-1 Tx | 6.5D.2.4.2_1 | UTRA ACLR for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for for n84 (NS_05/05U) |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.521-1 Tx | 6.5D.3_2 | Spurious emissions for SUL with UL MIMO
24 | Y | 38.521-1 Tx | 6.5D.3_2.1 | General spurious emissions for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
25 | Y | 38.521-1 Tx | 6.5D.3_2.2 | Spurious emission for UE co-existence for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-1 Tx | 6.5D.3_2.3 | Additional spurious emissions for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
27 | Y | 38.521-1 Tx | 6.5D.4_1 | Transmit intermodulation for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 |  | RAN5#99 (May-23) | R5-231099 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
28 | Y | 38.521-1 Rx | 7.3D.2_1 | Reference sensitivity power level for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226853 |  | 1 | 100% | 100% |  | 100%
29 | Y | 38.521-1 Rx | 7.3D.2_2 | Reference sensitivity power level for SUL with UL MIMO (3CC) | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226854 |  | 1 | 100% | 100% |  | 100%
40 | Y | 38.521-1 Rx | 7.4D_1 | Maximum input level for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226855 |  | 1 | 100% | 100% |  | 100%
41 | Y | 38.521-1 Rx | 7.5D_1 | Adjacent channel selectivity for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226856 |  | 1 | 100% | 100% |  | 100%
42 | Y | 38.521-1 Rx | 7.6D.2_1 | In-band blocking for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226857 R5-231807 |  | 1 | 100% | 100% |  | 100%
43 | Y | 38.521-1 Rx | 7.6D.3_1 | Out-of-band blocking for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226858 |  | 1 | 100% | 100% |  | 100%
44 | Y | 38.521-1 Rx | 7.6D.4_1 | Narrow band blocking for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226859 |  | 1 | 100% | 100% |  | 100%
45 | Y | 38.521-1 Rx | 7.7D_1 | Spurious response for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226860 |  | 1 | 100% | 100% |  | 100%
46 | Y | 38.521-1 Rx | 7.8D.2_1 | Wide band Intermodulation for SUL with UL MIMO | Adding a new test case for SUL with UL MIMO configuration for band n84 n95 n97 n98 n99 | Huawei | RAN5#99 (May-23) | R5-226861 R5-231807 |  | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
30 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new selection criteria |  | RAN5#99 (May-23) | R5-225755 |  | 1 | 100% | 100% |  | 100%
31 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding applicability for test cases in 38.521-1 |  | RAN5#99 (May-23) | R5-225755 R5-226936 R5-231091 R5-231658 |  | 1 | 50% | 50% |  | 50%
TR 38.905: Test Point analysis receiver and transmitter test cases
32 |  | 38.905 | 4.1.1.2 | FR1 SUL test cases | Adding test point selection criteria for SUL with UL MIMO configuration | Huawei | RAN5#101 (Nov-23) |  |  | 1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.