## R5#99
3GPP TSG RAN WG5 (RAN5) Meeting #99 | [9 empty] | R5-232034
Incheon, South Korea, 22 - 26 May 2023
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-232787 | 2023-06-01 | 42% | 42% | 2023-12-01 | +6 | CMCC
870061 | UE Conformance Test Aspects - RF requirements for NR frequency range 1 (FR1) | Rel-16 | R5-233115 | 2023-09-01 | 69% | 72% | 2023-09-01 |  | Huawei
880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | Rel-16 | R5-232512 | 2023-06-01 | 62% | 63% | 2023-12-01 | +6 | Huawei
890047 | UE Conformance Test Aspects - Cross Link Interference (CLI) handling for NR | Rel-16 | R5-232843 | 2023-06-01 | 43% | 67% | 2023-06-01 |  | Qualcomm | Plan to close the WI with reduced scope
900054 | UE Conformance Test Aspects - Physical Layer Enhancements for NR URLLC | Rel-16 | R5-233058 | 2023-12-01 | 92% | 97% | 2023-12-01 |  | Huawei
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-233109 | 2023-12-01 | 11% | 11% | 2023-12-01 |  | Huawei
900057 | UE Conformance Test Aspects - NR positioning support | Rel-16 | R5-232399 | 2023-06-01 | 89% | 94% | 2023-09-01 | +3 | CATT
910098 | UE Conformance Test Aspects - NR RF requirement enhancements for frequency range 2 (FR2) | Rel-16 | R5-232121 | 2023-06-01 | 94% | 98% | 2023-09-01 | +3 | Nokia
911000 | UE Conformance - High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band | Rel-17 | R5-232582 | 2023-06-01 | 55% | 100% | 2023-06-01 |  | China Unicom
911003 | UE Conformance Test Aspects - NR-based access to unlicensed spectrum | Rel-16 | R5-232845 | 2023-06-01 | 33% | 50% | 2023-12-01 | +6 | Qualcomm
911004 | UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | Rel-16 | R5-232902 | 2023-06-01 | 97% | 99% | 2023-06-01 |  | Nokia | TCD to be extended in RP version
920066 | UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) | Rel-17 | R5-232829 | 2023-12-01 | 25% | 35% | 2023-12-01 |  | China Telecom
930051 | UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) | Rel-17 | R5-232909 | 2023-12-01 | 6% | 6% | 2023-12-01 |  | Ericsson
930054 | UE Conformance - High power UE (power class 2) for NR band n39 | Rel-17 | R5-232800 | 2023-06-01 | 85% | 99% | 2023-09-01 | +3 | CMCC
940090 | UE Conformance - Additional NR bands for UL-MIMO in Rel-17 | Rel-17 | R5-233111 | 2023-06-01 | 73% | 100% | 2023-06-01 |  | Huawei
940092 | UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR | Rel-17 | R5-232728 | 2023-06-01 | 95% | 99% | 2023-09-01 | +3 | Huawei
950060 | UE Conformance - Multi-SIM devices for LTE/NR | Rel-17 | R5-232304 | 2023-09-01 | 89% | 99% | 2023-09-01 |  | China Telecom
950061 | UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects | Rel-17 | R5-232935 | 2023-06-01 | 51% | 77% | 2023-12-01 | +6 | Huawei
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-233113 | 2023-12-01 | 19% | 24% | 2023-12-01 |  | Huawei
950063 | UE Conformance - NR coverage enhancements | Rel-17 | R5-232828 | 2023-06-01 | 13% | 83% | 2023-12-01 | +6 | China Telecom
950064 | UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) | Rel-17 | R5-232779 | 2023-06-01 | 31% | 56% | 2023-12-01 | +6 | CMCC
950065 | UE Conformance - Enhancement of Network Slicing Phase 2 | Rel-17 | R5-232775 | 2023-06-01 | 87% | 100% | 2023-06-01 |  | CMCC
950066 | UE Conformance - Support of reduced capability NR devices | Rel-17 | R5-232584 | 2023-06-01 | 71% | 76% | 2023-12-01 | +6 | China Unicom
960072 | UE Conformance - NR small data transmissions in INACTIVE state | Rel-17 | R5-233197 | 2023-12-01 | 75% | 80% | 2023-12-01 |  | Qualcomm
960073 | UE Conformance - Introduction of DL 1024QAM for NR frequency range 1 | Rel-17 | R5-232850 | 2023-09-01 | 34% | 50% | 2023-09-01 |  | Qualcomm
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-232847 | 2023-12-01 | 24% | 40% | 2023-12-01 |  | Qualcomm
960075 | UE Conformance - Further enhancement on NR demodulation performance | Rel-17 | R5-232831 | 2023-12-01 | 5% | 30% | 2023-12-01 |  | China Telecom
960076 | UE Conformance - Enhancement of Private Network Support for NG-RAN including CT aspects | Rel-17 | R5-232423 | 2023-12-23 | 6% | 8.3% | 2023-12-23 |  | China Telecom
960077 | UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 | Rel-17 | R5-232807 | 2023-06-01 | 71% | 100% | 2023-06-01 |  | CMCC
960078 | UE Conformance - Enhancement of RAN slicing for NR | Rel-17 | R5-232782 | 2023-09-23 | 65% | 88% | 2023-09-23 |  | CMCC
960079 | UE Conformance - Further enhancements on MIMO for NR | Rel-17 | R5-232885 | 2023-12-23 | 10% | 31% | 2023-12-01 |  | Samsung
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-233497 | 2023-12-23 | 18% | 27% | 2023-12-23 |  | Samsung
960082 | UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication | Rel-17 | R5-232904 | 2023-06-01 | 71% | 80% | 2023-12-01 | +6 | Nokia
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-232407 | 2023-09-23 | 7% | 7% | 2023-09-23 |  | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-232405 | 2023-09-23 | 5% | 5% | 2023-09-23 |  | CATT
960085 | UE Conformance - NR Uplink Data Compression (UDC) | Rel-17 | R5-232403 | 2023-06-23 | 67% | 100% | 2023-06-23 |  | CATT
960086 | UE Conformance - UE power saving enhancements for NR | Rel-17 | R5-233277 | 2023-12-01 | 68% | 80% | 2023-12-01 |  | MediaTek
960087 | UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects | Rel-17 | R5-232565 | 2023-09-01 | 96% | 98% | 2023-09-01 |  | MediaTek
960088 | UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | Rel-17 | R5-233237 | 2023-12-01 | 16% | 28% | 2023-12-01 |  | Apple
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-233239 | 2023-12-01 | 12% | 13% | 2023-12-01 |  | Apple
960090 | UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) | Rel-17 | R5-233060 | 2023-12-01 | 20% | 20% | 2023-12-01 |  | Huawei
970070 | UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) | Rel-17 | R5-232123 | 2023-12-01 | 14% | 23% | 2023-12-01 |  | Nokia
970071 | UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR Ues | Rel-17 | R5-232696 | 2023-12-01 | 8% | 9% | 2023-12-01 |  | Apple
970072 | UE Conformance - NR QoE management and optimizations for diverse services | Rel-17 | R5-232256 | 2023-09-01 | 5% | 5% | 2024-03-01 | +6 | Ericsson
970074 | UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) | Rel-17 | R5-232225 | 2023-09-01 | 5% | 27% | 2023-09-01 |  | Vodafone
970075 | UE Conformance - NR Positioning Enhancements | Rel-17 | R5-232401 | 2024-06-01 | 7% | 11% | 2024-06-01 |  | CATT
970076 | UE Conformance - Access Traffic Steering, Switch and Splitting support in 5G system | Rel-17 | R5-232301 | 2023-12-01 | 55% | 100% | 2023-06-01 | -6 | China Telecom
970077 | Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) | Rel-16 | R5-232651 | 2024-09-01 | 8% | 19% | 2024-09-01 |  | NIST
981033 | UE Conformance - Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink | Rel-17 | R5-232833 | 2023-12-01 | 5% | 52% | 2023-12-01 |  | China Telecom
981034 | UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks | Rel-18 | R5-232813 | 2023-12-01 | 30% | 30% | 2023-12-01 |  | CMCC
981035 | UE Conformance - NR and MR-DC measurement gap enhancements | Rel-17 | R5-232563 | 2024-03-01 | 31% | 55% | 2024-03-01 |  | MediaTek
981036 | UE Conformance - Increasing UE power high limit for CA and DC | Rel-17 | R5-232157 | 2023-09-01 | 52.5% | 81% | 2023-09-01 |  | Qualcomm
991032 | UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz | Rel-18 | R5-232328 | 2023-09-01 |  | 83% | 2023-12-01 | +3 | Ligado Networks
991033 | UE Conformance - Further Multi-RAT Dual-Connectivity enhancement | Rel-17 | R5-232759 | 2024-03-01 |  | 5% | 2024-03-01 |  | Huawei
991034 | UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | Rel-17 | R5-233199 | 2024-12-01 |  | 6% | 2024-12-01 |  | Qualcomm