## Cover sheet
3GPP TSG-RAN WG5 Meeting #96-e | [10 empty] | R5-225051
Electronic Meeting, 15th Aug 2022 - 26th Aug 2022
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP - UE Conformance - Inter-system mobility between untrusted Non-3GPP and 3GPP system
Work item code: | TEI15_Test
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+100%) | 10.5 (+10.5) | 10.5 (+10.5)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+100%) | 7.5 (+7.5) | 7.5 (+7.5)
FR1 |  | 100% (+100%) | 7.5 (+7.5) | 7.5 (+7.5)
FR2 |  | 100% (+100%) | 7.5 (+7.5) | 7.5 (+7.5)
LTE |  | 100% (+100%) | 3 (+3) | 3 (+3)
FDD |  | 100% (+100%) | 3 (+3) | 3 (+3)
TDD |  | 100% (+100%) | 3 (+3) | 3 (+3)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 100% (+100%) | 2 (+2) | 2 (+2) | [7 empty] | 100% (+100%) | 2 (+2) | 2 (+2) | 100% (+100%) | 2 (+2) | 2 (+2)
Applicability Protocol test cases | 36.523-2 | 100% (+100%) | 1 (+1) | 1 (+1) | [7 empty] | 100% (+100%) | 1 (+1) | 1 (+1) | 100% (+100%) | 1 (+1) | 1 (+1)
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 100% (+100%) | 0.5 (+0.5) | 0.5 (+0.5) | 100% (+100%) | 0.5 (+0.5) | 0.5 (+0.5) | 100% (+100%) | 0.5 (+0.5) | 0.5 (+0.5)
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+100%) | 6 (+6) | 6 (+6) | 100% (+100%) | 6 (+6) | 6 (+6) | 100% (+100%) | 6 (+6) | 6 (+6)
Applicability Protocol test cases | 38.523-2 | 100% (+100%) | 1 (+1) | 1 (+1) | 100% (+100%) | 1 (+1) | 1 (+1) | 100% (+100%) | 1 (+1) | 1 (+1)
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Inter-system mobility between untrusted Non-3GPP and 3GPP system | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | TEI15_Test
WP Scope: |  | UE Conformance Test Aspects for Rel-15 Inter-system mobility between untrusted Non-3GPP and 3GPP system(UID=750034) | [13 empty] | vs Area
WP Resp: |  | Jin Gao，China Telecom |  |  | gaoj8@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | FDD | TDD
[15 empty] | 100% (+100%) | 100% (+100%) | 100% (+100%) | 100% (+100%)
[15 empty] | 9 (+9) | 9 (+9) | 4 (+4) | 4 (+4)
[15 empty] | 7.5 (+7.5) | 7.5 (+7.5) | 3 (+3) | 3 (+3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
NAS
|  | 36.523-1 | 13.6 | Inter-system mobility between untrusted Non-3GPP and 3GPP system
1 | Y | 36.523-1 | 13.6.1 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from E-UTRAN/EPC to ePDG/EPC | ****TP1: [TS 23.402: 8.2.3]**** WITH: the UE supports S1 mode, IP address preservation between EPC/ePDG and EUTRAN and at least one PDN connection have been established between the UE and the EPC via EUTRAN. WHEN: When UE detects EUTRAN becomes not suitable, UE performs a handover of existing PDN connections to ePDG/EPC. THEN: the UE shall indicates Handover Attach and included its IP address. | China Telecom | RAN5#97 (Nov-22) | 36.523-1： R5-227566 | gaoj8@chinatelecom.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
2 | Y | 36.523-1 | 13.6.2 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from ePDG/EPC to E-UTRAN/EPC | ****TP1: [TS 23.402: 8.2.1]**** WITH: the UE supports S1 mode, IP address preservation between EPC/ePDG and EUTRAN and at least one PDN connection have been established between the UE and the EPC via ePDG, UE is in EMM-DERIGESTERED status. WHEN: When UE detects WiFi becomes not suitable, UE performs a handover of existing PDN connections to EUTRAN. THEN: the UE shall indicates Handover Attach and include the corresponding APN. | China Telecom | RAN5#99 (Mar-23) | 36.523-1： R5-233316 | gaoj8@chinatelecom.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
TS 36.523-2: Applicability for Protocol test cases
|  | 36.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
3 | Y | 36.523-2 | 4 | <Title> | Add Applicability Conditions for new Inter-system mobility between untrusted Non-3GPP and 3GPP system test cases. | China Telecom | RAN5#99 (Mar-23) | 36.523-2： R5-227568 R5-232309 | gaoj8@chinatelecom.cn | 0.5 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
4 | Y | 36.523-2 | A.4 | <Title> | Add ICS for the new test cases introduced in 36.523-1. | China Telecom | RAN5#99 (Mar-23) | 36.523-2： R5-227568 R5-232309 | gaoj8@chinatelecom.cn | 0.5 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
5 |  | 36.523-3 | <Clause> | <Title of task> | <Describe task>
5GS
5GS Common
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
6 | Y | 38.508-2 | A4.3 | Introduction of common implementation conformance statements for Rel-15 Inter-system mobility between untrusted Non-3GPP and 3GPP system testing | Add PICS as needed for the test case applicability statements for the new test cases introduced with protocol test cases. | China Telecom，ZTE | RAN5#99 (Mar-23) | 38.508-2： R5-225370 R5-233357 | gaoj8@chinatelecom.cn， ma.wei4@zte.com.cn | 0.5 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
NAS
7 | Y | 38.523-1 | 11.8.1 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from NR to N3IWF/5GC | ****TP1: [TS 23.502: 4.9.2.2]**** WITH: the UE supports N1 mode and S1 mode, the UE supports IP address preservation between NR and N3IWF/5GS, at least one PDN Connections have been established between the UE and the N3IWF/5GC via untrusted non-3GPP, UE in state EMM-REGISTERED. WHEN: UE detects NR becomes not suitable and performs a handover of existing PDN connection from NR to N3IWF/5GC. THEN: UE requested PDU Session Establishment with Existing PDU Session indication in 5GC via Untrusted non-3GPP Access via N3IWF. | ZTE | RAN5#99 (Mar-23) | 38.508-1： R5-233355 | ma.wei4@zte.com.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
8 | Y | 38.523-1 | 11.8.2 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from N3IWF/5GC to NR / UE in 5GMM-DEREGISTERED states | ****TP1: [TS 23.502: 4.9.2.1]**** WITH: the UE supports N1 mode, the UE supports IP address preservation between N3IWF/5GC and NR, at least one PDN Connections have been established between the UE and the N3IWF/5GC via untrusted non-3GPP, UE is in state 5GMM-DEREGISTERED. WHEN: UE detects WiFi becomes not suitable, performs Registration procedure and handover of existing PDU session from N3IWF/5GC to NR. THEN: UE performs the PDU Session Establishment procedure with the PDU Session ID of the PDU Session to be transferred. | ZTE | RAN5#99 (Mar-23) | 38.508-1： R5-231418 | ma.wei4@zte.com.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
9 | Y | 38.523-1 | 11.8.3 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from E-UTRAN/EPC to N3IWF/5GC | ****TP1: [TS 23.502: 4.9.2.2]**** WITH: the UE supports N1 mode and S1 mode, the UE supports IP address preservation between EPC and N3IWF/5GS, at least one PDN Connections have been established between the UE and the EPC via E-UTRAN, UE in state EMM-REGISTERED. WHEN: UE detects E-UTRAN becomes not suitable and performs a handover of existing PDN connection from EPC/E-UTRAN to N3IWF/5GC. THEN: UE requested PDU Session Establishment with Existing PDU Session indication in 5GC via Untrusted non-3GPP Access via N3IWF. | ZTE | RAN5#99 (Mar-23) | 38.508-1： R5-233356 | ma.wei4@zte.com.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
10 | Y | 38.523-1 | 11.8.4 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from N3IWF/5GC to E-UTRAN/EPC | ****TP1: [TS 23.502: 4.9.2.1]**** WITH: the UE supports N1 mode and S1 mode, the UE supports IP address preservation between E-UTRAN/EPC and N3IWF/5GS, at least one PDU sessions have been established in 5GC via untrusted non-3GPP access and N3IWF, UE is in 5GMM-DEREGISTERED state and EMM-DEREGISTERED state. WHEN: UE detects WiFi becomes not suitable, attach to E-UTRAN and handover of existing PDU session from N3IWF/5GC to E-UTRAN/EPC. THEN:UE initiates Handover Attach procedure in E-UTRAN with "Handover" indication and PDN Connection establishment with "Handover" indication. | ZTE | RAN5#99 (Mar-23) | 38.508-1： R5-231419 | ma.wei4@zte.com.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
11 | Y | 38.523-1 | 11.8.5 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from 5GS to EPC/ePDG | ****TP1: [TS 24.302:7.2.2.1]**** WITH: the UE supports N1 mode and S1 mode and IP address preservation between EPC/ePDG and 5GS, at least one PDU Sessions have been established between the UE and the SMF/UPF via NG-RAN. WHEN: When UE detect cellular not available and performs a handover of existing PDU session to ePDG/EPC. THEN: the UE shall include the CFG_REQUEST Configuration payload containing the type of IP address, the "IDr" payload containing the APN in the Identification Data, the "IDi" payload containing the NAI, the N1_MODE_CAPABILITY Notify payload and provide an indication of Handover Attach within the IKE_AUTH request message. | China Telecom | RAN5#96 (Aug-22) | 38.523-1： R5-225412 | gaoj8@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
12 | Y | 38.523-1 | 11.8.6 | Inter-system mobility between untrusted Non-3GPP and 3GPP system/Handover from EPC/ePDG to 5GS/ UE in 5GMM-DEREGISTERED and EMM-DEREGISTERED states | ****TP1: [TS 23.502: 4.11.4.1]**** WITH: the UE supports N1 mode and S1 mode and supports IP address preservation between EPC/ePDG and 5GS, at least one PDN Connections have been established between the UE and the EPC/ePDG via untrusted non-3GPP, UE is in 5GMM-DEREGISTERED state and EMM-DEREGISTERED state. WHEN: UE detects WiFi becomes not suitable, performs Registration procedure and handover of existing PDU session from ePDG/EPC to 5GC. THEN:the UE includes the "Existing PDU Session" indication and the DNN, the PDU Session ID and S-NSSAI corresponding to the existing PDN connection it wants to transfer from EPC/ePDG to 5GS during the PDU session establishment. | China Telecom | RAN5#97 (Nov-22) | 38.523-1： R5-227576 | fuh2@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
|  | 38.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
13 | Y | 38.523-2 | 4.1 | <Title> | Add new ICS statements. | China Telecom，ZTE | RAN5#99 (Aug-22) | 38.523-2： R5-225452 R5-226476 R5-231401 R5-231420 | gaoj8@chinatelecom.cn， ma.wei4@zte.com.cn | 0.5 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
14 | Y | 38.523-2 | 4.2 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | China Telecom，ZTE | RAN5#99 (Aug-22) | 38.523-2： R5-225452 R5-226476 R5-231401 R5-231420 | gaoj8@chinatelecom.cn， ma.wei4@zte.com.cn | 0.5 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
15 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task>
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.