## WP scope
Work plan for introduction of NR SUL PC3 FR1 configurations into 3GPP UE conformance test specifications
| WP Template: | WP NR SUL PC3 FR1 v1.5.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP NR SUL PC3 FR1 v1.5.0 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | TBD | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
Overall completion
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version

## WP NR SUL PC3 FR1
Work plan for introduction of NR SUL PC3 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP Template: WP NR SUL PC3 FR1 v1.5.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New NR SUL configurations |  |  |  | SUL BCS0
|  | New NR CA SUL configurations |  |  |  | CA SUL BCS0
|  | New BCS for NR SUL configuration |  |  |  | SUL new BCS
|  | New BCS for NR CA SUL configuration |  |  |  | CA SUL new BCS
|  | All configurations |  |  |  | All
|  | All BCS0 configurations (No BCS included in config.name) |  |  |  | All BCS0
|  | All new BCS configurations with BCS>0 |  |  |  | All new BCS
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
Overall completeness
Step 1: Work plan pre-requisite
Step 2: Complete Test Point (TP) analysis for impacted SUL configurations
Step 3.1: CR(s) to common test environment (TS 38.508-1)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Bands completed | TCs available | BSC0 completed | Impacted CBWs identified | Bands new CBWs completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All BCS0 | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands completed for BCS0 |  | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in RAN5 PRD21 worksheet "NR bands". |  | TBD |  |  | 1 |  |  | 0%
All new BCS | 1-1a | Pre-requisite | PRD21 | NR bands worksheet | All NR bands completed for new BCS |  | Set status in column "Bands new CBWs completed" to 100% when all channel bandwidths of the involved NR bands for the new BCS of the configuration have been confirmed completed in RAN5 PRD21 worksheet "NR bands". |  | TBD |  |  | 1 | [6 empty] | 0%
All new BCS | 1-2 | Pre-requisite | 38.101-1 | 5.5A.1 | BCS0 completed for the SUL configuration |  | Set status in column "BCS0 completed" to 100% when the BCS0 of all the new BSC configurations have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC configurations". BSC0 configuration is listed in PRD21 as SUL configuration without "BSC" suffix in the name. |  | TBD |  |  | 1 |  |  |  |  | 0%
All new BCS | 1-3 | Pre-requisite | 38.101-1 | 5.5A.1 | Bandwidth included in the new BCS |  | Set status in column "Impacted CBWs identified" when all new CBWs added by the new BCS of the configuration(s) have been identified and listed in the "Comments" column. |  | TBD |  |  | 1 | [5 empty] | 0%
All BCS0 | 1-4 | Pre-requisite | 38.521-1 | 6, 7 | All applicable Transmitter (clause 6) and Receiver (clause 7) for the type of SUL configuration completed |  | Set status in column "TCs available" to 100% when all applicable test cases in 38.521-1 are completed for at least one of the same SUL type of configuration. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. |  | TBD |  |  | 1 |  |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted SUL configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
SUL BCS0 | 2 | TP Analysis | 38.905 | 4.1.1.2 | Test point (TP) analysis for A-MPR |  | For each SUL configuration check if an A-MPR TP analysis as described in TR 38.905 clause 4.1.1.2 is needed. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been performed and included in TR 38.905. |  | TBD |  |  | 1 |  |  | 0%
All BCS0 | 2-2a | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity for BCS0 |  | For each SUL configuration >=2DL perform reference sensitivity TP analysis as described in TR 38.905, Annex B.9. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | TBD |  |  | 1 |  |  | 0%
All new BCS | 2-2b | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity for new BCS > 0 |  | For each SUL configuration >= 2DL update the reference sensitivity TP analysis as described in TR 38.905, Annex B.9 for the new BCSs. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis for the new BCSs have been included in TR 38.905. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
All BCS0 | 3.1-1a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.x | Test frequencies BSC0 |  | No additional changes needed. Completion of test frequencies for impacted SUL bands covered by WP item 1-1. |  | TBD |  |  | 1
All new BCS | 3.1-1b | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.x | Test frequencies BCS>0 |  | No additional changes needed. Completion of test frequencies for impacted SUL bands covered by WP item 1-1a. |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Clause 5 | Discussion paper
[15 empty] | 1 | 1
All BCS0 | 3.2-0 | 38.521-1 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. |  | If it is thought there are no configuration specific changes needed for Chapter 6/7 or only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7 or why only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | TBD |  |  | 1 |  |  |  | 0%
All BCS0 | 3.2-1 | 38.521-1 - General | 38.521-1 | 3.2 | Symbols |  | No additional changes needed. Completion of test frequencies for impacted SUL bands covered by WP item 1-1. |  | TBD |  |  | 1 |  |  | 0%
All BCS0 | 3.2-2 | 38.521-1 - General | 38.521-1 | 5.2C | Operating band combination for SUL |  | No additional changes needed. Completion of test frequencies for impacted SUL bands covered by WP item 1-1a. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
All BCS0 | 3.2-3 | 38.521-1 - General | 38.521-1 | 5.5C | Configurations for SUL |  | Add the configurations for SUL operation to the relevant table in clause 5.5C. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
All new BCS | 3.2-4 | 38.521-1 - General | 38.521-1 | 6.2C.2 | ΔTIB,c |  | Adding ΔTIB,c for SUL configurations to the relevant table in clause 6.2C.2. |  | TBD |  |  | 1 |  |  | 0%
All BCS0 | 3.2-5 | 38.521-1 - General | 38.521-1 | 7.3C.0.2 | Minimum conformance requirements for Reference sensitivity power level |  | Add supplementary uplink configuration,Reference sensitivity exceptions, and supplementary uplink configuration (exceptions) for SUL band combinations to the relevant table in clause 7.3C.0.2. |  | TBD |  |  | 1 |  |  | 0%
All new BCS | 3.2-6 | 38.521-1 - General | 38.521-1 | 7.3C.0.3 | ΔRIB,c for SUL |  | Add ΔRIB,c for SUL configurations to the relevant table in clause 7.3C.0.3. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All BCS0 | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.xC |  |  | No additional changes needed. Completion of SUL Rx test cases and addiiton of ΔRIB,c for SUL as covered by WP item 1-4 and WP item 3.2-4b. |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All BCS0 | 3.4-1a | 38.521-1 RF Rx | 38.521-1 | 7.3C.2 | Reference sensitivity power level for SUL Note! This WP item is dependent on Reference Sensitivity TP analysis (Step 2, WP item 2-2a) |  | Add test configuration, SUL configuration and test requirements for non-exceptional and any exceptional requirements. |  | TBD |  |  | 1 |  |  | 0%
All new BCS | 3.4-1b | 38.521-1 RF Rx | 38.521-1 | 7.3C.3 | Reference sensitivity power level for SUL (3CC) Note! This WP item is dependent on Reference Sensitivity TP analysis (Step 2, WP item 2-2b) |  | Add test band combinations and configuration of SUL band configuration in table 7.3C.3.4-1. |  | TBD |  |  | 1 |  |  | 0%
SUL BCS0 | 3.4-2a | 38.521-1 RF Rx | 38.521-1 | 7.6C.2 | In-band blocking for SUL |  | Add test configuration for SUL band in table 7.6C.2.4-1. |  | TBD |  |  | 1 |  |  | 0%
SUL new BCS | 3.4-2b | 38.521-1 RF Rx | 38.521-1 | 7.6C.2 | In-band blocking for SUL |  | Check if the test configuration for the SUL band in table 7.6C.2.4-1 need to be updated due to the new BCS. |  | TBD |  |  | 1 |  |  | 0%
CA SUL BCS0 | 3.2-3a | 38.521-1 RF Rx | 38.521-1 | 7.6C.2_1 | Inband Blocking for SUL with DL CA |  | For SUL with intra-band DL CA: add test channel bandwidth in table 7.6C.2_1.1.4.1 For SUL with inter-band DL CA: add test combinations and configuration in table Table 7.6C.2_1.1.4-2 |  | TBD |  |  | 1 |  |  | 0%
CA SUL new BCS | 3.2-3b | 38.521-1 RF Rx | 38.521-1 | 7.6C.2_1 | Inband Blocking for SUL with DL CA |  | For SUL with intra-band DL CA: Check if test channel bandwidth is impacted by the new BCS in table 7.6C.2_1.1.4.1 For SUL with inter-band DL CA: Check if test combinations and configuration need to be updated due to the new BCS in table Table 7.6C.2_1.1.4-2 |  | TBD |  |  | 1 |  |  | 0%
SUL BCS0 | 3.4-3a | 38.521-1 RF Rx | 38.521-1 | 7.6C.3 | Out-of-band blocking for SUL |  | 1. Add minimum requirement in table 7.6C.3.3-1 and test requirement in table 7.6C.3.4-1 for SUL band combination if exception allowed. 2. Adding SUL band in test configuration table 7.6C.3.4-1. |  | TBD |  |  | 1 |  |  | 0%
SUL new BCS | 3.4-3b | 38.521-1 RF Rx | 38.521-1 | 7.6C.3 | Out-of-band blocking for SUL |  | 1. Check if minimum requirementin table 7.6C.3.3-1 and test requirement in table 7.6C.3.4-1 need to be updated due to the new BCS for the SUL band combination if exception allowed. 2. Check if the SUL band in test configuration table 7.6C.3.4-1 need to be updated sue to the new BCS. |  | TBD |  |  | 1 |  |  | 0%
CA SUL BCS0 | 3.2-4a | 38.521-1 RF Rx | 38.521-1 | 7.6C.3_1.1 | Out-of-band Blocking for SUL with 2 DL CA |  | 1. Add minimum requirement in table 7.6C.3_1.1.3-1 and test requirement in table 7.6C.3_1.1.5-1 for SUL band combination if exception allowed. 2. Adding SUL band in test configuration table 7.6C.3.4-2. |  | TBD |  |  | 1 |  |  | 0%
CA SUL new BCS | 3.2-4b | 38.521-1 RF Rx | 38.521-1 | 7.6C.3_1.1 | Out-of-band Blocking for SUL with 2 DL CA |  | 1. Check if minimum requirement in table 7.6C.3_1.1.3-1 and test requirement in table 7.6C.3_1.1.5-1 need to be updated due to the new BCS for SUL band combination if exception allowed. 2. Check if SUL band in test configuration table 7.6C.3.4-2 need to be updated due to the new BCS. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
SUL BCS0 | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.2C.2 | Configurations for SUL operation without CA |  | Add the SUL configuration to table A.4.3.2C.2-1 |  | TBD |  |  | 1 |  |  | 0%
CA SUL BCS0 | 4-2 | 38.508-2 - ICS | 38.508-2 | A.4.3.2C.3 | Configurations for SUL operation with CA |  | Add the SUL band combinations to the relevant table in column C. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N31: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N42: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N52: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N60: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N73: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N80: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N96: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N103: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N110: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.5.0 | RAN5#99 | No changes. Same as v1.4.0.
v1.4.0 | RAN5#98 | No changes. Same as v1.3.0.
v1.3.0 | RAN5#97 | 1. Corrected referenced TS in header row for steps 3.3 and 3.4.
v1.2.0 | RAN5#96-e | 1. Extended the number of rows in the input table to cope with the case when multiple cut and paste of configurations from PRD21 CADC list are done. 2. Clarify references to TP analysis in dependent test cases.
v1.1.0 | RAN5#95-e | 1. Updated WP template version in WP scope worksheet to get version number from cell A3 in the "Revision History WP template" worksheet. 2. Correcting TS reference in "area" and "TS" columns from 36.521-1 to 38.521-1. 3. Added a note to WP items 3.2-1 to 3.2-2 to remind about merge with "jumbo" CR. 4. Added WP item 3.2-0 about need for discussion paper to add configuration information to chapter 5.
v1.0.0 | RAN5#94-e | Initial version