## Cover sheet
3GPP TSG-RAN5 Meeting #99 | [8 empty] | R5-232846
Incheon, Korea (Republic Of), 22nd May 2023 - 26th May 2023
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Work item code: | NR_NTN_solutions_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 40% (+15%) | 0 | 50 (+24)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 40.1% (+14.8%) | 0 | 50 (+24)
FR1 |  | 40.1% (+14.8%) | 0 | 50 (+24)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 35% (+10%) |  |  | 35% (+10%)
Common ICS | 38.508-2 | 10% |  |  | 10%
UE specific testing functions | 38.509
Conducted RF Transmitter Test cases | 38.101-5
5 References
[1] RP-221299 | New WID on UE Conformance - Further enhancement on NR demodulation performance
[2] R5-231336 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance- Solutions for NR to support non-terrestrial networks (NTN) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_NTN_solutions_plus_CT-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for Solutions for NR to support non-terrestrial networks (NTN) Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
40.1% (+14.8%)
90 (+3)
58.8 (+23.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and RF Demod Test Environment for Rel17 NTN solutions |  | Google, Qualcomm |  | R5-227480 R5-230882, R5-230884 R5-225352 R5-225353 R5-225354 R5-225355 R5-233434 R5-233435 R5-233436 R5-232693 R5-233369 R5-232520 |  | 1 | 35% (+28.7%) | 35% (+22.5%) |  | 35%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-17 NTN solutions |  | Qualcomm |  | R5-226551 |  | 1 | 5% | 5% |  | 10%
TS 38.509: UE specific testing functions
|  | 38.509 | TBD | TBD | [5 empty] | 1
TS 38.521-5: Conducted RF Transmitter Test cases
3 |  | 38.521-5 | 4 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-226639 R5-226640 |  | 0.2 | 50% | 100% |  | 100%
4 |  | 38.521-5 | 5 | Operating bands and channel arrangement |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
5 |  | 38.521-5 | 5.1 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
6 |  | 38.521-5 | 5.2 | Operating bands |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
7 |  | 38.521-5 | 5.3 | UE Channel Bandwidth |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
8 |  | 38.521-5 | 5.4 | Channel arrangment |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
9 |  | 38.521-5 | 6 | Conducted Transmitter characteristics |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 50% | 100% |  | 100%
10 |  | 38.521-5 | 6.1 | General |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 50% | 100% |  | 100%
11 |  | 38.521-5 | 6.2 | Transmitter Power |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 50% | 100% |  | 100%
12 | Y | 38.521-5 | 6.2.1 | UE maximum output power |  | Google | RAN5#97 (Nov-22) | R5-227885, R5-231854 | Editor’s Note: - Addition to applicability spec is pending - Initial condition and Test procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 3 | 60% (+30%) | 60% |  | 60%
13 | Y | 38.521-5 | 6.2.2 | UE maximum output power reduction |  | Google | RAN5#97 (Nov-22) | R5-227886. R5-231854 | Editor’s Note: - Addition to applicability spec is pending - Initial condition and Test procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 3 | 60% (+30%) | 60% |  | 60%
14 | Y | 38.521-5 | 6.2.3 | UE additional maximum output power reduction |  | Google | RAN5#97 (Nov-22) | R5-233569 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 3 | 40% (+40%) | 40% (+40%) |  | 40%
15 | Y | 38.521-5 | 6.2.4 | Configured transmitted power |  | Google | RAN5#97 (Nov-22) | R5-232519 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 3 | 40% (+40%) | 40% (+40%) |  | 40%
16 |  | 38.521-5 | 6.3 | Output power dynamics | [9 empty] | 0%
17 | Y | 38.521-5 | 6.3.1 | Minimum output power |  | Keysight | TBD | R5-231738 |  | 1 | 7.5% | 15% |  | 15%
18 | Y | 38.521-5 | 6.3.2 | Transmit off power |  | Keysight | TBD | R5-231739 |  | 1 | 7.5% | 15% |  | 15%
19 | Y | 38.521-5 | 6.3.3 | Transmit on/off time mask |  | Apple |  | R5-231367 R5-233571 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 3 | 50% (+42.5%) | 50% (+35%) |  | 50%
20 | Y | 38.521-5 | 6.3.4 | Power control | [5 empty] | 1 | 0% | 0% |  | 0%
21 |  | 38.521-5 | 6.4 | Transmit signal quality | [9 empty] | 0%
22 | Y | 38.521-5 | 6.4.1 | Frequency error |  | Qualcomm |  |  |  | 1 | 0% | 0% |  | 0%
23 | Y | 38.521-5 | 6.4.2 | Transmit modulation quality | [5 empty] | 1 | 0% | 0% |  | 0%
24 |  | 38.521-5 | 6.5 | Output RF spectrum emissions | [9 empty] | 0%
25 | Y | 38.521-5 | 6.5.1 | Occupied Bandwidth | [5 empty] | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-5 | 6.5.2 | Out of band emissions | [9 empty] | 0%
27 |  | 38.521-5 | 6.5.2.1 | General | [5 empty] | 0.2 | 0% | 0% |  | 0%
28 | Y | 38.521-5 | 6.5.2.2 | Spectrum emission mask |  | Apple |  | R5-231368 R5-233572 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 3 | 50% (+42.5%) | 50% (+35%) |  | 50%
29 | Y | 38.521-5 | 6.5.2.4 | Adjacent channel leakage ratio |  | Apple |  | R5-231369 R5-233573 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 3 | 50% (+42.5%) | 50% (+35%) |  | 50%
30 |  | 38.521-5 | 6.5.3 | Spurious emission |  | Qualcomm | [7 empty] | 0%
31 | Y | 38.521-5 | 6.5.3.1 | General spurious emission |  | Qualcomm |  | R5-230877 R5-233158 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 3 | 60% (+35%) | 60% (+10%) |  | 60%
32 | Y | 38.521-5 | 6.5.3.2 | Spurious emissions for UE co-existence |  | Qualcomm |  | R5-230879 |  | 2 | 50% (+25%) | 50% |  | 50%
33 | Y | 38.521-5 | 6.5.3.3 | Additional spurious emissions |  | Qualcomm |  |  |  | 1 | 0% | 0% |  | 0%
34 | Y | 38.521-5 | 6.5.4 | Transmit intermodulation |  | Qualcomm |  |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-5: Conducted RF Receiver Test cases
35 |  | 38.521-5 | 7.1 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 |  | 0.5 | 50% (+25%) | 50% |  | 50%
36 |  | 38.521-5 | 7.2 | Diversity Characteristics |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
37 |  | 38.521-5 | 7.3 | Reference sensitivity |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 | [5 empty] | 100%
38 |  | 38.521-5 | 7.3.1 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 |  | 0.2 | 100% (+50%) | 100% |  | 100%
39 | Y | 38.521-5 | 7.3.2 | Reference sensitivity power level |  | Qualcomm |  | R5-230878 |  | 2 | 50% (+25%) | 50% |  | 50%
40 | Y | 38.521-5 | 7.4 | Maximum input level |  | Keysight |  | R5-232346 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 2 | 40% (+40%) | 40% (+40%) |  | 40%
41 | Y | 38.521-5 | 7.5 | Adjacent channel selectivity |  | CAICT | RAN5#98 (Feb-23) | R5-233567 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 2 | 40% (+40%) | 40% (+40%) |  | 40%
42 |  | 38.521-5 | 7.6 | Blocking characteristics |  | CAICT | [7 empty] | 0%
43 |  | 38.521-5 | 7.6.1 | General |  | Apple |  |  |  | 0.2 | 0% | 0% |  | 0%
44 | Y | 38.521-5 | 7.6.2 | In-band blocking |  | Apple |  |  |  | 1 | 0% | 0% |  | 0%
45 | Y | 38.521-5 | 7.6.3 | Out-of-band blocking |  | Apple |  | R5-231383 |  | 2 | 15% (+7.5%) | 15% |  | 15%
45 | Y | 38.521-5 | 7.6.4 | Narrow band blocing |  | Apple |  |  |  | 1 | 0% | 0% |  | 0%
46 | Y | 38.521-5 | 7.7 | Spurious response |  | CAICT |  |  |  | 1 | 0% | 0% |  | 0%
47 | Y | 38.521-5 | 7.8 | Intermodulation characteristics |  | CAICT |  |  |  | 1 | 0% | 0% |  | 0%
48 | Y | 38.521-5 | 7.9 | Spurious emissions |  | CAICT |  | R5-231740 R5-232372 |  | 2 | 15% (+7.5%) | 15% |  | 15%
TS 38.521-5: Demodulation Performance Test Cases
49 |  | 38.521-5 | 8 | General |  | Qualcomm | RAN5#97 (Nov-22)
50 |  | 38.521-5 | 8.1 | General |  | Qualcomm | RAN5#97 (Nov-22)
51 |  | 38.521-5 | 8.1.1 | Relationship between minimum requirements and test requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
52 |  | 38.521-5 | 8.1.2 | Applicability of minimum requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
53 |  | 38.521-5 | 8.1.3 | Conducted requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
54 |  | 38.521-5 | 8.2 | Demodulation performance requirements |  | Qualcomm | RAN5#97 (Nov-22)
55 |  | 38.521-5 | 8.2.1 | General |  | Qualcomm | RAN5#97 (Nov-22)
56 |  | 38.521-5 | 8.2.1.2 | PDSCH demodulation requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231742 |  | 0.2 | 100% | 100% |  | 100%
57 |  | 38.521-5 | 8.2.1.2.1 | 1RX requirements |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0%
58 |  | 38.521-5 | 8.2.1.2.2 | 2RX requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231742 |  |  | 20% | 20% |  | 20%
61 | Y | 38.521-5 | 8.2.1.2.2.1.1_1 | 2Rx FDD FR1 PDSCH Mapping Type A for Satellite Access |  | Qualcomm |  | R5-233570 | Editor's Note: This test cases is incomplete in following aspects: - NTN specific message contents - Initial condition and call setup procedure to support NR satellite access are TBD - Annex F MU/TT analysis - Annex G Minimum test time - Applicability spec update | 2 | 40% (+40%) | 40% (+40%) |  | 40%
TS 38.521-5: Annex
59 |  | 38.521-5 | A | Measurement channels |  | CAICT |  | R5-233568 |  | 0.2 | 100% (+50%) | 50% |  | 100%
59 |  | 38.521-5 | B | Propagation conditions |  | CAICT |  | R5-233568 |  | 0.2 | 100% (+50%) | 50% |  | 100%
59 |  | 38.521-5 | C.3 | Connection (Conducted) |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% (+50%) | 50% |  | 100%
TS 38.522: Applicability for RF Transmitter and Receiver Test cases
60 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-5 | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.523-1: Protocol test cases - FFS on several aspects of GSO, NGSO etc
Idle Mode
|  | 38.523-1 | 6.1 | [6 empty] | 0 | 0% | 0% |  | 0%
28 | Y | 38.523-1 | 6.7.x.x | Cell Selection / GNSS location / NTN | TS 23.122 4.4.3.1.1; |  |  |  |  | 0 | 0% | 0% |  | 0%
Cell reselection / Neighbor cell ephermis validaty/ ntn-UlSyncValidityDuration
29 | Y | 38.523-1 | 6.7.x.x | Cell Selection / MultiTAC / NTN/ trackingAreaList-r17 | TS 38.331 5.2.2.4.2; TS 24.501 4.23.5
| Y | 38.523-1 | 6.7.x.x | Cell Selection / Serving cell becomes non-suitable (CellBarredNTN) | TS 38.304, 5.3.1
| Y | 38.523-1 | 6.7.x.x | Cell Reselection / enhancedMeasurementLEO / ServingCellConfigCommonSIB / SIB1 | TS 38.331; TS 38.133
TS38.304, Cl 5.2.4.2 Measurement rules for cell re-selection
| Y | 38.523-1 | 6.7.x.x | Cell reselection, distanceThresh , referenceLocation | TS38.304, Cl 5.2.4.2 |  |  |  |  | 0 | 0% | 0% |  | 0%
MAC
17 |  | 38.523-1 | 7.1 | NR Layer 2 | [5 empty] | 0 | 0% | 0% |  | 0%
18 |  | 38.523-1 | 7.1.1 | MAC | [5 empty] | 0 | 0% | 0% |  | 0%
19 |  | 38.523-1 | 7.1.1.1 | Random Access Procedures | [5 empty] | 0 | 0% | 0% |  | 0%
20 | Y | 38.523-1 | 7.1.1.1.x | Random access procedure / Successful / Contention resolution timer expired / NTN | TS 38.321 Cl 5.1.4; 5.1.5 |  |  |  |  | 0 | 0% | 0% |  | 0%
22 | Y | 38.523-1 | 7.1.1.x.x | NTN / UE specific TA report / UE specific Koffset | TS 38.321 , Cl 5.4.8; 5.18.24 |  |  |  |  | 0 | 0% | 0% |  | 0%
21 |  | 38.523-1 | 7.1.1.3.x | [6 empty] | 0 | 0% | 0% |  | 0%
26 | Y | 38.523-1 | 7.1.1.3.x | NTN / DRX / (UL)HARQ RTT/ HARQ-RTT-TimerDL-NTN / HARQ-RTT-TimerUL-NTN | TS 38.321 Cl 5.7 |  |  |  |  | 0 | 0% | 0% |  | 0%
| Y | 38.523-1 |  | UE failing to acquire sufficiently accurate UE location to calculate UE's TA, should not perform any UL transmissions ( TS 38.211, Clause 4.3.1)
21 |  | 38.523-1 | 7.1.2.x
26 | Y | 38.523-1 | 7.1.2.x.x | NTN / AM RLC / Receiver status triggers / extended t-Reordering configured | [5 empty] | 0 | 0% | 0% |  | 0%
RRC
4 |  | 38.523-1 | 8.1 | Existing sub-clause header | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
5 |  | 38.523-1 | 8.1.5 | Existing sub-clause header | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
11 |  | 38.523-1 | 8.1.5.1 | [6 empty] | 0 | 0% | 0% |  | 0%
12 |  | 38.523-1 | 8.1.5.1.1 | UE capability - nonTerrestrialNetwork-r17 | [5 empty] | 0 | 0% | 0% |  | 0%
6 |  | 38.523-1 | 8.1.5.x.x | [6 empty] | 0 | 0% | 0% |  | 0%
7 | Y | 38.523-1 |  | start timer T430 with the timer value set to ntn-UlSyncValidityDuration - NTN / T430 expiry | TS 38.331 5.2.2.6; 5.3.5.5.2; 5.2.2.4.21 |  |  |  |  | 0 | 0% | 0% |  | 0%
8 | Y | 38.523-1 |  | GEO / SIB2 Relaxed measurements - relaxedMeasurement-r17 | [5 empty] | 0 | 0% | 0% |  | 0%
|  |  | 8.1.3 | Measurement configuration control and reporting | [5 empty] | 0 | 0% | 0% |  | 0%
9 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / Event D1 | TS 38.331 5.5.4.15; 5.5.4.1 |  |  |  |  | 0 | 0% | 0% |  | 0%
27 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / Event T1 | ??
|  | 38.523-1 | 8.1.4.4 | Conditional handover
30 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / CondEventD1 / CondEventA4/ condEventA4-r17 | TS 38.331 5.3.5.13.1; 5.3.5.13.4
31 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / CondEventD1 | TS 38.331 5.3.5.13.1; 5.3.5.13.4 |  |  |  |  | 0 | 0% | 0% |  | 0%
NAS
4 |  | 38.523-1 | 9.1.x | Existing sub-clause header | Existing sub-clause header |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
5 |  | 38.523-1 | 9.1.x.x | Existing sub-clause header | Existing sub-clause header |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
11 | Y | 38.523-1 | 9.1.x.x.x | NTN / GNSS position reporting / reject cause #78 "PLMN not allowed to operate at the present UE location" | TS 23.122 3.1, TS 24.501 4.23.2; 5.5.1.2.5 |  |  |  |  | 0 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | NTN / Mobility registration update / supported TACs not part of UE registration area | 23.501 Cl 5.4.11.6 |  |  |  |  | 0 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | TAI(s) not allowed / forbidden TAI(s) in the Registration Accept message | 23.501, Cl 5.4.11.8 | [5 empty] | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | Timer expiry | ?? |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | new 5QI value
| Y | 38.523-1 | 9.1.x.x.x | IMS emergency
|  |  |  | PDU session release procedure for #78 | TS 24.501, 6.3.3 and 6.4.3 |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
24 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for NR-NTN |  |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.