## Cover sheet
3GPP TSG-RAN5 Meeting #99 | [8 empty] | R5-232848
Incheon, Korea, 22th May 2023 – 26th May 2023
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Further enhancement on NR demodulation performance
Work item code: | NR_demod_enh2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 30% (+25%) | 0 | 31 (+23)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 29.3% (+24.3%) | 0 | 31 (+23)
FR1 |  | 29.3% (+24.3%) | 0 | 31 (+23)
NSA Option 3 (EN-DC) |  | 31.5% (+26.5%) | 0 | 31 (+23)
FR1 |  | 31.5% (+26.5%) | 0 | 31 (+23)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  |  |  | 0%
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  |  |  | 100% (+100%)
UE specific testing functions | 38.509
Demodulation performance requirements (conducted requirements) | 38.521-4 | 27.6% (+27.6%) | 0 | 31 (+23) | 26.4% (+26.4%) | 0 | 31 (+23) |  |  | 28.8% (+28.8%) | 0 | 31 (+23)
5 References
[1] RP-221299 | New WID on UE Conformance - Further enhancement on NR demodulation performance
[2] R5-231338 | WP UE Conformance Test Aspects - Further enhancement on NR demodulation performance
[3] R5-232848 | WP UE Conformance Test Aspects - Further enhancement on NR demodulation performance
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance- Further enhancement on NR demodulation performance | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_demod_enh2-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for Further enhancement on NR demodulation performance Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 29.3% (+24.3%) | 31.5% (+26.5%)
[15 empty] | 31 (+13) | 28 (+16)
[15 empty] | 37.3 (+20.3) | 34.3 (+23.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
15 |  | 38.508-1 | 4, 5 | Introduction of General and RF Demod Test Environment for Rel17 Further enhancement on NR demodulation performance | [5 empty] | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
16 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-17 Further enhancement on NR demodulation performance |  | China Telecom |  | R5-232837 |  | 0.2 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.509: UE specific testing functions
|  | 38.509 | TBD | TBD | [5 empty] | 1
TS 38.521-4: Demodulation performance requirements (conducted requirements)
1 |  | 38.521-4 | 5.1 | General | Exisiting sub-clause header | China Telecom |  | R5-232835 |  | 0.2 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
2 | Y | 38.521-4 | 5.2.2.1.15_1 | 2Rx FDD FR1 PDSCH with inter-cell intereference | 38.101-4 requirements in TC 5.2.2.1.15 | China Telecom |  | R5-233707 | Editor's Note: This test case is incomplete in following aspects: - Test description part is missing. - MU/TT analysis pending. | 1 | 25% (+25%) | 25% (+25%) | 25% (+25%) |  | 25% | 25%
21 | Y | 38.521-4 | 5.2.2.1.16_1 | 2Rx FDD FR1 for PDSCH with intra cell inter user interference performance – 2x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.1.16 | Qualcomm |  | R5-233581 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
22 | Y | 38.521-4 | 5.2.2.1.17_1 |  | 38.101-4 requirements in TC 5.2.2.1.17 |  |  |  |  | 2 | 0% | 0% | 0% |  | 0% | 0%
23 | Y | 38.521-4 | 5.2.2.1.18_1 | 2Rx FDD FR1 for PDSCH CRS interference mitigation under NR-LTE coexistence scenario – 2x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.1.18 | Qualcomm |  | R5-233582 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
23 | Y | 38.521-4 | 5.2.2.1.19_1 | 2Rx FDD FR1 for PDSCH with inter cell CRS interference scenario – 4x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.1.19 | Qualcomm |  | R5-233583 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
3 | Y | 38.521-4 | 5.2.2.2.16_1 | 2Rx TDD FR1 for PDSCH with inter-cell interference performance – 2x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.2.16 | Qualcomm |  | R5-233580 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
24 | Y | 38.521-4 | 5.2.2.2.17_1 | 2Rx TDD FR1 for PDSCH with intra cell inter user interference performance – 2x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.2.17 | Qualcomm |  | R5-233581 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
25 | Y | 38.521-4 | 5.2.2.2.19_1 | 2Rx TDD FR1 for PDSCH CRS interference mitigation under NR-LTE coexistence scenario – 4x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.2.19 | Qualcomm |  | R5-233582 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
26 | Y | 38.521-4 | 5.2.2.2.20_1 | 2Rx TDD FR1 for PDSCH with inter cell CRS interference scenario – 4x2 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.2.2.20 | Qualcomm |  | R5-233583 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
4 | Y | 38.521-4 | 5.2.3.1.15_1 | 4Rx FDD FR1 PDSCH with inter-cell intereference | 38.101-4 requirements in TC 5.2.3.1.15 | China Telecom |  | R5-233708 | Editor's Note: This test case is incomplete in following aspects: - Test description part is missing. - MU/TT analysis pending. | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
27 | Y | 38.521-4 | 5.2.3.1.16_1 | 4Rx FDD FR1 for PDSCH with intra cell inter user interference performance – 2x4 and 4x4 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.3.1.16 | Qualcomm |  | R5-233581 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
28 | Y | 38.521-4 | 5.2.3.1.17_1 | 4Rx FDD FR1 for PDSCH CRS interference mitigation under NR-LTE coexistence scenario – 2x4 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.3.1.17 | Qualcomm |  | R5-233582 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
29 | Y | 38.521-4 | 5.2.3.1.18_1 | 4Rx FDD FR1 for PDSCH with inter cell CRS interference scenario – 4x4 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.3.1.18 | Qualcomm |  | R5-233583 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
5 | Y | 38.521-4 | 5.2.3.2.16_1 | 4Rx TDD FR1 PDSCH with inter-cell intereference | 38.101-4 requirements in TC 5.2.3.2.16 |  |  |  | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 2 | 0% | 0% | 0% |  | 0% | 0%
30 | Y | 38.521-4 | 5.2.3.2.17_1 | 4Rx TDD FR1 for PDSCH with intra cell inter user interference performance – 2x4 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.3.2.17 | Qualcomm |  | R5-233581 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
31 | Y | 38.521-4 | 5.2.3.2.18_1 | 4Rx TDD FR1 for PDSCH CRS interference mitigation under NR-LTE coexistence scenario – 4x4 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.3.2.18 |  |  | R5-233582 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
32 | Y | 38.521-4 | 5.2.3.2.19_1 | 4Rx TDD FR1 for PDSCH with inter cell CRS interference scenario – 4x4 MIMO for both NSA and SA | 38.101-4 requirements in TC 5.2.3.2.29 | Qualcomm |  | R5-233583 | Editor’s Note: This test case is incomplete in following aspects - Message exceptions are FFS - MU/TT analysis is pending | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% | 60%
TS 38.521-4: CSI reporting requirements (conducted requirements)
8 |  | 38.521-4 | 6.1 | General | Exisiting sub-clause header |  |  |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
17 | Y | 38.521-4 | 6.2.2.1.2.3_1 | 2Rx FDD FR1 Wideband CQI reporting with inter-cell intereference | 38.101-4 requirements in TC 6.2.2.1.2.3 |  |  |  |  | 3 | 0% | 0% | 0% |  | 0% | 0%
18 | Y | 38.521-4 | 6.2.2.2.2.3_1 | 2Rx TDD FR1 Wideband CQI reporting with inter-cell intereference | 38.101-4 requirements in TC 6.2.2.2.2.3 |  |  |  |  | 3 | 0% | 0% | 0% |  | 0% | 0%
19 | Y | 38.521-4 | 6.2.3.1.2.3_1 | 4Rx FDD FR1 PDSCH with inter-cell intereference | 38.101-4 requirements in TC 6.2.3.1.2.3 |  |  |  |  | 3 | 0% | 0% | 0% |  | 0% | 0%
20 | Y | 38.521-4 | 6.2.3.2.2.3_1 | 4Rx TDD FR1 PDSCH with inter-cell intereference | 38.101-4 requirements in TC 6.2.3.2.2.3 |  |  |  |  | 3 | 0% | 0% | 0% |  | 0% | 0%
TS 38.521-4: Annex
9 |  | 38.521-4 | Annex A | Measurements Channels |  | Qualcomm, China Telecom |  | R5-232836 R5-233581 R5-233582 R5-233583 |  | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
10 |  | 38.521-4 | Annex B | Propagation conditions |  | Qualcomm |  | R5-233580 |  | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
11 |  | 38.521-4 | Annex C | Downlink physical channels | [5 empty] | 1 | 0% | 0% |  |  | 0%
12 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | [5 empty] | 1 | 0% | 0% |  |  | 0%
13 |  | 38.521-4 | Annex G | Statistical testing | [5 empty] | 1 | 0% | 0% |  |  | 0%
TS 38.522: Applicability for Demodulation and CSI test cases
14 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-4 |  | China Telecom, Qualcomm |  | R5-232834 |  | 1 | 5% (+5%) | 5% (+5%) | 5% (+5%) |  | 10% | 10%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.