## Cover sheet
3GPP TSG-RAN5 Meeting #99 | [10 empty] | R5-232936
Incheon, Korea, 22th May 2023 - 26th May 2023
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon, CMCC
Title: | WP UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects
Work item code: | NR_MBS_5MBS_5MBUSA-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
3GPP Rel-17 has specified the feature support of multicast and broadcast services (MBS) over 5GS. The objective of UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects work item is to provide conformance test specifications for the core requirements of Rel-17, including CT aspects of NR MBS, Security Aspects of NR MBS, and RAN aspects of NR MBS. This work item will cover Protocol conformance test specifications with NR-MBS operation. At the RAN#95e meeting in March 2022 the Rel-17 RAN5 work item for UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 77% (+25%) | 0 | 43 (-1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 76.7% (+25.4%) | 0 | 43 (-1)
FR1 |  | 84.1% (+28.8%) | 35 (+14) | 43 (-1)
FR2 |  | 69.4% (+21.9%) | 0 | 43 (-1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 78.7% |  |  | 78.7% |  |  | 78.7%
Common ICS | 38.508-2 | 30% |  |  | 30% |  |  | 30%
UE specific test functions | 38.509 | 100% |  |  | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 74.2% (+31.2%) | 0 | 43 (-1) | 83.3% (+35.5%) | 35 (+14) | 43 (-1) | 65.1% (+26.9%) | 0 | 43 (-1)
Applicability Protocol test cases | 38.523-2 | 5% |  |  | 5% |  |  | 5%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-220423 | New WID on UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects | [8 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MBS_5MBS_5MBUSA-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of Rel-17, including CT aspects of NR MBS, Security Aspects of NR MBS, and RAN aspects of NR MBS. | [10 empty] | vs Area
WP Resp: |  | Zhao Ya(Huawei) | [6 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Company | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[12 empty] | 84.1% (+28.8%) | 69.4% (+21.9%)
[12 empty] | 61 (-1) | 61 (-1)
[12 empty] | 50.5 (-1) | 50.5 (-1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | TBD
1 |  | 38.508-1 | 4.3.6.1 | Downlink physical layer parameters for MBS test | Huawei,Hisilicon | R5-224740 R5-224741 R5-225280 R5-227142 |  | 0.1 | 100% | 100% |  | 100% | 100%
2 |  | 38.508-1 | 4.4.3.1.2 | SI combination for MBS test | Huawei,Hisilicon | R5-227138 |  | 0.1 | 100% | 100% |  | 100% | 100%
3 |  | 38.508-1 | 4.4.3.1.2 | Scheduling of SIB20 and SIB21 for MBS test | Huawei,Hisilicon | R5-227138 |  | 0.5 | 100% | 100% |  | 100% | 100%
4 |  | 38.508-1 | 4.6.2 | System information blocks | Huawei,Hisilicon | R5-225326 R5-225327 R5-232946 |  | 0.5 | 100% | 100% |  | 100% | 100%
81 |  | 38.508-1 | 4.6.1 | Contents of RRC messages | Huawei,Hisilicon | R5-225328 R5-225329 R5-227507 R5-231468 |  | 0.5 | 100% | 100% |  | 100% | 100%
5 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Huawei,Hisilicon | R5-224817 R5-227509 R5-227512 R5-231470 R5-231471 R5-231472 R5-233383 |  | 0.5 | 80% | 80% |  | 80% | 80%
6 |  | 38.508-1 | 4.6.X | MBS information elements | Huawei,Hisilicon | R5-225330 R5-227139 R5-227508 |  | 1 | 30% | 30% |  | 30% | 30%
7 |  | 38.508-1 | 4.7.2 | Contents of 5GSM messages | Huawei,Hisilicon | R5-225180 R5-231469 |  | 0.5 | 100% | 100% |  | 100% | 100%
8 |  | 38.508-1 | 4.8.4 | DNN/APN configurations | Huawei,Hisilicon | R5-227510 |  | 0.5 | 100% | 100% |  | 100% | 100%
9 |  | 38.508-1 | 4.9 | Test procedures | Huawei,Hisilicon | R5-225325 R5-227511 R5-231467 R5-233382 |  | 0.5 | 60% | 60% |  | 60% | 60%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | TBD
10 |  | 38.508-2 | <Clause> | PICs for MBS testing | Huawei,Hisilicon | R5-223105 R5-227513 R5-231473 R5-232947 |  | 0.1 | 30% | 30% |  | 30% | 30%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | TBD
11 |  | 38.509 | 5.2 | Test mode for MBS | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
12 |  | 38.509 | 5.3 | Loop back function for MBS | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
13 |  | 38.509 | 5.9 | Test protocal procedure for MBS | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
14 |  | 38.509 | 6.9 | TMC message for MBS | Huawei,Hisilicon | R5-225331 R5-227514 |  | 0.5 | 100% | 100% |  | 100% | 100%
15 |  | 38.509 | 7.1 | State variables for MBS | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | TBD
16 |  | 38.523-1 | 14 | MBS |  |  |  | 0
17 |  | 38.523-1 | 14.1 | MBS Broadcast |  |  |  | 0
18 |  | 38.523-1 | 14.1.1 | MBS Broadcast/ MCCH Information Acquisition |  |  |  | 0
19 | Y | 38.523-1 | 14.1.1.1 | MBS Broadcast/ MCCH Information Acquisition/ entering the cell providing SIB20 | Huawei,Hisilicon | R5-227130 R5-232948 |  | 1 | 90% | 90% |  | 100% | 80%
20 | Y | 38.523-1 | 14.1.1.2 | MBS Broadcast/ MCCH Information Acquisition/ becoming interested to receive MBS broadcast services | CMCC | R5-233384 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
21 | Y | 38.523-1 | 14.1.1.3 | MBS Broadcast/ MCCH Information Acquisition/ MCCH Information change notification | CMCC | R5-232951 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
83 | Y | 38.523-1 | 14.1.1.4 | MBS Broadcast/ MCCH Information Acquisition/ receiving SIB20 of an SCell via dedicated signalling | Huawei,Hisilicon | R5-232952 |  | 1 | 40% (+40%) | 40% (+40%) |  | 80% | 0%
22 |  | 38.523-1 | 14.1.2 | MBS Broadcast/ Service Continuity |  |  |  | 0
23 | Y | 38.523-1 | 14.1.2.1 | MBS Broadcast/ Service Continuity/ Cell reselection/ frequency prioritization | Huawei,Hisilicon | R5-227131 R5-232948 |  | 1 | 90% | 90% |  | 100% | 80%
24 | Y | 38.523-1 | 14.1.2.2 | MBS Broadcast/ Service Continuity/ Handover/ MBS Interest Indication/ inter-frequency | Huawei,Hisilicon | R5-227132 R5-232948 |  | 1 | 90% | 90% |  | 100% | 80%
82 | Y | 38.523-1 | 14.1.2.3 | MBS Broadcast/ Service Continuity/ Handover/ MBS Interest Indication/ intra-frequency | Huawei,Hisilicon | R5-227133 R5-232948 |  | 1 | 90% | 90% |  | 100% | 80%
25 |  | 38.523-1 | 14.1.3 | MBS Broadcast/ MAC |  |  |  | 0
26 | Y | 38.523-1 | 14.1.3.1 | MBS Broadcast/ MAC/ Correct HARQ process handling | Huawei,Hisilicon | R5-227134 R5-232948 |  | 1 | 90% | 90% |  | 100% | 80%
27 | Y | 38.523-1 | 14.1.3.2 | MBS Broadcast/ MAC/ DRX operation | Huawei,Hisilicon | R5-227135 R5-232948 |  | 1 | 90% | 90% |  | 100% | 80%
28 |  | 38.523-1 | 14.2 | MBS Multicast |  |  |  | 0
31 |  | 38.523-1 | 14.2.1 | MBS Multicast/ MAC |  |  |  | 0
32 |  | 38.523-1 | 14.2.1.1 | MBS Multicast/ MAC / DL Data Transfer |  |  |  | 0
33 | Y | 38.523-1 | 14.2.1.1.1 | MBS Multicast / MAC / DL Data Transfer / PTM transmission / PTP transmission / DCI format 4_1 | Huawei,Hisilicon | R5-227515 R5-231483 |  | 1 | 90% | 90% |  | 100% | 80%
34 | Y | 38.523-1 | 14.2.1.1.2 | MBS Multicast / MAC / DL Data Transfer/ PTM transmission/ DCI format 4_2 | Huawei,Hisilicon | R5-232953 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
35 | Y | 38.523-1 | 14.2.1.1.3 | MBS Multicast / MAC / DL Data Transfer/ PTM transmission / PTP transmission / Multiple G-RNTIs |  |  |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
36 | Y | 38.523-1 | 14.2.1.1.4 | MBS Multicast/ MAC / DL Data Transfer/ PTM retransmission for multicast/ RRC-based enabling-disabling HARQ feedback for Multicast / ACK-NACK | Huawei,Hisilicon | R5-227516 R5-231483 |  | 1 | 90% | 90% |  | 100% | 80%
37 | Y | 38.523-1 | 14.2.1.1.5 | MBS Multicast/ MAC / DL Data Transfer/ PTP retransmission for multicast/ RRC-based enabling-disabling HARQ feedback for Multicast/ ACK-NACK | Huawei,Hisilicon | R5-227517 R5-231483 |  | 1 | 90% | 90% |  | 100% | 80%
38 | Y | 38.523-1 | 14.2.1.1.6 | MBS Multicast/ MAC / DL Data Transfer/ PTM retransmission for multicast/ DCI-based enabling-disabling HARQ feedback for Multicast/ ACK-NACK | Huawei,Hisilicon | R5-232954 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
39 | Y | 38.523-1 | 14.2.1.1.7 | MBS Multicast/ MAC / DL Data Transfer/ RRC-based enabling-disabling HARQ feedback for Multicast / NACK-only | Huawei,Hisilicon | R5-231474 |  | 1 | 90% | 90% |  | 100% | 80%
40 | Y | 38.523-1 | 14.2.1.1.8 | MBS Multicast/ MAC / DL Data Transfer/ Multiplex multicast HARQ-ACK information with unicast HARQ-ACK information | Huawei,Hisilicon | R5-231475 |  | 1 | 90% | 90% |  | 100% | 80%
84 | Y | 38.523-1 | 14.2.1.1.9 | MBS Multicast/ MAC / DL Data Transfer/ DCI-based enabling-disabling HARQ feedback for Multicast/ NACK-only | Huawei,Hisilicon | R5-232955 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
41 |  | 38.523-1 | 14.2.1.2 | MBS Multicast/ MAC/ DRX operation |  |  |  | 0
42 | Y | 38.523-1 | 14.2.1.2.1 | MBS Multicast/ MAC/ DRX operation/ PTM transmission / PTP transmission | Huawei,Hisilicon | R5-231476 |  | 1 | 90% | 90% |  | 100% | 80%
43 | Y | 38.523-1 | 14.2.1.2.2 | MBS Multicast/ MAC/ DRX operation/ PTM retransmission for multicast | Huawei,Hisilicon | R5-232956 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
44 | Y | 38.523-1 | 14.2.1.2.3 | MBS Multicast/ MAC/ DRX operation/ PTP retransmission for multicast | Huawei,Hisilicon | R5-232957 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
45 |  | 38.523-1 | 14.2.1.3 | MBS Multicast/ MAC/ SPS |  |  |  | 0
46 | Y | 38.523-1 | 14.2.1.3.1 | MBS Multicast/ MAC/ SPS/ PTM transmission |  |  |  | 1 | 0% | 0% |  | 0% | 0%
47 | Y | 38.523-1 | 14.2.1.3.2 | MBS Multicast/ MAC/ SPS/ PTM retransmission for multicast |  |  |  | 1 | 0% | 0% |  | 0% | 0%
48 | Y | 38.523-1 | 14.2.1.3.3 | MBS Multicast/ MAC/ SPS/ PTP retransmission for multicast |  |  |  | 1 | 0% | 0% |  | 0% | 0%
49 | Y | 38.523-1 | 14.2.1.3.4 | MBS Multicast/ MAC/ SPS/ CS-RNTI release |  |  |  | 1 | 0% | 0% |  | 0% | 0%
50 |  | 38.523-1 | 14.2.2 | MBS Multicast/ RLC |  |  |  | 0
51 | Y | 38.523-1 | 14.2.2.1 | MBS Multicast/ UM RLC / 6bit SN /Correct set initial value for UM receive state variable/ PTM | Huawei,Hisilicon | R5-231477 |  | 1 | 90% | 90% |  | 100% | 80%
52 | Y | 38.523-1 | 14.2.2.2 | MBS Multicast/ UM RLC / 12bit SN /Correct set initial value for UM receive state variable/ PTM | Huawei,Hisilicon | R5-231477 |  | 1 | 90% | 90% |  | 100% | 80%
53 |  | 38.523-1 | 14.2.3 | MBS Multicast / PDCP |  |  |  | 0
54 | Y | 38.523-1 | 14.2.3.1 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance / Non-Lossless handover / 12 bit SN | Huawei,Hisilicon | R5-231478 |  | 1 | 90% | 90% |  | 100% | 80%
55 | Y | 38.523-1 | 14.2.3.2 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance / Non-Lossless handover / 18 bit SN | Huawei,Hisilicon | R5-231478 |  | 1 | 90% | 90% |  | 100% | 80%
56 | Y | 38.523-1 | 14.2.3.3 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance /Lossless handover/ PDCP status report / 12 bit SN | Huawei,Hisilicon | R5-231479 |  | 1 | 90% | 90% |  | 100% | 80%
57 | Y | 38.523-1 | 14.2.3.4 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance /Lossless handover/ PDCP status report / 18 bit SN | Huawei,Hisilicon | R5-231479 |  | 1 | 90% | 90% |  | 100% | 80%
58 |  | 38.523-1 | 14.2.4 | MBS Multicast / RRC |  |  |  | 0
59 |  | 38.523-1 | 14.2.4.1 | MBS Multicast / RRC / Paging |  |  |  | 0
60 | Y | 38.523-1 | 14.2.4.1.1 | MBS Multicast / RRC / Paging for group notification / RRC_IDLE | Huawei,Hisilicon | R5-231480 R5-232949 |  | 1 | 90% | 90% |  | 100% | 80%
61 | Y | 38.523-1 | 14.2.4.1.2 | MBS Multicast / RRC / Paging for group notification / RRC_INACTIVE | Huawei,Hisilicon | R5-231481 R5-232949 |  | 1 | 90% | 90% |  | 100% | 80%
62 |  | 38.523-1 | 14.2.4.2 | MBS Multicast / RRC / MRB Reconfiguration |  |  |  | 0
63 | Y | 38.523-1 | 14.2.4.2.1 | MBS Multicast / RRC / MRB Reconfiguration / Establishment / Modification / Release / Success | Huawei,Hisilicon | R5-231482 |  | 1 | 90% | 90% |  | 100% | 80%
64 |  | 38.523-1 | 14.2.4.3 | MBS Multicast/ RRC/ Handover |  |  |  | 0
65 | Y | 38.523-1 | 14.2.4.3.1 | MBS Multicast/ RRC/ Handover between multicast supporting cell / Success | Huawei,Hisilicon | R5-233385 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
66 | Y | 38.523-1 | 14.2.4.3.2 | MBS Multicast / RRC / Handover between multicast supporting cell / Failure/ Re-establishment successful | Huawei,Hisilicon | R5-233386 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
67 | Y | 38.523-1 | 14.2.4.3.3 | MBS Multicast/ RRC/ Handover between Multicast-supporting cell and Multicast non-supporting cell / Success | Huawei,Hisilicon | R5-232960 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
68 |  | 38.523-1 | 14.2.4.3.4 | MBS Multicast / RRC / Handover from multicast supporting cell to multicast non-supporting cell / Full configuration / Success -> Void (emerge to 14.2.4.3.3 TP4) |  |  |  | 0
69 |  | 38.523-1 | 14.2.4.3.5 | MBS Multicast / RRC / Handover from multicast non-supporting cell to multicast supporting cell / Success -> Void (emerge to 14.2.4.3.3 TP3) |  |  |  | 0
70 |  | 38.523-1 | 14.2.5 | MBS Multicast/ Session management |  |  |  | 0
71 |  | 38.523-1 | 14.2.5.1 | MBS Multicast/ Session management / Network-requested PDU session modification |  |  |  | 0
72 | Y | 38.523-1 | 14.2.5.1.1 | MBS Multicast/ Session management / Network-requested PDU session modification / Remove UE from multicast MBS session | Huawei,Hisilicon | R5-233387 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
73 | Y | 38.523-1 | 14.2.5.1.2 | MBS Multicast/ Session management / Network-requested PDU session modification / MBS service area update | Huawei,Hisilicon | R5-233388 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
74 |  | 38.523-1 | 14.2.5.2 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification |  |  |  | 0
75 | Y | 38.523-1 | 14.2.5.2.1 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification / Join MBS multicast session / Accepted | Huawei,Hisilicon | R5-233389 |  | 1 | 90% (+90%) | 90% (+90%) |  | 100% | 80%
76 | Y | 38.523-1 | 14.2.5.2.2 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification / Join MBS multicast session / Rejected / User is outside of local MBS service area | Huawei,Hisilicon |  |  | 1 | 0% | 0% |  | 0% | 0%
77 | Y | 38.523-1 | 14.2.5.2.3 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification / Join MBS multicast session / Rejected / MBS session has not started or will not start soon | Huawei,Hisilicon |  |  | 1 | 0% | 0% |  | 0% | 0%
85 | Y | 38.523-1 | 14.2.5.2.4 | MBS Multicast/ Session management / UE-requested PDU session modification / Leave MBS multicast session / Accepted | Huawei,Hisilicon |  |  | 1 | 0% | 0% |  | 0% | 0%
78 |  | 38.523-1 | 14.2.5.3 | MBS Multicast/ Session management / UE-requested PDU session modification ->Void |  |  |  | 0
79 |  | 38.523-1 | 14.2.5.3.1 | MBS Multicast/ Session management / UE-requested PDU session modification / Leave MBS multicast session / Accepted -> Void(Move to 14.2.5.2.4) |  |  |  | 0
80 |  | 38.523-1 | 14.2.5.3.2 | MBS Multicast/ Session management / UE-requested PDU session modification / Join MBS multicast session/ Rejected / MBS session has not started or will not start soon ->Void(merge to 14.2.5.2.3) |  |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
29 |  | 38.523-2 | 4.1 | Applicability for MBS test cases |  | R5-227153 R5-231484 R5-233390 |  | 0.1 | 10% | 10% |  | 10% | 10%
30 |  | 38.523-2 | 4.2 | ICS for MBS test cases |  |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> |  |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on I6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.