## Slide 1: Time plan for defining MU and TT for RF tests
NTT DOCOMO, INC., Anritsu, CAICT, CMCC, Huawei, KDDI Corporation, Keysight Technologies UK Ltd, MVG Industries, PCTEST Engineering Lab, ROHDE & SCHWARZ
3GPP TSG-RAN WG5 Meeting #2-5G-NR R5-182092
Taoyuan, Taiwan, 9th – 13nd Apr 2018
Agenda item : 4.1.16
Document for : Discussion and Endorsement

## Slide 2: Introduction
Back Ground
  RAN5 has discussed defining MU and TT for NR (FR1, FR2) since RAN5#77 (Nov-18). However whole progress of this work is roughly estimated as 10 or 20% and much acceleration of the discussion is required to complete corresponding work on time (by RAN5#79 May-18). The purpose of this document is to define the time plan (milestone, action points, remaining issues, etc.) about MU and TT work and to progress RAN5 work.
  Defining MU and TT (test requirement) in 3GPP RAN5 is closely related to UE development, the regulation and Certification. Delay of the MU and TT work will directly affect launch of the 5G/NR service in the world. This situation doesn’t meet market demands and RAN5 need to progress this work systematically.
Purpose
  Purpose of this contribution is to clarify following aspects and to accelerate RAN5 MU/TT work for FR2 RF Tests.
    WF about how to define MU
    WF about how to define TT
    WF about how to update RAN5 specifications
    Remaining issues on MU/TT work
    Time plan about MU/TT work
  Moreover this document shares the MU/TT discussion during the RAN5#NR2 (Apr-18).

## Slide 3: MU/TT defining approach
RAN5 responsibility work
  [Step 3] Define MUs per following content.
    Test case, Metric, Environment, Test setup, Channel BW, Frequency range, aperture size
  [Step 4] Define TTs per following content.
    Test case, Metric, Environment, [Test setup], Channel BW, Frequency range, [aperture size]
  [Step 5] Define Test requirement (Test requirement = Minimum requirement + TT)
Step 1
Define Minimum requirement
Step 2
Define basic MU
(for MOP, REFSENS)
Step 3
Define MU for specific TCs
Step 4
Define TT for specific TCs
based on specific MU
Step 5
Define Test requirement
(Test req. = Min req. + TT)
RAN5 responsible
RAN4 responsible

## Slide 4: [MU] WF about how to define MU
Following table is the basic format which kind of MU to be calculated per TC.
  (Parameters)
    Environment, BW, Power level, Frequency range, aperture size, Test setup, DUT size
    Maximum number of the items per TC is 4. (Total of the items among RF tests is 88)
List of the items are summarized in the attached document.
  [Attached] List of the items to be calculated.xlsx
Specific parameter values for MU calculation
  Specific parameter values except for channel BW and Power level are clear.
  Specific values of channel BW and Power level depend on each TC.
Criteria to complete each TC
  RAN5 conclude MU work for each TC can be completed with agreement of MUs about 4 items.
Group | TC | Title | Metric | Environment | Bandwidth | Power level | Frequency range | Aperture size | DUT size | Test setup | MU
A | 6.2.1 | UE maximum output power | EIRP | NC | <= 400MHz | Max output > p > Mid power | FR2a | D<=5 cm | <= 15 cm | DFF | 
 |  |  |  |  |  |  |  | Any D | <= 15 cm | IFF | 
 |  |  |  |  |  |  | FR2b | D<=5 cm | <= 15 cm | DFF | 
 |  |  |  |  |  |  |  | Any D | <= 15 cm | IFF | 

## Slide 5: [MU] WF about how to define MU
Frequency range
  Derive the MU for the two frequency ranges FR2a and FR2b ranging from 22.65 – 31.1 GHz and 31.1 – 45.1 GHz, respectively. (endorsed in [4])
  Each MU contribution shall be derived for the upper and lower edge of each of the frequency ranges FR2a and FR2b. The maximum of the values at the edges of the respective frequency range shall be used for that frequency range. (endorsed in [4])
  RAN5 set both FR2a and FR2b as 1st priority to complete MU work.
Test setup / Aperture size
  RAN5 set DFF and IFF captured in TR 38.810 (v2.0.0) as 1st priority in terms of test setup.
  RAN5 set following 4 items as 1st priority.
    (FR2a, DFF, D<=5cm), (FR2a, IFF), (FR2b, DFF, D<=5cm), (FR2b, IFF)
  RAN5 define MU values for 1st priority TCs above as RAN5’s “MU threshold”.
    How to define MU threshold based on four MU values is TBD.
    In case MU of other item is larger than MU threshold, this item is not permitted as test method.

## Slide 6: [MU] Priority of the TCs
As described in [2], following TCs should be high prioritized in terms of interference on other systems.
  RAN5 set following 8 TCs as 2nd priority to complete MU work.
    1st priorities are Maximum output power and REFSENS (endorsed during the RAN5#78)
Clause | Title
6.3.2 | Transmit OFF power
6.4.1 | Frequency Error
6.5.1 | Occupied bandwidth
6.5.2.1 | Spectrum emission mask
6.5.2.2 | Adjacent Channel Leakage Ratio
6.5.3.1 | General spurious emissions
6.5.3.2 | Spurious emissions for UE co-existence
7.7 | Receiver Spurious emissions

## Slide 7: [MU] Remaining issues on MU work (inside RAN5)
Handling on Low/High PSD TCs (e.g. off power, Rx Spurious / Max input level)
  MU for some TCs is expected to become large due to Low/High PSD and RAN5 need to select solution for this.
    To Test with large relaxation
    To Test with test setup with smaller MU
    To avoid testing these TCs
  Action points
    RAN5 prepare some analyses about testability issue (e.g. MU calculation itself)
    RAN5 select any solution above.
Leverage of the RAN4’s MU
  RAN4’s MU is for MOP and REFSENS and RAN5 cannot reuse these analyses for some specific TCs.
    Occupied bandwidth, frequency error, Spurious etc.
Handling on Extreme condition (EC)
  Handling EC makes RAN5 MU larger.

## Slide 8: [MU] Remaining issues on MU work (related to RAN4)
Measurement grid (Method, Number of the points) is not defined in RAN4.
  Measurement grid has impact on MU calculation and defining Measurement grid during the RAN4#86-bis is required for RAN5’s MU work.
It is expected that additional test setups will be defined in TR 38.810 in the future.
  It is difficult for RAN5 to modify MU or TT after completing RAN5’s MU/TT work once.
  Additional test setup may not be taken into account to the TT.
Remaining issues related to RAN4 should be shared with RAN4 during RAN5#NR2.
  RAN5 send LS to RAN4 during RAN5#NR2.

## Slide 9: [MU] How to reflect MU analysis into the Specification (TS 38.521-2,3, TR 38.903)
This point is proposed in [5] and RAN5 can use this method.
  Format of the MU information in TS 38.521-2,3
    Define an Annex to specify MU limits (MU threshold) per test case. This MU limits are common for all testing methodologies. This annex can be similar as Annex F of TS 36.521-1.
    Define an Annex to specify applicability of permitted testing methodology per test requirement. This annex will contain a table describing per test requirement, permitted test methodologies as a function of DUT antenna implementation details available. The format of this table is proposed in R5-181931.
    Include references to TR 38.903 for details on MU limit calculation in above annexes.
  Format of the MU information in TR 38.903
    Sections per testing methodology
      Sub-section for MU factor definition describing possible values of such parameter to be used in final MU calculation. Similar to Annex B.1.X.4 in TR 38.810.
      Sub-section for MU factors affecting a given metric (for example EIRP) including a table listing MU factors with references to MU factors definition sub-section. As Annex B.1.X.2 in TR 38.810.
      Sub-section for MU calculation/assessment per test requirement:
    Final section of MU threshold determination, indicating definition of MU threshold and references to the sections where its calculation can be found.

## Slide 10: [TT] WF about how to define TT
Test Frequency range
  RAN5 define TT separately per frequency (FR2a, FR2b) range like LTE.
Test setup
  Define one TT regardless of the test setups.
    Based on the following sentence captured in TR 38.810.
    Common test tolerances apply for all test methods addressing the same test requirement.
  How to define representative TT among some test setup is TBD.
Aperture size
  A single TT value valid for D ≤ 15cm is determined from the MU values for D ≤ 5cm and 5cm < D ≤ 15cm. The details of the derivation procedure are TBD. (Noted in [4])
  Define one TT regardless of the aperture sizes.
  How to define representative TT among some aperture size is TBD.

## Slide 11: [TT] WF about how to define TT
Define TT for each TC and frequency range only based on MU of (DFF, D<=5cm) and (IFF, Any D).
  Common TT regardless of the test setup and aperture size.
    (The values in the table are example.)
TC | Title | Metric | Environment | Bandwidth | Power level | Frequency range | Aperture size | DUT size | Test setup | MU | TT
6.2.1 | MOP | EIRP | NC | <= 400MHz | Max output > p > Mid power | FR2a | D<=5 cm | <= 15 cm | DFF | 6.0 | 3.0
 |  |  |  |  |  |  | Any D | <= 15 cm | IFF | 5.0 | 
 |  |  |  |  |  | FR2b | D<=5 cm | <= 15 cm | DFF | 7.0 | 3.5
 |  |  |  |  |  |  | Any D | <= 15 cm | IFF | 6.0 | 

## Slide 12: [MU/TT] Priority of the items
Priority of the MU
  1st priority (12 items)
    TC : Maximum output power (TRP, EIRP), REFSENS
    Item : (FR2a, DFF, D<=5cm), (FR2a, IFF), (FR2b, DFF, D<=5cm), (FR2b, IFF)
  2nd priority (<= 32 items)
    TC : 8 TCs in Proposed table.
    Item : (FR2a, DFF, D<=5cm), (FR2a, IFF), (FR2b, DFF, D<=5cm), (FR2b, IFF)
  3rd priority (<= 44 items)
    TC : Other TCs
    Item : (FR2a, DFF, D<=5cm), (FR2a, IFF), (FR2b, DFF, D<=5cm), (FR2b, IFF)
  Lowest Priority (These items should not be considered about time plan)
    TC : All TCs
    Items : Other than (FR2a, DFF, D<=5cm), (FR2a, IFF), (FR2b, DFF, D<=5cm), (FR2b, IFF)
Priority of the TT
  Basically Priority of the TT work depends on the progress of the MU work.
  RAN5 can treat TT of each item after completion about MU work of corresponding items.

## Slide 13: [MU/TT] Time plan of the work
Proposed Time plan
  Target of the 1st priority : [MU] RAN5#NR3 (Oct-18) [TT] RAN5#XX (Jan-19)
  Target of the 2nd priority : [MU] RAN5#82 (Feb-19) [TT] RAN5#83 (May-19)
  Target of the 3rd priority : [MU] RAN5#83 (May-19) [TT] RAN5#84 (Aug-19)
  Detailed estimation of the work can be re-defined during the RAN5#79 based on the progress of 1st priority.
Meeting | Dates | 1st Priority (12) |  | 2nd Priority (32) |  | 3rd Priority (44) | 
 |  | MU | TT | MU | TT | MU | TT
RAN5 #NR2 | Apr-18 |  |  |  |  |  | 
RAN5 #79 | May-18 |  |  |  |  |  | 
RAN5 #80 | Aug-18 |  |  |  |  |  | 
RAN5 #NR3 | Oct-18 |  |  |  |  |  | 
RAN5 #81 | Nov-18 |  |  |  |  |  | 
RAN5 #XX | Jan-19 |  |  |  |  |  | 
RAN5 #82 | Feb-19 |  |  |  |  |  | 
RAN5 #83 | May-19 |  |  |  |  |  | 
RAN5 #84 | Aug-19 |  |  |  |  |  | 

## Slide 14: [Example] Specific approach of the MU/TT work
Maximum output power case
Companies submit documents about MU calculation for each item.
  MU work for each TC can be regarded as completed if step 1 is completed.
  This information should be captured in TS 38.521-2,3 and TR 38.903.
RAN5 defines “MU threshold” per frequency range based on the MUs in step 1.
  In case other interested companies calculate MU for other items.
    If MU is lower than MU threshold : This item (setup) are regarded as permitted method.
    If MU is higher than MU threshold : This item (setup) cannot be permitted.
Define one TT based on MUs defined in table per frequency range.
  How to define TTs from MUs is TBD
TC | Title | Metric | Environment | Bandwidth | Power level | Frequency range | Aperture size | DUT size | Test setup | MU | TT
6.2.1 | MOP | EIRP | NC | <= 400MHz | Max output > p > Mid power | FR2a | D<=5 cm | <= 15 cm | DFF | 6.0 | 3.0
 |  |  |  |  |  |  | Any D | <= 15 cm | IFF | 5.0 | 
 |  |  |  |  |  | FR2b | D<=5 cm | <= 15 cm | DFF | 7.0 | 3.5
 |  |  |  |  |  |  | Any D | <= 15 cm | IFF | 6.0 | 

## Slide 15: Reference
During the RAN5#NR adhoc-2 Meeting (Apr-18) following documents about MU/TT were treated.
  [1] R5-181829 : Update of TR 38.903 to introduce information of FR2 MU and TT (Huawei)
  [2] R5-181865 : Priority of the RF test cases about MU and TT discussion (NTT DOCOMO, INC)
  [3] R5-182007 : Priority of the test setup about defining MU (NTT DOCOMO, INC)
  [4] R5-181901 : Basic assumptions for the FR2 MU and TT work (ROHDE & SCHWARZ)
  [5] R5-181928 : Discussion on MU in NR FR2 (Keysight Technologies UK Ltd)