## Slide 1: Proposal for update of RAN5 5G NR phases and targets
RAN5#2-5G-NR-Adhoc meeting R5-182095
Taoyuan, Taiwan, 9th-13th April 2018

## Slide 2: Introduction
RAN#79 plenary update
RAN5 Time plan for defining MU and TT for RF tests
Proposal for update of RAN5 phases and targets
Proposal for content of NSA Option 3 (EN-DC) Phases
Proposed way forward

## Slide 3
RAN#79 plenary updates (Ref:RP-180554)
Rel-15 schedule unchanged
  Architecture Option 3: ASN.1 Freeze March 2018
  Architecture Option 2: ASN.1 Freeze September 2018
  Architecture Option 5: ASN.1 Freeze September 2018 (only impacts LTE ASN.1)
Introduce Late Rel-15 Drop
  Follows Rel-15 completion by 6 months
  The late drop is to exclusively contain NR architecture options that were not completed by September ASN.1 drop
  Options 4, 7 are part of the late drop
  In case Option 5 is not completed by September ASN.1 drop, it will be part of the late drop
  NR-NR DC to be considered to be added to the late drop at RAN#80
  Band combinations which are not completed by June 2018 (other than NR-NR DC combinations) will be moved to Rel-16 band specifications, but continue to be release independent.

## Slide 4: Timeline (Ref:RP-180554)

## Slide 5
RAN5#2-5G-NR-Adhoc FR2 MU/TT timeplan (Ref:R5-182092)
Proposed Time plan for MU/TT
  Target of the 1st priority : RAN5#80 (Aug-18)
  Target of the 2nd priority : RAN5#81 (Nov-18)
  Target of the 3rd priority : RAN5#XX (Jan-19) or #82 (Feb-19)
Prirority 1 test cases (regulatory):
  6.2.1 Max Output Power 7.3 Ref Sensitivity
Priority 2 test cases:
  6.3.2 Transmit OFF power 6.4.1 Frequency Error
  6.5.1 Occupied bandwidth 6.5.2.1 Spectrum emission mask
  6.5.2.2 Adjacent Channel Leakage Ratio 6.5.3.1 General spurious emissions
  6.5.3.2 Spurious emissions for UE co-existence 7.7 Receiver Spurious emissions
Priority 3 test cases: all other test cases

## Slide 6
Proposal for update of RAN5 phases and targets
(based on RAN#79 updates and RAN5 MU/TT time plan)
RAN5#79 May-18
  NSA Option 3 (EN-DC) Phase 1 --- No change
RAN5#81 Nov-18
  SA Option 2 (SA NR) Phase 1 --- No change
  SA Option 5 (SA E-UTRA) Phase 1** --- No change
  NSA Option 3 (EN-DC) Phase 2 --- No change
RAN5#83 May-19
  SA Option 2 (SA NR) Phase 2 --- Added phase 2
  SA Option 5 (SA E-UTRA) Phase 2** --- Added phase 2
  NSA Option 7 (NGEN-DC) Phase 1* --- Moved 6 Months
  NSA Option 4 (NE-DC) Phase 1* --- Target date added
  NSA Option 3 (EN-DC) Phase 1 --- Added phase 3
  *ASN.1 late drop freeze March-19 **May be deferred 6 months if Option 5 will be moved from ASN.1 Freeze in Sept-18 to the late drop freeze March-19

## Slide 7
Included EN-DC configurations: LTE 1CC + NR FR1 1CC
INCLUDED:
  RF - TS 38.521-3, TS 38.522, TS 38.521-1*, TR 38.903, TR 38.905
    Prio 1: LTE+FR1 6.2.1B Max Output Power and 7.3B Ref Sensitivity
    Prio 2: All other LTE+FR1 Rx and Tx test cases
    Dependency: RAN4 progress until RAN4#87 (May-18)
  Protocol - TS 38.523-x
    Layer 2: NR MAC, RLC and PDCP test cases
    RRC: All RRC test cases
    NAS: All test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE+FR1 MCG+SCG and Split bearer testing
    Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
  UE test functions - TS 38.509
    UE test loop mode A, UE test loop mode B and UBF.
NOT INCLUDED:
  RF LTE+FR2 (TS 38.521-3)
  Demod/CSI reporting (TS 38.521-4)
  RRM (TS 38.533)
  IMS (TS 34.229-x)
  Positioning (TS 37.571-x)
*) TS 38.521-3 referenced clauses in TS 38.521-1
Proposal for NSA Option 3 (EN-DC) Phase 1 content
- Target RAN5#79 MAY-18

## Slide 8
Included EN-DC configurations: LTE xCC + NR FR1 1CC, where x>=1; and LTE 1CC + NR FR2 1CC
INCLUDED:
  RF - TS 38.521-3, TS 38.522, TS 38.521-1*, TS 38.521-2*, TR 38.903, TR 38.905 (*TS 38.521-3 referenced clauses in TS 38.521-x)
    LTE+FR1: Rx and Tx test cases not completed in Phase 1
    LTE+FR2: 6.2.1B Max Output Power and 7.3B Ref Sensitivity
    Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 MU/TT progress
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in Phase 1
    LTE xCC + NR FR1 1CC test cases
    IMS IR.92 EN-DC test cases
    Positioning EN-DC test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable FR2 testing (RF and protocol)
    Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
  UE test functions - TS 38.509
    SS-RSRPB UE reporting
NOT INCLUDED:
  RF LTE+FR2 for other test cases than 6.2.1B and 7.3B (TS 38.521-3)
  Demod/CSI reporting (TS 38.521-4)
  RRM (TS 38.533)
Proposal for NSA Option 3 (EN-DC) Phase 2 content
- Target RAN5#81 NOV-18

## Slide 9
Proposal for NSA Option 3 (EN-DC) Phase 3 content
- Target RAN5#83 MAY-19
Included EN-DC configurations: LTE xCC + NR FR1 yCC, where x,y>=1; and LTE 1CC + NR FR2 1CC
INCLUDED:
  RF - TS 38.521-3, TS 38.522, TS 38.521-1*, TS 38.521-2*, TR 38.903, TR 38.905 LTE+FR2 Rx and Tx test cases where MU/TT analysis completed**
  Demod/CSI reporting (TS 38.521-4)**
  RRM (TS 38.533)**
  ** Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 MU/TT progress
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in Phase 2
    LTE xCC + NR FR1 yCC test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable to enable LTE xCC + NR FR1 yCC test cases
    Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
  UE test functions - TS 38.509
    TBD if any new UE test functions needed
NOT INCLUDED:
  None
*TS 38.521-3 referenced clauses in TS 38.521-x)

## Slide 10
EN-DC Phase 2 (Opt 3)
EN-DC Phase 2: Target RAN5#79 Nov-18
  Included EN-DC configurations: LTE xCC + NR FR1 1CC, where x>=1; and LTE 1CC + NR FR2 1CC
  INCLUDED:
    RF - TS 38.521-3, TS 38.522, TS 38.521-1*, TS 38.521-2*, TR 38.903, TR 38.905 (*TS 38.521-3 referenced clauses in TS 38.521-x)
      LTE+FR1: Rx and Tx test cases not completed in Phase 1
      LTE+FR2: 6.2.1 Max Output Power and 7.3 Ref Sensitivity
      Dependency: RAN4 progress until RAN4#89 (Nov-18)
    Protocol - TS 38.523-1, TS 38.523-2, TS 38.523-3)
      Remaining test cases not completed in Phase 1
      LTE xCC + NR FR1 1CC test cases
    Test environment (TS 36.508, TS 38.508-1, TS 38.508-2)
      Common test environment to enable FR2
      Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
    UE test functions (TS 38.509)
      UE test loop mode A, UE test loop mode B and UBF.
  NOT INCLUDED:
    LTE xCCRF LTE+FR2 (TS 38.521-3)
    Demod/CSI reporting (TS 38.521-4)
    RRM (TS 38.533)
    IMS (TS 34.229-x)
    Positioning (TS 37.571-x)

## Slide 11: Proposed way forward
It is proposed that the details of the content for NSA Option 3 (EN-DC) phases and the overall target dates for SA Option 2, SA Option 5, NSA Option 7 and NSA Option 4 phases as described in this document is used as base for the update of the RAN5 5GS work plan. The proposed targets are illustrated below.