## TC
Test Case | Name | Assigned Company | Target | RAN4 Status | RAN4 expected completion | Prio
4.3.2.2.1 | EN-DC FR1 contention based random access | Anritsu | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.3.2.2.2 | EN-DC FR1 non-contention based random access | Anritsu | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.6.1.1 | EN-DC FR1 event-triggered reporting without gap in non-DRX | Bureau Veritas | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.6.1.2 | EN-DC FR1 event-triggered reporting without gap in DRX | Bureau Veritas | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.6.1.3 | EN-DC FR1 event-triggered reporting with gap in non-DRX | Huawei | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.6.1.4 | EN-DC FR1 event-triggered reporting with gap in DRX | Huawei | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.6.1.5 | EN-DC FR1 event-triggered reporting without gap in non-DRX with SSB time index detection | Huawei | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.6.1.6 | EN-DC FR1 event-triggered reporting with gap in non-DRX with SSB time index detection | Huawei | Opt 3: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
4.7.1.1.1 | EN-DC FR1 SS-RSRP absolute measurement accuracy | Rohde&Schwarz | Opt 3: RAN5#82 (Feb-19) | No RAN4 dependency | Done | 1
4.7.1.1.2 | EN-DC FR1 SS-RSRP relative measurement accuracy | Rohde&Schwarz | Opt 3: RAN5#82 (Feb-19) | No RAN4 dependency | Done | 1
6.3.2.2.1 | NR SA FR1 contention based random access | Anritsu | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.3.2.2.2 | NR SA FR1 non-contention based random access | Anritsu | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.6.1.1 | NR SA FR1 event-triggered reporting without gap in non-DRX | Huawei | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.6.1.2 | NR SA FR1 event-triggered reporting without gap in DRX | Huawei | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.6.1.3 | NR SA FR1 event-triggered reporting with gap in non-DRX | Huawei | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.6.1.4 | NR SA FR1 event-triggered reporting with gap in DRX | Huawei | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.6.1.5 | NR SA FR1 event-triggered reporting without gap in non-DRX with SSB index reading | Huawei | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.6.1.6 | NR SA FR1 event-triggered reporting with gap in non-DRX with SSB index reading | Huawei | Opt 2: RAN5#82 (Feb-19) | No square brackets in Test requirements |  | 1
6.7.1.1.1 | NR SA FR1 SS-RSRP absolute measurement accuracy | Rohde&Schwarz | Opt 2: RAN5#82 (Feb-19) | No RAN4 dependency | Done | 1
6.7.1.1.2 | NR SA FR1 SS-RSRP relative measurement accuracy | Rohde&Schwarz | Opt 2: RAN5#82 (Feb-19) | No RAN4 dependency | Done | 1
4.5.1.1 | EN-DC FR1 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Qualcomm | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 1
4.5.1.2 | EN-DC FR1 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Qualcomm | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 1
4.5.1.3 | EN-DC FR1 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Qualcomm | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 1
4.5.1.4 | EN-DC FR1 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Qualcomm | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 1
6.5.1.1 | NR SA FR1 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Qualcomm | Opt 2: RAN5#82 (Feb-19) | Several [.] and editor's notes |  | 1
6.5.1.2 | NR SA FR1 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Qualcomm | Opt 2: RAN5#82 (Feb-19) | Several [.] and editor's notes |  | 1
6.5.1.3 | NR SA FR1 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Qualcomm | Opt 2: RAN5#82 (Feb-19) | Several [.] and editor's notes |  | 1
6.5.1.4 | NR SA FR1 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Qualcomm | Opt 2: RAN5#82 (Feb-19) | Several [.] and editor's notes |  | 1
6.6.3.1 | NR SA FR1 – E-UTRAN event-triggered reporting in non-DRX | Bureau Veritas | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 1
4.4.3.1 | EN-DC FR1 timing advance adjustment accuracy | Qualcomm | Opt 3: RAN5#82 (Feb-19) | TRS TBD |  | 1
6.4.3.1 | NR SA FR1 timing advance adjustment accuracy | Qualcomm | Opt 2: RAN5#82 (Feb-19) | TRS TBD |  | 1
4.4.1.1 | EN-DC FR1 UE transmit timing accuracy | Qualcomm | Opt 3: RAN5#82 (Feb-19) | 2.DRX config TBD |  | 2
4.5.2.1 | EN-DC FR1 interruptions at transitions between active and non-active during DRX in synchronous EN-DC |  | Opt 3: RAN5#82 (Feb-19) | Powers in [.] |  | 2
4.5.2.2 | EN-DC FR1 interruptions at transitions between active and non-active during DRX in asynchronous EN-DC |  | Opt 3: RAN5#82 (Feb-19) | Powers in [.] |  | 2
4.5.2.3 | EN-DC FR1 interruptions during measurements on deactivated NR SCC in synchronous EN-DC |  | Opt 3: RAN5#82 (Feb-19) | Powers in [.] |  | 2
4.5.2.4 | EN-DC FR1 interruptions during measurements on deactivated NR SCC in asynchronous EN-DC |  | Opt 3: RAN5#82 (Feb-19) | Powers in [.] |  | 2
4.5.2.5 | EN-DC FR1 interruptions during measurements on deactivated E-UTRAN SCC in synchronous EN-DC |  | Opt 3: RAN5#82 (Feb-19) | Powers in [.] |  | 2
4.5.2.6 | EN-DC FR1 interruptions during measurements on deactivated E-UTRAN SCC in asynchronous EN-DC |  | Opt 3: RAN5#82 (Feb-19) | Powers in [.] |  | 2
4.5.2.7 | EN-DC FR1 interruptions at UL carrier RRC reconfiguration for NR Scell | Huawei | Opt 3: RAN5#82 (Feb-19) | PUSCH and PUCCH TBD, Cell 3 TBD |  | 2
4.5.3.1 | EN-DC FR1 SCell activation and deactivation of known SCell in non-DRX for 160ms SCell measurement cycle | Bureau Veritas | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 2
4.5.3.2 | EN-DC FR1 SCell activation and deactivation of known Scell in non-DRX for 320ms SCell measurement cycle | Bureau Veritas | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 2
4.5.3.3 | EN-DC FR1 SCell activation and deactivation of unknown SCell in non-DRX | Bureau Veritas | Opt 3: RAN5#82 (Feb-19) | Several [.] |  | 2
4.7.1.2.1 | EN-DC FR1-FR1 SS-RSRP absolute measurement accuracy | Rohde&Schwarz | Opt 3: RAN5#82 (Feb-19) | Several TBD | 2019-02-01 | 2
4.7.1.2.2 | EN-DC FR1-FR1 SS-RSRP relative measurement accuracy | Rohde&Schwarz | Opt 3: RAN5#82 (Feb-19) | Several TBD | 2019-02-01 | 2
6.6.2.1 | NR SA FR1-FR1 event-triggered reporting in non-DRX | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.2 | NR SA FR1-FR1 event-triggered reporting in DRX | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.3 | NR SA FR1-FR2 event-triggered reporting in non-DRX | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.4 | NR SA FR1-FR2 event-triggered reporting in DRX | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.5 | NR SA FR1-FR1 event-triggered reporting in non-DRX with SSB time index detection | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.6 | NR SA FR1-FR1 event-triggered reporting in DRX with SSB time index detection | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.7 | NR SA FR1-FR2 event-triggered reporting in non-DRX with SSB time index detection | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.6.2.8 | NR SA FR1-FR2 event-triggered reporting in DRX with SSB time index detection | Ericsson | Opt 2: RAN5#82 (Feb-19) | Several TBD |  | 2
6.7.1.2.1 | NR SA FR1-FR1 SS-RSRP absolute measurement accuracy | Rohde&Schwarz | Opt 2: RAN5#82 (Feb-19) | Several TBD | 2019-02-01 | 2
6.7.1.2.2 | NR SA FR1-FR1 SS-RSRP relative measurement accuracy | Rohde&Schwarz | Opt 2: RAN5#82 (Feb-19) | Several TBD | 2019-02-01 | 2
4.6.2.1 | EN-DC FR1-FR1 event-triggered reporting in non-DRX | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.2 | EN-DC FR1-FR1 event-triggered reporting in DRX | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.3 | EN-DC FR1-FR2 event-triggered reporting in non-DRX | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.4 | EN-DC FR1-FR2 event-triggered reporting in DRX | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.5 | EN-DC FR1-FR1 event-triggered reporting in non-DRX with SSB time index detection | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.6 | EN-DC FR1-FR1 event-triggered reporting in DRX with SSB time index detection | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.7 | EN-DC FR1-FR2 event-triggered reporting in non-DRX with SSB time index detection | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2
4.6.2.8 | EN-DC FR1-FR2 event-triggered reporting in DRX with SSB time index detection | Ericsson | Opt 3: RAN5#82 (Feb-19) | T2 TBD |  | 2

## RMCs
PDSCH | Status | CORESET | Status | CSI-RS | Status | TDD UL/DL | Status | OCGN | Status | DRX | Status | PRACH | Status | BWP | Status | SSB | Status | SMTC | Status
SR.1.1 FDD | With [.] | CR.1.1 FDD | No [.] | CSI-RS.1.1 FDD | With TBD | TDDConf.1.1 | No [.] | OP.1 | Complete | DRX.1 | No [.] | PRACH.1 FR1 | No [.] | DLBWP.0.1 | No [.] | SSB.1 FR1 | No [.] | SMTC.1 | No [.]
SR.1.1 TDD | With [.] | CR.1.1 TDD | No [.] | CSI-RS.1.2 FDD | With TBD | TDDConf.2.1 | No [.] |  |  | DRX.2 | No [.] | PRACH.2 FR1 | No [.] | DLBWP.0.2 | No [.] | SSB.2 FR1 | No [.] | SMTC.2 | No [.]
SR.2.1 TDD | With [.] | CR.2.1 TDD | No [.] | CSI-RS.1.3 FDD | With TBD |  |  |  |  | DRX.3 | No [.] | PRACH.3 FR1 | No [.] | DLBWP.1.1 | No [.] | SSB.3 FR1 | No [.]
SR.3.1 TDD | With [.] | CR.3.1 TDD | No [.] | CSI-RS.1.1 TDD | With TBD | [6 empty] | PRACH.4 FR1 | No [.] | DLBWP.1.2 | No [.] | SSB.4 FR1 | No [.]
|  | CCR.1.1 FDD | No [.] | CSI-RS.1.2 TDD | With TBD | [6 empty] | PRACH.1 FR2 | No [.] | DLBWP.1.3 | No [.] | SSB.1 FR2 | No [.]
|  | CCR.1.1 TDD | No [.] | CSI-RS.1.3 TDD | With TBD | [6 empty] | PRACH.2 FR2 | No [.] | ULBWP.0.1 | No [.] | SSB.2 FR2 | No [.]
|  | CCR.2.1 TDD | No [.] | CSI-RS.2.1 TDD | With TBD | [6 empty] | PRACH.3 FR2 | No [.] | ULBWP.0.2 | No [.] | SSB.3 FR2 | No [.]
|  | CCR.3.1 TDD | No [.] | CSI-RS.2.2 TDD | With TBD | [8 empty] | ULBWP.1.1 | No [.] | SSB.4 FR2 | No [.]
|  |  |  | CSI-RS.2.3 TDD | With TBD | [8 empty] | ULBWP.1.2 | No [.]
|  |  |  | CSI-RS.3.1 TDD | With TBD | [8 empty] | ULBWP.1.3 | No [.]
|  |  |  | CSI-RS.3.2 TDD | With TBD
|  |  |  | CSI-RS.3.3 TDD | With TBD