## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: SS: System Simulator
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-15:
    Endorsed corrections to default UL Grants.
    Discussed potential updates to ASP NR_PDCP_DRB_Config_Parameters_Type.
  Rel-16:
    5G V2X: endorsed new NR Sidelink test models for RLC & PDCP testing.
    NR 2-step RACH: endorsed NR ASP updates to add support for 2-step Random Access type with MSGA.
  Rel-17:
    MUSIM: endorsed initial test model for MUSIM support over NR/5GC.
    UDC: endorsed NR ASP updates to add support for NR UDC.
  Prose CRs to TS 38.523-3 submitted at RAN5#99 for the above.
Test models & ASPs design Progress at TTCN Workshop #61 (20th Apr’23)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – NB-IoT:
  Rel-17 NTN: endorsed NTN test model & NB-IoT ASP updates for GSO support.
  Prose CR to TS 36.523-3 submitted at RAN5#99 for the above.
Test Models – LTE:
  Rel-13 eMTC: endorsed updates to latency procedure to accommodate CatM1 UEs.
  Prose CR to TS 36.523-3 submitted at RAN5#99 for the above.
Test Models – IMS:
  Endorsed removal of explicit encoding rule “XML” for alias definitions.
Test Models – POS:
  Endorsed updates to LTE POS & NR POS ASPs to add explicit PRS power level configuration.
RAN5 TTCN Workshop #61 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=60536
Test models & ASPs design Progress at TTCN Workshop #61 (20th Apr’23)

## Slide 5: TTCN development Progress for period: Feb to May’23
Completed:
  5G Rel-16:
    RRC DL segmentation
  IMS over NR/5GC:
    Rel-16 IMS eCall
Progressed 5G:
  5G Rel-15:
    NE-DC
  5G Rel-16:
    MR-DC & NR CA enhancements
    V2X
  5G Rel-17:
    RedCap
    Network slicing enhancements phase2
  IMS over NR/5GC:
    Rel-15 IMS emergency
Started:
  5G Rel-17:
    5GC eCPSOR
    SON/MDT enhancements
  POS:
    Rel-17 NR positioning enhancements
Progressed 4G:
  Mission Critical over LTE:
    MCVideo
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 22nd Feb --> 17th May’23
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
VoLTE (GSMA IR.92) | Rel-8 | 103 | 42 / 42 | = | 
SMS over IMS | Rel-8 | 128 | 2 / 2 | = | 
IMS emergency over LTE | Rel-9 | 154 | 31 / 31 | = | 
LTE / UMTS Inter-RAT | Rel-9 | 167 | 11 / 11 | = | 
LTE / GERAN Inter-RAT | Rel-9 | 168 | 3 / 3 | = | 
VoWiFi (GSMA IR.51) | Rel-11 | 267 | 17 / 17 | = | 
VoLTE over CAT-M1 (GSMA NG.108) | Rel-13 | 283 | 10 / 10 | = | 
SMS over CAT-M1 (GSMA NG.108) | Rel-13 | 128M | 1 / 1 | = | 
NR RACS | Rel-16 | 520 | 8 / 8 | +1 | 
5G network slicing enhancements | Rel-16 | 523 | 5 / 5 | +1 | 
Additional protocol test cases | Rel-16 | 529 | 1 / 1 | +1 | TC 11.3.10
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 22nd Feb --> 17th May’23
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 94 / 102 | +1 | +1 under verification
NR/5GC access stratum | Rel-15 | 503 | 150 / 160 | +3 | Prio1: 91/95 ; Prio2: 59/65
NR/5GC NR-DC | Rel-15 | 503 | 11 / 13 | +1 | Prio1: 9/11 ; Prio2: 2/2
NR/5GC NAS | Rel-15 | 504 | 75 / 76 | = | Prio1: 35/35 ; Prio2: 40/41
NR/5GC NR CA | Rel-15 | 510 | 30 / 32 | = | Prio1: 14/15 ; Prio2: 16/17
EN-DC NR CA | Rel-15 | 512 | 13 / 17 | +3 | Prio1: 12/13 ; Prio2: 1/4
Inter-RAT SON/MDT | Rel-16 | none | 3 / 4 | = | +1 under verification
5G private network - SNPN | Rel-16 | 518 | 6 / 7 | +1 | Prio1: 3/3 ; Prio2: 3/4
NR mobility enhancements | Rel-16 | 522 | 10 / 13 | +4 | Prio1: 5/7 ; Prio2: 5/6
NR UE power saving | Rel-16 | none | 1 / 9 | = | +1 under verification
MR-DC & NR CA enhancements | Rel-16 | none | 3 / 29 | +1 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 22nd Feb --> 17th May’23
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166 | 15 / 27 | = | +2 under verification
MCPTT over LTE | Rel-14 | 288, RFT-153 | 37 / 51 | = | Prio1: 32/42 ; Prio2: 5/9
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE | Rel-14 | 329, RFT-153 | 4 / 28 | = | Prio1: 3/15 ; Prio2: 1/13
MCPTT enh. over LTE | Rel-15 | 330, RFT-153 | 2 / 22 | = | Prio1: 2/15 ; Prio2: 0/7
IMS over NR/5GC | Rel-15 | 505 | 93 / 96 | = | Prio1: 21/21 ; Prio2: 72/77 +1 under verification
5G Positioning | Rel-15 | 506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 22nd Feb --> 17th May’23
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | WI-088 | 13 / 14 | = | Left: TC 8.4.5.4(LTE to HRPD HO)
LTE/C2K Inter-RAT | Rel-10 | WI-180 | 1 / 2 | = | Left: TC 8.6.5.3(MDT RLF logging)
LTE/GERAN Inter-RAT | Rel-10 | WI-182/184 | 1 / 2 | = | Left: TC 8.6.5.2(MDT RLF logging)
CA intra-band contiguous | Rel-11 | WI-162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | WI-245 | 6 / 9 | = | 
eDRX | Rel-13 | WI-253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | WI-254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | WI-254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | WI-257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | WI-272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | WI-295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
L2 latency reduction | Rel-14 | WI-306 | 1 / 4 | = | 
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 22nd Feb --> 17th May’23
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
IMS eCall over LTE (36.523) | Rel-14 | 298 | 3 / 9 | +2 | 
Reduced capability NR UE (RedCap) | Rel-17 | 530 | 3 / 6 | +3 | Prio1: 3/4 ; Prio2: 0/2 +1 under verification
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
5G network slicing enhancements – Phase 2 | Rel-17 | none | 0 / 13 |  | +2 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2022 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | TTCN Status (as of May’23) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q3’23 | 34 | Q1’22-Q3’23 | 1 | 73% (@iwd-23wk12)
5G V2X with NR sidelink | Rel-16 | N,L | Q4’23 | 72 | Q4’20-Q4’23 | 2 | 40% (@iwd-23wk12)
MR-DC & NR CA enhancements | Rel-16 | N,L | Q2’23 | 29 | Q1’22-Q2’23 | 1 | 65% (@iwd-23wk12)
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q4’23 | 15 | Q1’22-Q4’23 | 2 | Not started
IMS eCall over NR | Rel-16 | N | Q1’23 | 20 | Q3’21-Q1’23 | 0.5 | 100% (@iwd-23wk12)
NR positioning | Rel-16 | N | Q3’23 | 29 | Q2’21-Q3’23 | 0.2 | 90% (@iwd-22wk49)
NR MIMO enhancements | Rel-16 | N | Q4’22 | 1 | Q4’22-Q3’23 | 0.3 | Not started
NR 2-step RACH | Rel-16 | N | Q4’22 | 12 | Q3’22-Q2’23 | 1 | 10% ; Test Model work
NW slicing enhancements - Phase2 | Rel-17 | N | Q2’23 | 13 | Q4’22-Q2’23 | 0.5 | 70% (@iwd-23wk12)
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q4’23 | >11 | Q4’22-Q4’23 | 2 | 8% (@iwd-23wk12)
Reduced capability NR UE (RedCap) | Rel-17 | N | Q4’23 | >11 | Q4’22-Q4’23 | 1.5 | 72% (@iwd-23wk12)
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 43 | Q4’22-Q4’23 | 4 | Not started
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q4’23 | 1.5 | 5% ; Test Model work
NR UE power saving enhancements | Rel-17 | N | Q3’23 | 5 | Q4’22-Q4’23 | 1.5 | Not started
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 1.5 | Not started
NR sidelink enhancements | Rel-17 | N | Q3’23 | 2 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q3’23 | 19 | Q4’22-Q4’23 | 2 | Not started ; no prose
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’23-Q4’23 | 1 | 2023 total after RAN5#99: 4 new tests
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >348 |  | 75 | person-months
TTCN workplan 2023
Status of 2022 tasks carried over and maintenance
Notes: Note: TTCN of some features initially started in 2022 will only be completed in 2023 due to availability of prose late in CY2022, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2023 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | TTCN Status (as of May’23) / Comments
MCX enhancements | R15to16 | L | Q3’24 | 79 | Q1’23-Q4’24 | 4 | 45% (@iwd-23wk12)
Inter-system mobility between untrusted non-3GPP and 3GPP | Rel-15 | L,N | Q2’23 | 7 | Q1’23-Q4’23 | 3 | Not started
5G access traffic steering, switch and splitting | Rel-16 | N | Q2’23 | 7 | Q1’23-Q4’23 | 1.5 | Not started
NB-IoT/eMTC for non-terrestrial networks (NTN) | Rel-17 | L | Q3’23 | >14 | Q1’23-Q4’23 | 3 | 5% ; Test Model work
5G control plane steering of roaming for UE in connected mode enhancements (CP SOR) | Rel-17 | N | Q1’23 | 6 | Q1’23-Q2’23 | 1 | 80% (@iwd-23wk12)
NR UL data compression (UDC) | Rel-17 | N | Q2’23 | 9 | Q1’23-Q3’23 | 2 | 5% ; Test Model work
NR industrial IoT and URLLC enhancements | Rel-17 | N | Q4’23 | 6 | Q1’23-Q4’23 | 1.5 | Not started
User plane integrity protection for EPC (UPIP) | Rel-17 | L,N | Q2’23 | 9 | Q1’23-Q3’23 | 1.5 | Not started ; no prose
NR coverage enhancements | Rel-17 | N | Q4’23 | 9 | Q1’23-Q4’23 | 1.5 | Not started ; no prose
NR small data transmissions in INACTIVE state | Rel-17 | N | Q3’23 | 8 | Q1’23-Q4’23 | 1.5 | Not started
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’23 | >22 | Q1’23-Q1’24 | 3 | Not started ; no prose
5G non-public network enhancements | Rel-17 | N | Q4’23 | 17 | Q1’23-Q1’24 | 2 | Not started ; no prose
NR QoE management and optimizations | Rel-17 | N | Q1’24 | 4 | Q1’23-Q1’24 | 1 | Not started ; no prose
NR MIMO further enhancements | Rel-17 | N | Q4’23 | 3 | Q1’23-Q1’24 | 1 | Not started ; no prose
NR positioning enhancements | Rel-17 | N | Q2’24 | 3 | Q1’23-Q3’24 | 1 | Not started ; no prose
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | 17% (@iwd-22wk49)
Total: |  |  |  | >203 |  | 29 | person-months
TTCN workplan 2023
Status of new 2023 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2023 workload is estimated at 104 person-months (pm), see previous slides.
PCG#49/OP#48 approved the 3GPP funding of 58 pm for 2023 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2023.
Current commitments for 2023 are as follows:
3GPP companies / 3GPP MRPs committed to provide 20 pm as voluntary contributions for 2023 TTCN development.
Total resources of 104 pm  no estimated funding gap.
TTCN funding 2023
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#49/OP#48 approved (decision OP48/05)
CTIA/PTCRB | 12 | NE-DC, NR IIoT/URLLC, MCX, RedCap
GCF | 12 | NR V2X, NR 2-step RACH, NR Rel-17 enh., RedCap, MCX
Qualcomm | 2 | NR-U, SDT, NTN-IoT
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Anritsu | 1 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | NTN-IoT
Total: | 20 | 

## Slide 14: Annexes

## Slide 15: TTCN deliveries and baseline 2023 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and four TTCN-3 full deliveries.
No type definitions baseline upgrade planned in 2023.
  Note: Rel-18 ASN.1 freeze scheduled by 3GPP in June 2024.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk05 |  |  | 03-Feb |  | GCF CAG#73 (7-9 Feb)
wk07 |  |  | 17-Feb |  | PTCRB PVG#100 (21-23 Feb)
wk12 | 24-Mar | 20-Mar | 24-Mar | TTCN-3 | 
wk16 |  |  | 21-Apr |  | GCF CAG#74 (25-28 Apr)
wk19 |  |  | 12-May |  | PTCRB PVG#101 (16-18 May)
wk24 | 16-Jun | 12-Jun | 16-Jun | TTCN-3 | 
wk29 |  |  | 21-Jul |  | GCF CAG#75 (25-27 Jul)
wk32 |  |  | 11-Aug |  | PTCRB PVG#102 (15-17 Aug)
wk37 | 15-Sep | 11-Sep | 15-Sep | TTCN-3 | 
wk41 |  |  | 13-Oct |  | GCF CAG#76 (17-19 Oct)
wk44 |  |  | 03-Nov |  | PTCRB PVG#103 (7-9 Nov)
wk48 | 30-Nov | 27-Nov |  | TTCN2 (FDD) | 
wk48 | 01-Dec | 27-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 08-Dec | 04-Dec | 08-Dec | TTCN-3 | 

## Slide 16
2024 Potential Candidate | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | Work Item Code / Status
Further MR-DC enhancement | Rel-17 | N | Q1’24 | FFS | FFS | FFS | LTE_NR_DC_enh2-UEConTest
Uncrewed aerial systems connectivity, identification and tracking | Rel-17 | N | Q4’24 | FFS | FFS | FFS | ID_UAS-UEConTest
IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS | Rel-17 | N,L | Q1’24 | FFS | FFS | FFS | ING_5GS-UEConTest / New
IMS data channel | Rel-17 | N,L | Q3’23 | FFS | FFS | FFS | ING_5GS-UEConTest / New
TTCN workplan: 2024 early candidates WIs with no 2023 budget, candidate for 2024 budgeting
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.