## Cover sheet
3GPP TSG RAN WG5#101 | [8 empty] | R5-236087
Chicago, US, 13-17 Nov, 2023
Agenda Item: | 7.5.2
Source: | Nokia
Title: | WP UE Conformance – High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands
Work item code: | LTE_NR_HPUE_FWVM_R18-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
This Work Item is to develop measurement procedures for a new feature to enable HPUE (power class 1) for the bands supporting +31 dBm corresponding to WID (1000059) on High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands. This work item will cover RF conformance test specifications. At the RAN#100 meeting in Jun 2023 the Rel-18 RAN5 work item was approved [1] and revised in [2] at RAN#101 in Sep 2023. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core work item. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 18% | 2 (+2) | 16 (+5)
Completion Compensation |  | 1.08%
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed configurations | Number of new configurations | Comments
SA Option 2 (SA NR) (FR1) |  | 16.9% (-1.1%) | 2 (+2) | 16 (+5)
FR1 |  | 16.9% (-1.1%) | 2 (+2) | 16 (+5)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed PC1 configurations | Number of new PC1 configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NR HPUE (PC1) FR1 configurations
HPUE (PC1) FR1 single band
HPUE (PC1) FR1 single band | PC1 FR1 single band
5 References
[1] RP-230869 [2] RP-231613 | New WID on UE Conformance - High power UE (power class 2) for NR FR1 FDD single band Revised WID on UE Conformance - High power UE (power class 2) for NR FR1 FDD single band
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance – High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [7 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NR_HPUE_FWVM_R18-UEConTest | [14 empty] | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [14 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 36.521-2: UE capabilities LTE | 36.521-1: LTE RF | 38.521-1: NR RF | 38.522: Test case applicability | 36.905: LTE Test point analysis | 38.905: NR Test point analysis
WP Resp: |  | Tuomo Säynäjäkangas, Nokia |  |  | tuomo.saynajakangas@nokia.com | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Frequency band | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
16.9% (-1.1%)
18
16 (+5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS | TS STATUS INPUT
HPUE (PC1) FR1 single band
1 | Y | PC1 LTE FR1 FDD single band | 5 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start after the RAN4 band is completed. | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | Y | PC1 LTE FR1 FDD single band | 12 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:completed, RAN5 testing shall only start when interested deployer indicated in RAN5 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3 | Y | PC1 LTE FR1 FDD single band | 13 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start after the RAN4 band is completed. | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Y | PC1 NR FR1 FDD single band | n5 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start after the RAN4 band is completed. | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | Y | PC1 NR FR1 FDD single band | n13 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start after the RAN4 band is completed. | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | Y | PC1 NR FR1 FDD single band | n26 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start after the RAN4 band is completed. | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Y | PC1 NR FR1 TDD single band | n41 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start after the RAN4 band is completed. | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | Y | PC1 NR FR1 FDD single band | n71 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:completed, RAN5 testing shall only start when interested deployer indicated in RAN5 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | Y | PC1 NR FR1 TDD single band | n77 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:completed, RAN5 testing shall only start when interested deployer indicated in RAN5 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | Y | PC1 NR FR1 FDD single band | n85 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:completed, RAN5 testing shall only start when interested deployer indicated in RAN5. Band n85 is not specified in RAN5 specifications | 1
11 | Y | PC1 NR FR1 FDD single band | n100 | Transmitter requirements and test frequencies | New PC1 Config | UIC | Nokia | Completed | RAN5#101 (Nov-23) | R5-235861, R5-235635, R5-236090 | Changes needed only for 38.521-1 and 38.508-2 | 1 | 100% (+25%) | 100% (+25%) |  | 100% |  | 100% |  |  | 100%
12 | Y | PC1 NR FR1 TDD single band | n101 | Transmitter requirements and test frequencies | New PC1 Config | UIC | Nokia | Completed | RAN5#101 (Nov-23) | R5-235861, R5-235635, R5-236090 | Changes needed only for 38.521-1 and 38.508-2 | 1 | 100% (+25%) | 100% (+25%) |  | 100% |  | 100% |  |  | 100%
13 | Y | PC1 NR FR1 TDD single band | n28 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start when interested deployer indicated in RAN5 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | Y | PC1 NR FR1 TDD single band | n78 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:ongoing, RAN5 testing shall only start when interested deployer indicated in RAN6 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | Y | PC1 NR FR1 TDD single band | n7 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:new, RAN5 testing shall only start when interested deployer indicated in RAN5 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | Y | PC1 NR FR1 TDD single band | n25 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:new, RAN5 testing shall only start when interested deployer indicated in RAN6 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17 | Y | PC1 NR FR1 TDD single band | n66 |  | New PC1 Config |  |  | Pending | TBD |  | Note:RAN4 status:new, RAN5 testing shall only start when interested deployer indicated in RAN7 | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).