## Cover sheet
3GPP TSG-RAN5 Meeting #101 | [10 empty] | R5-236406
Chicago, USA, 13th Nov 2023 - 17th Nov 2023
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon, CMCC
Title: | WP UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects
Work item code: | NR_MBS_5MBS_5MBUSA-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
3GPP Rel-17 has specified the feature support of multicast and broadcast services (MBS) over 5GS. The objective of UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects work item is to provide conformance test specifications for the core requirements of Rel-17, including CT aspects of NR MBS, Security Aspects of NR MBS, and RAN aspects of NR MBS. This work item will cover Protocol conformance test specifications with NR-MBS operation. At the RAN#95e meeting in March 2022 the Rel-17 RAN5 work item for UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+9%) | 45 (+44) | 45
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+9.3%) | 45 (+44) | 45
FR1 |  | 100% (+1.2%) | 45 | 45
FR2 |  | 100% (+17.4%) | 45 (+44) | 45
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+12.8%) |  |  | 100% (+12.8%) |  |  | 100% (+12.8%)
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
UE specific test functions | 38.509 | 100% |  |  | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+9.9%) | 45 (+44) | 45 | 100% | 45 | 45 | 100% (+19.9%) | 45 (+44) | 45
Applicability Protocol test cases | 38.523-2 | 100% (+45%) |  |  | 100% (+45%) |  |  | 100% (+45%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-220423 | New WID on UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects | [9 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MBS_5MBS_5MBUSA-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of Rel-17, including CT aspects of NR MBS, Security Aspects of NR MBS, and RAN aspects of NR MBS. | [11 empty] | vs Area
WP Resp: |  | Zhao Ya(Huawei) |  |  | zhaoya@hisilicon.com |  |  |  |  | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[13 empty] | 100% (+1.2%) | 100% (+17.4%)
[13 empty] | 63 | 63
[13 empty] | 52.5 | 52.5
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TBD
1 |  | 38.508-1 | 4.3.6.1 | Downlink physical layer parameters for MBS test | To add Default configuration for DCI scheduling MBS, i.e. DCI format 4_0/4_1/4_2 | Huawei,Hisilicon | R5-224740 R5-224741 R5-225280 R5-227142 R5-234457 R5-235313 |  | 0.1 | 100% | 100% |  | 100% | 100%
2 |  | 38.508-1 | 4.4.3.1.2 | SI combination for MBS test | To add SI combination for MBS test | Huawei,Hisilicon | R5-227138 |  | 0.1 | 100% | 100% |  | 100% | 100%
3 |  | 38.508-1 | 4.4.3.1.2 | Scheduling of SIB20 and SIB21 for MBS test | To add Scheduling of SIB20 and SIB21 for MBS test | Huawei,Hisilicon | R5-227138 |  | 0.5 | 100% | 100% |  | 100% | 100%
4 |  | 38.508-1 | 4.6.2 | System information blocks | To update SIBs related to MBS test, i.e. SIB20 and SIB21[Ref: 38.331 cl. 6.3.1] | Huawei,Hisilicon | R5-225326 R5-225327 R5-232946 |  | 0.5 | 100% | 100% |  | 100% | 100%
81 |  | 38.508-1 | 4.6.1 | Contents of RRC messages | To update RRCMessage definitions related to MBS [Ref: 38.331 cl. 6.2.2] | Huawei,Hisilicon | R5-225328 R5-225329 R5-227507 R5-231468 R5-235415 |  | 0.5 | 100% | 100% |  | 100% | 100%
5 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | To update RRC IEs related to MBS [Ref: 38.331 cl. 6.3.2] | Huawei,Hisilicon | R5-224817 R5-227509 R5-227512 R5-231470 R5-231471 R5-231472 R5-233383 R5-234459 R5-235415 |  | 0.5 | 100% | 100% |  | 100% | 100%
6 |  | 38.508-1 | 4.6.X | MBS information elements | To add MBS ralated IEs used in RRC messages [Ref: 38.331 cl. 6.3.6] | Huawei,Hisilicon | R5-225330 R5-227139 R5-227508 |  | 1 | 100% (+50%) | 100% (+50%) |  | 100% | 100%
7 |  | 38.508-1 | 4.7.2 | Contents of 5GSM messages | To Update MBS related parameters into 5GSM message | Huawei,Hisilicon | R5-225180 R5-231469 |  | 0.5 | 100% | 100% |  | 100% | 100%
8 |  | 38.508-1 | 4.8.4 | DNN/APN configurations | To add DNN/APN configurations for the MBS | Huawei,Hisilicon | R5-227510 |  | 0.5 | 100% | 100% |  | 100% | 100%
9 |  | 38.508-1 | 4.9 | Test procedures | To add test procedures for MBS test | Huawei,Hisilicon | R5-225325 R5-227511 R5-231467 R5-233382 |  | 0.5 | 100% (+20%) | 100% (+20%) |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TBD
10 |  | 38.508-2 | <Clause> | PICs for MBS testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in protocol test cases. | Huawei,Hisilicon | R5-223105 R5-227513 R5-231473 R5-232947 R5-234461 |  | 0.1 | 100% | 100% |  | 100% | 100%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TBD
11 |  | 38.509 | 5.2 | Test mode for MBS | To add test mode C related description | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
12 |  | 38.509 | 5.3 | Loop back function for MBS | To add Loop back mode C related description | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
13 |  | 38.509 | 5.9 | Test protocal procedure for MBS | To add paclet counter reporting procedure for MBS | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
14 |  | 38.509 | 6.9 | TMC message for MBS | To add TMC message used in MBS packet counter reporting procedure | Huawei,Hisilicon | R5-225331 R5-227514 |  | 0.5 | 100% | 100% |  | 100% | 100%
15 |  | 38.509 | 7.1 | State variables for MBS | To add State variables for Loop back mode C and MBS packet counter | Huawei,Hisilicon | R5-225331 |  | 0.5 | 100% | 100% |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TBD
16 |  | 38.523-1 | 14 | MBS | New sub-clause header |  |  |  | 0
17 |  | 38.523-1 | 14.1 | MBS Broadcast | New sub-clause header |  |  |  | 0
18 |  | 38.523-1 | 14.1.1 | MBS Broadcast/ MCCH Information Acquisition | New sub-clause header |  |  |  | 0
19 | Y | 38.523-1 | 14.1.1.1 | MBS Broadcast/ MCCH Information Acquisition/ entering the cell providing SIB20 | TP1:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in switched off state and interested to receive MBS broadcast services. WHEN: UE is switched on and camped on a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception TP2:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_IDLE state and receiving MBS broadcast services. WHEN: UE reselects to a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. TP3:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_INACTIVE state and receiving MBS broadcast services. WHEN: UE reselects to a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. TP4:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_CONNECTED state and receiving MBS broadcast services. WHEN: UE handovers to a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. TP5:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE received SIB20 in a cell. WHEN: MCCH is only scheduled in the slot indicated by mcch-WindowStartSlot THEN: UE acquires the MBSBroadcastConfiguration message in the slot indicated by mcch-WindowStartSlot TP6:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE received SIB20 in a cell WHEN: MCCH is scheduled starting from the slot indicated by mcch-WindowStartSlot and during mcch-WindowDuration (larger than 1 slot) THEN: UE acquires the MBSBroadcastConfiguration message starting from the slot indicated by mcch-WindowStartSlot and during mcch-WindowDuration | Huawei,Hisilicon | R5-227130 R5-232948 R5-234463 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
20 | Y | 38.523-1 | 14.1.1.2 | MBS Broadcast/ MCCH Information Acquisition/ becoming interested to receive MBS broadcast services | TP1:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_IDLE state and camped on a cell providing SIB20 and did not interest to receive MBS broadcast services WHEN: UE is becomging interested to receive a MBS broadcast service THEN: UE acquires the MBSBroadcastConfiguration message and starts MBS reception for this MBS broadcast service. Note: 38.331 5.9.2.3 has no Timing requirement for this senario | CMCC | R5-233384 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
21 | Y | 38.523-1 | 14.1.1.3 | MBS Broadcast/ MCCH Information Acquisition/ MCCH Information change notification | TP1:[TS 38.331: 5.9.1.1, 5.9.1.2, 5.9.1.3, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC IDLE state and camped on a cell providing SIB20 and interested to receive MBS broadcast services WHEN: UE is receiving a notification that the MCCH information has changed due to the start of new MBS service(s) THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH from the slot in which the change notification was received TP2:[TS 38.331: 5.9.1.1, 5.9.1.2, 5.9.1.3, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC CONNECTED state and is receiving data via broadcast MRB WHEN:UE is receiving a notification that the MCCH information has changed due to MCCH information modification other than the change caused by the start of new MBS session(s) THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH from the slot in which the change notification was received | CMCC | R5-232951 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
83 |  | 38.523-1 | 14.1.1.4 | MBS Broadcast/ MCCH Information Acquisition/ receiving SIB20 of an SCell via dedicated signalling | New sub-clause header |  |  |  | 0
86 | Y | 38.523-1 | 14.1.1.4.1 | MBS Broadcast/ MCCH Information Acquisition/ receiving SIB20 of an SCell via dedicated signalling/ Intra-band Contiguous CA | TP1:[TS 38.331: 5.9.2.2] WITH: UE in NR RRC CONNECTED state and interested to receive MBS broadcast services and an Scell is added. WHEN: UE is receiving SIB20 for the Scell via dedicated signalling. THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH in the Scell at the next repetition period and starts MBS reception. | Huawei,Hisilicon | R5-232952 R5-234462 |  | 1 | 100% (+12.5%) | 100% (+12.5%) |  | 100% | 100%
87 | Y | 38.523-1 | 14.1.1.4.2 | MBS Broadcast/ MCCH Information Acquisition/ receiving SIB20 of an SCell via dedicated signalling / Inter-band CA | TP1:[TS 38.331: 5.9.2.2] WITH: UE in NR RRC CONNECTED state and interested to receive MBS broadcast services and an Scell is added. WHEN: UE is receiving SIB20 for the Scell via dedicated signalling. THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH in the Scell at the next repetition period and starts MBS reception. | Huawei,Hisilicon | R5-232952 R5-234462 |  | 1 | 100% (+12.5%) | 100% (+12.5%) |  | 100% | 100%
88 | Y | 38.523-1 | 14.1.1.4.3 | MBS Broadcast/ MCCH Information Acquisition/ receiving SIB20 of an SCell via dedicated signalling/ Intra-band non Contiguous CA | TP1:[TS 38.331: 5.9.2.2] WITH: UE in NR RRC CONNECTED state and interested to receive MBS broadcast services and an Scell is added. WHEN: UE is receiving SIB20 for the Scell via dedicated signalling. THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH in the Scell at the next repetition period and starts MBS reception. | Huawei,Hisilicon | R5-232952 R5-234462 |  | 1 | 100% (+12.5%) | 100% (+12.5%) |  | 100% | 100%
22 |  | 38.523-1 | 14.1.2 | MBS Broadcast/ Service Continuity | New sub-clause header |  |  |  | 0
23 | Y | 38.523-1 | 14.1.2.1 | MBS Broadcast/ Service Continuity/ Cell reselection/ frequency prioritization | TP1:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC IDLE state and is receiving MBS data via broadcast MRB and camped on a cell providing SIB20 and SIB21 indicating a MBS FSAI in mbs-FSAI-IntraFreq-r17 and the same MBS FSAI is also indicated for this MBS broadcast service in MBS User Service Description (USD) WHEN: an intra-frequency neighbour cell providing the MBS service and an inter-band neighbour cell not providing the MBS service becomes better than the serving cell THEN: UE performs cell reselection to the intra-frequency cell even if the inter-frequency cell is better and continues MBS reception TP2:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC IDLE state and interested to receive MBS broadcast service and camped on a cell not providing SIB20 WHEN: serving cell providing SIB21 indicating a MBS FSAI in mbs-FSAI-InterFreq-r17 and the same MBS FSAI is also indicated for this MBS broadcast service in MBS User Service Description (USD) THEN: UE performs cell reselection to the inter-frequency neighbour cell even if the serving cell is better and starts MBS reception TP3:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC INACTIVE state and is receiving MBS data via broadcast MRB and camped on a cell providing SIB20 and SIB21 indicating a MBS FSAI in mbs-FSAI-IntraFreq-r17 and the same MBS FSAI is also indicated for this MBS broadcast service in MBS User Service Description (USD) WHEN: an intra-frequency neighbour cell providing the MBS service and an inter-band neighbour cell not providing the MBS service becomes better than the serving cell THEN: UE performs cell reselection to the intra-frequency cell even if the inter-frequency cell is better and continues MBS reception | Huawei,Hisilicon | R5-227131 R5-232948 R5-236419 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
24 | Y | 38.523-1 | 14.1.2.2 | MBS Broadcast/ Service Continuity/ Handover/ MBS Interest Indication/ inter-frequency | TP1:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC CONNECTED state and is receiving MBS data via broadcast MRB and has not transmitted a MBSInterestIndication message WHEN: SIB21 provided in the serving cell indicates that the MBS service is available on a frequency of an inter-frequency neighbour cell and this frequency is also indicated in the USD for this session THEN: UE transmits a MBSInterestIndication message indicating interest in MBS reception on the frequency TP2:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message indicating interest in MBS reception on a frequency of an inter-frequency neighbour cell WHEN: 1s after the UE has transmitted the MBMSInterestIndication message the UE receives RRCReconfiguration message including a reconfigurationWithSync indicating a the NR frequency of the inter-frequency neighbour cell THEN: UE performs inter-frequency handover and starts MBS reception TP3:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message WHEN: UE handover from a cell not providing SIB20 to a cell providing SIB20 and SIB21 THEN: UE transmits a MBSInterestIndication message TP4:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message WHEN: The set of MBS broadcast frequencies of interest is different from mbs-FreqList included in the last transmission of the MBS Interest Indication THEN: UE transmits a MBSInterestIndication message indicating interest in MBS reception on the frequency TP5:[TS 38.331: 5.9.4,5.3.5.3 TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message WHEN: UE receives a RRCReconfiguration message including reconfigurationWithSync less than 1 second after the last transmission of an MBSInterestIndication message and target cell provides SIB21 THEN: UE re-transmit a MBSInterestIndication message | Huawei,Hisilicon | R5-227132 R5-232948 R5-235416 R5-236419 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
82 | Y | 38.523-1 | 14.1.2.3 | MBS Broadcast/ Service Continuity/ Handover/ MBS Interest Indication/ intra-frequency | TP1:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC CONNECTED state and is receiving MBS data via broadcast MRB and has not transmitted a MBSInterestIndication message WHEN: SIB21 provided in the serving cell indicates that the MBS service is available on a frequency of intra-frequency neighbour cell and the FSAI of this frequency is also indicated in the USD for this session THEN: UE transmits a MBSInterestIndication message indicating interest in MBS reception on the frequency TP2:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message indicating interest in MBS reception on a frequency of intra-frequency neighbour cell WHEN: 1s after the UE has transmitted the MBMSInterestIndication message the UE receives RRCReconfiguration message including a reconfigurationWithSync indicating a the NR frequency of the intra-frequency neighbour cell THEN: UE performs intra-frequency handover and continues to receive MBS reception TP3:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message WHEN: Since the last time the UE transmitted an MBS Interest Indication, UE handovers from a cell not providing SIB21 to a cell providing SIB21 THEN: UE transmits a MBSInterestIndication message TP4:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC_CONNECTED state and having transmitted a MBSInterestIndication message WHEN: The set of MBS broadcast services of interest is different from mbs-ServiceList included in the last transmission of the MBS Interest Indication THEN: UE transmits a MBSInterestIndication message indicating new mbs-ServiceList | Huawei,Hisilicon | R5-227133 R5-232948 R5-235416 R5-236419 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
25 |  | 38.523-1 | 14.1.3 | MBS Broadcast/ MAC | New sub-clause header |  |  |  | 0
26 | Y | 38.523-1 | 14.1.3.1 | MBS Broadcast/ MAC/ Correct HARQ process handling | TP1:[TS 38.321: 5.3.2.2] WITH: UE in NR RRC_IDLE state WHEN:UE receives data addressed to G-RNTI on broadcast MRB THEN: UE does not transmit the HARQ feedback for the MBS broadcast HARQ process TP2:[TS 38.321: 5.3.2.2] WITH: UE in NR RRC_IDLE state and is receiving data via broadcast MRB WHEN:UE receives a notification that the MCCH information has changed due to MCCH information modification other than the change caused by the start of new MBS session(s) THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH and UE does not transimit the HARQ feedback for the MBS broadcast HARQ process | Huawei,Hisilicon | R5-227134 R5-232948 R5-236421 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
27 | Y | 38.523-1 | 14.1.3.2 | MBS Broadcast/ MAC/ DRX operation | TP1:[TS 38.321: 5.7a] WITH: UE in NR RRC_IDLE state and is receiving data via broadcast MRB. WHEN:Long DRX cycle for MBS Broadcast is configured for a G-RNTI and [(SFN × 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM THEN: UE starts the OnDurationTimerPTM and monitors the PDCCH for this G-RNTI TP2:[TS 38.321: 5.7a] WITH: UE in NR RRC_INACTIVE state and is receiving data via broadcast MRB. WHEN:Long DRX cycle for MBS Broadcast is configured for a G-RNTI and [(SFN × 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM THEN: UE starts the OnDurationTimerPTM and monitors the PDCCH for this G-RNTI TP3:[TS 38.321: 5.7a] WITH: UE in NR RRC_CONNECTED state and is receiving data via broadcast MRB. WHEN:Long DRX cycle for MBS Broadcast is configured for a G-RNTI and [(SFN × 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM THEN: UE starts the OnDurationTimerPTM and monitors the PDCCH for this G-RNTI | Huawei,Hisilicon | R5-227135 R5-232948 R5-236422 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
28 |  | 38.523-1 | 14.2 | MBS Multicast | New sub-clause header |  |  |  | 0
31 |  | 38.523-1 | 14.2.1 | MBS Multicast/ MAC | New sub-clause header |  |  |  | 0
32 |  | 38.523-1 | 14.2.1.1 | MBS Multicast/ MAC / DL Data Transfer | New sub-clause header |  |  |  | 0
33 | Y | 38.523-1 | 14.2.1.1.1 | MBS Multicast / MAC / DL Data Transfer / PTM transmission / PTP transmission / DCI format 4_1 | TP1:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-AM entity for PTP transmission and HARQ feedback for Multicast is not enabled. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and successfully decodes it. THEN:UE receives the MAC PDU and forwards it to higher layer. TP2:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-AM entity for PTP transmission and HARQ feedback for Multicast is not enabled. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's C-RNTI and successfully decodes it. THEN:UE receives the MAC PDU and forwards it to higher layer. TP3:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-AM entity for PTP transmission and HARQ feedback for Multicast is not enabled. WHEN: UE receives downlink assignment with MAC PDU scheduled for unknown G-RNTI. THEN:UE does not receive the MAC PDU. TP4:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and LCID is used to configure MAC logical Channel for receving PTM transmission. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and LCID of the MAC PDU is matched with the LCID configured for receving PTM transmission. THEN:UE receives the MAC PDU and forwards it to higher layer. TP5:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and eLCID is used to configure MAC logical Channel for receving PTM transmission. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and eLCID of the MAC PDU is matched with the eLCID configured for receving PTM transmission. THEN:UE receives the MAC PDU and forwards it to higher layer. TP6:[TS 38.214:5.1.2.2.3; TS 38.212: 7.3.1.5.2] WITH:UE in RRC_Connected state and size of CFR configured in locationAndBandwidthMulticast-r17 is the same as the size of CORESET 0. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI. THEN:UE receives the MAC PDU and forwards it to higher layer. TP7:[TS 38.214:5.1.2.2.3; TS 38.212: 7.3.1.5.2] WITH:UE in RRC_Connected state and size of CFR configured in locationAndBandwidthMulticast-r17 is the same as the value of locationAndBandwidth of the DL BWP in which the cfr-ConfigMulticast is configured WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI. THEN:UE receives the MAC PDU and forwards it to higher layer. Editor note: C-RNTI is used for PTP transimssion and G-RNTI is used for PTM tansmission | Huawei,Hisilicon | R5-227515 R5-231483 R5-236424 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
34 | Y | 38.523-1 | 14.2.1.1.2 | MBS Multicast / MAC / DL Data Transfer/ PTM transmission/ DCI format 4_2 | TP1:[38.214:5.1.2.2.3,5.1.2.2.2;38.212: 7.3.1.5.3] WITH:UE in RRC_Connected state and locationAndBandwidthMulticast-r17 does not equal to the value of locationAndBandwidth of the DL BWP in which the cfr-ConfigMulticast is configured and resource allocation type 0 for pdsch-ConfigMulticast. WHEN: UE receives downlink assignment DCI format 4_2 with MAC PDU scheduled for UE's G-RNTI. THEN:UE receives the MAC PDU and forwards it to higher layer. TP2:[38.214:5.1.2.2.3,5.1.2.2.2;38.212: 7.3.1.5.3] WITH:UE in RRC_Connected state and locationAndBandwidthMulticast-r17 does not equal to the value of locationAndBandwidth of the DL BWP in which the cfr-ConfigMulticast is configured and resource allocation type 1 for pdsch-ConfigMulticast. WHEN: UE receives downlink assignment DCI format 4_2 with MAC PDU scheduled for UE's G-RNTI. THEN:UE receives the MAC PDU and forwards it to higher layer. | Huawei,Hisilicon | R5-232953 R5-236423 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
35 | Y | 38.523-1 | 14.2.1.1.3 | MBS Multicast / MAC / DL Data Transfer/ PTM transmission / Multiple G-RNTIs | TP1:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and two Multicast MRBs are established and two G-RNTIs(G-RNTI-1 and G-RNTI-2) are configured for PTM transmission.. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI-1 and successfully decodes it. THEN:UE receives the MAC PDU and forwards it to higher layer. TP2:[TS 38.321:5.3.1,5.3.2] WITH:UE in RRC_Connected state and two Multicast MRBs are established and two G-RNTIs(G-RNTI-1 and G-RNTI-2) are configured for PTM transmission.. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI-2 and successfully decodes it. THEN:UE receives the MAC PDU and forwards it to higher layer. | Huawei,Hisilicon | R5-234465 R5-236423 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
36 | Y | 38.523-1 | 14.2.1.1.4 | MBS Multicast/ MAC / DL Data Transfer/ PTM retransmission for multicast/ RRC-based enabling-disabling HARQ feedback for Multicast / ACK-NACK | TP1:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and successfully decodes it. THEN:UE sends ACK for the corresponding HARQ process and forwards it to higher layer. TP2:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and decodes it failure. THEN:UE sends NACK for the corresponding HARQ process. TP3:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC. WHEN: UE receives MAC PDU retransmission for UE's G-RNTI and successfully decodes it. THEN:UE sends ACK for the corresponding HARQ process and forwards it to higher layer. TP4:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18, 38.214:5.1.2.1] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC and pdsch-AggregationFactor > 1. WHEN: UE receives downlink assignment on the PDCCH for the UE’s G-RNTI and receives data in the associated slot and successive pdsch-AggregationFactor – 1 HARQ retransmissions within a bundle and UE coud not successfully decode the data . THEN:UE sends NACK on the HARQ process. TP5:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18, 38.214:5.1.2.1] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC and pdsch-AggregationFactor > 1. WHEN: UE receives downlink assignment on the PDCCH for the UE’s G-RNTI and receives data in the associated slot and successive pdsch-AggregationFactor – 1 HARQ retransmissions within a bundle and UE coud successfully decode the data. THEN:UE sends ACK on the HARQ process. TP6:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast is disabled by RRC. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI THEN:UE does not send HARQ feedback. | Huawei,Hisilicon | R5-227516 R5-231483 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
37 | Y | 38.523-1 | 14.2.1.1.5 | MBS Multicast/ MAC / DL Data Transfer/ PTP retransmission for multicast/ RRC-based enabling-disabling HARQ feedback for Multicast/ ACK-NACK | TP1:[TS 38.321:5.3.1,5.3.2 ; TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC and a MAC PDU for UE's G-RNTI is not successfully decoded. WHEN: UE receives MAC PDU retransmission for UE's C-RNTI and successfully decodes it. THEN:UE sends ACK for the corresponding HARQ process and forwards it to higher layer. | Huawei,Hisilicon | R5-227517 R5-231483 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
38 | Y | 38.523-1 | 14.2.1.1.6 | MBS Multicast/ MAC / DL Data Transfer/ PTM retransmission for multicast/ DCI-based enabling-disabling HARQ feedback for Multicast/ ACK-NACK | TP1:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by DCI 4_2. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and successfully decodes it. THEN:UE sends ACK for the corresponding HARQ process and forwards it to higher layer. TP2:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by DCI 4_2. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and decodes it failure. THEN:UE sends NACK for the corresponding HARQ process. TP3:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with ACK-NACK mode is enabled by DCI 4_2. WHEN: UE receives MAC PDU retransmission for UE's G-RNTI and successfully decodes it. THEN:UE sends ACK for the corresponding HARQ process and forwards it to higher layer. TP4:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast is disabled by DCI 4_2. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI THEN:UE does not send HARQ feedback. TP5:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and harq-FeedbackEnablerMulticast with value set to 'dci-enabler' for a G-RNTI. WHEN:UE receives downlink assignment with MAC PDU scheduled by multicast DCI format 4_1 associated with the G-RNTI and successfully decodes it. THEN:UE send HARQ feedback and forwards the MAC PDU to higher layer. | Huawei,Hisilicon | R5-232954 R5-236423 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
39 | Y | 38.523-1 | 14.2.1.1.7 | MBS Multicast/ MAC / DL Data Transfer/ RRC-based enabling-disabling HARQ feedback for Multicast / NACK-only | TP1:[TS 38.321:5.3.1,5.3.2 ; TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by RRC. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and successfully decodes it. THEN:UE does not send ACK for the corresponding HARQ process and UE forwards MAC PDU to higher layer. TP2:[TS 38.321:5.3.1,5.3.2 ; TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by RRC. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and decodes it failure. THEN:UE sends NACK for the corresponding HARQ process. TP3:[TS 38.321:5.3.1,5.3.2 ; TS 38.213: 18, 38.214:5.1.2.1] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by RRC and pdsch-AggregationFactor > 1. WHEN: UE receives downlink assignment on the PDCCH for the UE’s G-RNTI and receives data in the associated slot and successive pdsch-AggregationFactor – 1 HARQ retransmissions within a bundle and UE coud not successfully decode the data . THEN:UE sends NACK on the HARQ process. TP4:[TS 38.321:5.3.1,5.3.2 ; TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast is disabled by RRC. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI THEN:UE does not send HARQ feedback. TP5:[TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by RRC and moreThanOneNackOnlyMode is configured. WHEN: UE needs to provide more than one HARQ-ACK information bits in a PUCCH. THEN:UE provide more than one HARQ-ACK information bits in a PUCCH by selecting a resource from a set of resources for the PUCCH transmission based on the values of the HARQ-ACK information bits as described in 38.213 Table 18-1. TP6:[TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by RRC and moreThanOneNackOnlyMode is not configured. WHEN: UE needs to provide more than one HARQ-ACK information bits in a PUCCH. THEN:UE provide more than one HARQ-ACK information bits in a PUCCH according to ACK-NACK mode. | Huawei,Hisilicon | R5-231474 R5-236425 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
40 | Y | 38.523-1 | 14.2.1.1.8 | MBS Multicast/ MAC / DL Data Transfer/ Multiplex multicast HARQ-ACK information with unicast HARQ-ACK information | TP1:[TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-AM entity for PTP transimission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC and unicast is configured to use dynamic harq-ack codebook and multicast is configured to use semi-static harq-ack codebook. WHEN: UE needs to multiplex the unicast and multicast HARQ-ACK information in a same PUCCH based on SS scheduling. THEN:UE uses the last unicast DCI format to determine the PUCCH resource. TP2:[TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-AM entity for PTP transimission and HARQ feedback for Multicast with ACK-NACK mode is enabled by RRC and unicast is configured to use dynamic harq-ack codebook and multicast is configured to use semi-static harq-ack codebook. WHEN: UE needs to multiplex the unicast and multicast HARQ-ACK information in a same PUCCH based on SS scheduling. THEN:UE appens the HARQ-ACK codebooks for the multicast HARQ-ACK information to the HARQ-ACK codebooks for the unicast HARQ-ACK information. | Huawei,Hisilicon | R5-231475 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
84 | Y | 38.523-1 | 14.2.1.1.9 | MBS Multicast/ MAC / DL Data Transfer/ DCI-based enabling-disabling HARQ feedback for Multicast/ NACK-only | TP1:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by DCI 4_2. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and successfully decodes it. THEN:UE does not send HARQ feedback and UE forwards the MAC PDU to higher layer. TP2:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast with NACK-only mode is enabled by DCI 4_2. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and decodes it failure. THEN:UE sends NACK for the corresponding HARQ process. TP4:[TS 38.321:5.3.1,5.3.2 ;TS 38.213: 18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and HARQ feedback for Multicast is disabled by DCI 4_2. WHEN: UE receives downlink assignment with MAC PDU scheduled for UE's G-RNTI and decodes it failure. THEN:UE does not send HARQ feedback. | Huawei,Hisilicon | R5-232955 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
41 |  | 38.523-1 | 14.2.1.2 | MBS Multicast/ MAC/ DRX operation | New sub-clause header |  |  |  | 0
42 | Y | 38.523-1 | 14.2.1.2.1 | MBS Multicast/ MAC/ DRX operation/ PTM transmission / PTP transmission | TP1:[TS 38.321: 5.7b] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission ,and Multicast DRX and unicast DRX are configured. WHEN:Long DRX cycle for a G-RNTI is configured and [(SFN * 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM. THEN:UE starts the drx-OnDurationTimerPTM and monitors the PDCCH for this G-RNTI during drx-OnDurationTimerPTM. TP2:[TS 38.321: 5.7b] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission ,and Multicast DRX and unicast DRX are configured. WHEN:Long DRX cycle for a G-RNTI is configured and a new DL transmission is indicated on the PDCCH during Active Time. THEN:UE starts or restarts the drx-InactivityTimerPTM in the first symbol after the end of the PDCCH reception and monitors the PDCCH for this G-RNTI during drx-InactivityTimerPTM. TP3:[TS 38.321: 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission ,and Multicast DRX and unicast DRX are configured. WHEN:Long DRX cycle for C-RNTI is configured and [(SFN * 10) + subframe number] modulo (drx-LongCycle) = drx-StartOffset. THEN:UE monitors the PDCCH for C-RNTI during drx-OnDurationTimer. TP4:[TS 38.321: 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission ,and Multicast DRX and unicast DRX are configured. WHEN:Long DRX cycle for C-RNTI is configured and a new DL transmission is indicated on the PDCCH during Active Time. THEN:UE starts or restarts the drx-InactivityTimer in the first symbol after the end of the PDCCH reception and monitors the PDCCH for C-RNTI during drx-InactivityTimer. TP5:[TS 38.321: 5.7b] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, and Multicast DRX and unicast DRX are configured. WHEN:DRX Command MAC CE indicated by PDCCH addressed to with DCI scrambled with a G-RNTI is received. THEN:UE stops drx-onDurationTimerPTM of the DRX for this G-RNTI. TP6:[TS 38.321: 5.7b] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, and only unicast DRX is configured. WHEN:PDCCH indicated a DL multicast transmission is received. THEN:UE stops drx-RetransmissionTimerDL for the corresponding HARQ process. TP7:[TS 38.321: 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, both multicast DRX and unicast DRX are configured, and allowCSI-SRS-Tx-MulticastDRX-Active is configured. WHEN:Both unicast DRX and multicast DRX are not in Active Time. THEN:UE stop report CSI on PUCCH. TP8:[TS 38.321: 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, only unicast DRX is configured, and allowCSI-SRS-Tx-MulticastDRX-Active is not configured. WHEN:Unicast DRX is not in Active Time. THEN:UE stop report CSI on PUCCH. TP9:[TS 38.321: 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, both multicast DRX and unicast DRX are configured, and allowCSI-SRS-Tx-MulticastDRX-Active is configured. WHEN:Unicast DRX or multicast DRX are in Active Time. THEN:UE does not stop report CSI on PUCCH. TP10:[TS 38.321: 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, only unicast DRX is configured, and allowCSI-SRS-Tx-MulticastDRX-Active is not configured. WHEN:Unicast DRX is in Active Time. THEN:UE does not stop report CSI on PUCCH. | Huawei,Hisilicon | R5-231476 R5-236426 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
43 | Y | 38.523-1 | 14.2.1.2.2 | MBS Multicast/ MAC/ DRX operation/ PTM retransmission for multicast | TP1:[TS 38.321: 5.7b] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission, and multicast DRX is configured, and HARQ ACK/NACK feedback for multicast is enabled. WHEN:UE receives a PTM transmission with G-RNTI and the data in the soft buffer of the corresponding HARQ process for MBS multicast was not successfully decoded. THEN:UE starts the drx-RetransmissionTimerDL-PTM for the corresponding HARQ processs after expiry of drx-HARQ-RTT-TimerDL-PTM and monitors the G-RNTI PDCCH for drx-RetransmissionTimerDL-PTM consecutive PDCCH Occasion. TP2:[TS 38.321: 5.7b,5.7] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and one DRB established and HARQ ACK/NACK feedback for multicast is enabled. WHEN:Long DRX cycle for a G-RNTI is configured and Long DRX cycle for C-RNTI is configured and if a drx-HARQ-RTT-TimerDL-PTM expires in this PDCCH Occasion and the data in the soft buffer of the corresponding HARQ process was not successfully decoded. THEN:UE starts the drx-RetransmissionTimerDL for the corresponding HARQ process and monitors the C-RNTI PDCCH for drx-RetransmissionTimerDL consecutive PDCCH Occasion. ---Change to Void because if UE does not support PTP retransmission for multicast, UE does not need to start RTT timer for unicast TP3:[TS 38.321: 5.7b,5.7] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and period CSI report is configured and HARQ ACK/NACK feedback for multicast is enabled and allowCSI-SRS-Tx-MulticastDRX-Active-r17 is configured. WHEN: Long DRX cycle for a G-RNTI is configured and Long DRX cycle for C-RNTI is configured and UE receives PTM for PTM retransmission during drx-RetransmissionTimerDL-PTM for the corresponding HARQ process. THEN:UE stops the drx-RetransmissionTimerDL and drx-RetransmissionTimerDL-PTM for the corresponding HARQ process and does not report CSI on PUCCH when UE is not in DRX Active Time.---Change to Void because if UE does not support PTP retransmission for multicast, UE does not need to start RTT timer for unicast Editor Note: DRX for G-RNTI is used for PTM transmission and PTM for PTM retransmission. DRX for C-RNTI is used for DRB unicast transmission. | Huawei,Hisilicon | R5-232956 R5-236426 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
44 | Y | 38.523-1 | 14.2.1.2.3 | MBS Multicast/ MAC/ DRX operation/ PTP retransmission for multicast | TP1:[TS 38.321: 5.7b, 5.7] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission, both multicast DRX and unicast DRX are configured, and HARQ ACK/NACK feedback for multicast is enabled. WHEN:UE receives a PTM transmission with G-RNTI and the data in the soft buffer of the corresponding HARQ process for MBS multicast was not successfully decoded. THEN:UE starts the drx-RetransmissionTimerDL for the corresponding HARQ process for MBS multicast after expiry of drx-HARQ-RTT-TimerDL and monitors the PDCCH addressed to C-RNTI for drx-RetransmissionTimerDL consecutive PDCCH Occasion. TP2:[TS 38.321: 5.7b, 5.7] WITH: UE in RRC_Connected state and Multicast MRB established with a RLC-UM entity for PTM transmission and a RLC-UM entity for PTP transmission, both multicast DRX and unicast DRX are configured, and HARQ ACK/NACK feedback for multicast is enabled. WHEN: UE receives a DL transmission with C-RNTI during drx-RetransmissionTimerDL for the corresponding HARQ process for MBS multicast. THEN:UE stops the drx-RetransmissionTimerDL and drx-RetransmissionTimerDL-PTM for the corresponding HARQ process. TP3:[TS 38.321: 5.7b, 5.7] WITH: UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, both multicast DRX and unicast DRX are configured, and period CSI report is configured, and allowCSI-SRS-Tx-MulticastDRX-Active is configured. WHEN: Both unicast DRX and multicast DRX are not in Active Time. THEN:UE stop report CSI on PUCCH . TP4:[TS 38.321: 5.7b, 5.7] WITH: UE in RRC_Connected state and Multicast MRB established with one RLC-UM entity for PTM transmission and one RLC-UM entity for PTP transmission, both multicast DRX and unicast DRX are configured, and period CSI report is configured, and allowCSI-SRS-Tx-MulticastDRX-Active is configured. WHEN: Unicast DRX or multicast DRX are in Active Time. THEN:UE does not stop report CSI on PUCCH. Editor Note: HARQ ACK/NACK feedback for multicast need to be configured. DRX for G-RNTI is used for PTM transmission and DRX for C-RNTI is used for PTP for PTM retransmission | Huawei,Hisilicon | R5-232957 R5-236426 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
45 |  | 38.523-1 | 14.2.1.3 | MBS Multicast/ MAC/ SPS | New sub-clause header |  |  |  | 0
46 | Y | 38.523-1 | 14.2.1.3.1 | MBS Multicast/ MAC/ SPS/ PTM transmission | TP1:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and one sps-Configuration in sps-ConfigMulticastToAddModList-r17 is configured. WHEN:UE receives a DL assignment addressed to its stored G-CS-RNTI in slot y and with NDI set as 0 and PDCCH content indicates activation THEN:UE starts receiving DL MAC PDU in slots y+n*[semiPersistSchedIntervalDL] where 'n' is positive integer starting at zero TP2:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and used configured DL assignment to receive MAC PDU in slot y+n*[semiPersistSchedIntervalDL] for PTM transmission. WHEN:UE receives a DL assignment addressed to its stored G-CS-RNTI in slot p and with NDI set as 0 and PDCCH content indicates activation and p!= y+n*[semiPersistSchedIntervalDL] THEN:UE stops receiving DL MAC PDU at slots y+n*[semiPersistSchedIntervalDL]. where 'n' is positive integer starting at zero TP3:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and used configured DL assignment to receive MAC PDU in slot p+n*[semiPersistSchedIntervalDL] for PTM transmission. WHEN:UE receives a DL assignment addressed to its stored G-CS-RNTI in slot q and with NDI set as 0 and PDCCH content indicates activation and q!= p+n*[semiPersistSchedIntervalDL] THEN:UE starts receiving DL MAC PDU in slots q+n*[semiPersistSchedIntervalDL] where 'n' is positive integer starting at zero TP4:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and used configured DL assignment to receive MAC PDU in slot q+n*[semiPersistSchedIntervalDL] WHEN:UE receives a DL assignment addressed to its G-RNTI in slot z for PTM transmission, such that z= q+n*[semiPersistSchedIntervalDL] THEN:UE receives DL MAC PDU as per assignment addressed to its G-RNTI. where 'n' is positive integer starting at zero TP5:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and used configured DL assignment to receive MAC PDU in slot q+n*[semiPersistSchedIntervalDL] for PTM transmission. WHEN:UE receives a DL assignment addressed to its stored G-CS-RNTI in slot a and with NDI set as 0 and PDCCH content indicates deactivation and a!= q+n*[semiPersistSchedIntervalDL]. THEN:UE sends an ACK and stops receiving DL MAC PDU in slot q+n*[semiPersistSchedIntervalDL]. where 'n' is positive integer starting at zero TP6:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and used configured DL assignment to receive MAC PDU in slot y+n*[semiPersistSchedIntervalDL] for PTM transmission. WHEN:UE receives a RRCReconfiguration including sps-ConfigMulticastToReleaseList-r17 with SPS-ConfigIndex-r16 and hence resulting in MBS SPS released THEN:UE deletes the stored sps-Configuration DL parameters and stops receiving DL MAC PDU in slot y+n*[semiPersistSchedIntervalDL]. where 'n' is positive integer starting at zero. Editor Note: HARQ feedback for multicast is not configured in because HARQ feedback is not a mandatory feature for MBS multicast . | Huawei,Hisilicon | R5-234466 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
47 | Y | 38.523-1 | 14.2.1.3.2 | MBS Multicast/ MAC/ SPS/ PTM retransmission for multicast | TP1:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and one sps-Configuration in sps-ConfigMulticastToAddModList-r17 is configured and harq feedback is enabled. WHEN:UE receives a DL assignment addressed to its stored G-CS-RNTI in slot y and with NDI set as 0 and PDCCH content indicates activation THEN:UE starts receiving DL MAC PDU in slots y+n*[semiPersistSchedIntervalDL] where 'n' is positive integer starting at zero TP2:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and DL MBS SPS has been activated in slot y. WHEN:UE uses configured DL assignment to receive a valid MAC PDU in slot y+n*[semiPersistSchedIntervalDL] THEN:UE sends ACK for the corresponding HARQ process and forwards it to higher layer. TP3:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and DL MBS SPS has been activated in slot y. WHEN:UE uses configured DL assignment to receive an invalid MAC PDU in slot y+n*[semiPersistSchedIntervalDL] THEN:UE sends NACK for the corresponding HARQ process and forwards it to higher layer. TP4:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and used configured DL assignment to receive an invalid MAC PDU in slot y+n*[semiPersistSchedIntervalDL] WHEN:UE receives a DL assignment for PTM retransmission addressed to its G-CS-RNTI in Slot p and with NDI set as 1, where p!= y+n*[semiPersistSchedIntervalDL] THEN:UE receives MAC PDU as per the retransmission grant for G-CS-RNTI | Huawei,Hisilicon | R5-234467 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
48 | Y | 38.523-1 | 14.2.1.3.3 | MBS Multicast/ MAC/ SPS/ PTP retransmission for multicast | TP1:[TS 38.321: 5.8.1a,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and CS-RNTI is configured and UE has received an invalid MAC PDU in slot y+n*[semiPersistSchedIntervalDL] based on configured DL assignment. WHEN:UE receives a DL assignment for PTP retransmission addressed to its CS-RNTI in Slot p and with NDI set as 1, where p!= y+n*[semiPersistSchedIntervalDL] THEN:UE receives MAC PDU as per the retransmission grant for CS-RNTI | Huawei,Hisilicon | R5-234468 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
49 | Y | 38.523-1 | 14.2.1.3.4 | MBS Multicast/ MAC/ SPS/ CS-RNTI release | TP1:[TS 38.321: 5.8.1a,5.3.1,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and one sps-Configuration in sps-ConfigMulticastToAddModList-r17 is configured and CS-RNTI is configured. WHEN:UE receives a DL assignment addressed to its stored G-CS-RNTI in slot y and with NDI set as 0 and PDCCH content indicates activation THEN:UE starts receiving DL MAC PDU in slots y+n*[semiPersistSchedIntervalDL] where 'n' is positive integer starting at zero TP1:[TS 38.321: 5.8.1a,TS 38.213: 10.2,18] WITH:UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission and used configured DL assignment to receive MAC PDU in slot y+n*[semiPersistSchedIntervalDL]. WHEN:UE receives a DL assignment addressed to its stored CS-RNTI in slot p and with NDI set as 0 and PDCCH content indicates deactivation where p!= y+n*[semiPersistSchedIntervalDL] THEN:UE sends an ACK and stops receiving DL MAC PDU in slot y+n*[semiPersistSchedIntervalDL]. | Huawei,Hisilicon | R5-234469 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
50 |  | 38.523-1 | 14.2.2 | MBS Multicast/ RLC | New sub-clause header |  |  |  | 0
51 | Y | 38.523-1 | 14.2.2.1 | MBS Multicast/ UM RLC / 6bit SN /Correct set initial value for UM receive state variable/ PTM | TP1:[TS 38.322: 7.1, 5.2.2.2] WITH: UE in RRC_Connected state and Multicast MRB established with DL only RLC-UM entity for PTM transmission WHEN: UE receives first UMD PDU including SN and ' 2^[sn-FieldLength - 1] <= SN <= 2^[sn-FieldLength] -1' THEN: The UE sets the initial value of RX_Next_Highest to the SN of the first UMD PDU including SN and initial value of RX_Next_Reassembly to a value before RX_Next_Highest and stores the UMD PDU in receive buffer. TP2:[TS 38.322: 7.1, 5.2.2.2] WITH: UE in RRC_Connected state and Multicast MRB established with DL only RLC-UM entity for PTM transmission WHEN: UE receives a UMD PDU, which is not the first UMD PDU, including SN and 'SN = SN of first UMD PDU - 1' before t-reassembly expiry THEN: The UE stores the UMD PDU in receive buffer. TP3:[TS 38.322: 7.1, 5.2.2.2] WITH: UE in RRC_Connected state and Multicast MRB established with DL only RLC-UM entity for PTM transmission WHEN: UE receives a UMD PDU, which is not the first UMD PDU, including SN and '(RX_Next_Highest – UM_Window_Size) <= SN < RX_Next_Reassembly' THEN: The UE discard the received UMD PDU. TP4:[TS 38.322: 7.1, 5.2.2.2.3] WITH: UE in RRC_Connected state and Multicast MRB established with DL only RLC-UM entity for PTM transmission WHEN: UE places a UMD PDU including SN into the reception buffer and all byte segments with that SN are received THEN: UE delivers the reassembled SDU to upper layers TP5:[TS 38.322: 7.1, 5.1.2] WITH: UE in RRC_Connected state and using Multicast MRB with DL only RLC-UM entity for PTM transmission WHEN: RLC re-establishment is performed upon request by RRC THEN: The UE resets initial value of RX_Next_Highest to the SN of the first received UMD PDU containing an SN and initial value of RX_Next_Reassembly to a value before RX_Next_Highest and stores the UMD PDU in receive buffer. | Huawei,Hisilicon | R5-231477 R5-236427 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
52 | Y | 38.523-1 | 14.2.2.2 | MBS Multicast/ UM RLC / 12bit SN /Correct set initial value for UM receive state variable/ PTM | Editor Note: TP is the same as 15.2.2.1 except 12bit SN. | Huawei,Hisilicon | R5-231477 R5-236427 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
53 |  | 38.523-1 | 14.2.3 | MBS Multicast / PDCP | New sub-clause header |  |  |  | 0
54 | Y | 38.523-1 | 14.2.3.1 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance / Non-Lossless handover / 12 bit SN | TP1:[TS 38.323: 7.1 5.2.2 ] WITH: UE in RRC_Connected state and Multicast MRB established with DL only RLC-UM entity for PTM transmission and initialRXDELIV-r17 in PDCP-Config for this Multicast MRB is not zero. WHEN: UE receives a PDCP Data PDU with RCVD_COUNT < RX_DELIV. THEN: UE sets the initial value of RX_DELIV to initialRXDELIV and discards the PDCP DATA PDU with RCVD_COUNT. TP2:[TS 38.323: 7.1 5.2.2 ] WITH: UE in RRC_Connected state and Multicast MRB established with DL only RLC-UM entity for PTM transmission and initialRXDELIV-r17 in PDCP-Config for this Multicast MRB is not zero. WHEN: UE receives a PDCP Data PDU with RCVD_COUNT = RX_DELIV. THEN: UE delivers PDCP Data PDU to upper layers. TP3:[TS 38.323: 7.1 5.2.2 ] WITH: UE in RRC_Connected state and Multicast MRB established with RLC-AM entity for PTP transmission and initialRXDELIV-r17 in PDCP-Config for this Multicast MRB is not zero. WHEN: UE receives a PDCP Data PDU with RCVD_COUNT < RX_DELIV. THEN: UE sets the initial value of RX_DELIV to initialRXDELIV and discards the PDCP DATA PDU with RCVD_COUNT. TP4:[TS 38.323: 7.1 5.2.2 ] WITH: UE in RRC_Connected state and Multicast MRB established with RLC-AM entity for PTP transmission and initialRXDELIV-r17 in PDCP-Config for this Multicast MRB is not zero. WHEN: UE receives a PDCP Data PDU with RCVD_COUNT = RX_DELIV. THEN: UE delivers PDCP Data PDU to upper layers. | Huawei,Hisilicon | R5-231478 R5-236429 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
55 | Y | 38.523-1 | 14.2.3.2 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance / Non-Lossless handover / 18 bit SN | Editor Note: TP is the same as 14.2.3.1 except 18 bit SN. | Huawei,Hisilicon | R5-231478 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
56 | Y | 38.523-1 | 14.2.3.3 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance /Lossless handover/ PDCP status report / 12 bit SN | TP1:[TS 38.323: 5.4.1, 5.5, 38.331: 5.3.5.1, 38.300: 16.10.5.3.2] WITH: UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission. WHEN: UE is requested to make a lossless handover with pdcp data recovery and UE is configured with RLC-AM entity for PTP transmission by SS. THEN: UE creates a PDCP status report to SS. TP2:[TS 38.323: 5.4.1, 5.5, 38.331: 5.3.5.1, 38.300: 16.10.5.3.2] WITH: UE in RRC_Connected state and Multicast MRB established with RLC-UM entity for PTM transmission. WHEN: UE is requested to make a lossless handover with pdcp data recovery and UE is configured with RLC-AM entity for PTP transmission by SS. THEN: UE achieves in-order delivery and discards a PDCP PDU already received in the downlink. TP3:[TS 38.323: 5.4.1, 5.5, 38.331: 5.3.5.1, 38.300: 16.10.5.3.2] WITH: UE in RRC_Connected state and Multicast MRB established with RLC-AM entity for PTP transmission. WHEN: UE is requested to make a lossless handover with pdcp re-establishment and UE is configured with a RLC-AM entity for PTP transmission and a RLC-UM entity for PTM transmission by SS. THEN: UE creates a PDCP status report to SS. TP4:[TS 38.323: 5.4.1, 5.5, 38.331: 5.3.5.1, 38.300: 16.10.5.3.2] WITH: UE in RRC_Connected state and Multicast MRB established with RLC-AM entity for PTP transmission. WHEN: UE is requested to make a lossless handover with pdcp re-establishment and UE is configured with RLC-AM entity for PTP transmission and a RLC-UM entity for PTM transmission by SS. THEN: UE achieves in-order delivery and discards a PDCP PDU already received in the downlink. | Huawei,Hisilicon | R5-231479 R5-236429 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
57 | Y | 38.523-1 | 14.2.3.4 | MBS Multicast / PDCP/ PDCP HFN and SN maintenance /Lossless handover/ PDCP status report / 18 bit SN | Editor Note: TP is the same as 14.2.3.3 except 18 bit SN. | Huawei,Hisilicon | R5-231479 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
58 |  | 38.523-1 | 14.2.4 | MBS Multicast / RRC | New sub-clause header |  |  |  | 0
59 |  | 38.523-1 | 14.2.4.1 | MBS Multicast / RRC / Paging | New sub-clause header |  |  |  | 0
60 | Y | 38.523-1 | 14.2.4.1.1 | MBS Multicast / RRC / Paging for group notification / RRC_IDLE | TP1:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_IDLE state and UE has joined one MBS multicast session. WHEN: UE receives a Paging message including TMGIs unmatched with MBS multicast session which the UE has joined, not including ue-Identity. THEN: UE does not establish any RRC connection. TP2:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_IDLE state and UE has joined one MBS multicast session WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has joined, not including ue-Identity. THEN: UE successfully establishes the RRC connection. TP3:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_IDLE state and UE has released MBS multicast session. WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has released, not including ue-Identity. THEN: UE does not establish any RRC connection | Huawei,Hisilicon | R5-231480 R5-232949 R5-236428 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
61 | Y | 38.523-1 | 14.2.4.1.2 | MBS Multicast / RRC / Paging for group notification / RRC_INACTIVE | TP1:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_INACTIVE state and UE has joined one MBS multicast session. WHEN: UE receives a Paging message including TMGIs unmatched with MBS multicast session which the UE has joined, not including ue-Identity. THEN: UE does not resume RRC connection. TP2:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_INACTIVE state and UE has joined one MBS multicast session WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has joined, not including ue-Identity. THEN: UE successfully resumes the RRC connection with resumecause set to mt-Access. TP3:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_INACTIVE state and UE has released MBS multicast session. WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has released, not including ue-Identity. THEN: UE does not resume RRC connection. TP4:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_INACTIVE state and UE has joined one MBS multicast session. WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has joined, and including a matched identity fullI-RNTI. THEN: UE successfully resumes the RRC connection with resumecause set to mt-Access. TP5:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_INACTIVE state and UE has joined one MBS multicast session. WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has joined, and including a matched identity ng-5G-S-TMSI THEN: UE releases RRC connection with release cause ‘other’ and goes to NR RRC_IDLE state. TP6:[TS 38.300: 16.10.5.2, TS 38.331: 5.3.2.3, TS 24.501: 5.6.2.2.1 ] WITH: UE in NR RRC_INACTIVE state and UE has joined one MBS multicast session. WHEN: UE receives a Paging message including a TMGI matched with MBS multicast session which the UE has joined, and including a unmatched identity ng-5G-S-TMSI THEN: UE successfully resumes the RRC connection with resumecause set to mt-Access. | Huawei,Hisilicon | R5-231481 R5-232949 R5-236428 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
62 |  | 38.523-1 | 14.2.4.2 | MBS Multicast / RRC / MRB Reconfiguration | New sub-clause header |  |  |  | 0
63 | Y | 38.523-1 | 14.2.4.2.1 | MBS Multicast / RRC / MRB Reconfiguration / Establishment / Modification / Release / Success | TP1:[TS 38.331: 5.3.5.5.4,5.3.5.6.7] WITH: UE in NR RRC_IDLE state and UE has joined one MBS multicast session. WHEN: UE receives a Paging with matched TMGI and moves to RRC_CONNECTED state and receives RRCReconfiguration message including a MRB-ToAddModList to add an UM MRB with one UM RLC for PTM transmission as MRB-Identity 1 and an AM MRB with one AM RLC for PTP transmission as MRB-Identity 2 . THEN: UE successfully establishes the MRBs. TP2:[TS 38.331: 5.3.5.6.6] WITH: UE in NR RRC_CONNECTED state and MRB-Identity 1 and MRB-Identity 2 have established. WHEN: UE receives RRCReconfiguration message including a MRB-ToReleaseList to release a MRB-Identity which is not part of current UE configuration THEN: UE does not consider the message as erroneous and replies RRCReconfigurationComplete. TP3:[TS 38.331: 5.3.5.5.4, 5.3.5.6.6] WITH: UE in NR RRC_CONNECTED state and MRB-Identity 1 and MRB-Identity 2 have established. WHEN: UE receives RRCReconfiguration message including a MRB-ToReleaseList to release MRB-Identity 2 and including rlc-BearerToaddModList to modify MRB-Identity 1 by adding a RLC-AM for PTP transmission. THEN: UE releases PDCP entity for MRB-Identity 2 and MRB-Identity 2 and changes MRB-Identity 1 to AM MRB with one UM RLC for PTM transmission and one AM RLC for PTP transmission and could receives MBS data of MRB-Identity 1 with PTM transmission and PTP transmission. TP4:[TS 38.331: 5.3.5.5.4, 5.3.5.6.7] WITH: UE in NR RRC_CONNECTED state and MRB-Identity 1 have established. WHEN: UE receives RRCReconfiguration message including a MRB-ToAddModList to update the MRB-Identity 1 to the MRB-Identity 3 by setting the value of MRB-IdentityNew to 3. THEN: UE updates the MRB-Identity to the value MRB-IdentityNew. TP5:[TS 38.331: 5.3.5.5.4, 5.3.5.6.6] WITH: UE in NR RRC_CONNECTED state and MRB(s) have established. WHEN: UE receives RRCReconfiguration message including a MRB-ToReleaseList to release all the MRB configured with same mbs-SessionId . THEN: UE releases PDCP entity and the MRB-Identity and indicate release of the user plane resources for mbs-SessionId to upper layers. | Huawei,Hisilicon | R5-231482 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
64 |  | 38.523-1 | 14.2.4.3 | MBS Multicast/ RRC/ Handover | New sub-clause header |  |  |  | 0
65 | Y | 38.523-1 | 14.2.4.3.1 | MBS Multicast/ RRC/ Handover between multicast supporting cell / Success | TP1:[TS 38.300: 16.10.5.3.2,TS 38.331 5.3.5] WITH: UE in NR RRC_CONNECTED state and UE has joined one MBS multicast session and receives MBS data in MRB. WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover to a multicast supporting cell . THEN: UE performs handover to the target cell and transmits an RRCReconfigurationComplete message and receives MBS data in MRB. | Huawei,Hisilicon | R5-233385 R5-237391 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
66 | Y | 38.523-1 | 14.2.4.3.2 | MBS Multicast / RRC / Handover between multicast supporting cell / Failure/ Re-establishment successful | TP1:[TS 38.300: 16.10.5.3.2,TS 38.331 5.3.5, 5.3.7] WITH: UE in NR RRC_CONNECTED state and UE has joined one MBS multicast session and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the target cell. WHEN: UE detects handover failure and the initial cell is selectable . THEN: UE performs an RRCReestablishment procedure on the source cell. TP2: [TS 38.331 5.3.5, 5.3.7] WITH: UE detects handover failure and having performed an RRCReestablishment procedure. WHEN: UE receives first RRCReconfiguration message . THEN: UE transmits an RRCReconfigurationComplete message and resumes multicast MRB . | Huawei,Hisilicon | R5-233386 R5-237391 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
67 | Y | 38.523-1 | 14.2.4.3.3 | MBS Multicast/ RRC/ Handover between Multicast-supporting cell and Multicast non-supporting cell / Success | TP1:[TS 38.300: 16.10.5.3.3,TS 38.331 5.3.5] WITH: UE in NR RRC_CONNECTED state and UE has joined one MBS multicast session and receives MBS data in MRB. WHEN: UE receives an RRCReconfiguration message to switch the MBS data transmission from the MRB to DRB . THEN: UE transmits an RRCReconfigurationComplete. TP2:[TS 38.300: 16.10.5.3.3,TS 38.331 5.3.5] WITH: UE in NR RRC_CONNECTED state and UE has switched to receive MBS data in DRB. WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover to a multicast non-supporting cell . THEN: UE performs handover to the target cell and transmits an RRCReconfigurationComplete message. TP3:[TS 38.300: 16.10.5.3.3,TS 38.331 5.3.5] WITH: UE in NR RRC_CONNECTED state and UE has joined one MBS multicast session and configured to receive MBS data in DRB. WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover to a multicast supporting cell . THEN: UE performs handover to the target cell and transmits an RRCReconfigurationComplete message and successfully established MRB and receives MBS data in MRB. TP4:[TS 38.300: 16.10.5.3.3,TS 38.331 5.3.5] WITH: UE in NR RRC_CONNECTED state and UE has joined one MBS multicast session and receives MBS data in MRB. WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync and full configuration for handover to a multicast non-supporting cell . THEN: UE performs handover to the target cell and transmits an RRCReconfigurationComplete message. Editor Note: according to 23.247 associated Qos Flows does not have UL so it is not appropriated to test UE receving MBS data in DRB and then loop the DRB back to SS. Therefore checking point for UE receiving MBS data in DRB is deleted. [23.247 6.6] - For multicast MBS sessions, the QoS rule and QoS Flow level QoS parameters of MBS QoS Flow are not provided to UE. - For multicast MBS sessions, the handling of QoS rule and QoS Flow level QoS parameters of the associated QoS Flow(s) is the same as for other QoS Flow without UL in a PDU Session. | Huawei,Hisilicon | R5-232960 R5-236429 R5-237391 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
68 |  | 38.523-1 | 14.2.4.3.4 | Void (emerge to 14.2.4.3.3 TP4) | Editor Note: emerged to 14.2.4.3.3 TP3 |  |  |  | 0
69 |  | 38.523-1 | 14.2.4.3.5 | Void (emerge to 14.2.4.3.3 TP3) | Editor Note: emerged to 14.2.4.3.3 TP2 |  |  |  | 0
70 |  | 38.523-1 | 14.2.5 | MBS Multicast/ Session management | New sub-clause header |  |  |  | 0
71 |  | 38.523-1 | 14.2.5.1 | MBS Multicast/ Session management / Network-requested PDU session modification | New sub-clause header |  |  |  | 0
72 | Y | 38.523-1 | 14.2.5.1.1 | MBS Multicast/ Session management / Network-requested PDU session modification / Remove UE from multicast MBS session | TP1:[TS 24.501:6.3.2.2,6.3.2.3] WITH: UE is in 5GMM-REGISTERED state and has joined two MBS multicast session associated with a PDU session. One MBS session Id is TMGI-1, and another MBS session Id is TMGI-2. WHEN: UE receives PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "Remove UE from multicast MBS session" and Rejection cause setting to "MBS session is released" for TMGI-1. THEN: UE sends PDU SESSION MODIFICATION COMPLETE and UE shall consider the MBS session for TMGI-1 as released and MBS session for TMGI-2 is not released. . | Huawei,Hisilicon | R5-233387 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
73 | Y | 38.523-1 | 14.2.5.1.2 | MBS Multicast/ Session management / Network-requested PDU session modification / MBS service area update | TP1:[TS 24.501:6.3.2.2,6.3.2.3] WITH: UE is in 5GMM-REGISTERED state and UE is camping on a cell that is outside the received MBS service area WHEN: UE receives PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "MBS service area update" for including the current cell into MBS servcie area. THEN: UE sends PDU SESSION MODIFICATION COMPLETE and UE shall store the received MBS service area associated with the received TMGI and replace the current MBS service area with the received one. TP2:[TS 24.501:6.3.2.2,6.3.2.3] WITH: UE is in 5GMM-REGISTERED state and UE updates MBS service area associated with TMGI based on received MBS service area in PDU SESSION MODIFICATION COMMAND message WHEN: UE is camping on a cell that is inside the received MBS service area associated with one TMGI and join MBS session with this TMGI is still needed. THEN: UE sends PDU SESSION MODIFICATION REQUEST message to join MBS session with this TMGI. | Huawei,Hisilicon | R5-233388 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
74 |  | 38.523-1 | 14.2.5.2 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification | New sub-clause header Editor Note: According to 24.501"the UE at the same time intends to join one or more multicast MBS sessions that is associated to the PDU session, the UE should include the Requested MBS container IE in the PDU SESSION ESTABLISHMENT REQUEST message" (introduced by C1-215085), spec recommand UE to include MBS join request in PDU session establishment request rather than executing PDU session establishment and then join MBS in PDU session modification procedure. However, It is still possible that UE could use separate procedure to join in MBS session. Therefore UE-requested PDU session establishment and UE-requested PDU session modification need to be tested together. |  |  |  | 0
75 | Y | 38.523-1 | 14.2.5.2.1 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification / Join MBS multicast session / Accepted | TP1:[TS 24.501:6.4.1.2] WITH: UE is in 5GMM-REGISTERED state. WHEN: UE requests to establish a new PDU session associated with MBS multicast sessions and the UE at the same time intends to join two MBS multicast sessions . THEN: UE sends PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session" TP2:[TS 24.501:6.4.1.3] WITH: UE is in 5GMM-REGISTERED state and has sent PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session". WHEN: UE receives PDU SESSION ESTABLISHMENT ACCEPT or PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "MBS join is accepted" THEN: UE shall consider that it has successfully joined the MBS session and shall store the received TMGI. | Huawei,Hisilicon | R5-233389 R5-236432 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
76 | Y | 38.523-1 | 14.2.5.2.2 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification / Join MBS multicast session / Rejected / User is outside of local MBS service area | TP1:[TS 24.501:6.4.1.3] WITH: UE is in 5GMM-REGISTERED state and has sent PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session". WHEN: UE receives PDU SESSION ESTABLISHMENT ACCEPT or PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "MBS join is rejected" and Rejection cause setting to "User is outside of local MBS service area" THEN: UE shall not request to join the same MBS session if the UE is camping on a cell that is outside the received MBS service area. TP2:[TS 24.501:6.4.1.3] WITH: UE is in 5GMM-REGISTERED state and has received the "MBS join is rejected" with Rejection cause setting to "User is outside of local MBS service area" WHEN: UE move to another cell that is inside the received MBS service area. THEN: UE could join the MBS session in the new cell if this MBS session is still needed. | Huawei,Hisilicon | R5-234470 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
77 | Y | 38.523-1 | 14.2.5.2.3 | MBS Multicast/ Session management / UE-requested PDU session establishment / UE-requested PDU session modification / Join MBS multicast session / Rejected / MBS session has not started or will not start soon | TP1:[TS 24.501:6.4.1.2,6.4.1.3,10.4] WITH: UE is in 5GMM-REGISTERED state and has sent PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session". WHEN: UE receives PDU SESSION ESTABLISHMENT ACCEPT or PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "MBS join is rejected" and Rejection cause setting to "MBS session has not started or will not start soon" and MBS back-off timer setting to neither zero nor deactivated. THEN: UE shall start a back-off timer T3587 with the value provided in the MBS back-off timer value for the received TMGI, and shall not attempt to join the MBS session with the same TMGI until the expiry of T3587. TP2:[TS 24.501:6.4.1.2,6.4.1.3,10.4] WITH: UE is in 5GMM-REGISTERED state and UE has received the "MBS join is rejected" with non-zero back-off timer and PDU session that can be associated with MBS multicast sessions has been released. WHEN: upon expiry of T3587 and join this MBS session is still needed . THEN: UE sends PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session" TP3:[TS 24.501:6.4.1.2,6.4.1.3,10.4] WITH: UE is in 5GMM-REGISTERED state and has sent PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session". WHEN: UE receives PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "MBS join is rejected" and Rejection cause setting to "MBS session has not started or will not start soon" and MBS back-off timer setting to deactivated. THEN: UE shall not attempt to join the MBS session with the same TMGI until the UE is switched off, the USIM is removed. TP4:[TS 24.501:6.4.1.2,6.4.1.3,10.4] WITH: UE is in 5GMM-REGISTERED state and UE has received the "MBS join is rejected" with MBS back-off timer setting to deactivated and UE is switched off or the USIM is removed WHEN: UE switchs on or inserts USIM again and join this MBS session is still needed THEN: UE sends PDU SESSION ESTABLISHMENT REQUEST or PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Join MBS session" | Huawei,Hisilicon | R5-234471 R5-236432 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
85 | Y | 38.523-1 | 14.2.5.2.4 | MBS Multicast/ Session management / UE-requested PDU session modification / Leave MBS multicast session / Accepted | TP1:[TS 24.501:6.4.2.2, 6.3.2.2] WITH: UE is in 5GMM-REGISTERED state and UE has joined two MBS multicast session associated with a PDU session. One MBS session Id is TMGI-1, and another MBS session Id is TMGI-2. WHEN: UE requests to leave MBS multicast session associated with TMGI-1 THEN: UE sends PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Leave MBS session" and multicast MBS session ID is TMGI-1 TP2:[TS 24.501:6.4.2.2, 6.3.2.2] WITH: UE is in 5GMM-REGISTERED state and has sent PDU SESSION MODIFICATION REQUEST including the Requested MBS container IE with MBS operation setting to "Leave MBS session" and multicast MBS session ID is TMGI-1. WHEN: UE receives PDU SESSION MODIFICATION COMMAND message including Received MBS container IE with MBS decision setting to "Remove UE from MBS session" and TMGI setting to TMGI-1 THEN: UE considers that multicast MBS session associated with TMGI-1 has successfully left the MBS session and multicast MBS session associated with TMGI-2 has not successfully left the MBS session, and deletes the stored TMGI-1, and sends PDU SESSION MODIFICATION COMPLETE | Huawei,Hisilicon | R5-234472 R5-236432 |  | 1 | 100% | 100% |  | 100% | 100%
78 |  | 38.523-1 | 14.2.5.3 | Void | New sub-clause header |  |  |  | 0
79 |  | 38.523-1 | 14.2.5.3.1 | Void(Move to 14.2.5.2.4) |  |  |  |  | 0
80 |  | 38.523-1 | 14.2.5.3.2 | Void(merge to 14.2.5.2.3) |  |  |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
29 |  | 38.523-2 | 4.1 | Applicability for MBS test cases | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | R5-227153 R5-231484 R5-233390 R5-234473 |  | 0.1 | 100% (+90%) | 100% (+90%) |  | 100% | 100%
30 |  | 38.523-2 | 4.2 | ICS for MBS test cases | Add test case applicability expressions for the new test cases introduced in 38.523-1 |  | R5-234473 |  | 0.1 | 100% | 100% |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.